## AP1-1
WIP No | Date Created | Project ID | Project Description | Project Manager | Department Id | Client | CBU | Complexity | Type | Stop Booking Hrs | Closing Project: Action(s) to close | RAG | Approx. PO Burndown (weeks) | Turnover vs Contract Value | Invoice To Date vs Turnover | Cash in vs Turnover | Open Amount Overdue | Actual PM% to Baseline PM% delta | Contract Value | Total Project Turnover | Contract Value - Total Turnover | Run Rate (based on total turnover) | Total BOI Spend to Date | Total Committed PO (supplier/best shore) | Current AA in PT3 | Invoiced To Date | DSO | Unbilled (WIP) | Total Open Amount | Cash in (Invoiced - (Open amount -VAT)) | Debt <=30 Days | Debt 31 - 60 Days | Debt 61 - 90 Days | Debt >= 90 Days | Open Amount Overdue2 | Baseline Project Margin | Project To Date (PTD) PM | Year to Date (YTD) PM | YTD Delta Actual PM% to BPM% | Forecast PM at Completion (Manual input from PTT) | Average Sale Rate | CSat score for last quarter (Manual input from PTT) | Comments and Actions | Judged income adjustment at completion | Profit to take now | Provision required now | Fully Traded | Last Months Comments and Actions
1720 | 2024-01-11 00:29 | P23730 | FLE Project | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 24000.00 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23637 | MBSE Proposal | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 |  | 0 | 0 | 49980 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23729 | Honda Tooling | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX | [7 empty] | 0 | -21% | 0 | 0 | 0 |  | 0 | 0 | 14430.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21% | 0% | 0% | -21% |  | 0 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23711 | DO NOT USE - RAISED IN ERROR | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23552 | FCAS AP Product Technology Development | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -25% | 597871 | 0 | 597871 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 25% | 0% | 0% | -25% |  | 0 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23543 | EXP-024 FCAS AP Transformation & Change Enablers | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -26% | 385921 | 0 | 385921 |  | 0 | 0 | 0.00 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 26% | 0% | 0% | -26% |  | 0 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23585 | Systems Design - Missile Systems, Meteor,Brimstone | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 |  | 0 | 0 | 49500.00 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23717 | GKN Ted Tomblin 2024 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 3672 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23741 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  |  | 0% |  |  | 0 | -28% | 526262 | 0 | 526262 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 0% | 0% | -28% |  | 0 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23739 | Lifing Services DACs | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  |  | 0% |  |  | 0 | -28% | 656508 | 0 | 656508 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 0% | 0% | -28% |  | 0 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23718 | Requalification of EJ200 GSS ESS EHM SW module | Vijayakumara Nanjundappa | ARZ | MTU AERO ENGINES AG | DET | Level 3 | FIX |  |  |  |  | 0% |  |  | 0 | -28% | 74463 | 0 | 74463 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 0% | 0% | -28% |  | 0 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23740 | Phase 2 - EJ200 ESS EHM Platform Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 3 | FIX |  |  |  |  | 0% |  |  | 0 | -28% | 175971 | 0 | 175971 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 0% | 0% | -28% |  | 0 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23743 | EHM Cloud Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  |  | 0% |  |  | 0 | -28% | 1016000 | 0 | 1016000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 0% | 0% | -28% |  | 0 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23598 | MRB Onsite support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -18% | 0 | 880 | -880 |  | 880 | 14079.58 | 13200 | 0 | 91 | 880 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 18% | 0% | 0% | -18% |  | 0 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23724 | GKN S McConnell 2024 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 15.74% | 0 | 1363 | -1363 |  | 0 | 0 | 7373.36 | 0 | 6 | 1363 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 15.74% | 15.74% | 15.74% |  | 47 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23463 | A220 Wing MaMo Design Checking | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 7.85% | 0 | 1628 | -1628 |  | 0 | 0 | 15000 | 0 | 1953.6 | 1628 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 3% | 10.85% | 0% | -3% |  | 44 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23597 | MRB Onsite support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -18% | 0 | 1682 | -1682 |  | 1682 | 17381.62 | 15700 | 0 | 91 | 1682 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 18% | 0% | 0% | -18% |  | 0 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P21028 | Rebate Collection (BACC) | David Catchpole | TOO | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | [5 empty] | 0% | 0% | 0 | 0% | 0 | 2680 | -2680 |  | 2680 | 2680 | 0 | 0 | 3216 | 2680 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23641 | Drawing Triage | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -80.46% | 0 | 10756 | -10756 |  | 0 | 0 | 11343.2 | 0 | 24.46 | 2891 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | -80.46% | 0% | 0% |  | 49 | [5 empty] | -7865
1720 | 2024-01-11 00:29 | P23578 | ESN Work Package | Hannah Mead | COZ | CHELTON LIMITED | DET | Level 3 | FIX | 2024-01-01 | 2 |  |  | 86.17% | 116.1% | 62.5% | 1368 | 35.86% | 4410 | 3800 | 610 |  | 0 | 0 | 0 | 4410 | 113.75 | -610 | 2442 | 2375 | 0 | 1074 | 1368 | 0 | 1368 | 24% | 59.86% | 0% | -24% |  | 95 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23628 | Design Assurance | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -6.67% | 0 | 3909 | -3909 |  | 0 | 0 | 4454.80 | 0 | 317.28 | 3909 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 7% | 0.33% | 0% | -7% |  | 15.05 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23002 | WoT MAJ Transit Flag Stress | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 30.9% | 323.7% | 323.7% | 0 | 53.84% | 4735 | 1463 | 3272 |  | 0 | 2242.5 | 0 | 4735 | 0.6 | 1 | 0 | 4735 | 0 | 0 | 0 | 0 | 0 | 10% | 63.84% | 0% | -10% |  | 45 | [5 empty] | 3273
1720 | 2024-01-11 00:29 | P23607 | SAFRAN - A330neo Turnover Frame | Gary Kempster | TOO | SAFRAN SEATS GB LIMITED | MPE | Level 3 | FIX |  |  |  |  | 95.68% | 0% | 0% | 0 | -19.75% | 8736 | 8359 | 377 |  | 0 | 0 | 0 | 0 | 10030.8 | 8359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23% | 3.25% | 0% | -23% |  | 52 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23274 | ME Support (Aim Altitude - Cambridge) | James Montgomery | AVI | AVIC CABIN SYSTEMS (UK) LIMITED | ME | Level 3 | FIX | 2023-08-18 | 0 |  |  | 51.88% | 56.29% | 56.29% | 0 | -0.17% | 17280 | 8964 | 8316 |  | 0 | 0 | 0 | 5046 | 4701.24 | 3918 | 0 | 5046 | 0 | 0 | 0 | 0 | 0 | 21% | 20.83% | 0% | -21% |  | 48 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23283 | Spirit Tooling Audit | Charidimos Valadakis | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-05-03 | 0 |  |  | 97.23% | 48.57% | 48.57% | 0 | -7.99% | 9910 | 9635 | 275 |  | 0 | 0 | 0 | 4680 | 5946.05 | 4955 | 0 | 4680 | N/A | N/A | N/A | N/A | 0 | 7% | -0.99% | 0% | -7% |  | 34.41 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23127 | Loft Hall Design Support | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 101% | 99.06% | 99.06% | 0 | -9.55% | 9680 | 9772 | -92 |  | 0 | 0 | 0 | 9680 | 110.4 | 92 | 0 | 9680 | N/A | N/A | N/A | N/A | 0 | 41% | 31.45% | 0% | -41% |  | 44 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23630 | 2Excel CFD Analysis Support | Dushan Fernando | BAX | STIRLING DYNAMICS LTD | MPE | Level NC | FIX |  |  |  |  | 61.2% | 100% | 100% | 0 | -1.87% | 16195 | 9911 | 6284 |  | 0 | 0 | 0 | 9912 | 0 | 0 | 0 | 9912 | 0 | 0 | 0 | 0 | 0 | 26% | 24.13% | 0% | -26% |  | 64.78 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23313 | Laser Trim Fixtures | Gary Kempster | TOO | ALKEN ENGINEERING LIMITED | MPE | Level 3 | FIX | 2023-11-20 | 0 |  |  | 89.87% | 111.3% | 111.3% | 0 | 0.53% | 13770 | 12375 | 1395 |  | 0 | 0 | 0 | 13770 | 0 | -1395 | 0 | 13770 | 0 | 0 | 0 | 0 | 0 | 17% | 17.53% | 0% | -17% |  | 45 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23700 | IPDT Leads | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 14.6% | 0 | 12391 | -12391 |  | 0 | 0 | 22200.00 | 0 | 56 | 12391 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 22% | 36.6% | 37.75% | 15.75% |  | 61.88 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P22761 | Red Bull Chassis Spit | James Montgomery | TOO | MANUFAX ENGINEERING LTD | MPE | Level 3 | FIX | 2022-11-15 | 0 |  |  | 72.19% | 96.98% | 96.98% | 0 | 7.92% | 12961 | 9356 | 3605 |  | 0 | 0 | 0 | 9073 | 4666.39 | 3889 | 0 | 9073 | 0 | 0 | 0 | 0 | 0 | 23% | 30.92% | 0% | -23% |  | 42.19 | [5 empty] | 3606
1720 | 2024-01-11 00:29 | P23635 | Engineering Services: FAI Support | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 35.76% | 0% | 0% | 0 | -3.61% | 37230 | 13313 | 23917 |  | 0 | 0 | 0.00 | 0 | 115.09 | 13313 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 8% | 4.39% | 4.39% | -3.61% |  | 38.7 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23685 | DAC LUC Support and Recompliance | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  |  | 1.902% | 0% | 0% | 0 | 2.17% | 720000 | 13696 | 706304 |  | 0 | 0 | 0 | 0 | 6 | 13696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 30.17% | 30.17% | 2.17% |  | 79.28 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23433 | Cavendish | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 32.81% | 100% | 100% | 0 | -0.34% | 42240 | 13859 | 28381 |  | 0 | 0 | 0 | 13859 | 0 | 0 | 0 | 13859 | N/A | N/A | N/A | N/A | 0 | 7% | 6.66% | 0% | -7% |  | 43.93 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23350 | Spirit 2023 - Stress Approve Man Serv (DH) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 14.15% | 72.64% | 72.64% | 0 | -0.29% | 97920 | 13860 | 84060 |  | 0 | 0 | 0 | 10068 | 4550.4 | 3792 | 0 | 10068 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23651 | PMO Spirit | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 24.51% | 0 | 16650 | -16650 |  | 0 | 0 | 30800.00 | 0 | 104.31 | 16650 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 24.51% | 24.51% | 24.51% |  | 36 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23343 | Spirit 2023 - John Agnew | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-08-09 | 0 |  |  | 28.56% | 86.27% | 86.27% | 0 | -0.02% | 65120 | 18601 | 46519 |  | 0 | 0 | 0 | 16047 | 3064.49 | 2554 | 0 | 16047 | N/A | N/A | N/A | N/A | 0 | 7% | 6.98% | 0% | -7% |  | 34.51 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23642 | MRB Belfast Support | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -18.1% | 0 | 19607 | -19607 |  | 1007 | 1007.24 | 30800.00 | 0 | 91 | 19607 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | -18.1% | -21.28% | -21.28% |  | 38.52 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23355 | Spirit Tooling Support 2023 | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-23 | 0 |  |  | 22.93% | 89.03% | 89.03% | 0 | -0.82% | 91800 | 21053 | 70747 |  | 0 | 0 | 0 | 18743 | 2773.01 | 2311 | 0 | 18743 | 0 | 0 | 0 | 0 | 0 | 20% | 19.18% | 0% | -20% |  | 44.46 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23351 | Spirit 2023 - Design Man Serv (KL) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 26.47% | 93.15% | 93.15% | 0 | 0.09% | 93840 | 24840 | 69000 |  | 0 | 0 | 0 | 23138 | 2042.4 | 1702 | 0 | 23138 | 0 | 0 | 0 | 0 | 0 | 26% | 26.09% | 0% | -26% |  | 46 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23356 | Spirit 2023 - Design Man Serv (AH) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX | 2023-08-09 | 1 |  |  |  | 76.66% | 0.001332% | 23018.4 | 0.48% | 0 | 25023 | -25023 |  | 0 | 0 | 25300.00 | 19182 | 30027.7 | 5841 | 23018 | 0.33333 | 0 | 0 | 0 | 23018.4 | 23018.4 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P22884 | Spirit Shorts Config Eng | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 66.3% | 100.1% | 100.1% | 0 | 0.56% | 38976 | 25842 | 13134 |  | 0 | 0 | 0 | 25863 | 0 | 0 | 0 | 25863 | N/A | N/A | N/A | N/A | 0 | 7% | 7.56% | 0% | -7% |  | 20.3 | [5 empty] | 21
1720 | 2024-01-11 00:29 | P23354 | Spirit 2023 - Design Man Serv (PC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 27.97% | 99.36% | 99.36% | 0 | 0.48% | 93840 | 26249 | 67591 |  | 0 | 0 | 0 | 26082 | 200.38 | 167 | 0 | 26082 | 0 | 0 | 0 | 0 | 0 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P22756 | A350 FLE Design Checker | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2022-03-23 | 1 |  |  | 68.39% | 119.7% | 119.7% | 0 | 16.46% | 34898 | 23867 | 11031 |  | 23867 | 24342.3 | 0 | 28571 | 0.06 | 0 | 0 | 28571 | N/A | N/A | N/A | N/A | 0 | 0% | 16.46% | 0% | 0% |  | 0 | [5 empty] | 4704
1720 | 2024-01-11 00:29 | P23458 | Spirit Belfast Tooling Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-08-11 | 0 |  |  | 101.3% | 94.65% | 94.65% | 0 | 8.64% | 30384 | 30785 | -401 |  | 0 | 0 | 0 | 29139 | 1974.96 | 1646 | 0 | 29139 | N/A | N/A | N/A | N/A | 0 | 7% | 15.64% | 0% | -7% |  | 42.2 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23365 | GKN 777x Lip Skin Fixture | Steven Lawton | TOO | GKN AEROSPACE SERVICES LTD | MPE | Level 3 | FIX | 2023-10-12 | 1 |  |  | 41.91% | 113.2% | 18.86% | 37544.22 | -9.26% | 79161 | 33176 | 45985 |  | 5110 | 5109.88 | 0 | 37544 | 33175.67 | -4369 | 37544 | 6257.3333 | 0 | 37544.22 | 0 | 0 | 37544.22 | 22% | 12.74% | 0% | -22% |  | 56 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P22768 | MRB Onsite Support - Spirit Belfast | James Montgomery | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2023-07-27 | 0 |  |  |  | 0% | 0% | 0 | -17.07% | 0 | 34614 | -34614 |  | 0 | 0 | 36800 | 0 | 41536.8 | 34614 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 10% | -7.07% | 0% | -10% |  | 36 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23051 | Spirit Shorts A350 PAX Door | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 3A | REIM |  |  |  |  | 205.9% | 105.4% | 105.4% | 0 | -0.63% | 18216 | 37513 | -19297 |  | 0 | 0 | 0 | 39537 | 0 | 0 | 0 | 39537 | N/A | N/A | N/A | N/A | 0 | 30% | 29.37% | 0% | -30% |  | 46 | [5 empty] | 2024
1720 | 2024-01-11 00:29 | P22752 | Tooling WoT - 2021 (Spirit) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | REIM | 2023-05-03 | 0 |  |  | 101.1% | 74.02% | 74.02% | 0 | -8.5% | 41525 | 41982 | -457 |  | 0 | 0 | 0 | 31076 | 13087.42 | 10906 | 0 | 31076 | N/A | N/A | N/A | N/A | 0 | 0% | -8.5% | 0% | 0% |  | 39.09 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23699 | A220 Stress Checkers | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -2.19% | 0 | 45754 | -45754 |  | 0 | 0 | 37000.00 | 0 | 56 | 45754 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 22% | 19.81% | 0% | -22% |  | 61.88 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23322 | GKN T Tomblin 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2023-12-31 | 3 |  |  | 83.13% | 100% | 88.98% | 691.2 | -0.33% | 58952 | 49008 | 9944 |  | 0 | 0 | 0 | 49008 | 59.18 | 0 | 6480 | 43608 | N/A | N/A | N/A | N/A | 691.2 | 17% | 16.67% | 0% | -17% |  | 48 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P22760 | SA Leading Edge Transport Media ('A' Frames) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-11-15 | 1 |  |  | 85.99% | 110.7% | 116.3% | -3082.8 | 3.97% | 53481 | 45986 | 7495 |  | 42804 | 42804 | 0 | 50912 | 0 | 0 | -3083 | 53481.1667 | 0 | 0 | 0 | -3082.8 | -3082.8 | 6% | 9.97% | 0% | -6% |  | 42 | [5 empty] | 4926
1720 | 2024-01-11 00:29 | P23341 | Spirit 2023 - Tom McFarlane | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 94.96% | 94.96% | 74.65% | 0 | -0.01% | 54282 | 51544 | 2738 |  | 0 | 0 | 0 | 48945 | 98.06 | 2599 | 12560 | 38478.3333 | N/A | N/A | N/A | N/A | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23382 | Performance Modelling | Dushan Fernando | BDX | MBDA UK LIMITED | MPE | Level NC | REIM | 2023-07-09 | 1 |  |  | 40.95% | 79.09% | 79.09% | 0 | -16.36% | 170010 | 69626 | 100384 |  | 14560 | 14659.9 | 0 | 55066 | 0 | 0 | 0 | 55066 | N/A | N/A | N/A | N/A | 0 | 20% | 3.64% | 0% | -20% |  | 77.05 | [5 empty] | -14560
1720 | 2024-01-11 00:29 | P23193 | Spirit Shorts Stephen Greer | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 90.98% | 97.73% | 73.69% | 6679.37 | 2.24% | 61472 | 55927 | 5545 |  | 0 | 0 | 0 | 54656 | 155.62 | 1272 | 16131 | 41213.5 | N/A | N/A | N/A | N/A | 6679.37 | 29% | 31.24% | 34.03% | 5.03% |  | 34.91 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23551 | Ian Berry 2023 H2 | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  |  | 74.7% | 48.83% | 48.83% | 0 | 13.91% | 75810 | 56630 | 19180 |  | 0 | 0 | 0 | 27652 | 100.9 | 28978 | 0 | 27652 | N/A | N/A | N/A | N/A | 0 | 20% | 33.91% | 0% | -20% |  | 75.81 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23349 | Spirit 2023 - Stress Approve Man Serv (SB) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 58.24% | 80.05% | 80.05% | 0 | -0.29% | 97920 | 57024 | 40896 |  | 0 | 0 | 0 | 45648 | 13651.2 | 11376 | 0 | 45648 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23465 | A220 ToW Design Offload (Wing) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 43.74% | 96.59% | 65.38% | 0 | -3.88% | 132000 | 57737 | 74263 |  | 0 | 0 | 0 | 55768 | 95.93 | 1969 | 21623 | 37748.8333 | N/A | N/A | N/A | N/A | 0 | 20% | 16.12% | 20.56% | 0.56% |  | 42.8 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23586 | Project Management Support | Peter Bowen | BDX | MBDA UK LIMITED | MPE | Level NC | REIM |  |  |  |  | 72.43% | 95.47% | 75.04% | 0 | -25.78% | 80000 | 57944 | 22056 |  | 1141 | 1140.6 | 0 | 55320 | 41.15 | 2624 | 14208 | 43480 | N/A | N/A | N/A | N/A | 0 | 49% | 23.22% | 0% | -49% |  | 80 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23560 | NJEWCS TAF202302 SM | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level 2 | FIX |  |  |  |  | 72.43% | 67.76% | 67.76% | 0 | 12.13% | 81500 | 59029 | 22471 |  | 0 | 0 | 0 | 40000 | 73.54 | 19029 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 28% | 40.13% | 40.4% | 12.4% |  | 73.01 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23561 | SAAB | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  |  | 82.46% | 121.1% | 96.66% | 0 | 3.5% | 67485 | 55649 | 11836 |  | 0 | 0 | 0 | 67399 | 48.41 | -4408 | 16332 | 53789 | N/A | N/A | N/A | N/A | 0 | 16% | 19.5% | 0% | -16% |  | 36.82 | [5 empty] | 7342
1720 | 2024-01-11 00:29 | P22967 | Spirit 2022 - Channapa Laxmeshwar | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2023-01-26 | 2 |  |  | 69.69% | 121.3% | 121.3% | 0 | 9.53% | 75159 | 52376 | 22783 |  | 52376 | 54898.1 | 0 | 63509 | 0.42 | 0 | 0 | 63509 | N/A | N/A | N/A | N/A | 0 | 8% | 17.53% | 0% | -8% |  | 0 | [5 empty] | 11133
1720 | 2024-01-11 00:29 | P23342 | Spirit 2023 - Channapa Laxmeshwar | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 78.75% | 104.3% | 88.16% | 0 | -2.64% | 79348 | 62484 | 16864 |  | 62484 | 63539 | 0 | 65178 | 65.39 | 157 | 12110 | 55086.3333 | N/A | N/A | N/A | N/A | 0 | 7% | 4.36% | 0% | -7% |  | 0 | [5 empty] | 2850
1720 | 2024-01-11 00:29 | P23340 | Spirit 2023 - John Cole | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 90.2% | 92.83% | 74.5% | 0 | -0.01% | 75065 | 67706 | 7359 |  | 0 | 0 | 0 | 62852 | 99.48 | 4853 | 14894 | 50440.3333 | N/A | N/A | N/A | N/A | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 39.78 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23438 | A220 Spirit Shorts DTC - Stephen Corry | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 149% | 57.38% | 57.38% | 0 | -5.48% | 47251 | 70405 | -23154 |  | 0 | 0 | 23745 | 40400 | 114.09 | 30006 | 0 | 40400 | N/A | N/A | N/A | N/A | 0 | 21% | 15.52% | 0% | -21% |  | 49.69 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23171 | Spirt Shorts Weights Eng | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 81.27% | 117.6% | 107.5% | 0 | -6.62% | 71760 | 58316 | 13444 |  | 58316 | 76495.95 | 0 | 68582 | 52.54 | 2004 | 7088 | 62675.3333 | N/A | N/A | N/A | N/A | 0 | 24% | 17.38% | 0% | -24% |  | 0 | [5 empty] | 12270
1720 | 2024-01-11 00:29 | P23336 | Spirit 2023 - Neil Rampling | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 105.4% | 93.29% | 67.81% | 0 | -0.01% | 66951 | 70587 | -3636 |  | 0 | 0 | 3938.28 | 65851 | 129.24 | 4737 | 21586 | 47862.6667 | N/A | N/A | N/A | N/A | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23080 | Spirit Shorts DManagement Cairan Cullen | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 48.46% | 99.7% | 94.08% | 0 | -0.76% | 149600 | 72498 | 77102 |  | 0 | 0 | 0 | 72284 | 96.03 | 214 | 4892 | 68207.3333 | N/A | N/A | N/A | N/A | 0 | 24% | 23.24% | 17.46% | -6.54% |  | 44.47 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23583 | Castalla - Test Rig Design | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 109.8% | 82.63% | 55.53% | 0 | -7.24% | 67520 | 74139 | -6619 |  | 0 | 0 | 9706 | 61258 | 120.19 | 12881 | 24105 | 41170.5 | N/A | N/A | N/A | N/A | 0 | 21% | 13.76% | 14.42% | -6.58% |  | 42.38 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23545 | Ultra CSS continuation 2023 H2 | Natalie Sinclair | ULT | ULTRA SONAR SYSTEMS LIMITED | EES | Level NC | REIM |  |  |  |  | 98.99% | 58.42% | 58.42% | 0 | 2.3% | 76000 | 75235 | 765 |  | 0 | 0 | 0 | 43956 | 99.72 | 31279 | 0 | 43956 | N/A | N/A | N/A | N/A | 0 | 23% | 25.3% | 0% | -23% |  | 80 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23600 | MBDA EXP-EE-023 Bristone Certification | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 59.65% | 100% | 84.61% | 0 | 0.4% | 126600 | 75517 | 51083 |  | 0 | 0 | 0 | 75517 | 33.09 | 0 | 13942 | 63898.6667 | N/A | N/A | N/A | N/A | 0 | 41% | 41.4% | 0% | -41% |  | 78.5 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P22505 | Spirit MRB Engineering Support 2021 | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 1 |  |  | 91.17% | 100% | 95.78% | 4020.48 | 21.2% | 87110 | 79415 | 7695 |  | 0 | 0 | 0 | 79415 | 4020.48 | 0 | 4020 | 76065 | 0 | 0 | 0 | 4020.48 | 4020.48 | 0% | 21.2% | 0% | 0% |  | 41.88 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23648 | EXP-032 Delivery of Datalink Eng support - FCAS AP | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 21.42% | 91.81% | 0.0006293% | 0 | 4.06% | 371000 | 79453 | 291547 |  | 265 | 265.32 | 0 | 72943 | 101.7 | 6510 | 87531 | 0.5 | N/A | N/A | N/A | N/A | 0 | 22% | 26.06% | 23.53% | 1.53% |  | 104.68 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23375 | GKN Jaap Peters NL 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2023-12-31 | 6 |  |  | 84.76% | 115.8% | 63.08% | 0 | -15.19% | 89795 | 76111 | 13684 |  | 76111 | 85308.08 | 0.00 | 88129 | 104.77 | -8168 | 48143 | 48009.8333 | N/A | N/A | N/A | N/A | 0 | 20% | 4.81% | 0% | -20% |  | 0 | [5 empty] | 3850
1720 | 2024-01-11 00:29 | P23079 | Spirit Shorts Nomenclature | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 91.27% | 95.55% | 72.96% | 10554.48 | 1.7% | 88455 | 80734 | 7721 |  | 0 | 0 | 0.00 | 77138 | 266.72 | 3595 | 21879 | 58905.5 | N/A | N/A | N/A | N/A | 10554.48 | 20% | 21.7% | 25.23% | 5.23% |  | 30.65 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P22885 | ME Support (Baxi) | James Montgomery | HUV | BAXI HEATING UK LIMITED | ME | Level 3 | FIX | 2023-01-12 | 0 |  |  | 68.78% | 108.7% | 108.7% | 0 | 13.05% | 106633 | 73340 | 33293 |  | 0 | 0 | 0 | 79748 | 1531.35 | 1276 | 0 | 79748 | 0 | 0 | 0 | 0 | 0 | 15% | 28.05% | 0% | -15% |  | 44.37 | [5 empty] | 7684
1720 | 2024-01-11 00:29 | P23335 | GKN S McConnell 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2023-12-31 | 4 |  |  | 96.61% | 100% | 65.44% | 0 | 0.74% | 87420 | 84459 | 2961 |  | 0 | 0 | 0 | 84459 | 138.85 | 0 | 35024 | 55272.3333 | N/A | N/A | N/A | N/A | 0 | 15% | 15.74% | 0% | -15% |  | 47 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P22965 | Spirit 2022 - Design Man Serv (AH) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 1 |  |  | 106.7% | 96.66% | 92.02% | 4759.75 | 3.14% | 80080 | 85441 | -5361 |  | 0 | 0 | 0 | 82589 | 8182.59 | 2852 | 4760 | 78622.3333 | 0 | 0 | 0 | 4759.75 | 4759.75 | 14% | 17.14% | 0% | -14% |  | 42.44 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23523 | Applique Armour Support | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 0 |  |  | 101.6% | 98.47% | 98.47% | 0 | 3.42% | 84300 | 85607 | -1307 |  | 0 | 0 | 0 | 84300 | 16.73 | 1307 | 0 | 84300 | 0 | 0 | 0 | 0 | 0 | 25% | 28.42% | 0% | -25% |  | 64.29 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P22964 | Spirit 2022 - MRB Man Serv (JC) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 100.6% | 97.95% | 97.95% | 0 | 1.91% | 85435 | 85960 | -525 |  | 0 | 0 | 0 | 84200 | 2112.62 | 1761 | 0 | 84200 | 0 | 0 | 0 | 0 | 0 | 16% | 17.91% | 0% | -16% |  | 42.69 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P22963 | Spirit 2022 - Design Man Serv (PC) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 1 |  |  | 108.6% | 104% | 94.46% | 9938.48 | 3.18% | 80080 | 86927 | -6847 |  | 0 | 0 | 0 | 90390 | 5782.63 | -3463 | 9938 | 82108.3333 | 0 | 0 | 0 | 9938.48 | 9938.48 | 13% | 16.18% | 0% | -13% |  | 42.39 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23353 | Spirit 2023 - MRB Man Serv (JC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  |  | 97.08% | 76.99% | 69.2% | 0 | -0.22% | 91800 | 89123 | 2677 |  | 0 | 0 | 0 | 68615 | 130.84 | 20507 | 8330 | 61673.3333 | 0 | 0 | 0 | 8329.5 | 0 | 18% | 17.78% | 0% | -18% |  | 45 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23352 | Spirit 2023 - Stress Approve Man Serv (CC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  |  | 96.1% | 74.29% | 62.87% | 0 | -2.37% | 97920 | 94104 | 3816 |  | 0 | 0 | 0 | 69912 | 159.25 | 24192 | 12902 | 59160.3333 | 0 | 0 | 0 | 12902.4 | 0 | 18% | 15.63% | 0% | -18% |  | 48 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P22918 | Spirit Shorts Graduates | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 88.31% | 72.43% | 72.43% | 0 | 9.35% | 110000 | 97136 | 12864 |  | 0 | 0 | 0.00 | 70352 | 132.34 | 26784 | 0 | 70352 | N/A | N/A | N/A | N/A | 0 | 7% | 16.35% | 18.07% | 11.07% |  | 23.16 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23282 | Tooling Support (MBDA) | Dushan Fernando | BDV | MBDA UK LIMITED | ME | Level 3 | FIX |  |  |  |  | 95.59% | 99.98% | 92.5% | 0 | -10.39% | 104834 | 100210 | 4624 |  | 0 | 0 | 0 | 100185 | 32.57 | 25 | 8984 | 92698.3333 | 8983.8 | 0 | 0 | 0 | 0 | 30% | 19.61% | 0% | -30% |  | 49.67 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23270 | Shorts Project X | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 72.72% | 92.79% | 71.32% | 9715.2 | 1.09% | 142248 | 103445 | 38803 |  | 0 | 0 | 0 | 95985 | 135.61 | 7460 | 26649 | 73777.5 | N/A | N/A | N/A | N/A | 9715.2 | 13% | 14.09% | 10.99% | -2.01% |  | 45.42 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23667 | Safety Systems Engineer | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 26.48% | 100% | 0% | 0 | -5.93% | 398000 | 105380 | 292620 |  | 0 | 0 | 0 | 105380 | 112.78 | 0 | 126456 | 0 | N/A | N/A | N/A | N/A | 0 | 47% | 41.07% | 0% | -47% |  | 110 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23421 | A220 DTC | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 84.15% | 97.42% | 60.01% | 0 | -12.11% | 130625 | 109925 | 20700 |  | 0 | 0 | 0.00 | 107094 | 101.83 | 2831 | 49358 | 65962.3333 | N/A | N/A | N/A | N/A | 0 | 10% | -2.11% | 14.89% | 4.89% |  | 45.1 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P22883 | Spirit Shorts Evtol PMO C. Hatton | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 59.2% | 99.04% | 82.94% | 0 | -12.59% | 185800 | 110000 | 75800 |  | 0 | 0 | 0 | 108947 | 94.19 | 1053 | 21252 | 91237 | N/A | N/A | N/A | N/A | 0 | 26% | 13.41% | 26.14% | 0.14% |  | 36.2 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P22736 | WoT Fixed Leading Edge - Industrial | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 106.7% | 93.42% | 91.32% | 3019.54 | 0.01% | 112196 | 119668 | -7472 |  | 0 | 0 | 0 | 111797 | 12465.69 | 7872 | 3020 | 109280.3333 | 0 | 0 | 0 | 3019.54 | 3019.54 | 7% | 7.01% | 0% | -7% |  | 32.26 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23437 | Embedded Software Engineer | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 81.37% | 95.33% | 86.27% | 0 | -6.41% | 150150 | 122177 | 27973 |  | 738 | 737.86 | 0 | 116473 | 44.43 | 5704 | 13282 | 105404.6667 | N/A | N/A | N/A | N/A | 0 | 22% | 15.59% | 15.92% | -6.08% |  | 78.5 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23518 | Systems Engineering support to FCAS | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 64.61% | 94.7% | 80.7% | 0 | 2.12% | 193737 | 125178 | 68559 |  | 3927 | 3927.4 | 0 | 118539 | 51.26 | 6638 | 21019 | 101023.1667 | N/A | N/A | N/A | N/A | 0 | 30% | 32.12% | 3.18% | -26.82% |  | 65.52 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P22861 | WoT FLE Lifting & Handling Tools | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2023-06-14 | 1 |  |  | 65.17% | 101.6% | 101.6% | 0 | 12.01% | 173987 | 113382 | 60605 |  | 50078 | 58423.58 | 0 | 115204 | 12813.9 | 10678 | 0 | 115204 | 0 | 0 | 0 | 0 | 0 | 1% | 13.01% | 0% | -1% |  | 45 | [5 empty] | 12500
1720 | 2024-01-11 00:29 | P23386 | Software Development - BMS | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 87.55% | 100% | 91.25% | 0 | 4.27% | 149650 | 131017 | 18633 |  | 0 | 0 | 0 | 131017 | 32.18 | 0 | 13753 | 119556.1667 | N/A | N/A | N/A | N/A | 0 | 18% | 22.27% | 0% | -18% |  | 78.5 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23464 | A220 Project X Design Offload | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 74.96% | 98.58% | 73.96% | 0 | -3.71% | 180400 | 135233 | 45167 |  | 0 | 0 | 0.00 | 133307 | 99.99 | 1926 | 39945 | 100019.5 | N/A | N/A | N/A | N/A | 0 | 21% | 17.29% | 19.45% | -1.55% |  | 42.9 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23650 | MBDA Recruitment Management costs | Brian Maddrell | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 31.5% | 0 | 136012 | -136012 |  | 0 | 0 | 266000 | 0 | 94.95 | 136012 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 3% | 34.5% | 38.18% | 35.18% |  | 87.87 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23508 | Verification and Validation | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 65.06% | 96.78% | 65.06% | 0 | 11.11% | 212950 | 138553 | 74397 |  | 0 | 0 | 0 | 134098 | 75.87 | 4455 | 52752 | 90138 | N/A | N/A | N/A | N/A | 0 | 24% | 35.11% | 35.32% | 11.32% |  | 78.5 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23533 | External Stowage Design and Detail Support | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 0 |  |  | 136.5% | 73.24% | 73.24% | 0 | 6.33% | 105000 | 143369 | -38369 |  | 0 | 0 | 49220 | 105000 | 103.59 | 35000 | 0 | 105000 | 0 | 0 | 0 | 0 | 0 | 24% | 30.33% | 0% | -24% |  | 60.04 | [5 empty] | -3369
1720 | 2024-01-11 00:29 | P23506 | ASTER Mid-Life Refurbishment Project Manager | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 64.5% | 96.28% | 85.47% | 0 | 0.94% | 224900 | 145054 | 79846 |  | 2329 | 2329.13 | 0 | 139651 | 37.36 | 5403 | 18810 | 123976 | N/A | N/A | N/A | N/A | 0 | 25% | 25.94% | 26.36% | 1.36% |  | 110 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P22954 | Technical Support Step 1 | Owain Jones | HUV | HUARUI SPIRIT AEROSPACE MANUFACT | ME | Level 2 | REIM |  |  |  |  | 94.81% | 58.01% | 58.01% | 0 | 0.31% | 155501 | 147432 | 8069 |  | 23043 | 23043 | 0 | 85525 | 61906.09 | 61906 | 0 | 85525 | N/A | N/A | N/A | N/A | 0 | 30% | 30.31% | 0% | -30% |  | 60.79 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23505 | EXP-022 Meteor TBUS T&E support | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 60.22% | 100% | 35.51% | 0 | -0.01% | 246744 | 148579 | 98165 |  | 0 | 0 | 0 | 148579 | 226.28 | 0 | 114991 | 52753.1667 | N/A | N/A | N/A | N/A | 0 | 20% | 19.99% | 0% | -20% |  | 89.83 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P22440 | Spirit Managed Service - F&DT and Static Approval | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 3 |  |  | 88.56% | 92.56% | 92.56% | 0 | 11.51% | 173500 | 153656 | 19844 |  | 52115 | 55720 | 0 | 142225 | 13717.36 | 11431 | 0 | 142225 | 0 | 0 | 0 | 0 | 0 | 0% | 11.51% | 0% | 0% |  | 44.73 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23373 | Raytheon Michael Bellini | Natalie Sinclair | RAS | RAYTHEON UNITED KINGDOM LIMITED | EES | Level NC | REIM |  |  |  |  | 72.3% | 79.03% | 79.03% | 0 | -8.45% | 214367 | 154984 | 59383 |  | 0 | 0 | 0 | 122483 | 91.98 | 32501 | 0 | 122483 | N/A | N/A | N/A | N/A | 0 | 45% | 36.55% | 36.62% | -8.38% |  | 91.61 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23242 | Physical Architecture & System Engineering Support | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 54.81% | 99.79% | 94.59% | 0 | 11.47% | 305459 | 167426 | 138033 |  | 355 | 354.61 | 0 | 167081 | 28 | 346 | 10456 | 158367.6667 | N/A | N/A | N/A | N/A | 0 | 15% | 26.47% | 0% | -15% |  | 78.13 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23524 | Bombardier Regional Jets (BRJ) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 114.9% | 64.74% | 42.3% | 0 | -5.1% | 146288 | 168123 | -21835 |  | 0 | 0 | 46750 | 108838 | 105.11 | 59284 | 45261 | 71120.5 | N/A | N/A | N/A | N/A | 0 | 18% | 12.9% | 11.53% | -6.47% |  | 44.04 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23008 | Spirit Shorts Project Rachel | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 85.87% | 91.32% | 79.5% | 0 | -7.72% | 228880 | 196531 | 32349 |  | 0 | 0 | 0 | 179473 | 161.86 | 17058 | 27878 | 156241.3333 | N/A | N/A | N/A | N/A | 0 | 13% | 5.28% | -2.79% | -15.79% |  | 46.04 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23019 | EXP034-B Actuator Development | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 102.9% | 90.07% | 90.07% | 0 | -14.61% | 215541 | 221819 | -6278 |  | 11901 | 11992.81 | 0.00 | 199797 | 25.33 | 5045 | 0 | 199797 | N/A | N/A | N/A | N/A | 0 | 34% | 19.39% | 30.52% | -3.48% |  | 58.45 | [5 empty] | -16977
1720 | 2024-01-11 00:29 | P23694 | Systems Portfolio | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 37.47% | 92.84% | 45.79% | 0 | 7.22% | 591943 | 221789 | 370154 |  | 158 | 157.75 | 0 | 205909 | 37.98 | 15879 | 125228 | 101552.3333 | N/A | N/A | N/A | N/A | 0 | 21% | 28.22% | 27.69% | 6.69% |  | 95.21 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23316 | Model Factory IL and AW | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  |  | 88.13% | 104.1% | 96.46% | 0 | 2.12% | 250000 | 220328 | 29672 |  | 0 | 0 | 0 | 229409 | 26.27 | -913 | 20249 | 212534.8333 | 0 | 20248.8 | 0 | 0 | 0 | 30% | 32.12% | 29.97% | -0.03% |  | 45.31 | [5 empty] | 8168
1720 | 2024-01-11 00:29 | P23007 | EXP-006A - Brimstone 3 | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 90.52% | 98.79% | 88.35% | 0 | -8.87% | 264150 | 239114 | 25036 |  | 0 | 0 | 0 | 236210 | 82.32 | 2875 | 29956 | 211246.6667 | N/A | N/A | N/A | N/A | 0 | 30% | 21.13% | 0% | -30% |  | 68.75 | [5 empty] | -30
1720 | 2024-01-11 00:29 | P23317 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  |  | 95.89% | 104.3% | 98.16% | 0 | 3.76% | 251800 | 241447 | 10353 |  | 0 | 0 | 0 | 251800 | 23.48 | -2177 | 17760 | 237000 | 0 | 17760 | 0 | 0 | 0 | 25% | 28.76% | 24.39% | -0.61% |  | 36.29 | [5 empty] | 8176
1720 | 2024-01-11 00:29 | P22798 | CO2MAP MGSE | Harry James Kellett | DTW | THALES ALENIA SPACE UK (60DAYS) | EES | Level 2 | REIM | 2023-11-08 | 1 |  |  | 85.75% | 116.6% | 101.6% | 38880 | 3.94% | 252086 | 216158 | 35928 |  | 0 | 0 | 0 | 252086 | 7130.47 | 64 | 38880 | 219686 | N/A | N/A | N/A | N/A | 38880 | 29% | 32.94% | 0% | -29% |  | 50.31 | [5 empty] | 35992
1720 | 2024-01-11 00:29 | P21463 | Safety & Monitoring Systems at DM Beith & Gosport | Harry James Kellett | BXW | MOD | EES | Level 2 | FIX |  |  |  |  | 73.21% | 136.6% | 124.4% | 0 | -27.95% | 349405 | 255784 | 93621 |  | 53704 | 65553.91 | 11769 | 349387 | 0 | -93603 | 37495 | 318141.1667 | 37494.86 | 0 | 0 | 0 | 0 | 48% | 20.05% | 60.27% | 12.27% |  | 52.03 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23308 | NATO JEWCS | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  |  | 75.12% | 88.02% | 88.02% | 0 | -2.85% | 356307 | 267644 | 88663 |  | 338 | 338.05 | 0 | 235576 | 99.72 | 32068 | 0 | 235576 | N/A | N/A | N/A | N/A | 0 | 24% | 21.15% | 12.94% | -11.06% |  | 75.81 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23045 | Shotgun Adaptors - 10 Sets | Harry James Kellett | BDW | MBDA UK LIMITED | EES | Level 2 | FIX |  |  |  |  | 74.71% | 95.18% | 95.18% | 0 | -19.11% | 399276 | 298306 | 100970 |  | 214344 | 214551.21 | 0 | 283926 | 377.06 | 14381 | 0 | 283926 | 0 | 0 | 0 | 0 | 0 | 29% | 9.89% | 0% | -29% |  | 55.76 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P22515 | Shorts A220 100/300 ALI Phase III | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 75.5% | 98.34% | 94.32% | 0 | 1.04% | 400629 | 302484 | 98145 |  | 3451 | 3450.98 | 0 | 297465 | 79.9 | 5019 | 14584 | 285311.6667 | N/A | N/A | N/A | N/A | 0 | 10% | 11.04% | 15.63% | 5.63% |  | 40.24 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P22953 | Spirit Shorts eVTOL | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 103.1% | 79.36% | 79.36% | 0 | -6.74% | 324272 | 334484 | -10212 |  | 66697 | 67387.9 | 0 | 265432 | 179.02 | 69052 | 0 | 265432 | N/A | N/A | N/A | N/A | 0 | 17% | 10.26% | 0% | -17% |  | 46.19 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23520 | FCAS AP Portfolio Systems | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 41.38% | 98.04% | 85.25% | 0 | -7.14% | 810821 | 335505 | 475316 |  | 320 | 319.5 | 0 | 328919 | 35.38 | 6587 | 51480 | 286019 | N/A | N/A | N/A | N/A | 0 | 22% | 14.86% | 15.1% | -6.9% |  | 78.42 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P22842 | ME Support (Aim Altitude) | James Montgomery | AVI | AIM ALTITUDE UK LIMITED | ME | Level 3 | FIX | 2023-06-14 | 4 |  |  | 99.31% | 100.5% | 86.63% | 57290.84 | 0.49% | 346294 | 343918 | 2376 |  | 2910 | 2909.86 | 0 | 345673 | 55184.93 | -1755 | 57291 | 297930.5 | 0 | 0 | 0 | 57290.84 | 57290.84 | 13% | 13.49% | 0% | -13% |  | 46.3 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23023 | Spirit Shorts R Foster/M Gourley | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  |  | 79.13% | 103.8% | 99.82% | 0 | -20.11% | 416652 | 329710 | 86942 |  | 188776 | 216366 | 0 | 342363 | 54.42 | 1859 | 15899 | 329113.8333 | N/A | N/A | N/A | N/A | 0 | 27% | 6.89% | 7.6% | -19.4% |  | 29.42 | [5 empty] | 14511
1720 | 2024-01-11 00:29 | P23554 | Dornier Seawings 328 2023 H2 Support | Steven Lawton | DAX | EXPLEO GERMANY GMBH (EC) | MPE | Level 2 | REIM |  |  |  |  | 85.37% | 98.65% | 77.38% | 58597.74 | 7.39% | 416112 | 355252 | 60860 |  | 3551 | 3550.65 | 25985 | 350449 | 57.73 | 4804 | 90667 | 274893.1667 | N/A | N/A | N/A | N/A | 58597.74 | 21% | 28.39% | 32.28% | 11.28% |  | 67.38 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P22391 | GE System Engineering support | Vinayakumar Sugur | GEE | EXPERIS LIMITED | EES | Level NC | REIM |  |  |  |  | 82.01% | 94.11% | 92.77% | 0 | 0.13% | 434434 | 356261 | 78173 |  | 0 | 0 | 0 | 335263 | 90.34 | 20998 | 5694 | 330518 | N/A | N/A | N/A | N/A | 0 | 6% | 6.13% | 6.09% | 0.09% |  | 57.33 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23366 | Business Analyst Support | Peter Williams | BDZ | MBDA UK LIMITED | DET | Level NC | REIM |  |  |  |  | 23.58% | 281.5% | 245.4% | 0 | 19.02% | 583200 | 137511 | 445689 |  | 137510 | 416921.86 | 0 | 387040 | 59.32 | -21394 | 59520 | 337440 | N/A | N/A | N/A | N/A | 0 | 43% | 62.02% | 0% | -43% |  | 0.01 | [5 empty] | 228135
1720 | 2024-01-11 00:29 | P23602 | EXP-025 Portfolio Software Engineering Support | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 30.66% | 95.42% | 70.28% | 0 | -0.49% | 1221060 | 374385 | 846675 |  | 0 | 0 | 0 | 357244 | 39.76 | 17141 | 112951 | 263118.1667 | N/A | N/A | N/A | N/A | 0 | 24% | 23.51% | 26.07% | 2.07% |  | 82.37 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23432 | Spirit Belfast MRB On-Site Support (Mon & Clear) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 65.77% | 125.6% | 93.11% | 77391.6 | -11.53% | 449545 | 295665 | 153880 |  | 295665 | 451827.33 | 0 | 371466 | 40.74 | 36200 | 115405 | 275295.1667 | N/A | N/A | N/A | N/A | 77391.6 | 39% | 27.47% | 0% | -39% |  | 0 | [5 empty] | 112000
1720 | 2024-01-11 00:29 | P23320 | Lifing Services DACs | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  |  | 95.56% | 104.6% | 97.44% | 0 | 2.36% | 413300 | 394956 | 18344 |  | 0 | 0 | 0 | 413300 | 24.46 | -4050 | 34139 | 384850.8333 | 0 | 34138.8 | 0 | 0 | 0 | 26% | 28.36% | 24.35% | -1.65% |  | 33.15 | [5 empty] | 14294
1720 | 2024-01-11 00:29 | P22906 | Spirit Shorts - MRB JD Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  |  | 65.79% | 85.92% | 61.99% | 89722.8 | -7.51% | 614770 | 404431 | 210339 |  | 0 | 0 | 0.00 | 347478 | 301.26 | 64953 | 116125 | 250707.1667 | N/A | N/A | N/A | N/A | 89722.8 | 13% | 5.49% | 3.04% | -9.96% |  | 36.77 | [5 empty] | 8000
1720 | 2024-01-11 00:29 | P23140 | Spirit Shorts A220 MLG Stress Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  |  | 67.04% | 92.85% | 65.11% | 132992.4 | -15.16% | 595746 | 399398 | 196348 |  | 20870 | 87811.88 | 0.00 | 370857 | 182.6 | 53541 | 132992 | 260030.3333 | 0 | 0 | 84649.2 | 48343.2 | 132992.4 | 32% | 16.84% | 3.69% | -28.31% |  | 47.33 | [5 empty] | 25000
1720 | 2024-01-11 00:29 | P22652 | L3 - Saftey Engineering | Sean Simmons | LHW | L3HARRIS MAPPS LIMITED | EES | Level NC | FIX |  |  |  |  | 93.65% | 88.52% | 88.52% | 0 | 5.67% | 523390 | 490149 | 33241 |  | 0 | 0 | 0 | 433883 | 1400.88 | 56266 | 0 | 433883 | 0 | 0 | 0 | 0 | 0 | 21% | 26.67% | 0% | -21% |  | 83.01 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23001 | Spirit Shorts A220 Design | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 112.3% | 74.19% | 69.06% | 0 | -3.56% | 439560 | 493514 | -53954 |  | 0 | 0 | 65953.2 | 366148 | 313.94 | 127366 | 30405 | 340810.5 | N/A | N/A | N/A | N/A | 0 | 25% | 21.44% | 11.21% | -13.79% |  | 43.65 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23281 | Systems Portfolio | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 44.43% | 97.19% | 94.46% | 0 | -17.1% | 1177697 | 523237 | 654460 |  | 2133 | 2133.28 | 0 | 508545 | 62.71 | 14603 | 17142 | 494260 | N/A | N/A | N/A | N/A | 0 | 25% | 7.9% | 0% | -25% |  | 70.48 | [5 empty] | -89
1720 | 2024-01-11 00:29 | P21138 | D&A Vibration Reduc Damping Struc FOGV Components | Steven Lawton | ATC | AECC SICHUAN GAS TURBINE | MPE | Level 1 | FIX | 2022-09-07 | 0 |  |  | 96.12% | 104% | 104% | 0 | -3.44% | 569346 | 547228 | 22118 |  | 75182 | 75181.75 | 0 | 569346 | 0 | -11 | 0 | 569346 | 0 | 0 | 0 | 0 | 0 | 36% | 32.56% | 0% | -36% |  | 73.95 | [5 empty] | 22107
1720 | 2024-01-11 00:29 | P22790 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 2 | REIM |  |  |  |  | 194.5% | 90.44% | 90.44% | 0 | 1.37% | 352240 | 685262 | -333022 |  | 1612 | 1611.52 | 515246 | 619744 | 41098.04 | 34248 | 0 | 619744 | N/A | N/A | N/A | N/A | 0 | 13% | 14.37% | 0% | -13% |  | 45.06 | [5 empty] | -31270
1720 | 2024-01-11 00:29 | P23321 | EHM Cloud Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  |  | 86.88% | 115.1% | 107.2% | 0 | 1.43% | 839969 | 729731 | 110238 |  | 0 | 0 | 24980 | 839969 | 7.42 | -44698 | 69002 | 782467.3333 | 0 | 69002.4 | 0 | 0 | 0 | 28% | 29.43% | 0% | -28% |  | 49.93 | [5 empty] | 65540
1720 | 2024-01-11 00:29 | P23519 | Mechanical and Electrical Design Eng Support | Dushan Fernando | BAX | SAFRAN SEATS GB LIMITED | MPE | Level 2 | REIM |  |  |  |  | 106.6% | 91.81% | 65.92% | 0 | -1.56% | 839697 | 895319 | -55622 |  | 727 | 727 | 49914 | 821977 | 73.01 | 73342 | 278137 | 590196.1667 | N/A | N/A | N/A | N/A | 0 | 33% | 31.44% | 32.17% | -0.83% |  | 56.57 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P22350 | EMP 2020-2021 | Liam Jacob Lewis Bryant | ARY | GUIDANT GROUP (trading name) | PCPR | Level NC | REIM |  |  |  |  | 97.06% | 98.81% | 95.01% | 0 | -1.86% | 930212 | 902893 | 27319 |  | 400 | 400 | 0.00 | 892143 | 60.83 | 10750 | 41114 | 857881.3333 | N/A | N/A | N/A | N/A | 0 | 32% | 30.14% | 27.61% | -4.39% |  | 44 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23105 | Raytheon Supply Engineering Support | Natalie Sinclair | RAY | RAYTHEON UNITED KINGDOM LIMITED | MPE | Level 3A | REIM | 2023-07-13 | 1 |  |  | 79.67% | 90.07% | 90.07% | 0 | -1.83% | 1164044 | 927395 | 236649 |  | 0 | 0 | 0 | 835328 | 110481.3 | 92068 | 0 | 835328 | N/A | N/A | N/A | N/A | 0 | 26% | 24.17% | 0% | -26% |  | 48.97 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23152 | Project Aragon - Design and Stress Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  |  | 103.2% | 64.61% | 64.61% | 0 | -9.51% | 1093504 | 1128742 | -35238 |  | 0 | 0 | 0 | 729296 | 231.39 | 399446 | 0 | 729296 | N/A | N/A | N/A | N/A | 0 | 39% | 29.49% | 29.21% | -9.79% |  | 51.82 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P22671 | Spirit Shorts Pylon and Fairing Package | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX | 2023-05-03 | 4 |  |  | 105% | 95.27% | 95.27% | 0 | -7.21% | 1198495 | 1258028 | -59533 |  | 106451 | 174863.91 | 0 | 1198495 | 2492.21 | 2077 | 0 | 1198495 | 0 | 0 | 0 | 0 | 0 | 20% | 12.79% | 0% | -20% |  | 45.4 | [5 empty] | -57456
1720 | 2024-01-11 00:29 | P23435 | Andy Baker Portfolio | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 38.01% | 96.91% | 76.08% | 0 | -8.43% | 3377457 | 1283868 | 2093589 |  | 2353 | 2352.57 | 0 | 1244199 | 78.18 | 39669 | 320892 | 976789 | N/A | N/A | N/A | N/A | 0 | 25% | 16.57% | 17.83% | -7.17% |  | 77.73 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23315 | DAC LUC BAU and Service Workbench | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  |  | 78.28% | 127.7% | 114.5% | 0 | 1.23% | 1573630 | 1231842 | 341788 |  | 180 | 180.3 | 0 | 1573630 | 0 | -178991 | 195596 | 1410633.3333 | 0 | 195596.4 | 0 | 0 | 0 | 28% | 29.23% | 21.07% | -6.93% |  | 52.68 | [5 empty] | 162797
1720 | 2024-01-11 00:29 | P23411 | Agile & Scrum Delivery Service | Peter Williams | BDZ | MBDA UK LIMITED | DET | Level 2 | REIM | 2023-08-14 | 1 |  |  | 36.3% | 170.5% | 170.5% | 0 | 13.08% | 2487000 | 902904 | 1584096 |  | 894179 | 2337284.55 | 0 | 1539600 | 91 | 16141 | 0 | 1539600 | N/A | N/A | N/A | N/A | 0 | 29% | 42.08% | 0% | -29% |  | 74.57 | [5 empty] | 652837
1720 | 2024-01-11 00:29 | P23207 | A350 Approvers - Design and Stress Support | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  |  | 102.4% | 73.41% | 50.77% | 296187.37 | -10.59% | 1670400 | 1710457 | -40057 |  | 14330 | 14395.36 | 0 | 1255654 | 124.2 | 454803 | 464736 | 868374 | 0 | 91957.54 | 203002.06 | 169776.21 | 296187.37 | 29% | 18.41% | 20.02% | -8.98% |  | 54.63 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P23006 | Spirit Shorts A350 Freighter Toulouse | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 136.3% | 87.5% | 79.61% | 0 | 18.18% | 1035746 | 1411547 | -375801 |  | 1086670 | 1708220.2 | 0 | 1235101 | 301.27 | 487720 | 133601 | 1123766.8333 | N/A | N/A | N/A | N/A | 0 | 5% | 23.18% | 37.29% | 32.29% |  | 47.24 | [5 empty] | 311274
1720 | 2024-01-11 00:29 | P19020 | Spirit Concessions - 2018 | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX |  |  |  |  | 90.69% | 112% | 107.2% | 99792.83 | 2.11% | 1914847 | 1736578 | 178269 |  | 44318 | 44317.61 | 15178.88 | 1944711 | 1611.6 | 194547 | 99793 | 1861550.1667 | 0 | 0 | 0 | 99792.83 | 99792.83 | 25% | 27.11% | 7.8% | -17.2% |  | 40.87 | [5 empty] | 402680
1720 | 2024-01-11 00:29 | P23179 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX |  |  |  |  | 128% | 86.12% | 81.52% | 35500.91 | -9.48% | 1913715 | 2450302 | -536587 |  | 155464 | 246717.26 | 0.00 | 2110117 | 296.82 | 340185 | 135230 | 1997425.3333 | 0 | 99728.59 | 0 | 35500.91 | 35500.91 | 22% | 12.52% | 0% | -22% |  | 44.41 | [5 empty] | 0
1720 | 2024-01-11 00:29 | P19731 | Hapri HPC Rear Bearing Housing PDR & CDR | Steven Lawton | ATC | AECC Hunan Aviation Powerplant | MPE | Level 1 | FIX |  |  |  |  | 99.22% | 100.8% | 88.19% | 0 | -15.32% | 2980000 | 2956789 | 23211 |  | 358408 | 512832.98 | 0 | 2980000 | 612.25 | -248211 | 447000 | 2607500 | 0 | 447000 | 0 | 0 | 0 | 38% | 22.68% | 19.37% | -18.63% |  | 64.87 | [5 empty] | -225000
Extend Table

## AP1-2
WIP No | Date Created | Project ID | Project Description | Project Manager | Department Id | Client | CBU | Complexity | Type | Stop Booking Hrs | Closing Project: Action(s) to close | RAG | Approx. PO Burndown (weeks) | Turnover vs Contract Value | Invoice To Date vs Turnover | Cash in vs Turnover | Open Amount Overdue | Actual PM% to Baseline PM% delta | Contract Value | Total Project Turnover | Contract Value - Total Turnover | Run Rate (based on total turnover) | Total BOI Spend to Date | Total Committed PO (supplier/best shore) | Current AA in PT3 | Invoiced To Date | DSO | Unbilled (WIP) | Total Open Amount | Cash in (Invoiced - (Open amount -VAT)) | Debt <=30 Days | Debt 31 - 60 Days | Debt 61 - 90 Days | Debt >= 90 Days | Open Amount Overdue2 | Baseline Project Margin | Project To Date (PTD) PM | Year to Date (YTD) PM | YTD Delta Actual PM% to BPM% | Forecast PM at Completion (Manual input from PTT) | Average Sale Rate | CSat score for last quarter (Manual input from PTT) | Comments and Actions | Judged income adjustment at completion | Profit to take now | Provision required now | Fully Traded | Last Months Comments and Actions
1721 | 2024-01-18 00:29 | P23641 | Drawing Triage | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 1043368% | 0 | 10756 | -10756 |  | 0 | 0 | 11343.2 | 0 | 0 | -1 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 1043368% | 100% | 100% |  | 49 | [5 empty] | -10756
1721 | 2024-01-18 00:29 | P23730 | FLE Project | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 24000.00 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23637 | MBSE Proposal | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 |  | 0 | 0 | 49980 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23711 | DO NOT USE - RAISED IN ERROR | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23717 | GKN Ted Tomblin 2024 | Matthew Tweed | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 3672 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23552 | FCAS AP Product Technology Development | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -25% | 597871 | 0 | 597871 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 25% | 0% | 0% | -25% |  | 0 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23543 | EXP-024 FCAS AP Transformation & Change Enablers | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -26% | 385921 | 0 | 385921 |  | 0 | 0 | 0.00 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 26% | 0% | 0% | -26% |  | 0 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23585 | Systems Design - Missile Systems, Meteor,Brimstone | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 |  | 0 | 0 | 49500.00 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23718 | Requalification of EJ200 GSS ESS EHM SW module | Vijayakumara Nanjundappa | ARZ | MTU AERO ENGINES AG | DET | Level 3 | FIX |  |  |  |  | 0% |  |  | 0 | -28% | 74463 | 0 | 74463 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 0% | 0% | -28% |  | 0 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23598 | MRB Onsite support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -18% | 0 | 880 | -880 |  | 880 | 14079.58 | 13200 | 0 | 91 | 880 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 18% | 0% | 0% | -18% |  | 0 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23463 | A220 Wing MaMo Design Checking | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 7.85% | 0 | 1628 | -1628 |  | 0 | 0 | 15000 | 0 | 1953.6 | 1628 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 3% | 10.85% | 0% | -3% |  | 44 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23597 | MRB Onsite support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -18% | 0 | 1682 | -1682 |  | 1682 | 17381.62 | 15700 | 0 | 91 | 1682 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 18% | 0% | 0% | -18% |  | 0 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23740 | Phase 2 - EJ200 ESS EHM Platform Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 3 | FIX |  |  |  |  | 0.9774% | 0% | 0% | 0 | 2% | 175971 | 1720 | 174251 |  | 0 | 0 | 0 | 0 | 13 | 1720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 30% | 30% | 2% |  | 80 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P21028 | Rebate Collection (BACC) | David Catchpole | TOO | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | [5 empty] | 0% | 0% | 0 | 0% | 0 | 2680 | -2680 |  | 2680 | 2680 | 0 | 0 | 3216 | 2680 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23743 | EHM Cloud Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  |  | 0.3% | 0% | 0% | 0 | 4.58% | 1016000 | 3048 | 1012952 |  | 0 | 0 | 0 | 0 | 13 | 3048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 32.58% | 32.58% | 4.58% |  | 46.19 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23724 | GKN S McConnell 2024 | Matthew Tweed | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  |  | 6.6% | 0% | 0% | 0 | 1.51% | 49820 | 3288 | 46532 |  | 0 | 0 | 0.00 | 0 | 13 | 3288 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 19% | 20.51% | 20.51% | 1.51% |  | 49.82 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23578 | ESN Work Package | Hannah Mead | COZ | CHELTON LIMITED | DET | Level 3 | FIX | 2024-01-01 | 0 |  |  | 86.17% | 116.1% | 116.1% | 0 | 35.86% | 4410 | 3800 | 610 |  | 0 | 0 | 0 | 4410 | 0 | -610 | 0 | 4410 | 0 | 0 | 0 | 0 | 0 | 24% | 59.86% | 0% | -24% |  | 95 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23628 | Design Assurance | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -6.67% | 0 | 3909 | -3909 |  | 0 | 0 | 4454.80 | 0 | 638.84 | 3909 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 7% | 0.33% | 0% | -7% |  | 15.05 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23002 | WoT MAJ Transit Flag Stress | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 30.9% | 323.7% | 323.7% | 0 | 53.84% | 4735 | 1463 | 3272 |  | 0 | 2242.5 | 0 | 4735 | 0.6 | 1 | 0 | 4735 | 0 | 0 | 0 | 0 | 0 | 10% | 63.84% | 0% | -10% |  | 45 | [5 empty] | 3273
1721 | 2024-01-18 00:29 | P23729 | Honda Tooling | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX | [5 empty] | 0% | 0% | 0 | -6.91% | 0 | 4832 | -4832 |  | 0 | 0 | 14430.00 | 0 | 7 | 4832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21% | 14.09% | 14.09% | -6.91% |  | 42.2 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23744 | Model Factory | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  |  | 1.997% | 0% | 0% | 0 | 6.04% | 262300 | 5238 | 257062 |  | 0 | 0 | 0 | 0 | 13 | 5238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 34.04% | 34.04% | 6.04% |  | 50.6 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23607 | SAFRAN - A330neo Turnover Frame | Gary Kempster | TOO | SAFRAN SEATS GB LIMITED | MPE | Level 3 | FIX |  |  |  |  | 95.68% | 0% | 0% | 0 | -19.75% | 8736 | 8359 | 377 |  | 0 | 0 | 0 | 0 | 10030.8 | 8359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23% | 3.25% | 0% | -23% |  | 52 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23274 | ME Support (Aim Altitude - Cambridge) | James Montgomery | AVI | AVIC CABIN SYSTEMS (UK) LIMITED | ME | Level 3 | FIX | 2023-08-18 | 0 |  |  | 51.88% | 56.29% | 56.29% | 0 | -0.17% | 17280 | 8964 | 8316 |  | 0 | 0 | 0 | 5046 | 4701.24 | 3918 | 0 | 5046 | 0 | 0 | 0 | 0 | 0 | 21% | 20.83% | 0% | -21% |  | 48 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23283 | Spirit Tooling Audit | Charidimos Valadakis | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-05-03 | 0 |  |  | 97.23% | 48.57% | 48.57% | 0 | -7.99% | 9910 | 9635 | 275 |  | 0 | 0 | 0 | 4680 | 5946.05 | 4955 | 0 | 4680 | N/A | N/A | N/A | N/A | 0 | 7% | -0.99% | 0% | -7% |  | 34.41 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23127 | Loft Hall Design Support | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 101% | 99.06% | 99.06% | 0 | -9.55% | 9680 | 9772 | -92 |  | 0 | 0 | 0 | 9680 | 110.4 | 92 | 0 | 9680 | N/A | N/A | N/A | N/A | 0 | 41% | 31.45% | 0% | -41% |  | 44 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23630 | 2Excel CFD Analysis Support | Dushan Fernando | BAX | STIRLING DYNAMICS LTD | MPE | Level NC | FIX |  |  |  |  | 61.2% | 100% | 100% | 0 | -1.87% | 16195 | 9911 | 6284 |  | 0 | 0 | 0 | 9912 | 0 | 0 | 0 | 9912 | 0 | 0 | 0 | 0 | 0 | 26% | 24.13% | 0% | -26% |  | 64.78 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23741 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  |  | 1.938% | 0% | 0% | 0 | -0.07% | 526262 | 10197 | 516065 |  | 0 | 0 | 0 | 0 | 13 | 10197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 27.93% | 27.93% | -0.07% |  | 39.37 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23313 | Laser Trim Fixtures | Gary Kempster | TOO | ALKEN ENGINEERING LIMITED | MPE | Level 3 | FIX | 2023-11-20 | 0 |  |  | 89.87% | 111.3% | 111.3% | 0 | 0.53% | 13770 | 12375 | 1395 |  | 0 | 0 | 0 | 13770 | 0 | -1395 | 0 | 13770 | 0 | 0 | 0 | 0 | 0 | 17% | 17.53% | 0% | -17% |  | 45 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P22761 | Red Bull Chassis Spit | James Montgomery | TOO | MANUFAX ENGINEERING LTD | MPE | Level 3 | FIX | 2022-11-15 | 0 |  |  | 72.19% | 96.98% | 96.98% | 0 | 7.92% | 12961 | 9356 | 3605 |  | 0 | 0 | 0 | 9073 | 4666.39 | 3889 | 0 | 9073 | 0 | 0 | 0 | 0 | 0 | 23% | 30.92% | 0% | -23% |  | 42.19 | [5 empty] | 3606
1721 | 2024-01-18 00:29 | P23739 | Lifing Services DACs | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  |  | 2.103% | 0% | 0% | 0 | 3.65% | 656508 | 13805 | 642703 |  | 0 | 0 | 0 | 0 | 13 | 13805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 31.65% | 31.65% | 3.65% |  | 37.98 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23433 | Cavendish | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 32.81% | 100% | 100% | 0 | -0.34% | 42240 | 13859 | 28381 |  | 0 | 0 | 0 | 13859 | 0 | 0 | 0 | 13859 | N/A | N/A | N/A | N/A | 0 | 7% | 6.66% | 0% | -7% |  | 43.93 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23350 | Spirit 2023 - Stress Approve Man Serv (DH) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 14.15% | 72.64% | 72.64% | 0 | -0.29% | 97920 | 13860 | 84060 |  | 0 | 0 | 0 | 10068 | 4550.4 | 3792 | 0 | 10068 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23635 | Engineering Services: FAI Support | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 38.25% | 0% | 0% | 0 | -3.61% | 37230 | 14242 | 22988 |  | 0 | 0 | 0.00 | 0 | 123.12 | 14242 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 8% | 4.39% | 4.39% | -3.61% |  | 38.7 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23651 | PMO Spirit | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 24.51% | 0 | 16650 | -16650 |  | 0 | 0 | 30800.00 | 0 | 114.84 | 16650 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 24.51% | 24.51% | 24.51% |  | 36 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23700 | IPDT Leads | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 14.48% | 0 | 16971 | -16971 |  | 0 | 0 | 22200.00 | 0 | 63 | 16971 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 22% | 36.48% | 36.83% | 14.83% |  | 61.88 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23343 | Spirit 2023 - John Agnew | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-08-09 | 0 |  |  | 28.56% | 86.27% | 86.27% | 0 | -0.02% | 65120 | 18601 | 46519 |  | 0 | 0 | 0 | 16047 | 3064.49 | 2554 | 0 | 16047 | N/A | N/A | N/A | N/A | 0 | 7% | 6.98% | 0% | -7% |  | 34.51 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23355 | Spirit Tooling Support 2023 | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-23 | 0 |  |  | 22.93% | 89.03% | 89.03% | 0 | -0.82% | 91800 | 21053 | 70747 |  | 0 | 0 | 0 | 18743 | 2773.01 | 2311 | 0 | 18743 | 0 | 0 | 0 | 0 | 0 | 20% | 19.18% | 0% | -20% |  | 44.46 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23642 | MRB Belfast Support | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -17.41% | 0 | 22542 | -22542 |  | 2170 | 2169.99 | 30800.00 | 0 | 102.1 | 22542 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | -17.41% | -15.53% | -15.53% |  | 38.52 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23351 | Spirit 2023 - Design Man Serv (KL) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 26.47% | 93.15% | 93.15% | 0 | 0.09% | 93840 | 24840 | 69000 |  | 0 | 0 | 0 | 23138 | 2042.4 | 1702 | 0 | 23138 | 0 | 0 | 0 | 0 | 0 | 26% | 26.09% | 0% | -26% |  | 46 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23356 | Spirit 2023 - Design Man Serv (AH) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX | 2023-08-09 | 1 |  |  |  | 76.66% | 0.001332% | 23018.4 | 0.48% | 0 | 25023 | -25023 |  | 0 | 0 | 25300.00 | 19182 | 30027.7 | 5841 | 23018 | 0.33333 | 0 | 0 | 0 | 23018.4 | 23018.4 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P22884 | Spirit Shorts Config Eng | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 66.3% | 100.1% | 100.1% | 0 | 0.56% | 38976 | 25842 | 13134 |  | 0 | 0 | 0 | 25863 | 0 | 0 | 0 | 25863 | N/A | N/A | N/A | N/A | 0 | 7% | 7.56% | 0% | -7% |  | 20.3 | [5 empty] | 21
1721 | 2024-01-18 00:29 | P23354 | Spirit 2023 - Design Man Serv (PC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 27.97% | 99.36% | 99.36% | 0 | 0.48% | 93840 | 26249 | 67591 |  | 0 | 0 | 0 | 26082 | 200.38 | 167 | 0 | 26082 | 0 | 0 | 0 | 0 | 0 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P22756 | A350 FLE Design Checker | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2022-03-23 | 1 |  |  | 68.39% | 119.7% | 119.7% | 0 | 16.46% | 34898 | 23867 | 11031 |  | 23867 | 24342.3 | 0 | 28571 | 0.06 | 0 | 0 | 28571 | N/A | N/A | N/A | N/A | 0 | 0% | 16.46% | 0% | 0% |  | 0 | [5 empty] | 4704
1721 | 2024-01-18 00:29 | P23458 | Spirit Belfast Tooling Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-08-11 | 0 |  |  | 101.3% | 94.65% | 94.65% | 0 | 8.64% | 30384 | 30785 | -401 |  | 0 | 0 | 0 | 29139 | 1974.96 | 1646 | 0 | 29139 | N/A | N/A | N/A | N/A | 0 | 7% | 15.64% | 0% | -7% |  | 42.2 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23685 | DAC LUC Support and Recompliance | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  |  | 4.59% | 0% | 0% | 0 | 1.23% | 720000 | 33051 | 686949 |  | 0 | 0 | 0 | 0 | 13 | 33051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 29.23% | 29.23% | 1.23% |  | 73.24 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23365 | GKN 777x Lip Skin Fixture | Steven Lawton | TOO | GKN AEROSPACE SERVICES LTD | MPE | Level 3 | FIX | 2023-10-12 | 1 |  |  | 41.91% | 113.2% | 18.86% | 37544.22 | -9.26% | 79161 | 33176 | 45985 |  | 5110 | 5109.88 | 0 | 37544 | 33175.67 | -4369 | 37544 | 6257.3333 | 0 | 37544.22 | 0 | 0 | 37544.22 | 22% | 12.74% | 0% | -22% |  | 56 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P22768 | MRB Onsite Support - Spirit Belfast | James Montgomery | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2023-07-27 | 0 |  |  |  | 0% | 0% | 0 | -17.07% | 0 | 34614 | -34614 |  | 0 | 0 | 36800 | 0 | 41536.8 | 34614 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 10% | -7.07% | 0% | -10% |  | 36 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23051 | Spirit Shorts A350 PAX Door | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 3A | REIM |  |  |  |  | 205.9% | 105.4% | 105.4% | 0 | -0.63% | 18216 | 37513 | -19297 |  | 0 | 0 | 0 | 39537 | 0 | 0 | 0 | 39537 | N/A | N/A | N/A | N/A | 0 | 30% | 29.37% | 0% | -30% |  | 46 | [5 empty] | 2024
1721 | 2024-01-18 00:29 | P22752 | Tooling WoT - 2021 (Spirit) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | REIM | 2023-05-03 | 0 |  |  | 101.1% | 74.02% | 74.02% | 0 | -8.5% | 41525 | 41982 | -457 |  | 0 | 0 | 0 | 31076 | 13087.42 | 10906 | 0 | 31076 | N/A | N/A | N/A | N/A | 0 | 0% | -8.5% | 0% | 0% |  | 39.09 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23322 | GKN T Tomblin 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2023-12-31 | 3 |  |  | 83.13% | 100% | 88.98% | 691.2 | -0.33% | 58952 | 49008 | 9944 |  | 0 | 0 | 0 | 49008 | 71.34 | 0 | 6480 | 43608 | N/A | N/A | N/A | N/A | 691.2 | 17% | 16.67% | 0% | -17% |  | 48 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P22760 | SA Leading Edge Transport Media ('A' Frames) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-11-15 | 1 |  |  | 85.99% | 110.7% | 116.3% | -3082.8 | 3.97% | 53481 | 45986 | 7495 |  | 42804 | 42804 | 0 | 50912 | 0 | 0 | -3083 | 53481.1667 | 0 | 0 | 0 | -3082.8 | -3082.8 | 6% | 9.97% | 0% | -6% |  | 42 | [5 empty] | 4926
1721 | 2024-01-18 00:29 | P23341 | Spirit 2023 - Tom McFarlane | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 96.69% | 93.26% | 73.31% | 0 | -0.01% | 54282 | 52484 | 1798 |  | 0 | 0 | 0 | 48945 | 105.11 | 3539 | 12560 | 38478.3333 | N/A | N/A | N/A | N/A | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23382 | Performance Modelling | Dushan Fernando | BDX | MBDA UK LIMITED | MPE | Level NC | REIM | 2023-07-09 | 1 |  |  | 40.95% | 79.09% | 79.09% | 0 | -16.36% | 170010 | 69626 | 100384 |  | 14560 | 14659.9 | 0 | 55066 | 0 | 0 | 0 | 55066 | N/A | N/A | N/A | N/A | 0 | 20% | 3.64% | 0% | -20% |  | 77.05 | [5 empty] | -14560
1721 | 2024-01-18 00:29 | P23551 | Ian Berry 2023 H2 | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  |  | 74.7% | 48.83% | 48.83% | 0 | 13.91% | 75810 | 56630 | 19180 |  | 0 | 0 | 0 | 27652 | 113.4 | 28978 | 0 | 27652 | N/A | N/A | N/A | N/A | 0 | 20% | 33.91% | 0% | -20% |  | 75.81 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23193 | Spirit Shorts Stephen Greer | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 92.25% | 96.38% | 72.68% | 6679.37 | 2.28% | 61472 | 56709 | 4763 |  | 0 | 0 | 0 | 54656 | 150.24 | 2054 | 16131 | 41213.5 | N/A | N/A | N/A | N/A | 6679.37 | 29% | 31.28% | 34.03% | 5.03% |  | 34.92 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23349 | Spirit 2023 - Stress Approve Man Serv (SB) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 58.24% | 80.05% | 80.05% | 0 | -0.29% | 97920 | 57024 | 40896 |  | 0 | 0 | 0 | 45648 | 13651.2 | 11376 | 0 | 45648 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23560 | NJEWCS TAF202302 SM | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level 2 | FIX |  |  |  |  | 72.43% | 67.76% | 67.76% | 0 | 12.13% | 81500 | 59029 | 22471 |  | 0 | 0 | 0 | 40000 | 83.22 | 19029 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 28% | 40.13% | 40.4% | 12.4% |  | 73.01 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23465 | A220 ToW Design Offload (Wing) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 45.91% | 92.02% | 62.29% | 0 | -3.77% | 132000 | 60605 | 71395 |  | 0 | 0 | 0 | 55768 | 102.74 | 4836 | 21623 | 37748.8333 | N/A | N/A | N/A | N/A | 0 | 20% | 16.23% | 18.97% | -1.03% |  | 42.8 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23586 | Project Management Support | Peter Bowen | BDX | MBDA UK LIMITED | MPE | Level NC | REIM |  |  |  |  | 76.48% | 90.42% | 71.06% | 0 | -25.72% | 80000 | 61184 | 18816 |  | 1141 | 1140.6 | 0 | 55320 | 48.84 | 5864 | 14208 | 43480 | N/A | N/A | N/A | N/A | 0 | 49% | 23.28% | 24.32% | -24.68% |  | 80 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23561 | SAAB | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  |  | 82.46% | 121.1% | 96.66% | 0 | 3.5% | 67485 | 55649 | 11836 |  | 0 | 0 | 0 | 67399 | 67.01 | -4408 | 16332 | 53789 | N/A | N/A | N/A | N/A | 0 | 16% | 19.5% | 0% | -16% |  | 36.82 | [5 empty] | 7342
1721 | 2024-01-18 00:29 | P22967 | Spirit 2022 - Channapa Laxmeshwar | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2023-01-26 | 2 |  |  | 69.69% | 121.3% | 121.3% | 0 | 9.53% | 75159 | 52376 | 22783 |  | 52376 | 54898.1 | 0 | 63509 | 0.42 | 0 | 0 | 63509 | N/A | N/A | N/A | N/A | 0 | 8% | 17.53% | 0% | -8% |  | 0 | [5 empty] | 11133
1721 | 2024-01-18 00:29 | P23342 | Spirit 2023 - Channapa Laxmeshwar | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 78.75% | 104.3% | 88.16% | 0 | -2.64% | 79348 | 62484 | 16864 |  | 62484 | 63539 | 0 | 65178 | 83.77 | 157 | 12110 | 55086.3333 | N/A | N/A | N/A | N/A | 0 | 7% | 4.36% | 0% | -7% |  | 0 | [5 empty] | 2850
1721 | 2024-01-18 00:29 | P23340 | Spirit 2023 - John Cole | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 92.16% | 90.86% | 72.91% | 0 | -0.01% | 75065 | 69177 | 5888 |  | 0 | 0 | 0 | 62852 | 104.54 | 6325 | 14894 | 50440.3333 | N/A | N/A | N/A | N/A | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 39.78 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23171 | Spirt Shorts Weights Eng | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 81.27% | 117.6% | 107.5% | 0 | -6.62% | 71760 | 58316 | 13444 |  | 58316 | 76495.95 | 0 | 68582 | 9492.98 | 2004 | 7088 | 62675.3333 | N/A | N/A | N/A | N/A | 0 | 24% | 17.38% | 0% | -24% |  | 0 | [5 empty] | 12270
1721 | 2024-01-18 00:29 | P23438 | A220 Spirit Shorts DTC - Stephen Corry | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 150.2% | 56.93% | 56.93% | 0 | -5.5% | 47251 | 70962 | -23711 |  | 0 | 0 | 23745 | 40400 | 123.51 | 30562 | 0 | 40400 | N/A | N/A | N/A | N/A | 0 | 21% | 15.5% | 13.04% | -7.96% |  | 49.69 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23336 | Spirit 2023 - Neil Rampling | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 53.8% | 91.41% | 66.44% | 0 | -0.01% | 133902 | 72042 | 61860 |  | 0 | 0 | 0.00 | 65851 | 136 | 6191 | 21586 | 47862.6667 | N/A | N/A | N/A | N/A | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23080 | Spirit Shorts DManagement Cairan Cullen | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 48.55% | 99.53% | 93.91% | 0 | -0.77% | 149600 | 72627 | 76973 |  | 0 | 0 | 0 | 72284 | 104.69 | 342 | 4892 | 68207.3333 | N/A | N/A | N/A | N/A | 0 | 24% | 23.23% | 17.46% | -6.54% |  | 44.47 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23583 | Castalla - Test Rig Design | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 109.8% | 82.63% | 55.53% | 0 | -7.24% | 67520 | 74139 | -6619 |  | 0 | 0 | 9706 | 61258 | 136.06 | 12881 | 24105 | 41170.5 | N/A | N/A | N/A | N/A | 0 | 21% | 13.76% | 14.42% | -6.58% |  | 42.38 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23699 | A220 Stress Checkers | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -2.26% | 0 | 74171 | -74171 |  | 0 | 0 | 86440 | 0 | 63 | 74171 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 22% | 19.74% | 19.62% | -2.38% |  | 61.88 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23545 | Ultra CSS continuation 2023 H2 | Natalie Sinclair | ULT | ULTRA SONAR SYSTEMS LIMITED | EES | Level NC | REIM |  |  |  |  | 98.99% | 58.42% | 58.42% | 0 | 2.3% | 76000 | 75235 | 765 |  | 0 | 0 | 0 | 43956 | 109.26 | 31279 | 0 | 43956 | N/A | N/A | N/A | N/A | 0 | 23% | 25.3% | 0% | -23% |  | 80 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23600 | MBDA EXP-EE-023 Bristone Certification | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 59.65% | 100% | 84.61% | 0 | 0.4% | 126600 | 75517 | 51083 |  | 0 | 0 | 0 | 75517 | 36.4 | 0 | 13942 | 63898.6667 | N/A | N/A | N/A | N/A | 0 | 41% | 41.4% | 0% | -41% |  | 78.5 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P22505 | Spirit MRB Engineering Support 2021 | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 1 |  |  | 91.17% | 100% | 95.78% | 4020.48 | 21.2% | 87110 | 79415 | 7695 |  | 0 | 0 | 0 | 79415 | 4020.48 | 0 | 4020 | 76065 | 0 | 0 | 0 | 4020.48 | 4020.48 | 0% | 21.2% | 0% | 0% |  | 41.88 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23375 | GKN Jaap Peters NL 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2023-12-31 | 6 |  |  | 84.76% | 115.8% | 63.08% | 0 | -15.19% | 89795 | 76111 | 13684 |  | 76111 | 85308.08 | 0.00 | 88129 | 160.52 | -8168 | 48143 | 48009.8333 | N/A | N/A | N/A | N/A | 0 | 20% | 4.81% | 0% | -20% |  | 0 | [5 empty] | 3850
1721 | 2024-01-18 00:29 | P22885 | ME Support (Baxi) | James Montgomery | HUV | BAXI HEATING UK LIMITED | ME | Level 3 | FIX | 2023-01-12 | 0 |  |  | 68.78% | 108.7% | 108.7% | 0 | 13.05% | 106633 | 73340 | 33293 |  | 0 | 0 | 0 | 79748 | 1531.35 | 1276 | 0 | 79748 | 0 | 0 | 0 | 0 | 0 | 15% | 28.05% | 0% | -15% |  | 44.37 | [5 empty] | 7684
1721 | 2024-01-18 00:29 | P23079 | Spirit Shorts Nomenclature | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 92% | 94.79% | 72.39% | 10554.48 | 1.73% | 88455 | 81376 | 7079 |  | 0 | 0 | 0.00 | 77138 | 274.57 | 4237 | 21879 | 58905.5 | N/A | N/A | N/A | N/A | 10554.48 | 20% | 21.73% | 25.23% | 5.23% |  | 30.66 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23335 | GKN S McConnell 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2023-12-31 | 4 |  |  | 96.61% | 100% | 65.44% | 0 | 0.74% | 87420 | 84459 | 2961 |  | 0 | 0 | 0 | 84459 | 152.73 | 0 | 35024 | 55272.3333 | N/A | N/A | N/A | N/A | 0 | 15% | 15.74% | 0% | -15% |  | 47 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P22965 | Spirit 2022 - Design Man Serv (AH) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 1 |  |  | 106.7% | 96.66% | 92.02% | 4759.75 | 3.14% | 80080 | 85441 | -5361 |  | 0 | 0 | 0 | 82589 | 8182.59 | 2852 | 4760 | 78622.3333 | 0 | 0 | 0 | 4759.75 | 4759.75 | 14% | 17.14% | 0% | -14% |  | 42.44 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23523 | Applique Armour Support | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 0 |  |  | 101.6% | 98.47% | 98.47% | 0 | 3.42% | 84300 | 85607 | -1307 |  | 0 | 0 | 0 | 84300 | 26.86 | 1307 | 0 | 84300 | 0 | 0 | 0 | 0 | 0 | 25% | 28.42% | 0% | -25% |  | 64.29 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P22964 | Spirit 2022 - MRB Man Serv (JC) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 100.6% | 97.95% | 97.95% | 0 | 1.91% | 85435 | 85960 | -525 |  | 0 | 0 | 0 | 84200 | 2112.62 | 1761 | 0 | 84200 | 0 | 0 | 0 | 0 | 0 | 16% | 17.91% | 0% | -16% |  | 42.69 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P22963 | Spirit 2022 - Design Man Serv (PC) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 1 |  |  | 108.6% | 104% | 94.46% | 9938.48 | 3.18% | 80080 | 86927 | -6847 |  | 0 | 0 | 0 | 90390 | 5782.63 | -3463 | 9938 | 82108.3333 | 0 | 0 | 0 | 9938.48 | 9938.48 | 13% | 16.18% | 0% | -13% |  | 42.39 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23648 | EXP-032 Delivery of Datalink Eng support - FCAS AP | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 23.56% | 83.44% | 0.000572% | 0 | 4.27% | 371000 | 87418 | 283582 |  | 265 | 265.32 | 0 | 72943 | 106.08 | 14475 | 87531 | 0.5 | N/A | N/A | N/A | N/A | 0 | 22% | 26.27% | 24.78% | 2.78% |  | 104.44 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23353 | Spirit 2023 - MRB Man Serv (JC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  |  | 97.08% | 76.99% | 69.2% | 0 | -0.22% | 91800 | 89123 | 2677 |  | 0 | 0 | 0 | 68615 | 144.46 | 20507 | 8330 | 61673.3333 | 0 | 0 | 0 | 8329.5 | 0 | 18% | 17.78% | 0% | -18% |  | 45 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23352 | Spirit 2023 - Stress Approve Man Serv (CC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  |  | 97.28% | 73.39% | 62.11% | 0 | -2.37% | 97920 | 95256 | 2664 |  | 0 | 0 | 0 | 69912 | 173.69 | 25344 | 12902 | 59160.3333 | 0 | 0 | 0 | 12902.4 | 0 | 18% | 15.63% | 15.63% | -2.37% |  | 48 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P22918 | Spirit Shorts Graduates | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 88.31% | 72.43% | 72.43% | 0 | 9.35% | 110000 | 97136 | 12864 |  | 0 | 0 | 0.00 | 70352 | 143.45 | 26784 | 0 | 70352 | N/A | N/A | N/A | N/A | 0 | 7% | 16.35% | 18.07% | 11.07% |  | 23.16 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23282 | Tooling Support (MBDA) | Dushan Fernando | BDV | MBDA UK LIMITED | ME | Level 3 | FIX |  |  |  |  | 97.43% | 98.08% | 90.75% | 0 | -10.2% | 104834 | 102144 | 2690 |  | 0 | 0 | 0 | 100185 | 40.88 | 1959 | 8984 | 92698.3333 | 8983.8 | 0 | 0 | 0 | 0 | 30% | 19.8% | 29.87% | -0.13% |  | 49.68 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23270 | Shorts Project X | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 73.99% | 83.51% | 70.1% | 9715.2 | 1.03% | 142248 | 105243 | 37005 |  | 0 | 0 | 0 | 87889 | 142.86 | 17354 | 16933 | 73778.1667 | N/A | N/A | N/A | N/A | 9715.2 | 13% | 14.03% | 10.99% | -2.01% |  | 45.41 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23667 | Safety Systems Engineer | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 27.61% | 95.9% | 0% | 0 | -6.42% | 398000 | 109890 | 288110 |  | 0 | 0 | 0 | 105380 | 122.85 | 4510 | 126456 | 0 | N/A | N/A | N/A | N/A | 0 | 47% | 40.58% | 29.09% | -17.91% |  | 110 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P22883 | Spirit Shorts Evtol PMO C. Hatton | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 59.2% | 99.04% | 82.94% | 0 | -12.59% | 185800 | 110000 | 75800 |  | 0 | 0 | 0 | 108947 | 103.48 | 1053 | 21252 | 91237 | N/A | N/A | N/A | N/A | 0 | 26% | 13.41% | 26.14% | 0.14% |  | 36.2 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23421 | A220 DTC | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 87.9% | 93.27% | 57.45% | 0 | -12.17% | 130625 | 114824 | 15801 |  | 0 | 0 | 0.00 | 107094 | 108.58 | 7730 | 49358 | 65962.3333 | N/A | N/A | N/A | N/A | 0 | 10% | -2.17% | 0.58% | -9.42% |  | 45.1 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P22736 | WoT Fixed Leading Edge - Industrial | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 106.7% | 93.42% | 91.32% | 3019.54 | 0.01% | 112196 | 119668 | -7472 |  | 0 | 0 | 0 | 111797 | 12465.69 | 7872 | 3020 | 109280.3333 | 0 | 0 | 0 | 3019.54 | 3019.54 | 7% | 7.01% | 0% | -7% |  | 32.26 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23437 | Embedded Software Engineer | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 83.3% | 93.12% | 84.27% | 0 | -6.41% | 150150 | 125082 | 25068 |  | 738 | 737.86 | 0 | 116473 | 52.12 | 8609 | 13282 | 105404.6667 | N/A | N/A | N/A | N/A | 0 | 22% | 15.59% | 15.92% | -6.08% |  | 78.5 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P22861 | WoT FLE Lifting & Handling Tools | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2023-06-14 | 1 |  |  | 65.17% | 101.6% | 101.6% | 0 | 12.01% | 173987 | 113382 | 60605 |  | 50078 | 58423.58 | 0 | 115204 | 12813.9 | 10678 | 0 | 115204 | 0 | 0 | 0 | 0 | 0 | 1% | 13.01% | 0% | -1% |  | 45 | [5 empty] | 12500
1721 | 2024-01-18 00:29 | P23518 | Systems Engineering support to FCAS | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 66.11% | 92.55% | 78.87% | 0 | 1.47% | 193737 | 128082 | 65655 |  | 3927 | 3927.4 | 0 | 118539 | 62.43 | 9543 | 21019 | 101023.1667 | N/A | N/A | N/A | N/A | 0 | 30% | 31.47% | 3.18% | -26.82% |  | 65.78 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23386 | Software Development - BMS | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 90% | 97.27% | 88.76% | 0 | 4.27% | 149650 | 134690 | 14960 |  | 0 | 0 | 0 | 131017 | 41.41 | 3674 | 13753 | 119556.1667 | N/A | N/A | N/A | N/A | 0 | 18% | 22.27% | 22.29% | 4.29% |  | 78.5 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23464 | A220 Project X Design Offload | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 76.72% | 96.32% | 72.27% | 0 | -3.72% | 180400 | 138400 | 42000 |  | 0 | 0 | 0.00 | 133307 | 108.99 | 5093 | 39945 | 100019.5 | N/A | N/A | N/A | N/A | 0 | 21% | 17.28% | 17.73% | -3.27% |  | 42.9 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23533 | External Stowage Design and Detail Support | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 0 |  |  | 136.5% | 73.24% | 73.24% | 0 | 6.33% | 105000 | 143369 | -38369 |  | 0 | 0 | 49220 | 105000 | 129.23 | 35000 | 0 | 105000 | 0 | 0 | 0 | 0 | 0 | 24% | 30.33% | 0% | -24% |  | 60.04 | [5 empty] | -3369
1721 | 2024-01-18 00:29 | P23508 | Verification and Validation | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 67.31% | 93.55% | 62.88% | 0 | 11.16% | 212950 | 143341 | 69609 |  | 0 | 0 | 0 | 134098 | 83.46 | 9243 | 52752 | 90138 | N/A | N/A | N/A | N/A | 0 | 24% | 35.16% | 35.89% | 11.89% |  | 78.5 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P22954 | Technical Support Step 1 | Owain Jones | HUV | HUARUI SPIRIT AEROSPACE MANUFACT | ME | Level 2 | REIM |  |  |  |  | 94.81% | 58.01% | 58.01% | 0 | 0.31% | 155501 | 147432 | 8069 |  | 23043 | 23043 | 0 | 85525 | 61906.09 | 61906 | 0 | 85525 | N/A | N/A | N/A | N/A | 0 | 30% | 30.31% | 0% | -30% |  | 60.79 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23506 | ASTER Mid-Life Refurbishment Project Manager | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 66.33% | 93.61% | 83.11% | 0 | 0.95% | 224900 | 149179 | 75721 |  | 2329 | 2329.13 | 0 | 139651 | 44.67 | 9528 | 18810 | 123976 | N/A | N/A | N/A | N/A | 0 | 25% | 25.95% | 26.36% | 1.36% |  | 110 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P22440 | Spirit Managed Service - F&DT and Static Approval | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 3 |  |  | 88.56% | 92.56% | 92.56% | 0 | 11.51% | 173500 | 153656 | 19844 |  | 52115 | 55720 | 0 | 142225 | 13717.36 | 11431 | 0 | 142225 | 0 | 0 | 0 | 0 | 0 | 0% | 11.51% | 0% | 0% |  | 44.73 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23505 | EXP-022 Meteor TBUS T&E support | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 62.98% | 95.61% | 33.95% | 0 | -0.21% | 246744 | 155406 | 91338 |  | 0 | 0 | 0 | 148579 | 224.12 | 6827 | 114991 | 52753.1667 | N/A | N/A | N/A | N/A | 0 | 20% | 19.79% | 15.4% | -4.6% |  | 89.83 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23373 | Raytheon Michael Bellini | Natalie Sinclair | RAS | RAYTHEON UNITED KINGDOM LIMITED | EES | Level NC | REIM |  |  |  |  | 74.22% | 76.98% | 76.98% | 0 | -8.45% | 214367 | 159106 | 55261 |  | 0 | 0 | 0 | 122483 | 91.87 | 36624 | 0 | 122483 | N/A | N/A | N/A | N/A | 0 | 45% | 36.55% | 36.62% | -8.38% |  | 91.61 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23650 | MBDA Recruitment Management costs | Brian Maddrell | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 30.99% | 0 | 159174 | -159174 |  | 0 | 0 | 266000 | 0 | 96.32 | 159174 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 3% | 33.99% | 33.21% | 30.21% |  | 87.44 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23242 | Physical Architecture & System Engineering Support | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 55.9% | 97.85% | 92.75% | 0 | 11.09% | 305459 | 170752 | 134707 |  | 776 | 775.55 | 0 | 167081 | 38.28 | 3671 | 10456 | 158367.6667 | N/A | N/A | N/A | N/A | 0 | 15% | 26.09% | 6.68% | -8.32% |  | 78.14 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23524 | Bombardier Regional Jets (BRJ) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 119.1% | 62.49% | 40.83% | 0 | -5.12% | 146288 | 174175 | -27887 |  | 0 | 0 | 46750 | 108838 | 110.04 | 65336 | 45261 | 71120.5 | N/A | N/A | N/A | N/A | 0 | 18% | 12.88% | 11.84% | -6.16% |  | 44.02 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23008 | Spirit Shorts Project Rachel | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 85.87% | 91.32% | 79.5% | 0 | -7.72% | 228880 | 196531 | 32349 |  | 0 | 0 | 0 | 179473 | 178.24 | 17058 | 27878 | 156241.3333 | N/A | N/A | N/A | N/A | 0 | 13% | 5.28% | -2.79% | -15.79% |  | 46.04 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23019 | EXP034-B Actuator Development | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 102.9% | 90.07% | 90.07% | 0 | -14.61% | 215541 | 221819 | -6278 |  | 11901 | 11992.81 | 0.00 | 199797 | 26.97 | 5045 | 0 | 199797 | N/A | N/A | N/A | N/A | 0 | 34% | 19.39% | 30.52% | -3.48% |  | 58.45 | [5 empty] | -16977
1721 | 2024-01-18 00:29 | P23316 | Model Factory IL and AW | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX | 2024-01-12 | 13 |  |  | 88.13% | 104.1% | 96.46% | 0 | 2.12% | 250000 | 220328 | 29672 |  | 0 | 0 | 0 | 229409 | 29.08 | -913 | 20249 | 212534.8333 | 0 | 20248.8 | 0 | 0 | 0 | 30% | 32.12% | 29.97% | -0.03% |  | 45.31 | [5 empty] | 8168
1721 | 2024-01-18 00:29 | P23007 | EXP-006A - Brimstone 3 | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 91.62% | 97.6% | 87.29% | 0 | -8.76% | 264150 | 242019 | 22131 |  | 0 | 0 | 0 | 236210 | 90.91 | 5779 | 29956 | 211246.6667 | N/A | N/A | N/A | N/A | 0 | 30% | 21.24% | 29.94% | -0.06% |  | 68.85 | [5 empty] | -30
1721 | 2024-01-18 00:29 | P23694 | Systems Portfolio | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 41.24% | 84.35% | 41.6% | 0 | 7.03% | 591943 | 244121 | 347822 |  | 158 | 157.75 | 0 | 205909 | 45 | 38212 | 125228 | 101552.3333 | N/A | N/A | N/A | N/A | 0 | 21% | 28.03% | 26.76% | 5.76% |  | 94.98 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23317 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX | 2024-01-12 | 16 |  |  | 95.89% | 104.3% | 98.16% | 0 | 4.04% | 251800 | 241447 | 10353 |  | 0 | 0 | 0 | 251800 | 28.47 | -1177 | 17760 | 237000 | 0 | 17760 | 0 | 0 | 0 | 25% | 29.04% | 40.2% | 15.2% |  | 36.29 | [5 empty] | 9176
1721 | 2024-01-18 00:29 | P22798 | CO2MAP MGSE | Harry James Kellett | DTW | THALES ALENIA SPACE UK (60DAYS) | EES | Level 2 | REIM | 2023-11-08 | 3 |  |  | 85.75% | 105% | 101.6% | 38880 | 3.94% | 252086 | 216158 | 35928 |  | 0 | 0 | 0 | 227053 | 10299.56 | 25097 | 8840 | 219686.3333 | N/A | N/A | N/A | N/A | 38880 | 29% | 32.94% | 0% | -29% |  | 50.31 | [5 empty] | 35992
1721 | 2024-01-18 00:29 | P21463 | Safety & Monitoring Systems at DM Beith & Gosport | Harry James Kellett | BXW | MOD | EES | Level 2 | FIX |  |  |  |  | 73.95% | 135.2% | 135.2% | 0 | -27.87% | 349405 | 258401 | 91004 |  | 55119 | 65627.41 | 11769 | 349387 | 0 | -90986 | 0 | 349387 | 0 | 0 | 0 | 0 | 0 | 48% | 20.13% | 37.93% | -10.07% |  | 52.14 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23308 | NATO JEWCS | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  |  | 75.12% | 88.02% | 88.02% | 0 | -2.85% | 356307 | 267644 | 88663 |  | 338 | 338.05 | 0 | 235576 | 110.3 | 32068 | 0 | 235576 | N/A | N/A | N/A | N/A | 0 | 24% | 21.15% | 12.94% | -11.06% |  | 75.81 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23045 | Shotgun Adaptors - 10 Sets | Harry James Kellett | BDW | MBDA UK LIMITED | EES | Level 2 | FIX |  |  |  |  | 74.73% | 95.15% | 95.15% | 0 | -19.12% | 399276 | 298392 | 100884 |  | 214430 | 214551.21 | 0 | 283926 | 394.25 | 14467 | 0 | 283926 | 0 | 0 | 0 | 0 | 0 | 29% | 9.88% | 0% | -29% |  | 55.76 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P22515 | Shorts A220 100/300 ALI Phase III | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 75.83% | 97.92% | 93.92% | 0 | 1.06% | 400629 | 303791 | 96838 |  | 3451 | 3450.98 | 0 | 297465 | 88.95 | 6326 | 14584 | 285311.6667 | N/A | N/A | N/A | N/A | 0 | 10% | 11.06% | 15.63% | 5.63% |  | 40.26 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P22953 | Spirit Shorts eVTOL | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 103.1% | 79.36% | 79.36% | 0 | -6.74% | 324272 | 334484 | -10212 |  | 66697 | 67387.9 | 0 | 265432 | 179.02 | 69052 | 0 | 265432 | N/A | N/A | N/A | N/A | 0 | 17% | 10.26% | 0% | -17% |  | 46.19 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P22842 | ME Support (Aim Altitude) | James Montgomery | AVI | AIM ALTITUDE UK LIMITED | ME | Level 3 | FIX | 2023-06-14 | 4 |  |  | 99.31% | 100.5% | 86.63% | 57290.84 | 0.49% | 346294 | 343918 | 2376 |  | 2910 | 2909.86 | 0 | 345673 | 55184.93 | -1755 | 57291 | 297930.5 | 0 | 0 | 0 | 57290.84 | 57290.84 | 13% | 13.49% | 0% | -13% |  | 46.3 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23520 | FCAS AP Portfolio Systems | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 42.43% | 95.6% | 83.13% | 0 | -7.14% | 810821 | 344062 | 466759 |  | 320 | 319.5 | 0 | 328919 | 42.41 | 15143 | 51480 | 286019 | N/A | N/A | N/A | N/A | 0 | 22% | 14.86% | 15.09% | -6.91% |  | 78.43 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23023 | Spirit Shorts R Foster/M Gourley | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  |  | 79.7% | 103.1% | 99.11% | 0 | -20.1% | 416652 | 332086 | 84566 |  | 188776 | 216366 | 0 | 342363 | 61.57 | 4235 | 15899 | 329113.8333 | N/A | N/A | N/A | N/A | 0 | 27% | 6.9% | 7.57% | -19.43% |  | 29.44 | [5 empty] | 14511
1721 | 2024-01-18 00:29 | P22391 | GE System Engineering support | Vinayakumar Sugur | GEE | EXPERIS LIMITED | EES | Level NC | REIM |  |  |  |  | 82.01% | 94.11% | 93.44% | 0 | 0.13% | 434434 | 356261 | 78173 |  | 0 | 0 | 0 | 335263 | 90.27 | 20998 | 2829 | 332905.5 | N/A | N/A | N/A | N/A | 0 | 6% | 6.13% | 6.09% | 0.09% |  | 57.33 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23554 | Dornier Seawings 328 2023 H2 Support | Steven Lawton | DAX | EXPLEO GERMANY GMBH (EC) | MPE | Level 2 | REIM |  |  |  |  | 87.35% | 96.41% | 75.63% | 90667.3 | 7.48% | 416112 | 363490 | 52622 |  | 3551 | 3550.65 | 25985 | 350449 | 67.98 | 13041 | 90667 | 274893.1667 | N/A | N/A | N/A | N/A | 90667.3 | 21% | 28.48% | 32.24% | 11.24% |  | 67.39 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23366 | Business Analyst Support | Peter Williams | BDZ | MBDA UK LIMITED | DET | Level NC | REIM |  |  |  |  | 23.58% | 281.5% | 245.4% | 0 | 20.03% | 583200 | 137511 | 445689 |  | 137510 | 416921.86 | 0 | 387040 | 80.35 | -11394 | 59520 | 337440 | N/A | N/A | N/A | N/A | 0 | 43% | 63.03% | 100% | 57% |  | 0.01 | [5 empty] | 238135
1721 | 2024-01-18 00:29 | P23602 | EXP-025 Portfolio Software Engineering Support | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 32.97% | 88.73% | 65.35% | 0 | -0.53% | 1221060 | 402623 | 818437 |  | 0 | 0 | 0 | 357244 | 47.79 | 45380 | 112951 | 263118.1667 | N/A | N/A | N/A | N/A | 0 | 24% | 23.47% | 23.97% | -0.03% |  | 82.42 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23432 | Spirit Belfast MRB On-Site Support (Mon & Clear) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 65.77% | 125.6% | 93.11% | 77391.6 | -11.53% | 449545 | 295665 | 153880 |  | 295665 | 451827.33 | 0 | 371466 | 40.74 | 36200 | 115405 | 275295.1667 | N/A | N/A | N/A | N/A | 77391.6 | 39% | 27.47% | 0% | -39% |  | 0 | [5 empty] | 112000
1721 | 2024-01-18 00:29 | P23320 | Lifing Services DACs | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX | 2024-01-12 | 26 |  |  | 95.56% | 104.6% | 97.44% | 0 | 2.71% | 413300 | 394956 | 18344 |  | 0 | 0 | 0 | 413300 | 28.87 | -2050 | 34139 | 384850.8333 | 0 | 34138.8 | 0 | 0 | 0 | 26% | 28.71% | 43.64% | 17.64% |  | 33.15 | [5 empty] | 16294
1721 | 2024-01-18 00:29 | P22906 | Spirit Shorts - MRB JD Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  |  | 66.44% | 102.6% | 73.01% | 32745.6 | -7.54% | 614770 | 408436 | 206334 |  | 0 | 0 | 0.00 | 419106 | 221.85 | -2669 | 145102 | 298187.6667 | N/A | N/A | N/A | N/A | 32745.6 | 13% | 5.46% | 2.96% | -10.04% |  | 36.78 | [5 empty] | 8000
1721 | 2024-01-18 00:29 | P23140 | Spirit Shorts A220 MLG Stress Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  |  | 67.3% | 92.5% | 82.45% | 132992.4 | -15.11% | 595746 | 400916 | 194830 |  | 20870 | 87811.88 | 0.00 | 370857 | 111.11 | 55059 | 48343 | 330571.1667 | 0 | 0 | 0 | 48343.2 | 132992.4 | 32% | 16.89% | 10.96% | -21.04% |  | 47.34 | [5 empty] | 25000
1721 | 2024-01-18 00:29 | P23001 | Spirit Shorts A220 Design | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 112.9% | 73.81% | 68.7% | 0 | -3.61% | 439560 | 496050 | -56490 |  | 0 | 0 | 65953.2 | 366148 | 323.77 | 129902 | 30405 | 340810.5 | N/A | N/A | N/A | N/A | 0 | 25% | 21.39% | 11.21% | -13.79% |  | 43.64 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P22652 | L3 - Saftey Engineering | Sean Simmons | LHW | L3HARRIS MAPPS LIMITED | EES | Level NC | FIX |  |  |  |  | 95.63% | 86.69% | 86.69% | 0 | 5.66% | 523390 | 500498 | 22892 |  | 0 | 0 | 0 | 433883 | 1658.54 | 66615 | 0 | 433883 | 0 | 0 | 0 | 0 | 0 | 21% | 26.66% | 25.88% | 4.88% |  | 83.05 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23281 | Systems Portfolio | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 44.43% | 97.19% | 97.19% | 0 | -17.1% | 1177697 | 523237 | 654460 |  | 2133 | 2133.28 | 0 | 508545 | 64.09 | 14603 | 0 | 508545 | N/A | N/A | N/A | N/A | 0 | 25% | 7.9% | 0% | -25% |  | 70.48 | [5 empty] | -89
1721 | 2024-01-18 00:29 | P21138 | D&A Vibration Reduc Damping Struc FOGV Components | Steven Lawton | ATC | AECC SICHUAN GAS TURBINE | MPE | Level 1 | FIX | 2022-09-07 | 0 |  |  | 96.12% | 104% | 104% | 0 | -3.44% | 569346 | 547228 | 22118 |  | 75182 | 75181.75 | 0 | 569346 | 0 | -11 | 0 | 569346 | 0 | 0 | 0 | 0 | 0 | 36% | 32.56% | 0% | -36% |  | 73.95 | [5 empty] | 22107
1721 | 2024-01-18 00:29 | P22790 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 2 | REIM |  |  |  |  | 194.5% | 90.44% | 90.44% | 0 | 1.37% | 352240 | 685262 | -333022 |  | 1612 | 1611.52 | 515246 | 619744 | 41098.04 | 34248 | 0 | 619744 | N/A | N/A | N/A | N/A | 0 | 13% | 14.37% | 0% | -13% |  | 45.06 | [5 empty] | -31270
1721 | 2024-01-18 00:29 | P23321 | EHM Cloud Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  |  | 87.76% | 113.9% | 106.1% | 0 | 2.84% | 839969 | 737152 | 102817 |  | 0 | 0 | 24980 | 839969 | 22.77 | -20277 | 69002 | 782467.3333 | 0 | 69002.4 | 0 | 0 | 0 | 28% | 30.84% | 76.77% | 48.77% |  | 49.93 | [5 empty] | 82540
1721 | 2024-01-18 00:29 | P23519 | Mechanical and Electrical Design Eng Support | Dushan Fernando | BAX | SAFRAN SEATS GB LIMITED | MPE | Level 2 | REIM |  |  |  |  | 107.4% | 91.18% | 65.47% | 0 | -1.62% | 839697 | 901490 | -61793 |  | 727 | 727 | 49914 | 821977 | 79.52 | 79512 | 278137 | 590196.1667 | N/A | N/A | N/A | N/A | 0 | 33% | 31.38% | 30.29% | -2.71% |  | 56.58 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P22350 | EMP 2020-2021 | Liam Jacob Lewis Bryant | ARY | GUIDANT GROUP (trading name) | PCPR | Level NC | REIM |  |  |  |  | 97.06% | 99.25% | 95.65% | 0 | -1.86% | 930212 | 902893 | 27319 |  | 400 | 400 | 0.00 | 896162 | 59.01 | 6731 | 39084 | 863592 | N/A | N/A | N/A | N/A | 0 | 32% | 30.14% | 27.61% | -4.39% |  | 44 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23105 | Raytheon Supply Engineering Support | Natalie Sinclair | RAY | RAYTHEON UNITED KINGDOM LIMITED | MPE | Level 3A | REIM | 2023-07-13 | 1 |  |  | 79.67% | 90.07% | 90.07% | 0 | -1.83% | 1164044 | 927395 | 236649 |  | 0 | 0 | 0 | 835328 | 110481.3 | 92068 | 0 | 835328 | N/A | N/A | N/A | N/A | 0 | 26% | 24.17% | 0% | -26% |  | 48.97 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23152 | Project Aragon - Design and Stress Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  |  | 104.4% | 63.87% | 63.87% | 0 | -9.5% | 1093504 | 1141933 | -48429 |  | 0 | 0 | 0 | 729296 | 240.97 | 412637 | 0 | 729296 | N/A | N/A | N/A | N/A | 0 | 39% | 29.5% | 29.69% | -9.31% |  | 51.83 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P22671 | Spirit Shorts Pylon and Fairing Package | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX | 2023-05-03 | 4 |  |  | 105% | 95.27% | 95.27% | 0 | -7.21% | 1198495 | 1258028 | -59533 |  | 106451 | 174863.91 | 0 | 1198495 | 2492.21 | 2077 | 0 | 1198495 | 0 | 0 | 0 | 0 | 0 | 20% | 12.79% | 0% | -20% |  | 45.4 | [5 empty] | -57456
1721 | 2024-01-18 00:29 | P23435 | Andy Baker Portfolio | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 39.03% | 94.38% | 85.37% | 0 | -8.49% | 3377457 | 1318235 | 2059222 |  | 2353 | 2352.57 | 0 | 1244199 | 48.14 | 74036 | 142595 | 1125369.8333 | N/A | N/A | N/A | N/A | 0 | 25% | 16.51% | 15.23% | -9.77% |  | 77.79 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23315 | DAC LUC BAU and Service Workbench | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  |  | 79.67% | 125.5% | 112.5% | 0 | 2.81% | 1573630 | 1253668 | 319962 |  | 180 | 180.3 | 0 | 1573630 | 9.01 | -122165 | 195596 | 1410633.3333 | 0 | 195596.4 | 0 | 0 | 0 | 28% | 30.81% | 51.5% | 23.5% |  | 52.57 | [5 empty] | 197797
1721 | 2024-01-18 00:29 | P23411 | Agile & Scrum Delivery Service | Peter Williams | BDZ | MBDA UK LIMITED | DET | Level 2 | REIM | 2023-08-14 | 1 |  |  | 36.3% | 170.5% | 170.5% | 0 | 13.08% | 2487000 | 902904 | 1584096 |  | 894179 | 2337284.55 | 0 | 1539600 | 91 | 16141 | 0 | 1539600 | N/A | N/A | N/A | N/A | 0 | 29% | 42.08% | 0% | -29% |  | 74.57 | [5 empty] | 652837
1721 | 2024-01-18 00:29 | P23207 | A350 Approvers - Design and Stress Support | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  |  | 102.4% | 73.41% | 56.92% | 296187.37 | -10.59% | 1670400 | 1710562 | -40162 |  | 14330 | 14395.36 | 0 | 1255654 | 118.71 | 454907 | 338325 | 973716.5 | 0 | 91957.54 | 76590.9 | 169776.21 | 296187.37 | 29% | 18.41% | 19.96% | -9.04% |  | 54.63 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P23006 | Spirit Shorts A350 Freighter Toulouse | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 137.2% | 86.9% | 79.06% | 0 | 18.27% | 1035746 | 1421321 | -385575 |  | 1086670 | 1708220.2 | 0 | 1235101 | 298.69 | 497494 | 133601 | 1123766.8333 | N/A | N/A | N/A | N/A | 0 | 5% | 23.27% | 37.64% | 32.64% |  | 47.29 | [5 empty] | 311274
1721 | 2024-01-18 00:29 | P19020 | Spirit Concessions - 2018 | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX |  |  |  |  | 90.76% | 111.9% | 107.1% | 99792.83 | 2.1% | 1914847 | 1737898 | 176949 |  | 44318 | 44317.61 | 15178.88 | 1944711 | 1872.53 | 195867 | 99793 | 1861550.1667 | 0 | 0 | 0 | 99792.83 | 99792.83 | 25% | 27.1% | 7.8% | -17.2% |  | 40.87 | [5 empty] | 402680
1721 | 2024-01-18 00:29 | P23179 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX |  |  |  |  | 128% | 86.12% | 81.52% | 35500.91 | -9.48% | 1913715 | 2450302 | -536587 |  | 155464 | 246717.26 | 0.00 | 2110117 | 340.31 | 340185 | 135230 | 1997425.3333 | 0 | 99728.59 | 0 | 35500.91 | 35500.91 | 22% | 12.52% | 0% | -22% |  | 44.41 | [5 empty] | 0
1721 | 2024-01-18 00:29 | P19731 | Hapri HPC Rear Bearing Housing PDR & CDR | Steven Lawton | ATC | AECC Hunan Aviation Powerplant | MPE | Level 1 | FIX |  |  |  |  | 99.27% | 100.7% | 88.14% | 447000 | -15.32% | 2980000 | 2958274 | 21726 |  | 358408 | 512832.98 | 0 | 2980000 | 666.86 | -246726 | 447000 | 2607500 | 0 | 447000 | 0 | 0 | 447000 | 38% | 22.68% | 22.46% | -15.54% |  | 64.87 | [5 empty] | -225000
Extend Table

## AP1-3
WIP No | Date Created | Project ID | Project Description | Project Manager | Department Id | Client | CBU | Complexity | Type | Stop Booking Hrs | Closing Project: Action(s) to close | RAG | Approx. PO Burndown (weeks) | Turnover vs Contract Value | Invoice To Date vs Turnover | Cash in vs Turnover | Open Amount Overdue | Actual PM% to Baseline PM% delta | Contract Value | Total Project Turnover | Contract Value - Total Turnover | Run Rate (based on total turnover) | Total BOI Spend to Date | Total Committed PO (supplier/best shore) | Current AA in PT3 | Invoiced To Date | DSO | Unbilled (WIP) | Total Open Amount | Cash in (Invoiced - (Open amount -VAT)) | Debt <=30 Days | Debt 31 - 60 Days | Debt 61 - 90 Days | Debt >= 90 Days | Open Amount Overdue2 | Baseline Project Margin | Project To Date (PTD) PM | Year to Date (YTD) PM | YTD Delta Actual PM% to BPM% | Forecast PM at Completion (Manual input from PTT) | Average Sale Rate | CSat score for last quarter (Manual input from PTT) | Comments and Actions | Judged income adjustment at completion | Profit to take now | Provision required now | Fully Traded | Last Months Comments and Actions
1722 | 2024-01-25 00:32 | P23641 | Drawing Triage | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 1043368% | 0 | 10756 | -10756 |  | 0 | 0 | 11343.2 | 0 | 0 | -1 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 1043368% | 100% | 100% |  | 49 | [5 empty] | -10756
1722 | 2024-01-25 00:32 | P23637 | MBSE Proposal | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 |  | 0 | 0 | 49980 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23711 | DO NOT USE - RAISED IN ERROR | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23552 | FCAS AP Product Technology Development | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -25% | 597871 | 0 | 597871 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 25% | 0% | 0% | -25% |  | 0 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23543 | EXP-024 FCAS AP Transformation & Change Enablers | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -26% | 385921 | 0 | 385921 |  | 0 | 0 | 0.00 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 26% | 0% | 0% | -26% |  | 0 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23585 | Systems Design - Missile Systems, Meteor,Brimstone | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 |  | 0 | 0 | 49500.00 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23137 | BAE Management Support Collector | John Clements | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3A | REIM | [5 empty] | 0% | 0% | 0 | -44357052% | 0 | 100437 | -100437 |  | 1053 | 1053.38 | 100000 | 0 | 0.3 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | -44357052% | 0% | 0% |  | 50 | [5 empty] | -100437
1722 | 2024-01-25 00:32 | P23730 | FLE Project | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -36.6% | 0 | 105 | -105 |  | 0 | 0 | 24000.00 | 0 | 20 | 105 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | -36.6% | -36.6% | -36.6% |  | 35 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23598 | MRB Onsite support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -18% | 0 | 880 | -880 |  | 880 | 14079.58 | 13200 | 0 | 91 | 880 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 18% | 0% | 0% | -18% |  | 0 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23463 | A220 Wing MaMo Design Checking | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 7.85% | 0 | 1628 | -1628 |  | 0 | 0 | 15000 | 0 | 1953.6 | 1628 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 3% | 10.85% | 0% | -3% |  | 44 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23597 | MRB Onsite support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -18% | 0 | 1682 | -1682 |  | 1682 | 17381.62 | 15700 | 0 | 91 | 1682 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 18% | 0% | 0% | -18% |  | 0 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23740 | Phase 2 - EJ200 ESS EHM Platform Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 3 | FIX |  |  |  |  | 1.046% | 0% | 0% | 0 | 3.56% | 175971 | 1840 | 174131 |  | 0 | 0 | 0 | 0 | 20 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 31.56% | 31.56% | 3.56% |  | 80 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23717 | GKN Ted Tomblin 2024 | Matthew Tweed | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 21.57% | 0 | 1989 | -1989 |  | 0 | 0 | 3672 | 0 | 20 | 1989 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 21.57% | 21.57% | 21.57% |  | 51 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23718 | Requalification of EJ200 GSS ESS EHM SW module | Vijayakumara Nanjundappa | ARZ | MTU AERO ENGINES AG | DET | Level 3 | FIX |  |  |  |  | 3.438% | 0% | 0% | 0 | 3.56% | 74463 | 2560 | 71903 |  | 0 | 0 | 0 | 0 | 20 | 2560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 31.56% | 31.56% | 3.56% |  | 80 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P21028 | Rebate Collection (BACC) | David Catchpole | TOO | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | [5 empty] | 0% | 0% | 0 | 0% | 0 | 2680 | -2680 |  | 2680 | 2680 | 0 | 0 | 3216 | 2680 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23578 | ESN Work Package | Hannah Mead | COZ | CHELTON LIMITED | DET | Level 3 | FIX | 2024-01-01 | 0 |  |  | 86.17% | 116.1% | 116.1% | 0 | 35.86% | 4410 | 3800 | 610 |  | 0 | 0 | 0 | 4410 | 0 | -610 | 0 | 4410 | 0 | 0 | 0 | 0 | 0 | 24% | 59.86% | 0% | -24% |  | 95 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23628 | Design Assurance | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -6.67% | 0 | 3909 | -3909 |  | 0 | 0 | 4454.80 | 0 | 4691.09 | 3909 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 7% | 0.33% | 0% | -7% |  | 15.05 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23002 | WoT MAJ Transit Flag Stress | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 30.9% | 323.7% | 323.7% | 0 | 53.84% | 4735 | 1463 | 3272 |  | 0 | 2242.5 | 0 | 4735 | 0.6 | 1 | 0 | 4735 | 0 | 0 | 0 | 0 | 0 | 10% | 63.84% | 0% | -10% |  | 45 | [5 empty] | 3273
1722 | 2024-01-25 00:32 | P23724 | GKN S McConnell 2024 | Matthew Tweed | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  |  | 10.3% | 0% | 0% | 0 | 1.51% | 49820 | 5131 | 44689 |  | 0 | 0 | 0.00 | 0 | 20 | 5131 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 19% | 20.51% | 20.51% | 1.51% |  | 49.82 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23754 | Tempest Composites WP4 | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX | [5 empty] | 0% | 0% | 0 | 6.16% | 0 | 5973 | -5973 |  | 0 | 0 | 97140 | 0 | 35 | 5973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 34.16% | 34.16% | 6.16% |  | 68.65 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23760 | Land Ceptor V&V Systems Engineer | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 28.98% | 0 | 7889 | -7889 |  | 0 | 0 | 23550 | 0 | 20 | 7889 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 28.98% | 28.98% | 28.98% |  | 78.5 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23729 | Honda Tooling | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX | [5 empty] | 0% | 0% | 0 | -3.56% | 0 | 7955 | -7955 |  | 0 | 0 | 14430.00 | 0 | 14 | 7955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21% | 17.44% | 17.44% | -3.56% |  | 42.2 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23743 | EHM Cloud Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  |  | 0.8226% | 0% | 0% | 0 | 7.29% | 1016000 | 8358 | 1007642 |  | 0 | 0 | 0 | 0 | 20 | 8358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 35.29% | 35.29% | 7.29% |  | 47.22 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23607 | SAFRAN - A330neo Turnover Frame | Gary Kempster | TOO | SAFRAN SEATS GB LIMITED | MPE | Level 3 | FIX |  |  |  |  | 95.68% | 0% | 0% | 0 | -19.75% | 8736 | 8359 | 377 |  | 0 | 0 | 0 | 0 | 10030.8 | 8359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23% | 3.25% | 0% | -23% |  | 52 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23274 | ME Support (Aim Altitude - Cambridge) | James Montgomery | AVI | AVIC CABIN SYSTEMS (UK) LIMITED | ME | Level 3 | FIX | 2023-08-18 | 0 |  |  | 51.88% | 56.29% | 56.29% | 0 | -0.17% | 17280 | 8964 | 8316 |  | 0 | 0 | 0 | 5046 | 4701.24 | 3918 | 0 | 5046 | 0 | 0 | 0 | 0 | 0 | 21% | 20.83% | 0% | -21% |  | 48 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23663 | Spirit Tooling Verification and Inspection | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 45.31% | 0% | 0% | 0 | -7.71% | 19820 | 8981 | 10839 |  | 0 | 0 | 7392 | 0 | 91 | 8981 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 12% | 4.29% | 4.82% | -7.18% |  | 34.41 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23753 | Tempest Composites Maturation | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | [5 empty] | 0% | 0% | 0 | -26.21% | 0 | 9617 | -9617 |  | 0 | 0 | 54398.40 | 0 | 21 | 9617 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 37% | 10.79% | 10.79% | -26.21% |  | 64.76 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23283 | Spirit Tooling Audit | Charidimos Valadakis | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-05-03 | 0 |  |  | 97.23% | 48.57% | 48.57% | 0 | -7.99% | 9910 | 9635 | 275 |  | 0 | 0 | 0 | 4680 | 5946.05 | 4955 | 0 | 4680 | N/A | N/A | N/A | N/A | 0 | 7% | -0.99% | 0% | -7% |  | 34.41 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23127 | Loft Hall Design Support | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 101% | 99.06% | 99.06% | 0 | -9.55% | 9680 | 9772 | -92 |  | 0 | 0 | 0 | 9680 | 110.4 | 92 | 0 | 9680 | N/A | N/A | N/A | N/A | 0 | 41% | 31.45% | 0% | -41% |  | 44 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23630 | 2Excel CFD Analysis Support | Dushan Fernando | BAX | STIRLING DYNAMICS LTD | MPE | Level NC | FIX |  |  |  |  | 61.2% | 100% | 100% | 0 | -1.87% | 16195 | 9911 | 6284 |  | 0 | 0 | 0 | 9912 | 0 | 0 | 0 | 9912 | 0 | 0 | 0 | 0 | 0 | 26% | 24.13% | 0% | -26% |  | 64.78 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23744 | Model Factory | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  |  | 4.148% | 0% | 0% | 0 | 8.42% | 262300 | 10880 | 251420 |  | 0 | 0 | 0 | 0 | 20 | 10880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 36.42% | 36.42% | 8.42% |  | 50.72 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23313 | Laser Trim Fixtures | Gary Kempster | TOO | ALKEN ENGINEERING LIMITED | MPE | Level 3 | FIX | 2023-11-20 | 0 |  |  | 89.87% | 111.3% | 111.3% | 0 | 0.53% | 13770 | 12375 | 1395 |  | 0 | 0 | 0 | 13770 | 0 | -1395 | 0 | 13770 | 0 | 0 | 0 | 0 | 0 | 17% | 17.53% | 0% | -17% |  | 45 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P22761 | Red Bull Chassis Spit | James Montgomery | TOO | MANUFAX ENGINEERING LTD | MPE | Level 3 | FIX | 2022-11-15 | 0 |  |  | 72.19% | 96.98% | 96.98% | 0 | 7.92% | 12961 | 9356 | 3605 |  | 0 | 0 | 0 | 9073 | 4666.39 | 3889 | 0 | 9073 | 0 | 0 | 0 | 0 | 0 | 23% | 30.92% | 0% | -23% |  | 42.19 | [5 empty] | 3606
1722 | 2024-01-25 00:32 | P23433 | Cavendish | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 32.81% | 100% | 100% | 0 | -0.34% | 42240 | 13859 | 28381 |  | 0 | 0 | 0 | 13859 | 0 | 0 | 0 | 13859 | N/A | N/A | N/A | N/A | 0 | 7% | 6.66% | 0% | -7% |  | 43.93 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23350 | Spirit 2023 - Stress Approve Man Serv (DH) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 14.15% | 72.64% | 72.64% | 0 | -0.29% | 97920 | 13860 | 84060 |  | 0 | 0 | 0 | 10068 | 4550.4 | 3792 | 0 | 10068 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23344 | Spirit A320 Spoilers Support 2023 | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 38.75% | 100% | 100% | 0 | 5.82% | 35786 | 13867 | 21919 |  | 0 | 0 | 0 | 13867 | 0 | 0 | 0 | 13867 | N/A | N/A | N/A | N/A | 0 | 7% | 12.82% | 0% | -7% |  | 34.41 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23337 | Spirit 2023 - Steve Grimley | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 25.28% | 100% | 100% | 0 | 0.01% | 56813 | 14362 | 42451 |  | 0 | 0 | 0 | 14362 | 0 | 0 | 0 | 14362 | N/A | N/A | N/A | N/A | 0 | 7% | 7.01% | 0% | -7% |  | 30.11 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23635 | Engineering Services: FAI Support | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 40.75% | 0% | 0% | 0 | -3.5% | 37230 | 15170 | 22060 |  | 0 | 0 | 0.00 | 0 | 131.15 | 15170 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 8% | 4.5% | 5.04% | -2.96% |  | 38.7 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23700 | IPDT Leads | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 15.41% | 0 | 16971 | -16971 |  | 0 | 0 | 22200.00 | 0 | 70 | 16971 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 22% | 37.41% | 38.85% | 16.85% |  | 61.88 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23343 | Spirit 2023 - John Agnew | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-08-09 | 0 |  |  | 28.56% | 86.27% | 86.27% | 0 | -0.02% | 65120 | 18601 | 46519 |  | 0 | 0 | 0 | 16047 | 3064.49 | 2554 | 0 | 16047 | N/A | N/A | N/A | N/A | 0 | 7% | 6.98% | 0% | -7% |  | 34.51 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23651 | PMO Spirit | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 24.64% | 0 | 19476 | -19476 |  | 0 | 0 | 30800.00 | 0 | 120.66 | 19476 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 24.64% | 24.99% | 24.99% |  | 36 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23741 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  |  | 3.875% | 0% | 0% | 0 | 4.56% | 526262 | 20394 | 505868 |  | 0 | 0 | 0 | 0 | 20 | 20394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 32.56% | 32.56% | 4.56% |  | 39.37 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23355 | Spirit Tooling Support 2023 | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-23 | 0 |  |  | 22.93% | 89.03% | 89.03% | 0 | -0.82% | 91800 | 21053 | 70747 |  | 0 | 0 | 0 | 18743 | 2773.01 | 2311 | 0 | 18743 | 0 | 0 | 0 | 0 | 0 | 20% | 19.18% | 0% | -20% |  | 44.46 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23642 | MRB Belfast Support | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -17.57% | 0 | 24333 | -24333 |  | 2170 | 2169.99 | 30800.00 | 0 | 109.38 | 24333 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | -17.57% | -16.7% | -16.7% |  | 38.52 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23351 | Spirit 2023 - Design Man Serv (KL) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 26.47% | 93.15% | 93.15% | 0 | 0.09% | 93840 | 24840 | 69000 |  | 0 | 0 | 0 | 23138 | 2042.4 | 1702 | 0 | 23138 | 0 | 0 | 0 | 0 | 0 | 26% | 26.09% | 0% | -26% |  | 46 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23356 | Spirit 2023 - Design Man Serv (AH) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX | 2023-08-09 | 1 |  |  |  | 76.66% | 0.001332% | 23018.4 | 0.48% | 0 | 25023 | -25023 |  | 0 | 0 | 25300.00 | 19182 | 30027.7 | 5841 | 23018 | 0.33333 | 0 | 0 | 0 | 23018.4 | 23018.4 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23338 | Spirit 2023 - Blair Hainey | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 74.11% | 70.57% | 70.57% | 0 | 3.32% | 34494 | 25565 | 8929 |  | 0 | 0 | 0 | 18042 | 91 | 7522 | 0 | 18042 | N/A | N/A | N/A | N/A | 0 | 7% | 10.32% | 19.31% | 12.31% |  | 18.28 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P22884 | Spirit Shorts Config Eng | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 66.3% | 100.1% | 100.1% | 0 | 0.56% | 38976 | 25842 | 13134 |  | 0 | 0 | 0 | 25863 | 0 | 0 | 0 | 25863 | N/A | N/A | N/A | N/A | 0 | 7% | 7.56% | 0% | -7% |  | 20.3 | [5 empty] | 21
1722 | 2024-01-25 00:32 | P23354 | Spirit 2023 - Design Man Serv (PC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 27.97% | 99.36% | 99.36% | 0 | 0.48% | 93840 | 26249 | 67591 |  | 0 | 0 | 0 | 26082 | 200.38 | 167 | 0 | 26082 | 0 | 0 | 0 | 0 | 0 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23739 | Lifing Services DACs | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  |  | 4.238% | 0% | 0% | 0 | 7.46% | 656508 | 27824 | 628684 |  | 0 | 0 | 0 | 0 | 20 | 27824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 35.46% | 35.46% | 7.46% |  | 37.93 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P22756 | A350 FLE Design Checker | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2022-03-23 | 1 |  |  | 68.39% | 119.7% | 119.7% | 0 | 16.46% | 34898 | 23867 | 11031 |  | 23867 | 24342.3 | 0 | 28571 | 0.06 | 0 | 0 | 28571 | N/A | N/A | N/A | N/A | 0 | 0% | 16.46% | 0% | 0% |  | 0 | [5 empty] | 4704
1722 | 2024-01-25 00:32 | P23458 | Spirit Belfast Tooling Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-08-11 | 0 |  |  | 101.3% | 94.65% | 94.65% | 0 | 8.64% | 30384 | 30785 | -401 |  | 0 | 0 | 0 | 29139 | 1974.96 | 1646 | 0 | 29139 | N/A | N/A | N/A | N/A | 0 | 7% | 15.64% | 0% | -7% |  | 42.2 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23365 | GKN 777x Lip Skin Fixture | Steven Lawton | TOO | GKN AEROSPACE SERVICES LTD | MPE | Level 3 | FIX | 2023-10-12 | 1 |  |  | 41.91% | 113.2% | 18.86% | 37544.22 | -9.26% | 79161 | 33176 | 45985 |  | 5110 | 5109.88 | 0 | 37544 | 33175.67 | -4369 | 37544 | 6257.3333 | 0 | 37544.22 | 0 | 0 | 37544.22 | 22% | 12.74% | 0% | -22% |  | 56 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P22768 | MRB Onsite Support - Spirit Belfast | James Montgomery | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2023-07-27 | 0 |  |  |  | 0% | 0% | 0 | -17.07% | 0 | 34614 | -34614 |  | 0 | 0 | 36800 | 0 | 41536.8 | 34614 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 10% | -7.07% | 0% | -10% |  | 36 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23347 | WoT Fixed Leading Edge - Industrial 2023 | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 112.8% | 42.03% | 42.03% | 0 | -0.41% | 31034 | 35002 | -3968 |  | 0 | 0 | 10500 | 14711 | 24349.85 | 20292 | 0 | 14711 | N/A | N/A | N/A | N/A | 0 | 7% | 6.59% | 0% | -7% |  | 32.26 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23051 | Spirit Shorts A350 PAX Door | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 3A | REIM |  |  |  |  | 205.9% | 105.4% | 105.4% | 0 | -0.63% | 18216 | 37513 | -19297 |  | 0 | 0 | 0 | 39537 | 0 | 0 | 0 | 39537 | N/A | N/A | N/A | N/A | 0 | 30% | 29.37% | 0% | -30% |  | 46 | [5 empty] | 2024
1722 | 2024-01-25 00:32 | P22752 | Tooling WoT - 2021 (Spirit) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | REIM | 2023-05-03 | 0 |  |  | 101.1% | 74.02% | 74.02% | 0 | -8.5% | 41525 | 41982 | -457 |  | 0 | 0 | 0 | 31076 | 13087.42 | 10906 | 0 | 31076 | N/A | N/A | N/A | N/A | 0 | 0% | -8.5% | 0% | 0% |  | 39.09 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23339 | Spirit 2023 - Stewart Russell | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 64.51% | 100% | 100% | 0 | 0.62% | 72767 | 46942 | 25825 |  | 0 | 0 | 0 | 46942 | 0 | 0 | 0 | 46942 | N/A | N/A | N/A | N/A | 0 | 7% | 7.62% | 0% | -7% |  | 35.67 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23322 | GKN T Tomblin 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2023-12-31 | 1 |  |  | 83.13% | 100% | 97.01% | 0 | -0.33% | 58952 | 49008 | 9944 |  | 0 | 0 | 0 | 49008 | 24.35 | 0 | 1757 | 47543.8333 | N/A | N/A | N/A | N/A | 0 | 17% | 16.67% | 0% | -17% |  | 48 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P22760 | SA Leading Edge Transport Media ('A' Frames) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-11-15 | 1 |  |  | 85.99% | 110.7% | 116.3% | -3082.8 | 3.97% | 53481 | 45986 | 7495 |  | 42804 | 42804 | 0 | 50912 | 0 | 0 | -3083 | 53481.1667 | 0 | 0 | 0 | -3082.8 | -3082.8 | 6% | 9.97% | 0% | -6% |  | 42 | [5 empty] | 4926
1722 | 2024-01-25 00:32 | P23341 | Spirit 2023 - Tom McFarlane | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 98.58% | 91.46% | 71.9% | 0 | -0.01% | 54282 | 53513 | 769 |  | 0 | 0 | 0 | 48945 | 112.02 | 4568 | 12560 | 38478.3333 | N/A | N/A | N/A | N/A | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23685 | DAC LUC Support and Recompliance | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  |  | 7.514% | 0% | 0% | 0 | 2.48% | 720000 | 54100 | 665900 |  | 0 | 0 | 0 | 0 | 20 | 54100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 30.48% | 30.48% | 2.48% |  | 69.78 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23382 | Performance Modelling | Dushan Fernando | BDX | MBDA UK LIMITED | MPE | Level NC | REIM | 2023-07-09 | 1 |  |  | 40.95% | 79.09% | 79.09% | 0 | -16.36% | 170010 | 69626 | 100384 |  | 14560 | 14659.9 | 0 | 55066 | 0 | 0 | 0 | 55066 | N/A | N/A | N/A | N/A | 0 | 20% | 3.64% | 0% | -20% |  | 77.05 | [5 empty] | -14560
1722 | 2024-01-25 00:32 | P23551 | Ian Berry 2023 H2 | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  |  | 74.7% | 48.83% | 48.83% | 0 | 13.91% | 75810 | 56630 | 19180 |  | 0 | 0 | 0 | 27652 | 129.19 | 28978 | 0 | 27652 | N/A | N/A | N/A | N/A | 0 | 20% | 33.91% | 0% | -20% |  | 75.81 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23677 | ME Managed Service - Phase 1 | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  |  | 65.55% | 0% | 0% | 0 | -11.24% | 86400 | 56633 | 29767 |  | 0 | 0 | 0.00 | 0 | 84 | 56633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16% | 4.76% | 8.88% | -7.12% |  | 45 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23349 | Spirit 2023 - Stress Approve Man Serv (SB) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 58.24% | 80.05% | 80.05% | 0 | -0.29% | 97920 | 57024 | 40896 |  | 0 | 0 | 0 | 45648 | 13651.2 | 11376 | 0 | 45648 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23193 | Spirit Shorts Stephen Greer | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 93.49% | 95.1% | 71.71% | 6679.37 | 2.32% | 61472 | 57473 | 3999 |  | 0 | 0 | 0 | 54656 | 158.26 | 2818 | 16131 | 41213.5 | N/A | N/A | N/A | N/A | 6679.37 | 29% | 31.32% | 34.03% | 5.03% |  | 34.94 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23465 | A220 ToW Design Offload (Wing) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 47.05% | 89.8% | 60.78% | 0 | -3.75% | 132000 | 62103 | 69897 |  | 0 | 0 | 0 | 55768 | 109.93 | 6334 | 21623 | 37748.8333 | N/A | N/A | N/A | N/A | 0 | 20% | 16.25% | 18.4% | -1.6% |  | 42.8 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23106 | ME Support to NPD - Bobby Haggart | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  |  | 95.79% | 97.03% | 97.03% | 0 | 0.3% | 65675 | 62912 | 2763 |  | 0 | 0 | 0 | 61043 | 2243.24 | 1869 | 0 | 61043 | 0 | 0 | 0 | 0 | 0 | 15% | 15.3% | 0% | -15% |  | 35.65 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23561 | SAAB | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  |  | 82.46% | 121.1% | 96.66% | 0 | 3.5% | 67485 | 55649 | 11836 |  | 0 | 0 | 0 | 67399 | 81.52 | -4408 | 16332 | 53789 | N/A | N/A | N/A | N/A | 0 | 16% | 19.5% | 0% | -16% |  | 36.82 | [5 empty] | 7342
1722 | 2024-01-25 00:32 | P22967 | Spirit 2022 - Channapa Laxmeshwar | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2023-01-26 | 2 |  |  | 69.69% | 121.3% | 121.3% | 0 | 9.53% | 75159 | 52376 | 22783 |  | 52376 | 54898.1 | 0 | 63509 | 0.42 | 0 | 0 | 63509 | N/A | N/A | N/A | N/A | 0 | 8% | 17.53% | 0% | -8% |  | 0 | [5 empty] | 11133
1722 | 2024-01-25 00:32 | P23586 | Project Management Support | Peter Bowen | BDX | MBDA UK LIMITED | MPE | Level NC | REIM |  |  |  |  | 80.18% | 86.24% | 67.78% | 0 | -25.64% | 80000 | 64144 | 15856 |  | 1141 | 1140.6 | 0 | 55320 | 57 | 8824 | 14208 | 43480 | N/A | N/A | N/A | N/A | 0 | 49% | 23.36% | 24.63% | -24.37% |  | 80 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23560 | NJEWCS TAF202302 SM | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level 2 | FIX |  |  |  |  | 79.15% | 62.01% | 62.01% | 0 | 12.24% | 81500 | 64504 | 16996 |  | 0 | 0 | 0 | 40000 | 94.7 | 24504 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 28% | 40.24% | 41.09% | 13.09% |  | 73.01 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23342 | Spirit 2023 - Channapa Laxmeshwar | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 78.75% | 104.3% | 88.16% | 0 | -2.64% | 79348 | 62484 | 16864 |  | 62484 | 63539 | 0 | 65178 | 83.77 | 157 | 12110 | 55086.3333 | N/A | N/A | N/A | N/A | 0 | 7% | 4.36% | 0% | -7% |  | 0 | [5 empty] | 2850
1722 | 2024-01-25 00:32 | P23171 | Spirt Shorts Weights Eng | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 81.27% | 117.6% | 107.5% | 0 | -6.62% | 71760 | 58316 | 13444 |  | 58316 | 76495.95 | 0 | 68582 | 9492.98 | 2004 | 7088 | 62675.3333 | N/A | N/A | N/A | N/A | 0 | 24% | 17.38% | 0% | -24% |  | 0 | [5 empty] | 12270
1722 | 2024-01-25 00:32 | P23340 | Spirit 2023 - John Cole | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 94.12% | 88.96% | 71.4% | 0 | -0.01% | 75065 | 70649 | 4416 |  | 0 | 0 | 0 | 62852 | 110.59 | 7797 | 14894 | 50440.3333 | N/A | N/A | N/A | N/A | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 39.78 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23438 | A220 Spirit Shorts DTC - Stephen Corry | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 150.2% | 56.93% | 56.93% | 0 | -5.49% | 47251 | 70962 | -23711 |  | 0 | 0 | 23745 | 40400 | 134.72 | 30562 | 0 | 40400 | N/A | N/A | N/A | N/A | 0 | 21% | 15.51% | 13.54% | -7.46% |  | 49.69 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23345 | Spirit 2023- Jonathan Escosio | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 95.07% | 89.24% | 70.96% | 0 | -0.35% | 75971 | 72226 | 3745 |  | 0 | 0 | 0 | 64456 | 115.64 | 7770 | 15846 | 51251 | N/A | N/A | N/A | N/A | 0 | 1% | 0.65% | 0.65% | -0.35% |  | 40.26 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23080 | Spirit Shorts DManagement Cairan Cullen | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 48.66% | 99.29% | 93.69% | 3787.8 | -0.78% | 149600 | 72798 | 76802 |  | 0 | 0 | 0 | 72284 | 117.59 | 514 | 4892 | 68207.3333 | N/A | N/A | N/A | N/A | 3787.8 | 24% | 23.22% | 18.05% | -5.95% |  | 44.46 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23336 | Spirit 2023 - Neil Rampling | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 54.91% | 89.55% | 65.09% | 0 | -0.01% | 133902 | 73532 | 60370 |  | 0 | 0 | 0.00 | 65851 | 144.07 | 7681 | 21586 | 47862.6667 | N/A | N/A | N/A | N/A | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23583 | Castalla - Test Rig Design | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 111.2% | 81.61% | 54.85% | 24104.64 | -7.08% | 67520 | 75063 | -7543 |  | 0 | 0 | 9706 | 61258 | 144.04 | 13805 | 24105 | 41170.5 | N/A | N/A | N/A | N/A | 24104.64 | 21% | 13.92% | 18.67% | -2.33% |  | 42.4 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23545 | Ultra CSS continuation 2023 H2 | Natalie Sinclair | ULT | ULTRA SONAR SYSTEMS LIMITED | EES | Level NC | REIM |  |  |  |  | 98.99% | 58.42% | 58.42% | 0 | 2.3% | 76000 | 75235 | 765 |  | 0 | 0 | 0 | 43956 | 120.96 | 31279 | 0 | 43956 | N/A | N/A | N/A | N/A | 0 | 23% | 25.3% | 0% | -23% |  | 80 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23600 | MBDA EXP-EE-023 Bristone Certification | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 59.65% | 100% | 84.61% | 0 | 0.4% | 126600 | 75517 | 51083 |  | 0 | 0 | 0 | 75517 | 40.44 | 0 | 13942 | 63898.6667 | N/A | N/A | N/A | N/A | 0 | 41% | 41.4% | 0% | -41% |  | 78.5 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P22505 | Spirit MRB Engineering Support 2021 | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 1 |  |  | 91.17% | 100% | 95.78% | 4020.48 | 21.2% | 87110 | 79415 | 7695 |  | 0 | 0 | 0 | 79415 | 4020.48 | 0 | 4020 | 76065 | 0 | 0 | 0 | 4020.48 | 4020.48 | 0% | 21.2% | 0% | 0% |  | 41.88 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23375 | GKN Jaap Peters NL 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2023-12-31 | 5 |  |  | 84.76% | 115.8% | 80.21% | 0 | -15.19% | 89795 | 76111 | 13684 |  | 76111 | 85308.08 | 0.00 | 88129 | 95.02 | -8168 | 32497 | 61048.1667 | N/A | N/A | N/A | N/A | 0 | 20% | 4.81% | 0% | -20% |  | 0 | [5 empty] | 3850
1722 | 2024-01-25 00:32 | P22885 | ME Support (Baxi) | James Montgomery | HUV | BAXI HEATING UK LIMITED | ME | Level 3 | FIX | 2023-01-12 | 0 |  |  | 68.78% | 108.7% | 108.7% | 0 | 13.05% | 106633 | 73340 | 33293 |  | 0 | 0 | 0 | 79748 | 1531.35 | 1276 | 0 | 79748 | 0 | 0 | 0 | 0 | 0 | 15% | 28.05% | 0% | -15% |  | 44.37 | [5 empty] | 7684
1722 | 2024-01-25 00:32 | P23079 | Spirit Shorts Nomenclature | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 92.72% | 94.05% | 71.82% | 21879.36 | 1.75% | 88455 | 82018 | 6437 |  | 0 | 0 | 0.00 | 77138 | 282.41 | 4879 | 21879 | 58905.5 | N/A | N/A | N/A | N/A | 21879.36 | 20% | 21.75% | 25.23% | 5.23% |  | 30.67 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23335 | GKN S McConnell 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2023-12-31 | 3 |  |  | 96.61% | 100% | 75.29% | 0 | 0.74% | 87420 | 84459 | 2961 |  | 0 | 0 | 0 | 84459 | 121.33 | 0 | 25042 | 63590.6667 | N/A | N/A | N/A | N/A | 0 | 15% | 15.74% | 0% | -15% |  | 47 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23664 | Tempest Composites WP3 | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  |  | 69.23% | 19.48% | 0.0007863% | 0 | -5.52% | 122455 | 84780 | 37675 |  | 0 | 0 | 0.00 | 16519 | 95.99 | 68261 | 19822 | 0.66667 | 19822.44 | 0 | 0 | 0 | 0 | 37% | 31.48% | 36.12% | -0.88% |  | 60.26 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P22965 | Spirit 2022 - Design Man Serv (AH) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 1 |  |  | 106.7% | 96.66% | 92.02% | 4759.75 | 3.14% | 80080 | 85441 | -5361 |  | 0 | 0 | 0 | 82589 | 8182.59 | 2852 | 4760 | 78622.3333 | 0 | 0 | 0 | 4759.75 | 4759.75 | 14% | 17.14% | 0% | -14% |  | 42.44 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23523 | Applique Armour Support | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 0 |  |  | 101.6% | 98.47% | 98.47% | 0 | 3.42% | 84300 | 85607 | -1307 |  | 0 | 0 | 0 | 84300 | 63.17 | 1307 | 0 | 84300 | 0 | 0 | 0 | 0 | 0 | 25% | 28.42% | 0% | -25% |  | 64.29 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P22964 | Spirit 2022 - MRB Man Serv (JC) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 100.6% | 97.95% | 97.95% | 0 | 1.91% | 85435 | 85960 | -525 |  | 0 | 0 | 0 | 84200 | 2112.62 | 1761 | 0 | 84200 | 0 | 0 | 0 | 0 | 0 | 16% | 17.91% | 0% | -16% |  | 42.69 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P22963 | Spirit 2022 - Design Man Serv (PC) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 1 |  |  | 108.6% | 104% | 94.46% | 9938.48 | 3.18% | 80080 | 86927 | -6847 |  | 0 | 0 | 0 | 90390 | 5782.63 | -3463 | 9938 | 82108.3333 | 0 | 0 | 0 | 9938.48 | 9938.48 | 13% | 16.18% | 0% | -13% |  | 42.39 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23588 | BAE Typhoon MRB MC Shop Concessions | Andrew Houghton | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 50.28% | 58.55% | 58.55% | 0 | -4.36% | 175061 | 88024 | 87037 |  | 0 | 0 | 0.00 | 51537 | 80.84 | 36487 | 0 | 51537 | N/A | N/A | N/A | N/A | 0 | 31% | 26.64% | 29.11% | -1.89% |  | 55.51 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23353 | Spirit 2023 - MRB Man Serv (JC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  |  | 97.08% | 76.99% | 76.99% | 0 | -0.22% | 91800 | 89123 | 2677 |  | 0 | 0 | 0 | 68615 | 120.47 | 20507 | 0 | 68615 | 0 | 0 | 0 | 0 | 0 | 18% | 17.78% | 0% | -18% |  | 45 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23699 | A220 Stress Checkers | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -1.4% | 0 | 94329 | -94329 |  | 0 | 0 | 86440 | 0 | 70 | 94329 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 22% | 20.6% | 21.34% | -0.66% |  | 61.88 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23648 | EXP-032 Delivery of Datalink Eng support - FCAS AP | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 25.9% | 75.9% | 0.0005203% | 0 | 4.25% | 371000 | 96100 | 274900 |  | 1033 | 1032.95 | 0 | 72943 | 110.32 | 23158 | 87531 | 0.5 | N/A | N/A | N/A | N/A | 0 | 22% | 26.25% | 25.04% | 3.04% |  | 104.3 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P22918 | Spirit Shorts Graduates | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 88.31% | 72.43% | 72.43% | 0 | 9.37% | 110000 | 97136 | 12864 |  | 0 | 0 | 0.00 | 70352 | 153.11 | 26784 | 0 | 70352 | N/A | N/A | N/A | N/A | 0 | 7% | 16.37% | 19.11% | 12.11% |  | 23.16 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23352 | Spirit 2023 - Stress Approve Man Serv (CC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  |  | 99.63% | 71.66% | 71.66% | 0 | -2.36% | 97920 | 97560 | 360 |  | 0 | 0 | 0 | 69912 | 132.03 | 27648 | 0 | 69912 | 0 | 0 | 0 | 0 | 0 | 18% | 15.64% | 16.15% | -1.85% |  | 48 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23282 | Tooling Support (MBDA) | Dushan Fernando | BDV | MBDA UK LIMITED | ME | Level 3 | FIX |  |  |  |  | 99.61% | 95.94% | 88.77% | 0 | -10.03% | 104834 | 104423 | 411 |  | 0 | 0 | 0 | 100185 | 49.99 | 4238 | 8984 | 92698.3333 | 8983.8 | 0 | 0 | 0 | 0 | 30% | 19.97% | 28.47% | -1.53% |  | 49.73 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23270 | Shorts Project X | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 75.19% | 82.18% | 68.98% | 0 | 0.98% | 142248 | 106951 | 35297 |  | 0 | 0 | 0 | 87889 | 150.27 | 19061 | 16933 | 73778.1667 | N/A | N/A | N/A | N/A | 0 | 13% | 13.98% | 10.99% | -2.01% |  | 45.4 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P22883 | Spirit Shorts Evtol PMO C. Hatton | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 60.08% | 97.6% | 81.73% | 0 | -12.39% | 185800 | 111628 | 74172 |  | 0 | 0 | 0 | 108947 | 112.46 | 2681 | 21252 | 91237 | N/A | N/A | N/A | N/A | 0 | 26% | 13.61% | 26.7% | 0.7% |  | 36.29 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23667 | Safety Systems Engineer | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 28.99% | 91.33% | 0% | 0 | -6.95% | 398000 | 115390 | 282610 |  | 0 | 0 | 0 | 105380 | 133.32 | 10010 | 126456 | 0 | N/A | N/A | N/A | N/A | 0 | 47% | 40.05% | 29.32% | -17.68% |  | 110 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23421 | A220 DTC | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 90.55% | 90.54% | 55.77% | 0 | -11.89% | 130625 | 118284 | 12341 |  | 0 | 0 | 0.00 | 107094 | 115.57 | 11190 | 49358 | 65962.3333 | N/A | N/A | N/A | N/A | 0 | 10% | -1.89% | 3.06% | -6.94% |  | 45.09 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P22736 | WoT Fixed Leading Edge - Industrial | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 106.7% | 93.42% | 91.32% | 3019.54 | 0.01% | 112196 | 119668 | -7472 |  | 0 | 0 | 0 | 111797 | 12465.69 | 7872 | 3020 | 109280.3333 | 0 | 0 | 0 | 3019.54 | 3019.54 | 7% | 7.01% | 0% | -7% |  | 32.26 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P22861 | WoT FLE Lifting & Handling Tools | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2023-06-14 | 1 |  |  | 65.17% | 101.6% | 101.6% | 0 | 12.01% | 173987 | 113382 | 60605 |  | 50078 | 58423.58 | 0 | 115204 | 12813.9 | 10678 | 0 | 115204 | 0 | 0 | 0 | 0 | 0 | 1% | 13.01% | 0% | -1% |  | 45 | [5 empty] | 12500
1722 | 2024-01-25 00:32 | P23437 | Embedded Software Engineer | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 85.24% | 91% | 82.36% | 0 | -6.38% | 150150 | 127986 | 22164 |  | 738 | 737.86 | 0 | 116473 | 59.81 | 11513 | 13282 | 105404.6667 | N/A | N/A | N/A | N/A | 0 | 22% | 15.62% | 16.24% | -5.76% |  | 78.5 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23518 | Systems Engineering support to FCAS | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 67.71% | 90.36% | 77.01% | 0 | 0.82% | 193737 | 131183 | 62554 |  | 3927 | 3927.4 | 0 | 118539 | 71.63 | 12643 | 21019 | 101023.1667 | N/A | N/A | N/A | N/A | 0 | 30% | 30.82% | 3.5% | -26.5% |  | 66.04 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23629 | F35 FTI | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level NC | REIM | [5 empty] | 91.16% | 72.84% | 0 | -0.06% | 0 | 134079 | -134079 |  | 0 | 0 | 0 | 122231 | 33.5 | 11849 | 29474 | 97669.3333 | N/A | N/A | N/A | N/A | 0 | 31% | 30.94% | 29.04% | -1.96% |  | 62.3 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23550 | Tempest Composites | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  |  | 107.3% | 93.23% | 74.33% | 24179.64 | 4.75% | 126361 | 135544 | -9183 |  | 0 | 0 | 20441 | 126361 | 210.45 | 9183 | 30735 | 100748.5 | 6555.8 | 0 | 0 | 24179.64 | 24179.64 | 26% | 30.75% | 33.58% | 7.58% |  | 62.05 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23386 | Software Development - BMS | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 92.26% | 94.89% | 86.59% | 0 | 4.29% | 149650 | 138074 | 11576 |  | 0 | 0 | 0 | 131017 | 49.84 | 7057 | 13753 | 119556.1667 | N/A | N/A | N/A | N/A | 0 | 18% | 22.29% | 22.61% | 4.61% |  | 78.5 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23533 | External Stowage Design and Detail Support | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 0 |  |  | 136.5% | 73.24% | 73.24% | 0 | 6.33% | 105000 | 143369 | -38369 |  | 0 | 0 | 49220 | 105000 | 184.06 | 35000 | 0 | 105000 | 0 | 0 | 0 | 0 | 0 | 24% | 30.33% | 0% | -24% |  | 60.04 | [5 empty] | -3369
1722 | 2024-01-25 00:32 | P23464 | A220 Project X Design Offload | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 78.47% | 94.16% | 70.65% | 0 | -3.74% | 180400 | 141568 | 38832 |  | 0 | 0 | 0.00 | 133307 | 112.43 | 8260 | 39945 | 100019.5 | N/A | N/A | N/A | N/A | 0 | 21% | 17.26% | 17.32% | -3.68% |  | 42.9 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P22982 | Spirit 2022 - Hugh Sloan | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 85.9% | 93.8% | 84.82% | 0 | -0.01% | 166046 | 142640 | 23406 |  | 0 | 0 | 0.00 | 133795 | 135.45 | 8845 | 15370 | 120986.6667 | N/A | N/A | N/A | N/A | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 35.42 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P22954 | Technical Support Step 1 | Owain Jones | HUV | HUARUI SPIRIT AEROSPACE MANUFACT | ME | Level 2 | REIM |  |  |  |  | 94.81% | 58.01% | 58.01% | 0 | 0.31% | 155501 | 147432 | 8069 |  | 23043 | 23043 | 0 | 85525 | 61906.09 | 61906 | 0 | 85525 | N/A | N/A | N/A | N/A | 0 | 30% | 30.31% | 0% | -30% |  | 60.79 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23508 | Verification and Validation | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 69.59% | 90.49% | 60.83% | 29107.8 | 11.23% | 212950 | 148188 | 64762 |  | 0 | 0 | 0 | 134098 | 91 | 14091 | 52752 | 90138 | N/A | N/A | N/A | N/A | 29107.8 | 24% | 35.23% | 36.36% | 12.36% |  | 78.5 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23506 | ASTER Mid-Life Refurbishment Project Manager | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 66.33% | 93.61% | 83.11% | 0 | 0.96% | 224900 | 149179 | 75721 |  | 2329 | 2329.13 | 0 | 139651 | 49.26 | 9528 | 18810 | 123976 | N/A | N/A | N/A | N/A | 0 | 25% | 25.96% | 26.59% | 1.59% |  | 110 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P22440 | Spirit Managed Service - F&DT and Static Approval | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 3 |  |  | 88.56% | 92.56% | 92.56% | 0 | 11.51% | 173500 | 153656 | 19844 |  | 52115 | 55720 | 0 | 142225 | 13717.36 | 11431 | 0 | 142225 | 0 | 0 | 0 | 0 | 0 | 0% | 11.51% | 0% | 0% |  | 44.73 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23505 | EXP-022 Meteor TBUS T&E support | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 64.62% | 93.18% | 33.08% | 0 | -0.3% | 246744 | 159448 | 87296 |  | 0 | 0 | 0 | 148579 | 231.57 | 10869 | 114991 | 52753.1667 | N/A | N/A | N/A | N/A | 0 | 20% | 19.7% | 15.67% | -4.33% |  | 89.83 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23373 | Raytheon Michael Bellini | Natalie Sinclair | RAS | RAYTHEON UNITED KINGDOM LIMITED | EES | Level NC | REIM |  |  |  |  | 78.07% | 92.9% | 73.19% | 0 | -8.35% | 214367 | 167351 | 47016 |  | 0 | 0 | 0 | 155462 | 91.71 | 11889 | 39576 | 122482 | N/A | N/A | N/A | N/A | 0 | 45% | 36.65% | 37.42% | -7.58% |  | 91.61 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23242 | Physical Architecture & System Engineering Support | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 56.85% | 96.21% | 91.2% | 0 | 10.79% | 305459 | 173656 | 131803 |  | 776 | 775.55 | 0 | 167081 | 46.72 | 6576 | 10456 | 158367.6667 | N/A | N/A | N/A | N/A | 0 | 15% | 25.79% | 7.42% | -7.58% |  | 78.14 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23650 | MBDA Recruitment Management costs | Brian Maddrell | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 31.46% | 0 | 181189 | -181189 |  | 0 | 0 | 266000 | 0 | 99.6 | 181189 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 3% | 34.46% | 35.06% | 32.06% |  | 87.14 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23524 | Bombardier Regional Jets (BRJ) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 124.4% | 59.82% | 39.09% | 16409.52 | -4.85% | 146288 | 181938 | -35650 |  | 0 | 0 | 46750 | 108838 | 115.83 | 73100 | 45261 | 71120.5 | N/A | N/A | N/A | N/A | 16409.52 | 18% | 13.15% | 14.9% | -3.1% |  | 43.98 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23472 | Tempest Wing Design | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 67.76% | 120.9% | 94.53% | 0 | -20.4% | 281146 | 190497 | 90649 |  | 177975 | 206400 | 0 | 230237 | 18.56 | -39740 | 60182 | 180085.3333 | N/A | N/A | N/A | N/A | 0 | 23% | 2.6% | 23.37% | 0.37% |  | 44.52 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23008 | Spirit Shorts Project Rachel | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 85.87% | 91.32% | 79.5% | 18585.6 | -7.7% | 228880 | 196531 | 32349 |  | 0 | 0 | 0 | 179473 | 191.78 | 17058 | 27878 | 156241.3333 | N/A | N/A | N/A | N/A | 18585.6 | 13% | 5.3% | 0.31% | -12.69% |  | 46.04 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23603 | Typhoon IMDLR | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | [5 empty] | 0% | 0% | 0 | -3.12% | 0 | 200375 | -200375 |  | 0 | 0 | 189459 | 0 | 187.65 | 200375 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 34% | 30.88% | 32.17% | -1.83% |  | 58.46 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23019 | EXP034-B Actuator Development | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 102.9% | 90.07% | 90.07% | 0 | -14.61% | 215541 | 221819 | -6278 |  | 11901 | 11992.81 | 0.00 | 199797 | 31.84 | 5045 | 0 | 199797 | N/A | N/A | N/A | N/A | 0 | 34% | 19.39% | 30.52% | -3.48% |  | 58.45 | [5 empty] | -16977
1722 | 2024-01-25 00:32 | P23316 | Model Factory IL and AW | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX | 2024-01-12 | 13 |  |  | 88.13% | 104.1% | 96.46% | 0 | 2.17% | 250000 | 220328 | 29672 |  | 0 | 0 | 0 | 229409 | 32.72 | -913 | 20249 | 212534.8333 | 0 | 20248.8 | 0 | 0 | 0 | 30% | 32.17% | 32.57% | 2.57% |  | 45.31 | [5 empty] | 8168
1722 | 2024-01-25 00:32 | P23007 | EXP-006A - Brimstone 3 | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 92.66% | 96.5% | 86.31% | 17427 | -8.66% | 264150 | 244766 | 19384 |  | 0 | 0 | 0 | 236210 | 99.54 | 8527 | 29956 | 211246.6667 | N/A | N/A | N/A | N/A | 17427 | 30% | 21.34% | 29.94% | -0.06% |  | 68.95 | [5 empty] | -30
1722 | 2024-01-25 00:32 | P23617 | Tempest Composites WP2 | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  |  | 100.8% | 23.81% | 4.137% | 29536.68 | 3.91% | 244405 | 246260 | -1855 |  | 0 | 0 | 0 | 58643 | 152.32 | 187617 | 58145 | 10188.8333 | 28608.29 | 0 | 0 | 29536.68 | 29536.68 | 30% | 33.91% | 35.95% | 5.95% |  | 62.14 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23255 | BAE Tempest WP 1 Circuits | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | 2023-10-20 | 1 |  |  | 70.38% | 99.34% | 99.34% | 0 | -2.72% | 355782 | 250395 | 105387 |  | 1654 | 1654.32 | 0 | 248740 | 0.38 | 0 | 0 | 248740 | N/A | N/A | N/A | N/A | 0 | 31% | 28.28% | 100% | 69% |  | 50.3 | [5 empty] | -1654
1722 | 2024-01-25 00:32 | P23317 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX | 2024-01-12 | 16 |  |  | 95.89% | 104.3% | 98.16% | 0 | 4.05% | 251800 | 241447 | 10353 |  | 0 | 0 | 0 | 251800 | 32.05 | -1177 | 17760 | 237000 | 0 | 17760 | 0 | 0 | 0 | 25% | 29.05% | 40.59% | 15.59% |  | 36.29 | [5 empty] | 9176
1722 | 2024-01-25 00:32 | P22798 | CO2MAP MGSE | Harry James Kellett | DTW | THALES ALENIA SPACE UK (60DAYS) | EES | Level 2 | REIM | 2023-11-08 | 0 |  |  | 85.75% | 105% | 105% | 0 | 3.94% | 252086 | 216158 | 35928 |  | 0 | 0 | 0 | 227053 | 11943.56 | 25097 | 0 | 227053 | N/A | N/A | N/A | N/A | 0 | 29% | 32.94% | 0% | -29% |  | 50.31 | [5 empty] | 35992
1722 | 2024-01-25 00:32 | P21463 | Safety & Monitoring Systems at DM Beith & Gosport | Harry James Kellett | BXW | MOD | EES | Level 2 | FIX |  |  |  |  | 73.87% | 135.4% | 135.4% | 0 | -27.83% | 349405 | 258110 | 91295 |  | 54828 | 65691.93 | 11769 | 349387 | 0 | -91277 | 0 | 349387 | 0 | 0 | 0 | 0 | 0 | 48% | 20.17% | 42.12% | -5.88% |  | 52.14 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23694 | Systems Portfolio | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 44.97% | 77.35% | 38.15% | 0 | 6.97% | 591943 | 266199 | 325744 |  | 158 | 157.75 | 0 | 205909 | 51.95 | 60290 | 125228 | 101552.3333 | N/A | N/A | N/A | N/A | 0 | 21% | 27.97% | 26.97% | 5.97% |  | 94.9 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23308 | NATO JEWCS | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  |  | 76.77% | 86.12% | 86.12% | 0 | -3.04% | 356307 | 273530 | 82777 |  | 614 | 613.89 | 0 | 235576 | 116.92 | 37953 | 0 | 235576 | N/A | N/A | N/A | N/A | 0 | 24% | 20.96% | 12.52% | -11.48% |  | 75.81 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23045 | Shotgun Adaptors - 10 Sets | Harry James Kellett | BDW | MBDA UK LIMITED | EES | Level 2 | FIX |  |  |  |  | 74.73% | 95.15% | 95.15% | 0 | -19.12% | 399276 | 298392 | 100884 |  | 214430 | 214551.21 | 0 | 283926 | 384.31 | 14467 | 0 | 283926 | 0 | 0 | 0 | 0 | 0 | 29% | 9.88% | 0% | -29% |  | 55.76 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P22515 | Shorts A220 100/300 ALI Phase III | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 76.15% | 97.5% | 93.51% | 0 | 1.12% | 400629 | 305098 | 95531 |  | 3451 | 3450.98 | 0 | 297465 | 99.12 | 7633 | 14584 | 285311.6667 | N/A | N/A | N/A | N/A | 0 | 10% | 11.12% | 19.08% | 9.08% |  | 40.27 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P22953 | Spirit Shorts eVTOL | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 103.1% | 79.36% | 79.36% | 0 | -6.74% | 324272 | 334484 | -10212 |  | 66697 | 67387.9 | 0 | 265432 | 179.02 | 69052 | 0 | 265432 | N/A | N/A | N/A | N/A | 0 | 17% | 10.26% | 0% | -17% |  | 46.19 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23531 | BAe Systems F35 MRB Support | Andrew Houghton | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM | [5 empty] | 78.31% | 70.69% | 0 | 2.1% | 0 | 341310 | -341310 |  | 287 | 287.44 | 0 | 267283 | 67.08 | 74027 | 31232 | 241256.3333 | N/A | N/A | N/A | N/A | 0 | 25% | 27.1% | 33.54% | 8.54% |  | 58.76 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P22842 | ME Support (Aim Altitude) | James Montgomery | AVI | AIM ALTITUDE UK LIMITED | ME | Level 3 | FIX | 2023-06-14 | 4 |  |  | 99.31% | 100.5% | 86.63% | 57290.84 | 0.49% | 346294 | 343918 | 2376 |  | 2910 | 2909.86 | 0 | 345673 | 55184.93 | -1755 | 57291 | 297930.5 | 0 | 0 | 0 | 57290.84 | 57290.84 | 13% | 13.49% | 0% | -13% |  | 46.3 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23023 | Spirit Shorts R Foster/M Gourley | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  |  | 80.28% | 102.3% | 98.39% | 0 | -20.05% | 416652 | 334506 | 82146 |  | 188776 | 216366 | 0 | 342363 | 68.81 | 6655 | 15899 | 329113.8333 | N/A | N/A | N/A | N/A | 0 | 27% | 6.95% | 9.93% | -17.07% |  | 29.46 | [5 empty] | 14511
1722 | 2024-01-25 00:32 | P22391 | GE System Engineering support | Vinayakumar Sugur | GEE | EXPERIS LIMITED | EES | Level NC | REIM |  |  |  |  | 82.01% | 94.79% | 94.11% | 0 | 0.13% | 434434 | 356261 | 78173 |  | 0 | 0 | 0 | 337712 | 90.59 | 18549 | 2939 | 335262.8333 | N/A | N/A | N/A | N/A | 0 | 6% | 6.13% | 6.09% | 0.09% |  | 57.33 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23520 | FCAS AP Portfolio Systems | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 44% | 92.19% | 80.17% | 0 | -7% | 810821 | 356767 | 454054 |  | 320 | 319.5 | 0 | 328919 | 51.14 | 27848 | 51480 | 286019 | N/A | N/A | N/A | N/A | 0 | 22% | 15% | 16.71% | -5.29% |  | 78.69 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23554 | Dornier Seawings 328 2023 H2 Support | Steven Lawton | DAX | EXPLEO GERMANY GMBH (EC) | MPE | Level 2 | REIM |  |  |  |  | 89.24% | 94.38% | 94.38% | 0 | 7.61% | 416112 | 371335 | 44777 |  | 3551 | 3550.65 | 25985 | 350449 | 14.68 | 20886 | 0 | 350449 | N/A | N/A | N/A | N/A | 0 | 21% | 28.61% | 33.06% | 12.06% |  | 67.38 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23366 | Business Analyst Support | Peter Williams | BDZ | MBDA UK LIMITED | DET | Level NC | REIM |  |  |  |  | 28.46% | 258.6% | 203.3% | 0 | 15.59% | 583200 | 165970 | 417230 |  | 165970 | 416921.86 | 0 | 429280 | 84.58 | -25175 | 110208 | 337440 | N/A | N/A | N/A | N/A | 0 | 43% | 58.59% | 26% | -17% |  | 0.01 | [5 empty] | 238135
1722 | 2024-01-25 00:32 | P23432 | Spirit Belfast MRB On-Site Support (Mon & Clear) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 65.77% | 125.6% | 93.11% | 89696.1 | -11.53% | 449545 | 295665 | 153880 |  | 295665 | 451827.33 | 0 | 371466 | 40.74 | 36200 | 115405 | 275295.1667 | N/A | N/A | N/A | N/A | 89696.1 | 39% | 27.47% | 0% | -39% |  | 0 | [5 empty] | 112000
1722 | 2024-01-25 00:32 | P23473 | Tempest Vertical Tail | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 56.42% | 96.28% | 71.91% | 0 | -2.94% | 723866 | 408378 | 315488 |  | 86413 | 100425 | 0 | 393177 | 72.99 | 15201 | 119404 | 293673.6667 | N/A | N/A | N/A | N/A | 0 | 24% | 21.06% | 27.05% | 3.05% |  | 62.68 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23320 | Lifing Services DACs | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX | 2024-01-12 | 26 |  |  | 95.56% | 104.6% | 97.44% | 0 | 2.72% | 413300 | 394956 | 18344 |  | 0 | 0 | 0 | 413300 | 31.82 | -2050 | 34139 | 384850.8333 | 0 | 34138.8 | 0 | 0 | 0 | 26% | 28.72% | 44.21% | 18.21% |  | 33.15 | [5 empty] | 16294
1722 | 2024-01-25 00:32 | P22906 | Spirit Shorts - MRB JD Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  |  | 67.1% | 101.6% | 72.29% | 38901.6 | -7.54% | 614770 | 412480 | 202290 |  | 0 | 0 | 0.00 | 419106 | 230.9 | 1375 | 145102 | 298187.6667 | N/A | N/A | N/A | N/A | 38901.6 | 13% | 5.46% | 3.61% | -9.39% |  | 36.8 | [5 empty] | 8000
1722 | 2024-01-25 00:32 | P23602 | EXP-025 Portfolio Software Engineering Support | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 35.19% | 83.14% | 61.23% | 0 | -0.48% | 1221060 | 429688 | 791372 |  | 0 | 96.65 | 0 | 357244 | 55.21 | 72445 | 112951 | 263118.1667 | N/A | N/A | N/A | N/A | 0 | 24% | 23.52% | 24.08% | 0.08% |  | 82.48 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23140 | Spirit Shorts A220 MLG Stress Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  |  | 68.23% | 91.24% | 81.33% | 48343.2 | -15.08% | 595746 | 406456 | 189290 |  | 20870 | 87811.88 | 0.00 | 370857 | 117.36 | 60599 | 48343 | 330571.1667 | 0 | 0 | 0 | 48343.2 | 48343.2 | 32% | 16.92% | 14.85% | -17.15% |  | 47.35 | [5 empty] | 25000
1722 | 2024-01-25 00:32 | P23372 | BAE Carbon Tooling Off-load | Gary Kempster | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  |  | 165.3% | 56.3% | 56.3% | 0 | -4.12% | 276718 | 457433 | -180715 |  | 0 | 0 | 197460.80 | 257522 | 168.77 | 199912 | 0 | 257522 | N/A | N/A | N/A | N/A | 0 | 27% | 22.88% | 21.55% | -5.45% |  | 53.57 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23323 | CNC-CMM Programming Support | Andrew Houghton | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  |  | 111.8% | 78.09% | 78.09% | 0 | -4.89% | 416048 | 464967 | -48919 |  | 13662 | 13661.56 | 95785.2 | 363077 | 98.72 | 101890 | 0 | 363077 | N/A | N/A | N/A | N/A | 0 | 32% | 27.11% | 30.25% | -1.75% |  | 56.08 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23001 | Spirit Shorts A220 Design | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 113.6% | 73.34% | 68.27% | 0 | -3.68% | 439560 | 499217 | -59657 |  | 0 | 0 | 65953.2 | 366148 | 330.37 | 133069 | 30405 | 340810.5 | N/A | N/A | N/A | N/A | 0 | 25% | 21.32% | 11.21% | -13.79% |  | 43.64 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P22652 | L3 - Saftey Engineering | Sean Simmons | LHW | L3HARRIS MAPPS LIMITED | EES | Level NC | FIX |  |  |  |  | 95.63% | 86.69% | 86.69% | 0 | 5.66% | 523390 | 500498 | 22892 |  | 0 | 0 | 0 | 433883 | 79938 | 66615 | 0 | 433883 | 0 | 0 | 0 | 0 | 0 | 21% | 26.66% | 25.88% | 4.88% |  | 83.05 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23426 | BAE Tempest WP 3 Harness Maturation | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 58.02% | 91.17% | 65.44% | 0 | -6.2% | 884012 | 512868 | 371144 |  | 213 | 213.34 | 0 | 467592 | 83.23 | 45276 | 158396 | 335595.3333 | N/A | N/A | N/A | N/A | 0 | 33% | 26.8% | 28.68% | -4.32% |  | 51 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23281 | Systems Portfolio | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 44.43% | 97.19% | 97.19% | 0 | -17.1% | 1177697 | 523237 | 654460 |  | 2133 | 2133.28 | 0 | 508545 | 17523.23 | 14603 | 0 | 508545 | N/A | N/A | N/A | N/A | 0 | 25% | 7.9% | 0% | -25% |  | 70.48 | [5 empty] | -89
1722 | 2024-01-25 00:32 | P23605 | Typhoon Work Package 2 Continuation | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM |  |  |  |  | 340.2% | 0% | 0% | 0 | -0.14% | 155094 | 527707 | -372613 |  | 4054 | 4054 | 356939.46 | 0 | 169.1 | 527707 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 28% | 27.86% | 27.09% | -0.91% |  | 55.34 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P21138 | D&A Vibration Reduc Damping Struc FOGV Components | Steven Lawton | ATC | AECC SICHUAN GAS TURBINE | MPE | Level 1 | FIX | 2022-09-07 | 0 |  |  | 96.12% | 104% | 104% | 0 | -3.44% | 569346 | 547228 | 22118 |  | 75182 | 75181.75 | 0 | 569346 | 0 | -11 | 0 | 569346 | 0 | 0 | 0 | 0 | 0 | 36% | 32.56% | 0% | -36% |  | 73.95 | [5 empty] | 22107
1722 | 2024-01-25 00:32 | P23219 | Tornado Air 800 Engineering Support | Richard Brook | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 3 | REIM |  |  |  |  | 95.46% | 98.51% | 98.51% | 0 | 1.46% | 615046 | 587098 | 27948 |  | 459 | 459.21 | 314840 | 578373 | 10470.24 | 8725 | 0 | 578373 | N/A | N/A | N/A | N/A | 0 | 31% | 32.46% | 0% | -31% |  | 81.76 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23451 | BAE Tempest - DFM-ASO Planning | Andrew Houghton | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  |  | 62.8% | 68.47% | 25.5% | 0 | -4.07% | 953905 | 599059 | 354846 |  | 0 | 0 | 0 | 410202 | 156.95 | 188857 | 308940 | 152752 | N/A | N/A | N/A | N/A | 0 | 28% | 23.93% | 24.84% | -3.16% |  | 53.19 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P22790 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 2 | REIM |  |  |  |  | 194.5% | 90.44% | 90.44% | 0 | 1.37% | 352240 | 685262 | -333022 |  | 1612 | 1611.52 | 515246 | 619744 | 41098.04 | 34248 | 0 | 619744 | N/A | N/A | N/A | N/A | 0 | 13% | 14.37% | 0% | -13% |  | 45.06 | [5 empty] | -31270
1722 | 2024-01-25 00:32 | P23321 | EHM Cloud Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  |  | 88.93% | 112.5% | 104.8% | 0 | 2.82% | 839969 | 746964 | 93005 |  | 0 | 0 | 24980 | 839969 | 30.27 | -10465 | 69002 | 782467.3333 | 0 | 69002.4 | 0 | 0 | 0 | 28% | 30.82% | 62.99% | 34.99% |  | 49.95 | [5 empty] | 82540
1722 | 2024-01-25 00:32 | P22350 | EMP 2020-2021 | Liam Jacob Lewis Bryant | ARY | GUIDANT GROUP (trading name) | PCPR | Level NC | REIM |  |  |  |  | 98.51% | 98.33% | 94.77% | 0 | -1.87% | 930212 | 916335 | 13877 |  | 400 | 400 | 0.00 | 901021 | 64.72 | 15313 | 39084 | 868451 | N/A | N/A | N/A | N/A | 0 | 32% | 30.13% | 28.69% | -3.31% |  | 44.02 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23105 | Raytheon Supply Engineering Support | Natalie Sinclair | RAY | RAYTHEON UNITED KINGDOM LIMITED | MPE | Level 3A | REIM | 2023-07-13 | 1 |  |  | 79.67% | 90.07% | 90.07% | 0 | -1.83% | 1164044 | 927395 | 236649 |  | 0 | 0 | 0 | 835328 | 110481.3 | 92068 | 0 | 835328 | N/A | N/A | N/A | N/A | 0 | 26% | 24.17% | 0% | -26% |  | 48.97 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23519 | Mechanical and Electrical Design Eng Support | Dushan Fernando | BAX | SAFRAN SEATS GB LIMITED | MPE | Level 2 | REIM |  |  |  |  | 114.6% | 85.4% | 61.32% | 0 | -1.48% | 839697 | 962527 | -122830 |  | 727 | 727 | 118098 | 821977 | 87.72 | 140549 | 278137 | 590196.1667 | N/A | N/A | N/A | N/A | 0 | 33% | 31.52% | 32.41% | -0.59% |  | 56.58 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23117 | BAE Typhoon Eng Support | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 107.6% | 88.52% | 88.52% | 0 | -1.44% | 950772 | 1022826 | -72054 |  | 19090 | 21165.02 | 69773.84 | 905368 | 108434.61 | 90362 | 0 | 905368 | N/A | N/A | N/A | N/A | 0 | 30% | 28.56% | 0% | -30% |  | 52.3 | [5 empty] | -27096
1722 | 2024-01-25 00:32 | P23292 | BAE Tempest WP 4 AV Trays | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 67.4% | 93.48% | 75.81% | 0 | 2.11% | 1498284 | 1009912 | 488372 |  | 0 | 0 | 0 | 944039 | 82.68 | 65874 | 214053 | 765661.5 | N/A | N/A | N/A | N/A | 0 | 32% | 34.11% | 33.42% | 1.42% |  | 52.77 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23152 | Project Aragon - Design and Stress Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  |  | 105.5% | 63.21% | 63.21% | 0 | -9.46% | 1093504 | 1153808 | -60304 |  | 0 | 0 | 0 | 729296 | 248.59 | 424512 | 0 | 729296 | N/A | N/A | N/A | N/A | 0 | 39% | 29.54% | 31.02% | -7.98% |  | 51.84 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P22671 | Spirit Shorts Pylon and Fairing Package | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX | 2023-05-03 | 4 |  |  | 105% | 95.27% | 95.27% | 0 | -7.21% | 1198495 | 1258028 | -59533 |  | 106451 | 174863.91 | 0 | 1198495 | 2492.21 | 2077 | 0 | 1198495 | 0 | 0 | 0 | 0 | 0 | 20% | 12.79% | 0% | -20% |  | 45.4 | [5 empty] | -57456
1722 | 2024-01-25 00:32 | P23435 | Andy Baker Portfolio | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 41.64% | 88.47% | 80.02% | 0 | -8.82% | 3377457 | 1406363 | 1971094 |  | 2353 | 2352.57 | 0 | 1244199 | 60.3 | 162164 | 142595 | 1125369.8333 | N/A | N/A | N/A | N/A | 0 | 25% | 16.18% | 12.72% | -12.28% |  | 77.87 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23315 | DAC LUC BAU and Service Workbench | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  |  | 81.02% | 123.4% | 110.6% | 0 | 2.84% | 1573630 | 1274977 | 298653 |  | 180 | 180.3 | 0 | 1573630 | 14.08 | -100856 | 195596 | 1410633.3333 | 0 | 195596.4 | 0 | 0 | 0 | 28% | 30.84% | 47.97% | 19.97% |  | 52.47 | [5 empty] | 197797
1722 | 2024-01-25 00:32 | P23411 | Agile & Scrum Delivery Service | Peter Williams | BDZ | MBDA UK LIMITED | DET | Level 2 | REIM | 2023-08-14 | 1 |  |  | 36.3% | 170.5% | 170.5% | 0 | 13.08% | 2487000 | 902904 | 1584096 |  | 894179 | 2337284.55 | 0 | 1539600 | 91 | 16141 | 0 | 1539600 | N/A | N/A | N/A | N/A | 0 | 29% | 42.08% | 0% | -29% |  | 74.57 | [5 empty] | 652837
1722 | 2024-01-25 00:32 | P23207 | A350 Approvers - Design and Stress Support | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  |  | 102.4% | 73.38% | 56.9% | 169776.21 | -10.57% | 1670400 | 1711276 | -40876 |  | 15044 | 15337.17 | 0 | 1255654 | 127.93 | 455622 | 338325 | 973716.5 | 0 | 91957.54 | 76590.9 | 169776.21 | 169776.21 | 29% | 18.43% | 21.11% | -7.89% |  | 54.63 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23006 | Spirit Shorts A350 Freighter Toulouse | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 138.4% | 86.14% | 78.37% | 0 | 18.39% | 1035746 | 1433836 | -398090 |  | 1086670 | 1708220.2 | 0 | 1235101 | 311.98 | 510009 | 133601 | 1123766.8333 | N/A | N/A | N/A | N/A | 0 | 5% | 23.39% | 38.6% | 33.6% |  | 47.36 | [5 empty] | 311274
1722 | 2024-01-25 00:32 | P22278 | TAI Supply Engineers to Ankara | Natalie Sinclair | TAI | TUSAS-TURK HAVACILIK VE UZAY | MPE | Level 3A | REIM |  |  |  |  | 18.99% | 474% | 467.3% | 0 | -15.49% | 2105282 | 399745 | 1705537 |  | 49400 | 49400.29 | 0 | 1894696 | 145.25 | -12895 | 32000 | 1868029.3333 | N/A | N/A | N/A | N/A | 0 | 95% | 79.51% | 64.17% | -30.83% |  | 34.35 | [5 empty] | 1482056
1722 | 2024-01-25 00:32 | P23257 | BAE Tempest WP 5 Centre Fuselage | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 92.35% | 98.46% | 89.17% | 0 | -5.88% | 2106861 | 1945624 | 161237 |  | 78100 | 78100 | 0 | 1915593 | 73.9 | 30031 | 216905 | 1734838.8333 | N/A | N/A | N/A | N/A | 0 | 33% | 27.12% | 26.72% | -6.28% |  | 61.04 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23175 | BAe Aero Typhoon Package 2 | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM |  |  |  |  | 103.8% | 96.32% | 96.32% | 0 | -1.63% | 1984265 | 2060012 | -75747 |  | 57678 | 86030.82 | 15444.64 | 1984257 | 84731.75 | 70610 | 0 | 1984257 | N/A | N/A | N/A | N/A | 0 | 29% | 27.37% | 0% | -29% |  | 51.76 | [5 empty] | -5145
1722 | 2024-01-25 00:32 | P19020 | Spirit Concessions - 2018 | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2024-01-23 | 17 |  |  | 90.82% | 111.8% | 107% | 99792.83 | 2.09% | 1914847 | 1739018 | 175829 |  | 44318 | 44317.61 | 15178.88 | 1944711 | 1891.21 | 196987 | 99793 | 1861550.1667 | 0 | 0 | 0 | 99792.83 | 99792.83 | 25% | 27.09% | 10.92% | -14.08% |  | 40.87 | [5 empty] | 402680
1722 | 2024-01-25 00:32 | P23487 | Tornado Air 800 Engineering Support | Richard Brook | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 2 | FIX |  |  |  |  | 105% | 86.25% | 61.31% | 0 | 1.27% | 2245732 | 2358000 | -112268 |  | 0 | 0 | 196775 | 2033785 | 120.08 | 324215 | 705741 | 1445667.5 | 0 | 705741.02 | 0 | 0 | 0 | 34% | 35.27% | 37.6% | 3.6% |  | 78.7 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P23179 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX |  |  |  |  | 128.3% | 85.57% | 81% | 35500.91 | -9.5% | 1921629 | 2465824 | -544195 |  | 155464 | 246717.26 | 492000 | 2110117 | 372.21 | 355707 | 135230 | 1997425.3333 | 0 | 99728.59 | 0 | 35500.91 | 35500.91 | 22% | 12.5% | 9.49% | -12.51% |  | 44.4 | [5 empty] | 0
1722 | 2024-01-25 00:32 | P19731 | Hapri HPC Rear Bearing Housing PDR & CDR | Steven Lawton | ATC | AECC Hunan Aviation Powerplant | MPE | Level 1 | FIX |  |  |  |  | 99.29% | 100.7% | 88.13% | 447000 | -15.32% | 2980000 | 2958856 | 21144 |  | 358408 | 512832.98 | 0 | 2980000 | 728.53 | -246144 | 447000 | 2607500 | 0 | 447000 | 0 | 0 | 447000 | 38% | 22.68% | 23.53% | -14.47% |  | 64.86 | [5 empty] | -225000
Extend Table

## AP1-4
WIP No | Date Created | Project ID | Project Description | Project Manager | Department Id | Client | CBU | Complexity | Type | Stop Booking Hrs | Closing Project: Action(s) to close | RAG | Approx. PO Burndown (weeks) | Turnover vs Contract Value | Invoice To Date vs Turnover | Cash in vs Turnover | Open Amount Overdue | Actual PM% to Baseline PM% delta | Contract Value | Total Project Turnover | Contract Value - Total Turnover | Run Rate (based on total turnover) | Total BOI Spend to Date | Total Committed PO (supplier/best shore) | Current AA in PT3 | Invoiced To Date | DSO | Unbilled (WIP) | Total Open Amount | Cash in (Invoiced - (Open amount -VAT)) | Debt <=30 Days | Debt 31 - 60 Days | Debt 61 - 90 Days | Debt >= 90 Days | Open Amount Overdue2 | Baseline Project Margin | Project To Date (PTD) PM | Year to Date (YTD) PM | YTD Delta Actual PM% to BPM% | Forecast PM at Completion (Manual input from PTT) | Average Sale Rate | CSat score for last quarter (Manual input from PTT) | Comments and Actions | Judged income adjustment at completion | Profit to take now | Provision required now | Fully Traded | Last Months Comments and Actions
1723 | 2024-02-01 00:34 | P23641 | Drawing Triage | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM | 2024-01-25 | 1 |  |  |  | 0% | 0% | 0 | 1043368% | 0 | 10756 | -10756 |  | 0 | 0 | 11343.2 | 0 | 0 | -1 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 1043368% | 100% | 100% |  | 49 | [5 empty] | -10756
1723 | 2024-02-01 00:34 | P23637 | MBSE Proposal | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 |  | 0 | 0 | 49980 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23711 | DO NOT USE - RAISED IN ERROR | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23585 | Systems Design - Missile Systems, Meteor,Brimstone | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 |  | 0 | 0 | 49500.00 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23543 | EXP-024 FCAS AP Transformation & Change Enablers | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -26% | 385921 | 0 | 385921 |  | 0 | 0 | 0.00 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 26% | 0% | 0% | -26% |  | 0 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23552 | FCAS AP Product Technology Development | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -25% | 597871 | 0 | 597871 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 25% | 0% | 0% | -25% |  | 0 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23137 | BAE Management Support Collector | John Clements | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3A | REIM | [5 empty] | 0% | 0% | 0 | -44357052% | 0 | 100437 | -100437 |  | 1053 | 1053.38 | 100000 | 0 | 0.3 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | -44357052% | 0% | 0% |  | 50 | [5 empty] | -100437
1723 | 2024-02-01 00:34 | P23730 | FLE Project | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -36.6% | 0 | 105 | -105 |  | 0 | 0 | 24000.00 | 0 | 27 | 105 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | -36.6% | -36.6% | -36.6% |  | 35 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23598 | MRB Onsite support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -18% | 0 | 880 | -880 |  | 880 | 14079.58 | 13200 | 0 | 91 | 880 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 18% | 0% | 0% | -18% |  | 0 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23463 | A220 Wing MaMo Design Checking | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 7.85% | 0 | 1628 | -1628 |  | 0 | 0 | 15000 | 0 | 1953.6 | 1628 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 3% | 10.85% | 0% | -3% |  | 44 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23597 | MRB Onsite support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -18% | 0 | 1682 | -1682 |  | 1682 | 17381.62 | 15700 | 0 | 91 | 1682 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 18% | 0% | 0% | -18% |  | 0 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23740 | Phase 2 - EJ200 ESS EHM Platform Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 3 | FIX |  |  |  |  | 1.432% | 997.6% | -0.006614% | 0 | 3.56% | 175971 | 2520 | 173451 |  | 0 | 0 | 0 | 25139 | 27 | -22619 | 30167 | -0.16667 | 30166.8 | 0 | 0 | 0 | 0 | 28% | 31.56% | 31.56% | 3.56% |  | 80 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P21028 | Rebate Collection (BACC) | David Catchpole | TOO | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | [5 empty] | 0% | 0% | 0 | 0% | 0 | 2680 | -2680 |  | 2680 | 2680 | 0 | 0 | 3216 | 2680 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23717 | GKN Ted Tomblin 2024 | Matthew Tweed | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 21.57% | 0 | 3162 | -3162 |  | 0 | 0 | 3672 | 0 | 27 | 3162 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 21.57% | 21.57% | 21.57% |  | 51 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23578 | ESN Work Package | Hannah Mead | COZ | CHELTON LIMITED | DET | Level 3 | FIX | 2024-01-01 | 0 |  |  | 86.17% | 116.1% | 116.1% | 0 | 35.86% | 4410 | 3800 | 610 |  | 0 | 0 | 0 | 4410 | 0 | -610 | 0 | 4410 | 0 | 0 | 0 | 0 | 0 | 24% | 59.86% | 0% | -24% |  | 95 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23628 | Design Assurance | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -6.67% | 0 | 3909 | -3909 |  | 0 | 0 | 4454.80 | 0 | 4691.09 | 3909 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 7% | 0.33% | 0% | -7% |  | 15.05 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23718 | Requalification of EJ200 GSS ESS EHM SW module | Vijayakumara Nanjundappa | ARZ | MTU AERO ENGINES AG | DET | Level 3 | FIX |  |  |  |  | 5.36% | 0% | 0% | 0 | -6.49% | 74463 | 3991 | 70472 |  | 881 | 881.46 | 0 | 0 | 27 | 3991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 21.51% | 21.51% | -6.49% |  | 80 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23002 | WoT MAJ Transit Flag Stress | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 30.9% | 323.7% | 323.7% | 0 | 53.84% | 4735 | 1463 | 3272 |  | 0 | 2242.5 | 0 | 4735 | 0.6 | 1 | 0 | 4735 | 0 | 0 | 0 | 0 | 0 | 10% | 63.84% | 0% | -10% |  | 45 | [5 empty] | 3273
1723 | 2024-02-01 00:34 | P23724 | GKN S McConnell 2024 | Matthew Tweed | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  |  | 14% | 0% | 0% | 0 | 1.51% | 49820 | 6975 | 42845 |  | 0 | 0 | 0.00 | 0 | 27 | 6975 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 19% | 20.51% | 20.51% | 1.51% |  | 49.82 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23607 | SAFRAN - A330neo Turnover Frame | Gary Kempster | TOO | SAFRAN SEATS GB LIMITED | MPE | Level 3 | FIX |  |  |  |  | 95.68% | 0% | 0% | 0 | -19.75% | 8736 | 8359 | 377 |  | 0 | 0 | 0 | 0 | 10030.8 | 8359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23% | 3.25% | 0% | -23% |  | 52 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23274 | ME Support (Aim Altitude - Cambridge) | James Montgomery | AVI | AVIC CABIN SYSTEMS (UK) LIMITED | ME | Level 3 | FIX | 2023-08-18 | 0 |  |  | 51.88% | 56.29% | 56.29% | 0 | -0.17% | 17280 | 8964 | 8316 |  | 0 | 0 | 0 | 5046 | 4701.24 | 3918 | 0 | 5046 | 0 | 0 | 0 | 0 | 0 | 21% | 20.83% | 0% | -21% |  | 48 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23283 | Spirit Tooling Audit | Charidimos Valadakis | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-05-03 | 0 |  |  | 97.23% | 48.57% | 48.57% | 0 | -7.99% | 9910 | 9635 | 275 |  | 0 | 0 | 0 | 4680 | 5946.05 | 4955 | 0 | 4680 | N/A | N/A | N/A | N/A | 0 | 7% | -0.99% | 0% | -7% |  | 34.41 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23127 | Loft Hall Design Support | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 101% | 99.06% | 99.06% | 0 | -9.55% | 9680 | 9772 | -92 |  | 0 | 0 | 0 | 9680 | 110.4 | 92 | 0 | 9680 | N/A | N/A | N/A | N/A | 0 | 41% | 31.45% | 0% | -41% |  | 44 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23663 | Spirit Tooling Verification and Inspection | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 49.48% | 0% | 0% | 0 | -7.67% | 19820 | 9807 | 10013 |  | 0 | 0 | 7392 | 0 | 99.37 | 9807 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 12% | 4.33% | 4.82% | -7.18% |  | 34.41 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23630 | 2Excel CFD Analysis Support | Dushan Fernando | BAX | STIRLING DYNAMICS LTD | MPE | Level NC | FIX |  |  |  |  | 61.2% | 100% | 100% | 0 | -1.87% | 16195 | 9911 | 6284 |  | 0 | 0 | 0 | 9912 | 0 | 0 | 0 | 9912 | 0 | 0 | 0 | 0 | 0 | 26% | 24.13% | 0% | -26% |  | 64.78 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23760 | Land Ceptor V&V Systems Engineer | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 28.98% | 0 | 10951 | -10951 |  | 0 | 0 | 23550 | 0 | 27 | 10951 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 28.98% | 28.98% | 28.98% |  | 78.5 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23313 | Laser Trim Fixtures | Gary Kempster | TOO | ALKEN ENGINEERING LIMITED | MPE | Level 3 | FIX | 2023-11-20 | 0 |  |  | 89.87% | 111.3% | 111.3% | 0 | 0.53% | 13770 | 12375 | 1395 |  | 0 | 0 | 0 | 13770 | 0 | -1395 | 0 | 13770 | 0 | 0 | 0 | 0 | 0 | 17% | 17.53% | 0% | -17% |  | 45 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23753 | Tempest Composites Maturation | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | [5 empty] | 0% | 0% | 0 | -26.21% | 0 | 12855 | -12855 |  | 0 | 0 | 54398.40 | 0 | 28 | 12855 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 37% | 10.79% | 10.79% | -26.21% |  | 64.76 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P22761 | Red Bull Chassis Spit | James Montgomery | TOO | MANUFAX ENGINEERING LTD | MPE | Level 3 | FIX | 2022-11-15 | 0 |  |  | 72.19% | 96.98% | 96.98% | 0 | 7.92% | 12961 | 9356 | 3605 |  | 0 | 0 | 0 | 9073 | 4666.39 | 3889 | 0 | 9073 | 0 | 0 | 0 | 0 | 0 | 23% | 30.92% | 0% | -23% |  | 42.19 | [5 empty] | 3606
1723 | 2024-02-01 00:34 | P23433 | Cavendish | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 32.81% | 100% | 100% | 0 | -0.34% | 42240 | 13859 | 28381 |  | 0 | 0 | 0 | 13859 | 0 | 0 | 0 | 13859 | N/A | N/A | N/A | N/A | 0 | 7% | 6.66% | 0% | -7% |  | 43.93 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23350 | Spirit 2023 - Stress Approve Man Serv (DH) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 14.15% | 72.64% | 72.64% | 0 | -0.29% | 97920 | 13860 | 84060 |  | 0 | 0 | 0 | 10068 | 4550.4 | 3792 | 0 | 10068 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23344 | Spirit A320 Spoilers Support 2023 | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 38.75% | 100% | 100% | 0 | 5.82% | 35786 | 13867 | 21919 |  | 0 | 0 | 0 | 13867 | 0 | 0 | 0 | 13867 | N/A | N/A | N/A | N/A | 0 | 7% | 12.82% | 0% | -7% |  | 34.41 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23337 | Spirit 2023 - Steve Grimley | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 25.28% | 100% | 100% | 0 | 0.01% | 56813 | 14362 | 42451 |  | 0 | 0 | 0 | 14362 | 0 | 0 | 0 | 14362 | N/A | N/A | N/A | N/A | 0 | 7% | 7.01% | 0% | -7% |  | 30.11 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23729 | Honda Tooling | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX | [5 empty] | 0% | 0% | 0 | -4.13% | 0 | 14696 | -14696 |  | 0 | 0 | 14430.00 | 0 | 21 | 14696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21% | 16.87% | 16.87% | -4.13% |  | 42.2 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23635 | Engineering Services: FAI Support | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 43.24% | 0% | 0% | 0 | -3.47% | 37230 | 16099 | 21131 |  | 0 | 0 | 0.00 | 0 | 139.18 | 16099 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 8% | 4.53% | 5.04% | -2.96% |  | 38.7 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23744 | Model Factory | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  |  | 6.299% | 138.3% | -0.002017% | 0 | 8.39% | 262300 | 16523 | 245777 |  | 0 | 0 | 0 | 22858 | 27 | -6336 | 27430 | -0.33333 | 27429.6 | 0 | 0 | 0 | 0 | 28% | 36.39% | 36.39% | 8.39% |  | 50.76 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23743 | EHM Cloud Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  |  | 1.668% | 504% | -0.001967% | 0 | 5.25% | 1016000 | 16945 | 999055 |  | 0 | 0 | 0 | 85408 | 27 | -68463 | 102490 | -0.33333 | 102489.6 | 0 | 0 | 0 | 0 | 28% | 33.25% | 33.25% | 5.25% |  | 48.69 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23700 | IPDT Leads | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 15.41% | 0 | 16971 | -16971 |  | 0 | 0 | 22200.00 | 0 | 77 | 16971 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 22% | 37.41% | 38.85% | 16.85% |  | 61.88 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23754 | Tempest Composites WP4 | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX | [5 empty] | 0% | 0% | 0 | 8.22% | 0 | 17290 | -17290 |  | 0 | 0 | 97140 | 0 | 42 | 17290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 36.22% | 36.22% | 8.22% |  | 66.69 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23343 | Spirit 2023 - John Agnew | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-08-09 | 0 |  |  | 28.56% | 86.27% | 86.27% | 0 | -0.02% | 65120 | 18601 | 46519 |  | 0 | 0 | 0 | 16047 | 3064.49 | 2554 | 0 | 16047 | N/A | N/A | N/A | N/A | 0 | 7% | 6.98% | 0% | -7% |  | 34.51 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23651 | PMO Spirit | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 24.67% | 0 | 20664 | -20664 |  | 0 | 0 | 30800.00 | 0 | 129.29 | 20664 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 24.67% | 25.03% | 25.03% |  | 36 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23355 | Spirit Tooling Support 2023 | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-23 | 0 |  |  | 22.93% | 89.03% | 89.03% | 0 | -0.82% | 91800 | 21053 | 70747 |  | 0 | 0 | 0 | 18743 | 2773.01 | 2311 | 0 | 18743 | 0 | 0 | 0 | 0 | 0 | 20% | 19.18% | 0% | -20% |  | 44.46 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23351 | Spirit 2023 - Design Man Serv (KL) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 26.47% | 93.15% | 93.15% | 0 | 0.09% | 93840 | 24840 | 69000 |  | 0 | 0 | 0 | 23138 | 2042.4 | 1702 | 0 | 23138 | 0 | 0 | 0 | 0 | 0 | 26% | 26.09% | 0% | -26% |  | 46 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23356 | Spirit 2023 - Design Man Serv (AH) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX | 2023-08-09 | 1 |  |  |  | 76.66% | 0.001332% | 23018.4 | 0.48% | 0 | 25023 | -25023 |  | 0 | 0 | 25300.00 | 19182 | 30027.7 | 5841 | 23018 | 0.33333 | 0 | 0 | 0 | 23018.4 | 23018.4 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P22884 | Spirit Shorts Config Eng | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 66.3% | 100.1% | 100.1% | 0 | 0.56% | 38976 | 25842 | 13134 |  | 0 | 0 | 0 | 25863 | 0 | 0 | 0 | 25863 | N/A | N/A | N/A | N/A | 0 | 7% | 7.56% | 0% | -7% |  | 20.3 | [5 empty] | 21
1723 | 2024-02-01 00:34 | P23642 | MRB Belfast Support | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -17.78% | 0 | 26163 | -26163 |  | 2170 | 2252.31 | 30800.00 | 0 | 107.86 | 26163 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | -17.78% | -17.61% | -17.61% |  | 38.52 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23338 | Spirit 2023 - Blair Hainey | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 76.07% | 68.76% | 68.76% | 0 | 3.55% | 34494 | 26241 | 8253 |  | 0 | 0 | 0 | 18042 | 99.18 | 8199 | 0 | 18042 | N/A | N/A | N/A | N/A | 0 | 7% | 10.55% | 19.31% | 12.31% |  | 18.28 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23354 | Spirit 2023 - Design Man Serv (PC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 27.97% | 99.36% | 99.36% | 0 | 0.48% | 93840 | 26249 | 67591 |  | 0 | 0 | 0 | 26082 | 200.38 | 167 | 0 | 26082 | 0 | 0 | 0 | 0 | 0 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P22756 | A350 FLE Design Checker | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2022-03-23 | 1 |  |  | 68.39% | 119.7% | 119.7% | 0 | 16.46% | 34898 | 23867 | 11031 |  | 23867 | 24342.3 | 0 | 28571 | 0.06 | 0 | 0 | 28571 | N/A | N/A | N/A | N/A | 0 | 0% | 16.46% | 0% | 0% |  | 0 | [5 empty] | 4704
1723 | 2024-02-01 00:34 | P23458 | Spirit Belfast Tooling Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-08-11 | 0 |  |  | 101.3% | 94.65% | 94.65% | 0 | 8.64% | 30384 | 30785 | -401 |  | 0 | 0 | 0 | 29139 | 1974.96 | 1646 | 0 | 29139 | N/A | N/A | N/A | N/A | 0 | 7% | 15.64% | 0% | -7% |  | 42.2 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23741 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  |  | 6.045% | 141.1% | 0% | 0 | 3.83% | 526262 | 31813 | 494449 |  | 0 | 0 | 0 | 44885 | 27 | -13072 | 53862 | 0 | 53862 | 0 | 0 | 0 | 0 | 28% | 31.83% | 31.83% | 3.83% |  | 39.08 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23365 | GKN 777x Lip Skin Fixture | Steven Lawton | TOO | GKN AEROSPACE SERVICES LTD | MPE | Level 3 | FIX | 2023-10-12 | 1 |  |  | 41.91% | 113.2% | 18.86% | 37544.22 | -9.26% | 79161 | 33176 | 45985 |  | 5110 | 5109.88 | 0 | 37544 | 33175.67 | -4369 | 37544 | 6257.3333 | 0 | 37544.22 | 0 | 0 | 37544.22 | 22% | 12.74% | 0% | -22% |  | 56 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P22768 | MRB Onsite Support - Spirit Belfast | James Montgomery | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2023-07-27 | 0 |  |  |  | 0% | 0% | 0 | -17.07% | 0 | 34614 | -34614 |  | 0 | 0 | 36800 | 0 | 41536.8 | 34614 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 10% | -7.07% | 0% | -10% |  | 36 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23347 | WoT Fixed Leading Edge - Industrial 2023 | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 112.8% | 42.03% | 42.03% | 0 | -0.41% | 31034 | 35002 | -3968 |  | 0 | 0 | 10500 | 14711 | 24349.85 | 20292 | 0 | 14711 | N/A | N/A | N/A | N/A | 0 | 7% | 6.59% | 0% | -7% |  | 32.26 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23051 | Spirit Shorts A350 PAX Door | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 3A | REIM |  |  |  |  | 205.9% | 105.4% | 105.4% | 0 | -0.63% | 18216 | 37513 | -19297 |  | 0 | 0 | 0 | 39537 | 0 | 0 | 0 | 39537 | N/A | N/A | N/A | N/A | 0 | 30% | 29.37% | 0% | -30% |  | 46 | [5 empty] | 2024
1723 | 2024-02-01 00:34 | P23739 | Lifing Services DACs | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  |  | 6.374% | 133.1% | -0.0003983% | 0 | 7.44% | 656508 | 41843 | 614665 |  | 0 | 0 | 0 | 55709 | 27 | -13866 | 66851 | -0.16667 | 66850.8 | 0 | 0 | 0 | 0 | 28% | 35.44% | 35.44% | 7.44% |  | 37.92 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P22752 | Tooling WoT - 2021 (Spirit) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | REIM | 2023-05-03 | 0 |  |  | 101.1% | 74.02% | 74.02% | 0 | -8.5% | 41525 | 41982 | -457 |  | 0 | 0 | 0 | 31076 | 13087.42 | 10906 | 0 | 31076 | N/A | N/A | N/A | N/A | 0 | 0% | -8.5% | 0% | 0% |  | 39.09 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23339 | Spirit 2023 - Stewart Russell | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 64.51% | 100% | 100% | 0 | 0.62% | 72767 | 46942 | 25825 |  | 0 | 0 | 0 | 46942 | 0 | 0 | 0 | 46942 | N/A | N/A | N/A | N/A | 0 | 7% | 7.62% | 0% | -7% |  | 35.67 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23322 | GKN T Tomblin 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2023-12-31 | 1 |  |  | 83.13% | 100% | 97.01% | 0 | -0.33% | 58952 | 49008 | 9944 |  | 0 | 0 | 0 | 49008 | 27.62 | 0 | 1757 | 47543.8333 | N/A | N/A | N/A | N/A | 0 | 17% | 16.67% | 0% | -17% |  | 48 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P22760 | SA Leading Edge Transport Media ('A' Frames) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-11-15 | 1 |  |  | 85.99% | 110.7% | 116.3% | -3082.8 | 3.97% | 53481 | 45986 | 7495 |  | 42804 | 42804 | 0 | 50912 | 0 | 0 | -3083 | 53481.1667 | 0 | 0 | 0 | -3082.8 | -3082.8 | 6% | 9.97% | 0% | -6% |  | 42 | [5 empty] | 4926
1723 | 2024-02-01 00:34 | P23341 | Spirit 2023 - Tom McFarlane | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 98.58% | 91.46% | 71.9% | 0 | -0.01% | 54282 | 53513 | 769 |  | 0 | 0 | 0 | 48945 | 130.38 | 4568 | 12560 | 38478.3333 | N/A | N/A | N/A | N/A | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23382 | Performance Modelling | Dushan Fernando | BDX | MBDA UK LIMITED | MPE | Level NC | REIM | 2023-07-09 | 1 |  |  | 40.95% | 79.09% | 79.09% | 0 | -16.36% | 170010 | 69626 | 100384 |  | 14560 | 14659.9 | 0 | 55066 | 0 | 0 | 0 | 55066 | N/A | N/A | N/A | N/A | 0 | 20% | 3.64% | 0% | -20% |  | 77.05 | [5 empty] | -14560
1723 | 2024-02-01 00:34 | P23551 | Ian Berry 2023 H2 | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  |  | 74.7% | 48.83% | 48.83% | 0 | 13.91% | 75810 | 56630 | 19180 |  | 0 | 0 | 0 | 27652 | 147.08 | 28978 | 0 | 27652 | N/A | N/A | N/A | N/A | 0 | 20% | 33.91% | 0% | -20% |  | 75.81 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23349 | Spirit 2023 - Stress Approve Man Serv (SB) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 58.24% | 80.05% | 80.05% | 0 | -0.29% | 97920 | 57024 | 40896 |  | 0 | 0 | 0 | 45648 | 13651.2 | 11376 | 0 | 45648 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23193 | Spirit Shorts Stephen Greer | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 94.71% | 93.88% | 77.57% | 8141.84 | 2.35% | 61472 | 58219 | 3253 |  | 0 | 0 | 0 | 54656 | 130.66 | 3564 | 11394 | 45161 | N/A | N/A | N/A | N/A | 8141.84 | 29% | 31.35% | 34.03% | 5.03% |  | 34.96 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23106 | ME Support to NPD - Bobby Haggart | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  |  | 95.79% | 97.03% | 97.03% | 0 | 0.3% | 65675 | 62912 | 2763 |  | 0 | 0 | 0 | 61043 | 2243.24 | 1869 | 0 | 61043 | 0 | 0 | 0 | 0 | 0 | 15% | 15.3% | 0% | -15% |  | 35.65 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23561 | SAAB | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  |  | 82.46% | 121.1% | 96.66% | 0 | 3.5% | 67485 | 55649 | 11836 |  | 0 | 0 | 0 | 67399 | 91 | -4408 | 16332 | 53789 | N/A | N/A | N/A | N/A | 0 | 16% | 19.5% | 0% | -16% |  | 36.82 | [5 empty] | 7342
1723 | 2024-02-01 00:34 | P22967 | Spirit 2022 - Channapa Laxmeshwar | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2023-01-26 | 2 |  |  | 69.69% | 121.3% | 121.3% | 0 | 9.53% | 75159 | 52376 | 22783 |  | 52376 | 54898.1 | 0 | 63509 | 0.42 | 0 | 0 | 63509 | N/A | N/A | N/A | N/A | 0 | 8% | 17.53% | 0% | -8% |  | 0 | [5 empty] | 11133
1723 | 2024-02-01 00:34 | P23465 | A220 ToW Design Offload (Wing) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 48.34% | 87.39% | 78.13% | 0 | -3.75% | 132000 | 63815 | 68185 |  | 0 | 0 | 0 | 55768 | 62.59 | 8046 | 7088 | 49861.3333 | N/A | N/A | N/A | N/A | 0 | 20% | 16.25% | 17.93% | -2.07% |  | 42.8 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23342 | Spirit 2023 - Channapa Laxmeshwar | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 78.75% | 104.3% | 88.16% | 0 | -2.64% | 79348 | 62484 | 16864 |  | 62484 | 63539 | 0 | 65178 | 83.77 | 157 | 12110 | 55086.3333 | N/A | N/A | N/A | N/A | 0 | 7% | 4.36% | 0% | -7% |  | 0 | [5 empty] | 2850
1723 | 2024-02-01 00:34 | P23677 | ME Managed Service - Phase 1 | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  |  | 75.99% | 0% | 0% | 0 | -10.38% | 86400 | 65655 | 20745 |  | 0 | 0 | 0.00 | 0 | 91 | 65655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16% | 5.62% | 9.66% | -6.34% |  | 45 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23560 | NJEWCS TAF202302 SM | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level 2 | FIX |  |  |  |  | 81.83% | 59.97% | 59.97% | 0 | 12.27% | 81500 | 66695 | 14805 |  | 0 | 0 | 0 | 40000 | 105.63 | 26695 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 28% | 40.27% | 41.09% | 13.09% |  | 73.01 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23586 | Project Management Support | Peter Bowen | BDX | MBDA UK LIMITED | MPE | Level NC | REIM |  |  |  |  | 83.88% | 96.09% | 64.79% | 0 | -25.59% | 80000 | 67104 | 12896 |  | 1141 | 1140.6 | 0 | 64480 | 62.88 | 2624 | 25200 | 43480 | N/A | N/A | N/A | N/A | 0 | 49% | 23.41% | 24.63% | -24.37% |  | 80 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23171 | Spirt Shorts Weights Eng | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 81.27% | 126.1% | 107.5% | 7087.68 | -6.62% | 71760 | 58316 | 13444 |  | 58316 | 76495.95 | 0 | 73553 | 9492.98 | -2967 | 13053 | 62675.5 | N/A | N/A | N/A | N/A | 7087.68 | 24% | 17.38% | 0% | -24% |  | 0 | [5 empty] | 12270
1723 | 2024-02-01 00:34 | P23438 | A220 Spirit Shorts DTC - Stephen Corry | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 150.2% | 56.93% | 56.93% | 0 | -5.49% | 47251 | 70962 | -23711 |  | 0 | 0 | 23745 | 40400 | 148.15 | 30562 | 0 | 40400 | N/A | N/A | N/A | N/A | 0 | 21% | 15.51% | 13.54% | -7.46% |  | 49.69 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23340 | Spirit 2023 - John Cole | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 96.08% | 87.15% | 69.94% | 0 | -0.01% | 75065 | 72121 | 2944 |  | 0 | 0 | 0 | 62852 | 118.65 | 9269 | 14894 | 50440.3333 | N/A | N/A | N/A | N/A | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 39.78 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23080 | Spirit Shorts DManagement Cairan Cullen | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 48.66% | 99.29% | 93.69% | 3787.8 | -0.78% | 149600 | 72798 | 76802 |  | 0 | 0 | 0 | 72284 | 134.15 | 514 | 4892 | 68207.3333 | N/A | N/A | N/A | N/A | 3787.8 | 24% | 23.22% | 18.05% | -5.95% |  | 44.46 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23345 | Spirit 2023- Jonathan Escosio | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 97.03% | 87.44% | 69.52% | 0 | -0.35% | 75971 | 73716 | 2255 |  | 0 | 0 | 0 | 64456 | 123.85 | 9260 | 15846 | 51251 | N/A | N/A | N/A | N/A | 0 | 1% | 0.65% | 0.65% | -0.35% |  | 40.26 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23336 | Spirit 2023 - Neil Rampling | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 55.98% | 87.86% | 63.86% | 6343.82 | -0.01% | 133902 | 74952 | 58950 |  | 0 | 0 | 0.00 | 65851 | 152.2 | 9101 | 21586 | 47862.6667 | N/A | N/A | N/A | N/A | 6343.82 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23545 | Ultra CSS continuation 2023 H2 | Natalie Sinclair | ULT | ULTRA SONAR SYSTEMS LIMITED | EES | Level NC | REIM |  |  |  |  | 98.99% | 58.42% | 58.42% | 0 | 2.3% | 76000 | 75235 | 765 |  | 0 | 0 | 0 | 43956 | 138.1 | 31279 | 0 | 43956 | N/A | N/A | N/A | N/A | 0 | 23% | 25.3% | 0% | -23% |  | 80 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23600 | MBDA EXP-EE-023 Bristone Certification | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 59.65% | 100% | 84.61% | 0 | 0.4% | 126600 | 75517 | 51083 |  | 0 | 0 | 0 | 75517 | 45.5 | 0 | 13942 | 63898.6667 | N/A | N/A | N/A | N/A | 0 | 41% | 41.4% | 0% | -41% |  | 78.5 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23685 | DAC LUC Support and Recompliance | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  |  | 10.59% | 329.6% | 0.000437% | 0 | 2.36% | 720000 | 76274 | 643726 |  | 0 | 0 | 0 | 251427 | 27 | -175154 | 301712 | 0.33333 | 301712.4 | 0 | 0 | 0 | 0 | 28% | 30.36% | 30.36% | 2.36% |  | 68.89 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23583 | Castalla - Test Rig Design | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 113.6% | 79.88% | 79.88% | 0 | -6.81% | 67520 | 76691 | -9171 |  | 0 | 0 | 9706 | 61258 | 65.39 | 15433 | 0 | 61258 | N/A | N/A | N/A | N/A | 0 | 21% | 14.19% | 21.71% | 0.71% |  | 42.43 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P22505 | Spirit MRB Engineering Support 2021 | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 1 |  |  | 91.17% | 100% | 95.78% | 4020.48 | 21.2% | 87110 | 79415 | 7695 |  | 0 | 0 | 0 | 79415 | 4020.48 | 0 | 4020 | 76065 | 0 | 0 | 0 | 4020.48 | 4020.48 | 0% | 21.2% | 0% | 0% |  | 41.88 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23375 | GKN Jaap Peters NL 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2023-12-31 | 5 |  |  | 84.76% | 115.8% | 80.21% | 0 | -15.19% | 89795 | 76111 | 13684 |  | 76111 | 85308.08 | 0.00 | 88129 | 95.02 | -8168 | 32497 | 61048.1667 | N/A | N/A | N/A | N/A | 0 | 20% | 4.81% | 0% | -20% |  | 0 | [5 empty] | 3850
1723 | 2024-02-01 00:34 | P22885 | ME Support (Baxi) | James Montgomery | HUV | BAXI HEATING UK LIMITED | ME | Level 3 | FIX | 2023-01-12 | 0 |  |  | 68.78% | 108.7% | 108.7% | 0 | 13.05% | 106633 | 73340 | 33293 |  | 0 | 0 | 0 | 79748 | 1531.35 | 1276 | 0 | 79748 | 0 | 0 | 0 | 0 | 0 | 15% | 28.05% | 0% | -15% |  | 44.37 | [5 empty] | 7684
1723 | 2024-02-01 00:34 | P23079 | Spirit Shorts Nomenclature | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 93.45% | 93.32% | 82.68% | 10554.48 | 1.78% | 88455 | 82660 | 5795 |  | 0 | 0 | 0.00 | 77138 | 174.94 | 5521 | 10554 | 68343 | N/A | N/A | N/A | N/A | 10554.48 | 20% | 21.78% | 25.23% | 5.23% |  | 30.68 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23335 | GKN S McConnell 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2023-12-31 | 3 |  |  | 96.61% | 100% | 75.29% | 0 | 0.74% | 87420 | 84459 | 2961 |  | 0 | 0 | 0 | 84459 | 136.5 | 0 | 25042 | 63590.6667 | N/A | N/A | N/A | N/A | 0 | 15% | 15.74% | 0% | -15% |  | 47 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P22965 | Spirit 2022 - Design Man Serv (AH) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 1 |  |  | 106.7% | 96.66% | 92.02% | 4759.75 | 3.14% | 80080 | 85441 | -5361 |  | 0 | 0 | 0 | 82589 | 8182.59 | 2852 | 4760 | 78622.3333 | 0 | 0 | 0 | 4759.75 | 4759.75 | 14% | 17.14% | 0% | -14% |  | 42.44 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23523 | Applique Armour Support | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 0 |  |  | 101.6% | 98.47% | 98.47% | 0 | 3.42% | 84300 | 85607 | -1307 |  | 0 | 0 | 0 | 84300 | 1567.8 | 1307 | 0 | 84300 | 0 | 0 | 0 | 0 | 0 | 25% | 28.42% | 0% | -25% |  | 64.29 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P22964 | Spirit 2022 - MRB Man Serv (JC) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 100.6% | 97.95% | 97.95% | 0 | 1.91% | 85435 | 85960 | -525 |  | 0 | 0 | 0 | 84200 | 2112.62 | 1761 | 0 | 84200 | 0 | 0 | 0 | 0 | 0 | 16% | 17.91% | 0% | -16% |  | 42.69 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P22963 | Spirit 2022 - Design Man Serv (PC) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 1 |  |  | 108.6% | 104% | 94.46% | 9938.48 | 3.18% | 80080 | 86927 | -6847 |  | 0 | 0 | 0 | 90390 | 5782.63 | -3463 | 9938 | 82108.3333 | 0 | 0 | 0 | 9938.48 | 9938.48 | 13% | 16.18% | 0% | -13% |  | 42.39 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23353 | Spirit 2023 - MRB Man Serv (JC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  |  | 97.08% | 76.99% | 76.99% | 0 | -0.22% | 91800 | 89123 | 2677 |  | 0 | 0 | 0 | 68615 | 136.3 | 20507 | 0 | 68615 | 0 | 0 | 0 | 0 | 0 | 18% | 17.78% | 0% | -18% |  | 45 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23588 | BAE Typhoon MRB MC Shop Concessions | Andrew Houghton | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 51.87% | 56.75% | 56.75% | 0 | -4.28% | 175061 | 90807 | 84254 |  | 0 | 0 | 0.00 | 51537 | 91.6 | 39270 | 0 | 51537 | N/A | N/A | N/A | N/A | 0 | 31% | 26.72% | 29.15% | -1.85% |  | 55.51 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23664 | Tempest Composites WP3 | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  |  | 74.77% | 18.04% | 0.0007281% | 0 | -5.27% | 122455 | 91563 | 30892 |  | 0 | 0 | 0.00 | 16519 | 102.86 | 75044 | 19822 | 0.66667 | 19822.44 | 0 | 0 | 0 | 0 | 37% | 31.73% | 35.55% | -1.45% |  | 60.43 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23699 | A220 Stress Checkers | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -1.4% | 0 | 94515 | -94515 |  | 0 | 0 | 86440 | 0 | 77 | 94515 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 22% | 20.6% | 21.35% | -0.65% |  | 61.88 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P22918 | Spirit Shorts Graduates | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 88.31% | 72.43% | 72.43% | 0 | 9.37% | 110000 | 97136 | 12864 |  | 0 | 0 | 0.00 | 70352 | 172.43 | 26784 | 0 | 70352 | N/A | N/A | N/A | N/A | 0 | 7% | 16.37% | 19.11% | 12.11% |  | 23.16 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23352 | Spirit 2023 - Stress Approve Man Serv (CC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  |  | 99.63% | 71.66% | 71.66% | 0 | -2.36% | 97920 | 97560 | 360 |  | 0 | 0 | 0 | 69912 | 146.82 | 27648 | 0 | 69912 | 0 | 0 | 0 | 0 | 0 | 18% | 15.64% | 16.15% | -1.85% |  | 48 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23648 | EXP-032 Delivery of Datalink Eng support - FCAS AP | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 28% | 99.01% | 0.0004813% | 0 | 4.41% | 371000 | 103875 | 267125 |  | 1033 | 1032.95 | 0 | 102843 | 113.92 | 1033 | 123411 | 0.5 | N/A | N/A | N/A | N/A | 0 | 22% | 26.41% | 25.6% | 3.6% |  | 104.14 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23282 | Tooling Support (MBDA) | Dushan Fernando | BDV | MBDA UK LIMITED | ME | Level 3 | FIX |  |  |  |  | 99.28% | 99.74% | 89.07% | 0 | -9.99% | 104834 | 104078 | 756 |  | 0 | 0 | 19964.00 | 103804 | 54.35 | 274 | 13326 | 92699 | 13325.98 | 0 | 0 | 0 | 0 | 30% | 20.01% | 30.37% | 0.37% |  | 49.68 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23270 | Shorts Project X | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 76.35% | 80.92% | 67.93% | 0 | 0.94% | 142248 | 108613 | 33635 |  | 0 | 0 | 0 | 87889 | 157.8 | 20724 | 16933 | 73778.1667 | N/A | N/A | N/A | N/A | 0 | 13% | 13.94% | 10.99% | -2.01% |  | 45.4 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P22883 | Spirit Shorts Evtol PMO C. Hatton | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 60.08% | 97.6% | 81.73% | 0 | -12.39% | 185800 | 111628 | 74172 |  | 0 | 0 | 0 | 108947 | 124.77 | 2681 | 21252 | 91237 | N/A | N/A | N/A | N/A | 0 | 26% | 13.61% | 26.7% | 0.7% |  | 36.29 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P22736 | WoT Fixed Leading Edge - Industrial | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 106.7% | 93.42% | 91.32% | 3019.54 | 0.01% | 112196 | 119668 | -7472 |  | 0 | 0 | 0 | 111797 | 12465.69 | 7872 | 3020 | 109280.3333 | 0 | 0 | 0 | 3019.54 | 3019.54 | 7% | 7.01% | 0% | -7% |  | 32.26 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23667 | Safety Systems Engineer | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 30.35% | 100% | 0% | 0 | -7.43% | 398000 | 120780 | 277220 |  | 0 | 0 | 0 | 120780 | 144.6 | 0 | 144936 | 0 | N/A | N/A | N/A | N/A | 0 | 47% | 39.57% | 29.32% | -17.68% |  | 110 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23421 | A220 DTC | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 93.27% | 87.9% | 54.14% | 14911.09 | -11.74% | 130625 | 121835 | 8790 |  | 0 | 0 | 0.00 | 107094 | 121.03 | 14740 | 49358 | 65962.3333 | N/A | N/A | N/A | N/A | 14911.09 | 10% | -1.74% | 3.13% | -6.87% |  | 45.09 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P22861 | WoT FLE Lifting & Handling Tools | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2023-06-14 | 1 |  |  | 65.17% | 101.6% | 101.6% | 0 | 12.01% | 173987 | 113382 | 60605 |  | 50078 | 58423.58 | 0 | 115204 | 12813.9 | 10678 | 0 | 115204 | 0 | 0 | 0 | 0 | 0 | 1% | 13.01% | 0% | -1% |  | 45 | [5 empty] | 12500
1723 | 2024-02-01 00:34 | P23437 | Embedded Software Engineer | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 87.12% | 97.44% | 80.58% | 0 | -6.37% | 150150 | 130812 | 19338 |  | 738 | 737.86 | 0 | 127463 | 67.45 | 3349 | 26470 | 105404.6667 | N/A | N/A | N/A | N/A | 0 | 22% | 15.63% | 16.24% | -5.76% |  | 78.5 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23518 | Systems Engineering support to FCAS | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 69.21% | 96.81% | 75.34% | 0 | 0.23% | 193737 | 134087 | 59650 |  | 3927 | 3927.4 | 0 | 129804 | 82.09 | 4283 | 34537 | 101023.1667 | N/A | N/A | N/A | N/A | 0 | 30% | 30.23% | 3.5% | -26.5% |  | 66.28 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23533 | External Stowage Design and Detail Support | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 0 |  |  | 136.5% | 73.24% | 73.24% | 0 | 6.33% | 105000 | 143369 | -38369 |  | 0 | 0 | 49220 | 105000 | 213.24 | 35000 | 0 | 105000 | 0 | 0 | 0 | 0 | 0 | 24% | 30.33% | 0% | -24% |  | 60.04 | [5 empty] | -3369
1723 | 2024-02-01 00:34 | P23386 | Software Development - BMS | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 94.32% | 100% | 84.7% | 0 | 4.29% | 149650 | 141151 | 8499 |  | 0 | 0 | 0 | 141151 | 58.1 | 0 | 25914 | 119556 | N/A | N/A | N/A | N/A | 0 | 18% | 22.29% | 22.61% | 4.61% |  | 78.5 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23550 | Tempest Composites | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  |  | 94.98% | 88.99% | 70.95% | 24179.64 | 4.96% | 149495 | 141997 | 7498 |  | 0 | 0 | 0 | 126361 | 199.89 | 15635 | 30735 | 100748.5 | 6555.8 | 0 | 0 | 24179.64 | 24179.64 | 26% | 30.96% | 34.68% | 8.68% |  | 61.91 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P22982 | Spirit 2022 - Hugh Sloan | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 86.48% | 93.17% | 84.25% | 0 | -0.01% | 166046 | 143598 | 22448 |  | 0 | 0 | 0.00 | 133795 | 144.26 | 9803 | 15370 | 120986.6667 | N/A | N/A | N/A | N/A | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 35.42 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23629 | F35 FTI | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level NC | REIM | [5 empty] | 84.86% | 67.81% | 0 | -0.06% | 0 | 144032 | -144032 |  | 0 | 0 | 0 | 122231 | 41.49 | 21801 | 29474 | 97669.3333 | N/A | N/A | N/A | N/A | 0 | 31% | 30.94% | 29.6% | -1.4% |  | 62.22 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23464 | A220 Project X Design Offload | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 79.89% | 92.5% | 69.4% | 0 | -3.71% | 180400 | 144114 | 36286 |  | 0 | 0 | 0.00 | 133307 | 121.56 | 10807 | 39945 | 100019.5 | N/A | N/A | N/A | N/A | 0 | 21% | 17.29% | 17.65% | -3.35% |  | 42.89 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P22954 | Technical Support Step 1 | Owain Jones | HUV | HUARUI SPIRIT AEROSPACE MANUFACT | ME | Level 2 | REIM |  |  |  |  | 94.81% | 58.01% | 58.01% | 0 | 0.31% | 155501 | 147432 | 8069 |  | 23043 | 23043 | 0 | 85525 | 61906.09 | 61906 | 0 | 85525 | N/A | N/A | N/A | N/A | 0 | 30% | 30.31% | 0% | -30% |  | 60.79 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23508 | Verification and Validation | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 71.82% | 100% | 58.94% | 29107.8 | 11.27% | 212950 | 152938 | 60012 |  | 0 | 0 | 0 | 152938 | 98.41 | 0 | 75360 | 90138 | N/A | N/A | N/A | N/A | 29107.8 | 24% | 35.27% | 36.42% | 12.42% |  | 78.5 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P22440 | Spirit Managed Service - F&DT and Static Approval | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 3 |  |  | 88.56% | 92.56% | 92.56% | 0 | 11.51% | 173500 | 153656 | 19844 |  | 52115 | 55720 | 0 | 142225 | 13717.36 | 11431 | 0 | 142225 | 0 | 0 | 0 | 0 | 0 | 0% | 11.51% | 0% | 0% |  | 44.73 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23506 | ASTER Mid-Life Refurbishment Project Manager | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 70.15% | 98.67% | 78.59% | 0 | 1% | 224900 | 157759 | 67141 |  | 2329 | 2329.13 | 0 | 155656 | 60.26 | 2103 | 38016 | 123976 | N/A | N/A | N/A | N/A | 0 | 25% | 26% | 26.59% | 1.59% |  | 110 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23505 | EXP-022 Meteor TBUS T&E support | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 66.26% | 100% | 32.27% | 0 | -0.4% | 246744 | 163491 | 83253 |  | 0 | 0 | 0 | 163491 | 238.68 | 0 | 132886 | 52752.6667 | N/A | N/A | N/A | N/A | 0 | 20% | 19.6% | 15.67% | -4.33% |  | 89.83 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23373 | Raytheon Michael Bellini | Natalie Sinclair | RAS | RAYTHEON UNITED KINGDOM LIMITED | EES | Level NC | REIM |  |  |  |  | 79.99% | 90.66% | 71.43% | 0 | -8.32% | 214367 | 171473 | 42894 |  | 0 | 0 | 0 | 155462 | 91.65 | 16011 | 39576 | 122482 | N/A | N/A | N/A | N/A | 0 | 45% | 36.68% | 37.51% | -7.49% |  | 91.61 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23242 | Physical Architecture & System Engineering Support | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 57.8% | 99.57% | 89.7% | 0 | 10.5% | 305459 | 176561 | 128898 |  | 776 | 775.55 | 0 | 175794 | 55.6 | 767 | 20912 | 158367.3333 | N/A | N/A | N/A | N/A | 0 | 15% | 25.5% | 7.59% | -7.41% |  | 78.15 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23524 | Bombardier Regional Jets (BRJ) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 126.5% | 58.81% | 45.82% | 25157.41 | -4.7% | 146288 | 185063 | -38775 |  | 0 | 0 | 46750 | 108838 | 107.11 | 76225 | 28851 | 84795.5 | N/A | N/A | N/A | N/A | 25157.41 | 18% | 13.3% | 15.87% | -2.13% |  | 43.96 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23008 | Spirit Shorts Project Rachel | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 85.87% | 91.32% | 79.5% | 18585.6 | -7.7% | 228880 | 196531 | 32349 |  | 0 | 0 | 0 | 179473 | 215.82 | 17058 | 27878 | 156241.3333 | N/A | N/A | N/A | N/A | 18585.6 | 13% | 5.3% | 0.31% | -12.69% |  | 46.04 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23472 | Tempest Wing Design | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 70.46% | 116.2% | 103.2% | 0 | -19.65% | 281146 | 198092 | 83054 |  | 182213 | 206400 | 0 | 230237 | 0 | -32145 | 31059 | 204354.5 | N/A | N/A | N/A | N/A | 0 | 23% | 3.35% | 23.03% | 0.03% |  | 46.74 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23019 | EXP034-B Actuator Development | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 103% | 90.03% | 90.03% | 0 | -14.62% | 215541 | 221919 | -6378 |  | 12001 | 12092.91 | 0.00 | 199797 | 39.26 | 5145 | 0 | 199797 | N/A | N/A | N/A | N/A | 0 | 34% | 19.38% | 31.68% | -2.32% |  | 58.45 | [5 empty] | -16977
1723 | 2024-02-01 00:34 | P23650 | MBDA Recruitment Management costs | Brian Maddrell | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 31.86% | 0 | 209882 | -209882 |  | 0 | 0 | 266000 | 0 | 101.92 | 209882 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 3% | 34.86% | 35.85% | 32.85% |  | 86.8 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23603 | Typhoon IMDLR | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 184.4% | 0% | 0% | 0 | -3.09% | 119880 | 221035 | -101155 |  | 0 | 0 | 189459 | 0 | 185.66 | 221035 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 34% | 30.91% | 31.51% | -2.49% |  | 57.89 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23316 | Model Factory IL and AW | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX | 2024-01-12 | 13 |  |  | 88.13% | 104.1% | 96.46% | 0 | 2.17% | 250000 | 220328 | 29672 |  | 0 | 0 | 0 | 229409 | 36.76 | -913 | 20249 | 212534.8333 | 0 | 20248.8 | 0 | 0 | 0 | 30% | 32.17% | 32.57% | 2.57% |  | 45.31 | [5 empty] | 8168
1723 | 2024-02-01 00:34 | P23007 | EXP-006A - Brimstone 3 | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 93.61% | 98.83% | 85.43% | 17427 | -8.58% | 264150 | 247278 | 16872 |  | 0 | 0 | 0 | 244374 | 108.4 | 2875 | 39752 | 211247.3333 | N/A | N/A | N/A | N/A | 17427 | 30% | 21.42% | 29.94% | -0.06% |  | 69.03 | [5 empty] | -30
1723 | 2024-02-01 00:34 | P23255 | BAE Tempest WP 1 Circuits | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | 2023-10-20 | 1 |  |  | 70.38% | 99.34% | 99.34% | 0 | -2.72% | 355782 | 250395 | 105387 |  | 1654 | 1654.32 | 0 | 248740 | 0.38 | 0 | 0 | 248740 | N/A | N/A | N/A | N/A | 0 | 31% | 28.28% | 100% | 69% |  | 50.3 | [5 empty] | -1654
1723 | 2024-02-01 00:34 | P23317 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX | 2024-01-12 | 16 |  |  | 95.89% | 104.3% | 98.16% | 0 | 4.05% | 251800 | 241447 | 10353 |  | 0 | 0 | 0 | 251800 | 35.65 | -1177 | 17760 | 237000 | 0 | 17760 | 0 | 0 | 0 | 25% | 29.05% | 40.59% | 15.59% |  | 36.29 | [5 empty] | 9176
1723 | 2024-02-01 00:34 | P22798 | CO2MAP MGSE | Harry James Kellett | DTW | THALES ALENIA SPACE UK (60DAYS) | EES | Level 2 | REIM | 2023-11-08 | 0 |  |  | 85.75% | 105% | 105% | 0 | 3.94% | 252086 | 216158 | 35928 |  | 0 | 0 | 0 | 227053 | 30116.66 | 25097 | 0 | 227053 | N/A | N/A | N/A | N/A | 0 | 29% | 32.94% | 0% | -29% |  | 50.31 | [5 empty] | 35992
1723 | 2024-02-01 00:34 | P21463 | Safety & Monitoring Systems at DM Beith & Gosport | Harry James Kellett | BXW | MOD | EES | Level 2 | FIX |  |  |  |  | 75.07% | 133.2% | 133.2% | 0 | -27.59% | 349405 | 262306 | 87099 |  | 55885 | 66564.38 | 21721 | 349387 | 0 | -87081 | 0 | 349387 | 0 | 0 | 0 | 0 | 0 | 48% | 20.41% | 38.62% | -9.38% |  | 52.38 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23617 | Tempest Composites WP2 | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  |  | 108.3% | 22.15% | 3.848% | 29536.68 | 3.97% | 244405 | 264789 | -20384 |  | 0 | 0 | 50000 | 58643 | 157.45 | 206147 | 58145 | 10188.8333 | 28608.29 | 0 | 0 | 29536.68 | 29536.68 | 30% | 33.97% | 35.24% | 5.24% |  | 62.15 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23308 | NATO JEWCS | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  |  | 77.36% | 85.46% | 85.46% | 0 | -3.1% | 356307 | 275653 | 80654 |  | 614 | 613.89 | 0 | 235576 | 125.97 | 40076 | 0 | 235576 | N/A | N/A | N/A | N/A | 0 | 24% | 20.9% | 12.61% | -11.39% |  | 75.81 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23694 | Systems Portfolio | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 46.87% | 103.2% | 36.61% | 0 | 3.65% | 591943 | 277417 | 314526 |  | 158 | 157.75 | 0 | 286290 | 62.99 | -8873 | 221685 | 101552.5 | N/A | N/A | N/A | N/A | 0 | 21% | 24.65% | 14.07% | -6.93% |  | 90.76 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23045 | Shotgun Adaptors - 10 Sets | Harry James Kellett | BDW | MBDA UK LIMITED | EES | Level 2 | FIX |  |  |  |  | 74.73% | 95.15% | 95.15% | 0 | -19.12% | 399276 | 298392 | 100884 |  | 214430 | 214551.21 | 0 | 283926 | 384.31 | 14467 | 0 | 283926 | 0 | 0 | 0 | 0 | 0 | 29% | 9.88% | 0% | -29% |  | 55.76 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P22515 | Shorts A220 100/300 ALI Phase III | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 77.03% | 96.39% | 92.45% | 0 | 1.09% | 400629 | 308605 | 92024 |  | 3451 | 3450.98 | 0 | 297465 | 106.83 | 11139 | 14584 | 285311.6667 | N/A | N/A | N/A | N/A | 0 | 10% | 11.09% | 14.23% | 4.23% |  | 40.3 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P22953 | Spirit Shorts eVTOL | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 103.1% | 79.36% | 79.36% | 0 | -6.74% | 324272 | 334484 | -10212 |  | 66697 | 67387.9 | 0 | 265432 | 179.02 | 69052 | 0 | 265432 | N/A | N/A | N/A | N/A | 0 | 17% | 10.26% | 0% | -17% |  | 46.19 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P22842 | ME Support (Aim Altitude) | James Montgomery | AVI | AIM ALTITUDE UK LIMITED | ME | Level 3 | FIX | 2023-06-14 | 4 |  |  | 99.31% | 100.5% | 86.63% | 57290.84 | 0.49% | 346294 | 343918 | 2376 |  | 2910 | 2909.86 | 0 | 345673 | 55184.93 | -1755 | 57291 | 297930.5 | 0 | 0 | 0 | 57290.84 | 57290.84 | 13% | 13.49% | 0% | -13% |  | 46.3 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23023 | Spirit Shorts R Foster/M Gourley | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  |  | 80.86% | 108.6% | 97.69% | 13364.92 | -20.03% | 416652 | 336897 | 79755 |  | 188776 | 216366 | 0 | 365804 | 76.29 | -14396 | 44029 | 329113.1667 | N/A | N/A | N/A | N/A | 13364.92 | 27% | 6.97% | 9.92% | -17.08% |  | 29.48 | [5 empty] | 14511
1723 | 2024-02-01 00:34 | P23531 | BAe Systems F35 MRB Support | Andrew Houghton | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM | [5 empty] | 75.72% | 68.35% | 0 | 2.33% | 0 | 352972 | -352972 |  | 287 | 287.44 | 0 | 267283 | 75.39 | 85689 | 31232 | 241256.3333 | N/A | N/A | N/A | N/A | 0 | 25% | 27.33% | 33.66% | 8.66% |  | 58.9 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P22391 | GE System Engineering support | Vinayakumar Sugur | GEE | EXPERIS LIMITED | EES | Level NC | REIM |  |  |  |  | 82.01% | 95.48% | 95.48% | 0 | 0.13% | 434434 | 356261 | 78173 |  | 0 | 0 | 0 | 340161 | 78.58 | 16100 | 0 | 340161 | N/A | N/A | N/A | N/A | 0 | 6% | 6.13% | 6.09% | 0.09% |  | 57.33 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23520 | FCAS AP Portfolio Systems | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 44.94% | 99.98% | 78.49% | 0 | -6.91% | 810821 | 364384 | 446437 |  | 320 | 319.5 | 0 | 364294 | 56.66 | 91 | 93930 | 286019 | N/A | N/A | N/A | N/A | 0 | 22% | 15.09% | 17.31% | -4.69% |  | 78.89 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23554 | Dornier Seawings 328 2023 H2 Support | Steven Lawton | DAX | EXPLEO GERMANY GMBH (EC) | MPE | Level 2 | REIM |  |  |  |  | 90.8% | 92.75% | 92.75% | 0 | 7.68% | 416112 | 377823 | 38289 |  | 3551 | 3550.65 | 25985 | 350449 | 20.87 | 27374 | 0 | 350449 | N/A | N/A | N/A | N/A | 0 | 21% | 28.68% | 33.05% | 12.05% |  | 67.37 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23366 | Business Analyst Support | Peter Williams | BDZ | MBDA UK LIMITED | DET | Level NC | REIM |  |  |  |  | 28.46% | 258.6% | 203.3% | 0 | 15.59% | 583200 | 165970 | 417230 |  | 165970 | 416921.86 | 0 | 429280 | 84.58 | -25175 | 110208 | 337440 | N/A | N/A | N/A | N/A | 0 | 43% | 58.59% | 26% | -17% |  | 0.01 | [5 empty] | 238135
1723 | 2024-02-01 00:34 | P23432 | Spirit Belfast MRB On-Site Support (Mon & Clear) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 65.77% | 125.6% | 93.11% | 89696.1 | -11.53% | 449545 | 295665 | 153880 |  | 295665 | 451827.33 | 0 | 371466 | 40.74 | 36200 | 115405 | 275295.1667 | N/A | N/A | N/A | N/A | 89696.1 | 39% | 27.47% | 0% | -39% |  | 0 | [5 empty] | 112000
1723 | 2024-02-01 00:34 | P23320 | Lifing Services DACs | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX | 2024-01-12 | 26 |  |  | 95.56% | 104.6% | 97.44% | 0 | 2.72% | 413300 | 394956 | 18344 |  | 0 | 0 | 0 | 413300 | 35.5 | -2050 | 34139 | 384850.8333 | 0 | 34138.8 | 0 | 0 | 0 | 26% | 28.72% | 44.21% | 18.21% |  | 33.15 | [5 empty] | 16294
1723 | 2024-02-01 00:34 | P23473 | Tempest Vertical Tail | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 58.18% | 93.35% | 82.53% | 0 | -2.77% | 723866 | 421172 | 302694 |  | 87913 | 100425 | 0 | 393177 | 45.68 | 27996 | 54691 | 347601.1667 | N/A | N/A | N/A | N/A | 0 | 24% | 21.23% | 26.94% | 2.94% |  | 62.74 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P22906 | Spirit Shorts - MRB JD Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  |  | 67.78% | 92.8% | 71.56% | 38901.6 | -7.56% | 614770 | 416678 | 198092 |  | 0 | 0 | 0.00 | 386688 | 239.59 | 37991 | 106200 | 298188 | N/A | N/A | N/A | N/A | 38901.6 | 13% | 5.44% | 3.64% | -9.36% |  | 36.81 | [5 empty] | 8000
1723 | 2024-02-01 00:34 | P23140 | Spirit Shorts A220 MLG Stress Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  |  | 69.5% | 89.57% | 79.84% | 48343.2 | -15.23% | 595746 | 414057 | 181689 |  | 20870 | 87811.88 | 0.00 | 370857 | 124.91 | 68200 | 48343 | 330571.1667 | 0 | 0 | 0 | 48343.2 | 48343.2 | 32% | 16.77% | 12.27% | -19.73% |  | 47.3 | [5 empty] | 25000
1723 | 2024-02-01 00:34 | P23372 | BAE Carbon Tooling Off-load | Gary Kempster | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  |  | 165.3% | 56.3% | 56.3% | 0 | -6.12% | 276718 | 457433 | -180715 |  | 0 | 0 | 272185.8 | 257522 | 186.83 | 199912 | 0 | 257522 | N/A | N/A | N/A | N/A | 0 | 29% | 22.88% | 21.55% | -7.45% |  | 53.57 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23602 | EXP-025 Portfolio Software Engineering Support | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 37.48% | 98.82% | 57.49% | 0 | -0.48% | 1221060 | 457693 | 763367 |  | 300 | 396.95 | 0 | 452291 | 62.26 | 5403 | 227007 | 263118.5 | N/A | N/A | N/A | N/A | 0 | 24% | 23.52% | 23.92% | -0.08% |  | 82.51 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23323 | CNC-CMM Programming Support | Andrew Houghton | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  |  | 114.4% | 76.27% | 76.27% | 0 | -4.8% | 416048 | 476051 | -60003 |  | 13662 | 13661.56 | 95785.2 | 363077 | 105.57 | 112975 | 0 | 363077 | N/A | N/A | N/A | N/A | 0 | 32% | 27.2% | 30.42% | -1.58% |  | 56.07 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P22652 | L3 - Saftey Engineering | Sean Simmons | LHW | L3HARRIS MAPPS LIMITED | EES | Level NC | FIX |  |  |  |  | 95.63% | 86.69% | 86.69% | 0 | 5.66% | 523390 | 500498 | 22892 |  | 0 | 0 | 0 | 433883 | 79938 | 66615 | 0 | 433883 | 0 | 0 | 0 | 0 | 0 | 21% | 26.66% | 25.88% | 4.88% |  | 83.05 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23001 | Spirit Shorts A220 Design | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 114.3% | 72.88% | 67.84% | 15202.56 | -3.74% | 439560 | 502384 | -62824 |  | 0 | 0 | 65953.2 | 366148 | 336.98 | 136237 | 30405 | 340810.5 | N/A | N/A | N/A | N/A | 15202.56 | 25% | 21.26% | 11.21% | -13.79% |  | 43.63 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23281 | Systems Portfolio | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 44.43% | 97.19% | 97.19% | 0 | -17.1% | 1177697 | 523237 | 654460 |  | 2133 | 2133.28 | 0 | 508545 | 17523.23 | 14603 | 0 | 508545 | N/A | N/A | N/A | N/A | 0 | 25% | 7.9% | 0% | -25% |  | 70.48 | [5 empty] | -89
1723 | 2024-02-01 00:34 | P23426 | BAE Tempest WP 3 Harness Maturation | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 59.88% | 88.34% | 76% | 0 | -6.14% | 884012 | 529324 | 354688 |  | 213 | 213.34 | 0 | 467592 | 59.78 | 61732 | 78397 | 402261.1667 | N/A | N/A | N/A | N/A | 0 | 33% | 26.86% | 28.68% | -4.32% |  | 51.02 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P21138 | D&A Vibration Reduc Damping Struc FOGV Components | Steven Lawton | ATC | AECC SICHUAN GAS TURBINE | MPE | Level 1 | FIX | 2022-09-07 | 0 |  |  | 96.12% | 104% | 104% | 0 | -3.44% | 569346 | 547228 | 22118 |  | 75182 | 75181.75 | 0 | 569346 | 0 | -11 | 0 | 569346 | 0 | 0 | 0 | 0 | 0 | 36% | 32.56% | 0% | -36% |  | 73.95 | [5 empty] | 22107
1723 | 2024-02-01 00:34 | P23219 | Tornado Air 800 Engineering Support | Richard Brook | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 3 | REIM |  |  |  |  | 95.46% | 98.51% | 98.51% | 0 | 1.46% | 615046 | 587098 | 27948 |  | 459 | 459.21 | 314840 | 578373 | 10470.24 | 8725 | 0 | 578373 | N/A | N/A | N/A | N/A | 0 | 31% | 32.46% | 0% | -31% |  | 81.76 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23605 | Typhoon Work Package 2 Continuation | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM |  |  |  |  | 384.8% | 0% | 0% | 0 | 3.09% | 155094 | 596865 | -441771 |  | 4054 | 4054 | 472441.54 | 0 | 166.47 | 596865 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 25% | 28.09% | 28.79% | 3.79% |  | 55.54 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23451 | BAE Tempest - DFM-ASO Planning | Andrew Houghton | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  |  | 65.12% | 66.03% | 24.59% | 0 | -4.04% | 953905 | 621226 | 332679 |  | 0 | 0 | 0 | 410202 | 163.83 | 211025 | 308940 | 152752 | N/A | N/A | N/A | N/A | 0 | 28% | 23.96% | 24.81% | -3.19% |  | 53.18 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P22790 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 2 | REIM |  |  |  |  | 194.5% | 90.44% | 90.44% | 0 | 1.37% | 352240 | 685262 | -333022 |  | 1612 | 1611.52 | 515246 | 619744 | 41098.04 | 34248 | 0 | 619744 | N/A | N/A | N/A | N/A | 0 | 13% | 14.37% | 0% | -13% |  | 45.06 | [5 empty] | -31270
1723 | 2024-02-01 00:34 | P23321 | EHM Cloud Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX | 2024-01-29 | 70 |  |  | 89.76% | 111.4% | 103.8% | 0 | 2.78% | 839969 | 753975 | 85994 |  | 0 | 0 | 24980 | 839969 | 37.47 | -3454 | 69002 | 782467.3333 | 0 | 69002.4 | 0 | 0 | 0 | 28% | 30.78% | 56.85% | 28.85% |  | 49.95 | [5 empty] | 82540
1723 | 2024-02-01 00:34 | P22350 | EMP 2020-2021 | Natalie Sinclair | ARY | GUIDANT GROUP (trading name) | PCPR | Level NC | REIM |  |  |  |  | 99.48% | 97.36% | 94.17% | 0 | -1.87% | 930212 | 925417 | 4795 |  | 400 | 400 | 0.00 | 901021 | 70.07 | 24395 | 35433 | 871493.5 | N/A | N/A | N/A | N/A | 0 | 32% | 30.13% | 29.34% | -2.66% |  | 44.03 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23105 | Raytheon Supply Engineering Support | Natalie Sinclair | RAY | RAYTHEON UNITED KINGDOM LIMITED | MPE | Level 3A | REIM | 2023-07-13 | 1 |  |  | 79.67% | 90.07% | 90.07% | 0 | -1.83% | 1164044 | 927395 | 236649 |  | 0 | 0 | 0 | 835328 | 110481.3 | 92068 | 0 | 835328 | N/A | N/A | N/A | N/A | 0 | 26% | 24.17% | 0% | -26% |  | 48.97 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23117 | BAE Typhoon Eng Support | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 107.6% | 88.52% | 88.52% | 0 | -1.44% | 950772 | 1022826 | -72054 |  | 19090 | 21165.02 | 69773.84 | 905368 | 108434.61 | 90362 | 0 | 905368 | N/A | N/A | N/A | N/A | 0 | 30% | 28.56% | 0% | -30% |  | 52.3 | [5 empty] | -27096
1723 | 2024-02-01 00:34 | P23519 | Mechanical and Electrical Design Eng Support | Dushan Fernando | BAX | SAFRAN SEATS GB LIMITED | MPE | Level 2 | REIM |  |  |  |  | 118.8% | 82.41% | 75.97% | 0 | -1.44% | 839697 | 997446 | -157749 |  | 727 | 727 | 186282 | 821977 | 56.19 | 175468 | 77014 | 757798.6667 | N/A | N/A | N/A | N/A | 0 | 33% | 31.56% | 32.5% | -0.5% |  | 56.58 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23292 | BAE Tempest WP 4 AV Trays | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 68.8% | 91.58% | 83.32% | 0 | 2.12% | 1498284 | 1030793 | 467491 |  | 0 | 0 | 0 | 944039 | 59.01 | 86754 | 102198 | 858874 | N/A | N/A | N/A | N/A | 0 | 32% | 34.12% | 33.7% | 1.7% |  | 52.9 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23152 | Project Aragon - Design and Stress Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  |  | 105.5% | 63.21% | 63.21% | 0 | -9.46% | 1093504 | 1153808 | -60304 |  | 0 | 0 | 0 | 729296 | 275.24 | 424512 | 0 | 729296 | N/A | N/A | N/A | N/A | 0 | 39% | 29.54% | 31.02% | -7.98% |  | 51.84 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P22671 | Spirit Shorts Pylon and Fairing Package | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX | 2023-05-03 | 4 |  |  | 105% | 95.27% | 95.27% | 0 | -7.21% | 1198495 | 1258028 | -59533 |  | 106451 | 174863.91 | 0 | 1198495 | 2492.21 | 2077 | 0 | 1198495 | 0 | 0 | 0 | 0 | 0 | 20% | 12.79% | 0% | -20% |  | 45.4 | [5 empty] | -57456
1723 | 2024-02-01 00:34 | P23435 | Andy Baker Portfolio | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 43.2% | 93.08% | 77.14% | 0 | -8.84% | 3377457 | 1458948 | 1918509 |  | 2353 | 2352.57 | 0 | 1357991 | 67.78 | 100957 | 279146 | 1125369.3333 | N/A | N/A | N/A | N/A | 0 | 25% | 16.16% | 13.5% | -11.5% |  | 77.94 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23315 | DAC LUC BAU and Service Workbench | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  |  | 82.38% | 121.4% | 108.8% | 0 | 2.73% | 1573630 | 1296408 | 277222 |  | 180 | 180.3 | 0 | 1573630 | 19.24 | -79425 | 195596 | 1410633.3333 | 0 | 195596.4 | 0 | 0 | 0 | 28% | 30.73% | 43.95% | 15.95% |  | 52.39 | [5 empty] | 197797
1723 | 2024-02-01 00:34 | P23411 | Agile & Scrum Delivery Service | Peter Williams | BDZ | MBDA UK LIMITED | DET | Level 2 | REIM | 2023-08-14 | 1 |  |  | 36.3% | 170.5% | 170.5% | 0 | 13.08% | 2487000 | 902904 | 1584096 |  | 894179 | 2337284.55 | 0 | 1539600 | 91 | 16141 | 0 | 1539600 | N/A | N/A | N/A | N/A | 0 | 29% | 42.08% | 0% | -29% |  | 74.57 | [5 empty] | 652837
1723 | 2024-02-01 00:34 | P23006 | Spirit Shorts A350 Freighter Toulouse | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 141% | 84.59% | 76.96% | 133600.64 | 18.58% | 1035746 | 1460164 | -424418 |  | 1086670 | 1708220.2 | 0 | 1235101 | 316.67 | 536337 | 133601 | 1123766.8333 | N/A | N/A | N/A | N/A | 133600.64 | 5% | 23.58% | 37.61% | 32.61% |  | 47.54 | [5 empty] | 311274
1723 | 2024-02-01 00:34 | P22278 | TAI Supply Engineers to Ankara | Natalie Sinclair | TAI | TUSAS-TURK HAVACILIK VE UZAY | MPE | Level 3A | REIM |  |  |  |  | 19.06% | 472.2% | 465.5% | 16000 | -15.54% | 2105282 | 401290 | 1703992 |  | 49400 | 49400.29 | 0 | 1894696 | 151.49 | -11350 | 32000 | 1868029.3333 | N/A | N/A | N/A | N/A | 16000 | 95% | 79.46% | 56.16% | -38.84% |  | 34.33 | [5 empty] | 1482056
1723 | 2024-02-01 00:34 | P23207 | A350 Approvers - Design and Stress Support | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  |  | 86.26% | 81.75% | 51.69% | 246367.11 | -4.35% | 2183628 | 1883661 | 299967 |  | 17140 | 17602.77 | 0 | 1539832 | 126.31 | 343829 | 679337 | 973717.8333 | 341012.63 | 91957.54 | 76590.9 | 169776.21 | 246367.11 | 23% | 18.65% | 20.87% | -2.13% |  | 54.69 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23257 | BAE Tempest WP 5 Centre Fuselage | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 93.34% | 97.41% | 92.92% | 0 | -5.85% | 2106861 | 1966506 | 140355 |  | 78100 | 78100 | 0 | 1915593 | 49.73 | 50913 | 105960 | 1827293 | N/A | N/A | N/A | N/A | 0 | 33% | 27.15% | 27.58% | -5.42% |  | 61.05 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23175 | BAe Aero Typhoon Package 2 | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM |  |  |  |  | 103.8% | 96.32% | 96.32% | 0 | -1.63% | 1984265 | 2060012 | -75747 |  | 57678 | 86030.82 | 15444.64 | 1984257 | 84731.75 | 70610 | 0 | 1984257 | N/A | N/A | N/A | N/A | 0 | 29% | 27.37% | 0% | -29% |  | 51.76 | [5 empty] | -5145
1723 | 2024-02-01 00:34 | P19020 | Spirit Concessions - 2018 | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2024-01-23 | 17 |  |  | 90.82% | 111.8% | 107% | 99792.83 | 2.09% | 1914847 | 1739018 | 175829 |  | 44318 | 44317.61 | 15178.88 | 1944711 | 2124.46 | 196987 | 99793 | 1861550.1667 | 0 | 0 | 0 | 99792.83 | 99792.83 | 25% | 27.09% | 10.92% | -14.08% |  | 40.87 | [5 empty] | 402680
1723 | 2024-02-01 00:34 | P23487 | Tornado Air 800 Engineering Support | Richard Brook | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 2 | FIX |  |  |  |  | 95.79% | 90.7% | 84.07% | 0 | -1.67% | 2525468 | 2419233 | 106235 |  | 0 | 0 | 0 | 2194207 | 50.04 | 225025 | 192507 | 2033784.5 | 192507.32 | 0 | 0 | 0 | 0 | 37% | 35.33% | 37.64% | 0.64% |  | 78.7 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P23179 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX |  |  |  |  | 130% | 84.77% | 79.95% | 135229.5 | -9.37% | 1921629 | 2498488 | -576859 |  | 155464 | 246717.26 | 492000 | 2118030 | 339.6 | 380457 | 144726 | 1997425 | 9496.08 | 99728.59 | 0 | 35500.91 | 135229.5 | 22% | 12.63% | 18.31% | -3.69% |  | 44.4 | [5 empty] | 0
1723 | 2024-02-01 00:34 | P19731 | Hapri HPC Rear Bearing Housing PDR & CDR | Steven Lawton | ATC | AECC Hunan Aviation Powerplant | MPE | Level 1 | FIX |  |  |  |  | 99.31% | 100.7% | 88.11% | 447000 | -15.32% | 2980000 | 2959429 | 20571 |  | 358408 | 512832.98 | 0 | 2980000 | 790.54 | -245571 | 447000 | 2607500 | 0 | 447000 | 0 | 0 | 447000 | 38% | 22.68% | 23.19% | -14.81% |  | 64.86 | [5 empty] | -225000
Extend Table

## AP2-1
WIP No | Date Created | Project ID | Project Description | Project Manager | Department Id | Client | CBU | Complexity | Type | Stop Booking Hrs | Closing Project: Action(s) to close | RAG | Approx. PO Burndown (weeks) | Turnover vs Contract Value | Invoice To Date vs Turnover | Cash in vs Turnover | Open Amount Overdue | Actual PM% to Baseline PM% delta | Contract Value | Total Project Turnover | Contract Value - Total Turnover | Run Rate (based on total turnover) | Total BOI Spend to Date | Total Committed PO (supplier/best shore) | Current AA in PT3 | Invoiced To Date | DSO | Unbilled (WIP) | Total Open Amount | Cash in (Invoiced - (Open amount -VAT)) | Debt <=30 Days | Debt 31 - 60 Days | Debt 61 - 90 Days | Debt >= 90 Days | Open Amount Overdue2 | Baseline Project Margin | Project To Date (PTD) PM | Year to Date (YTD) PM | YTD Delta Actual PM% to BPM% | Forecast PM at Completion (Manual input from PTT) | Average Sale Rate | CSat score for last quarter (Manual input from PTT) | Comments and Actions | Judged income adjustment at completion | Profit to take now | Provision required now | Fully Traded | Last Months Comments and Actions
1724 | 2024-02-08 00:29 | P23641 | Drawing Triage | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM | 2024-01-25 | 0 |  |  |  | 0% | 0% | 0 | 1043368% | 0 | 10756 | -10756 |  | 0 | 0 | 11343.2 | 0 | 0 | -1 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 1043368% | 100% | 100% |  | 49 | [5 empty] | -10756
1724 | 2024-02-08 00:29 | P23637 | MBSE Proposal | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 |  | 0 | 0 | 49980 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23711 | DO NOT USE - RAISED IN ERROR | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23552 | FCAS AP Product Technology Development | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -25% | 597871 | 0 | 597871 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 25% | 0% | 0% | -25% |  | 0 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23543 | EXP-024 FCAS AP Transformation & Change Enablers | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -26% | 385921 | 0 | 385921 |  | 0 | 0 | 0.00 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 26% | 0% | 0% | -26% |  | 0 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23585 | Systems Design - Missile Systems, Meteor,Brimstone | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 |  | 0 | 0 | 49500.00 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23137 | BAE Management Support Collector | John Clements | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3A | REIM | [5 empty] | 0% | 0% | 0 | -44357052% | 0 | 100437 | -100437 |  | 1053 | 1053.38 | 100000 | 0 | 0.3 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | -44357052% | 0% | 0% |  | 50 | [5 empty] | -100437
1724 | 2024-02-08 00:29 | P23730 | FLE Project | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -18.92% | 0 | 595 | -595 |  | 0 | 0 | 24000.00 | 0 | 34 | 595 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | -18.92% | -18.92% | -18.92% |  | 35 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23463 | A220 Wing MaMo Design Checking | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 7.85% | 0 | 1628 | -1628 |  | 0 | 0 | 15000 | 0 | 1953.6 | 1628 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 3% | 10.85% | 0% | -3% |  | 44 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P21028 | Rebate Collection (BACC) | David Catchpole | TOO | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | [5 empty] | 0% | 0% | 0 | 0% | 0 | 2680 | -2680 |  | 2680 | 2680 | 0 | 0 | 3216 | 2680 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23740 | Phase 2 - EJ200 ESS EHM Platform Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 3 | FIX |  |  |  |  | 1.568% | 910.8% | -0.006039% | 0 | 3.56% | 175971 | 2760 | 173211 |  | 0 | 0 | 0 | 25139 | 34 | -22379 | 30167 | -0.16667 | 30166.8 | 0 | 0 | 0 | 0 | 28% | 31.56% | 31.56% | 3.56% |  | 80 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23578 | ESN Work Package | Hannah Mead | COZ | CHELTON LIMITED | DET | Level 3 | FIX | 2024-01-01 | 0 |  |  | 86.17% | 116.1% | 116.1% | 0 | 35.86% | 4410 | 3800 | 610 |  | 0 | 0 | 0 | 4410 | 0 | -610 | 0 | 4410 | 0 | 0 | 0 | 0 | 0 | 24% | 59.86% | 0% | -24% |  | 95 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23628 | Design Assurance | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -6.67% | 0 | 3909 | -3909 |  | 0 | 0 | 4454.80 | 0 | 4691.09 | 3909 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 7% | 0.33% | 0% | -7% |  | 15.05 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23598 | MRB Onsite support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -1.39% | 0 | 4025 | -4025 |  | 880 | 14079.58 | 21700 | 0 | 91 | 4025 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 18% | 16.61% | 21.25% | 3.25% |  | 42.5 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23717 | GKN Ted Tomblin 2024 | Matthew Tweed | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 21.57% | 0 | 4361 | -4361 |  | 0 | 0 | 10047.00 | 0 | 34 | 4361 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 21.57% | 21.57% | 21.57% |  | 51 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23002 | WoT MAJ Transit Flag Stress | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 30.9% | 323.7% | 323.7% | 0 | 53.84% | 4735 | 1463 | 3272 |  | 0 | 2242.5 | 0 | 4735 | 0.6 | 1 | 0 | 4735 | 0 | 0 | 0 | 0 | 0 | 10% | 63.84% | 0% | -10% |  | 45 | [5 empty] | 3273
1724 | 2024-02-08 00:29 | P23597 | MRB Onsite support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -4.15% | 0 | 4827 | -4827 |  | 1682 | 17381.62 | 24200 | 0 | 91 | 4827 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 18% | 13.85% | 21.25% | 3.25% |  | 42.5 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23718 | Requalification of EJ200 GSS ESS EHM SW module | Vijayakumara Nanjundappa | ARZ | MTU AERO ENGINES AG | DET | Level 3 | FIX |  |  |  |  | 7.186% | 0% | 0% | 0 | -3.93% | 74463 | 5351 | 69112 |  | 881 | 881.46 | 0 | 0 | 34 | 5351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 24.07% | 24.07% | -3.93% |  | 80 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23607 | SAFRAN - A330neo Turnover Frame | Gary Kempster | TOO | SAFRAN SEATS GB LIMITED | MPE | Level 3 | FIX |  |  |  |  | 95.68% | 0% | 0% | 0 | -19.75% | 8736 | 8359 | 377 |  | 0 | 0 | 0 | 0 | 10030.8 | 8359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23% | 3.25% | 0% | -23% |  | 52 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23724 | GKN S McConnell 2024 | Matthew Tweed | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  |  | 17.7% | 79.1% | 0% | 0 | 1.51% | 49820 | 8818 | 41002 |  | 0 | 0 | 0.00 | 6975 | 34 | 1843 | 8370 | 0 | N/A | N/A | N/A | N/A | 0 | 19% | 20.51% | 20.51% | 1.51% |  | 49.82 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23274 | ME Support (Aim Altitude - Cambridge) | James Montgomery | AVI | AVIC CABIN SYSTEMS (UK) LIMITED | ME | Level 3 | FIX | 2023-08-18 | 0 |  |  | 51.88% | 56.29% | 56.29% | 0 | -0.17% | 17280 | 8964 | 8316 |  | 0 | 0 | 0 | 5046 | 4701.24 | 3918 | 0 | 5046 | 0 | 0 | 0 | 0 | 0 | 21% | 20.83% | 0% | -21% |  | 48 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23283 | Spirit Tooling Audit | Charidimos Valadakis | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-05-03 | 0 |  |  | 97.23% | 48.57% | 48.57% | 0 | -7.99% | 9910 | 9635 | 275 |  | 0 | 0 | 0 | 4680 | 5946.05 | 4955 | 0 | 4680 | N/A | N/A | N/A | N/A | 0 | 7% | -0.99% | 0% | -7% |  | 34.41 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23127 | Loft Hall Design Support | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 101% | 99.06% | 99.06% | 0 | -9.55% | 9680 | 9772 | -92 |  | 0 | 0 | 0 | 9680 | 110.4 | 92 | 0 | 9680 | N/A | N/A | N/A | N/A | 0 | 41% | 31.45% | 0% | -41% |  | 44 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23630 | 2Excel CFD Analysis Support | Dushan Fernando | BAX | STIRLING DYNAMICS LTD | MPE | Level NC | FIX |  |  |  |  | 61.2% | 100% | 100% | 0 | -1.87% | 16195 | 9911 | 6284 |  | 0 | 0 | 0 | 9912 | 0 | 0 | 0 | 9912 | 0 | 0 | 0 | 0 | 0 | 26% | 24.13% | 0% | -26% |  | 64.78 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23663 | Spirit Tooling Verification and Inspection | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 53.65% | 0% | 0% | 0 | -7.63% | 19820 | 10633 | 9187 |  | 0 | 0 | 7392 | 0 | 107.74 | 10633 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 12% | 4.37% | 4.82% | -7.18% |  | 34.41 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23313 | Laser Trim Fixtures | Gary Kempster | TOO | ALKEN ENGINEERING LIMITED | MPE | Level 3 | FIX | 2023-11-20 | 0 |  |  | 89.87% | 111.3% | 111.3% | 0 | 0.53% | 13770 | 12375 | 1395 |  | 0 | 0 | 0 | 13770 | 0 | -1395 | 0 | 13770 | 0 | 0 | 0 | 0 | 0 | 17% | 17.53% | 0% | -17% |  | 45 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P22761 | Red Bull Chassis Spit | James Montgomery | TOO | MANUFAX ENGINEERING LTD | MPE | Level 3 | FIX | 2022-11-15 | 0 |  |  | 72.19% | 96.98% | 96.98% | 0 | 7.92% | 12961 | 9356 | 3605 |  | 0 | 0 | 0 | 9073 | 4666.39 | 3889 | 0 | 9073 | 0 | 0 | 0 | 0 | 0 | 23% | 30.92% | 0% | -23% |  | 42.19 | [5 empty] | 3606
1724 | 2024-02-08 00:29 | P23433 | Cavendish | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 32.81% | 100% | 100% | 0 | -0.34% | 42240 | 13859 | 28381 |  | 0 | 0 | 0 | 13859 | 0 | 0 | 0 | 13859 | N/A | N/A | N/A | N/A | 0 | 7% | 6.66% | 0% | -7% |  | 43.93 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23350 | Spirit 2023 - Stress Approve Man Serv (DH) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 14.15% | 72.64% | 72.64% | 0 | -0.29% | 97920 | 13860 | 84060 |  | 0 | 0 | 0 | 10068 | 4550.4 | 3792 | 0 | 10068 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23344 | Spirit A320 Spoilers Support 2023 | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 38.75% | 100% | 100% | 0 | 5.82% | 35786 | 13867 | 21919 |  | 0 | 0 | 0 | 13867 | 0 | 0 | 0 | 13867 | N/A | N/A | N/A | N/A | 0 | 7% | 12.82% | 0% | -7% |  | 34.41 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23337 | Spirit 2023 - Steve Grimley | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 25.28% | 100% | 100% | 0 | 0.01% | 56813 | 14362 | 42451 |  | 0 | 0 | 0 | 14362 | 0 | 0 | 0 | 14362 | N/A | N/A | N/A | N/A | 0 | 7% | 7.01% | 0% | -7% |  | 30.11 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23760 | Land Ceptor V&V Systems Engineer | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 28.98% | 0 | 14640 | -14640 |  | 0 | 0 | 23550 | 0 | 34 | 14640 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 28.98% | 28.98% | 28.98% |  | 78.5 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23753 | Tempest Composites Maturation | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | [5 empty] | 0% | 0% | 0 | -26.21% | 0 | 16093 | -16093 |  | 0 | 0 | 54398.40 | 0 | 35 | 16093 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 37% | 10.79% | 10.79% | -26.21% |  | 64.76 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23635 | Engineering Services: FAI Support | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 44.9% | 0% | 0% | 0 | -3.45% | 37230 | 16718 | 20512 |  | 0 | 0 | 0.00 | 0 | 148.91 | 16718 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 8% | 4.55% | 5.04% | -2.96% |  | 38.7 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23729 | Honda Tooling | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX | [5 empty] | 0% | 0% | 0 | -3.9% | 0 | 17608 | -17608 |  | 0 | 0 | 14430.00 | 0 | 28 | 17608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21% | 17.1% | 17.1% | -3.9% |  | 42.2 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23343 | Spirit 2023 - John Agnew | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-08-09 | 0 |  |  | 28.56% | 86.27% | 86.27% | 0 | -0.02% | 65120 | 18601 | 46519 |  | 0 | 0 | 0 | 16047 | 3064.49 | 2554 | 0 | 16047 | N/A | N/A | N/A | N/A | 0 | 7% | 6.98% | 0% | -7% |  | 34.51 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23784 | Tempest Tooling Offload 2024 | Christopher McCarthy | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -3.86% | 0 | 20038 | -20038 |  | 0 | 0 | 74725 | 0 | 34 | 20038 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 30% | 26.14% | 26.14% | -3.86% |  | 53.22 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23651 | PMO Spirit | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 24.67% | 0 | 20664 | -20664 |  | 0 | 0 | 30800.00 | 0 | 142.33 | 20664 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 24.67% | 25.03% | 25.03% |  | 36 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23355 | Spirit Tooling Support 2023 | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-23 | 0 |  |  | 22.93% | 89.03% | 89.03% | 0 | -0.82% | 91800 | 21053 | 70747 |  | 0 | 0 | 0 | 18743 | 2773.01 | 2311 | 0 | 18743 | 0 | 0 | 0 | 0 | 0 | 20% | 19.18% | 0% | -20% |  | 44.46 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23744 | Model Factory | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  |  | 8.296% | 105% | -0.001532% | 0 | 8.35% | 262300 | 21760 | 240540 |  | 0 | 0 | 0 | 22858 | 34 | -1098 | 27430 | -0.33333 | 27429.6 | 0 | 0 | 0 | 0 | 28% | 36.35% | 36.35% | 8.35% |  | 50.72 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23351 | Spirit 2023 - Design Man Serv (KL) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 26.47% | 93.15% | 93.15% | 0 | 0.09% | 93840 | 24840 | 69000 |  | 0 | 0 | 0 | 23138 | 2042.4 | 1702 | 0 | 23138 | 0 | 0 | 0 | 0 | 0 | 26% | 26.09% | 0% | -26% |  | 46 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23356 | Spirit 2023 - Design Man Serv (AH) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX | 2023-08-09 | 1 |  |  |  | 76.66% | 0.001332% | 23018.4 | 0.48% | 0 | 25023 | -25023 |  | 0 | 0 | 25300.00 | 19182 | 30027.7 | 5841 | 23018 | 0.33333 | 0 | 0 | 0 | 23018.4 | 23018.4 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P22884 | Spirit Shorts Config Eng | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 66.3% | 100.1% | 100.1% | 0 | 0.56% | 38976 | 25842 | 13134 |  | 0 | 0 | 0 | 25863 | 0 | 0 | 0 | 25863 | N/A | N/A | N/A | N/A | 0 | 7% | 7.56% | 0% | -7% |  | 20.3 | [5 empty] | 21
1724 | 2024-02-08 00:29 | P23354 | Spirit 2023 - Design Man Serv (PC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 27.97% | 99.36% | 99.36% | 0 | 0.48% | 93840 | 26249 | 67591 |  | 0 | 0 | 0 | 26082 | 200.38 | 167 | 0 | 26082 | 0 | 0 | 0 | 0 | 0 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23338 | Spirit 2023 - Blair Hainey | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 78.03% | 67.03% | 67.03% | 0 | 3.77% | 34494 | 26917 | 7577 |  | 0 | 0 | 0 | 18042 | 107.43 | 8875 | 0 | 18042 | N/A | N/A | N/A | N/A | 0 | 7% | 10.77% | 19.31% | 12.31% |  | 18.28 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23754 | Tempest Composites WP4 | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX | [5 empty] | 0% | 0% | 0 | 8.36% | 0 | 27524 | -27524 |  | 0 | 0 | 97140 | 0 | 49 | 27524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 36.36% | 36.36% | 8.36% |  | 66.08 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23642 | MRB Belfast Support | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -17.97% | 0 | 27973 | -27973 |  | 2170 | 2252.31 | 30800.00 | 0 | 111.52 | 27973 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | -17.97% | -18.17% | -18.17% |  | 38.52 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P22756 | A350 FLE Design Checker | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2022-03-23 | 1 |  |  | 68.39% | 119.7% | 119.7% | 0 | 16.46% | 34898 | 23867 | 11031 |  | 23867 | 24342.3 | 0 | 28571 | 0.06 | 0 | 0 | 28571 | N/A | N/A | N/A | N/A | 0 | 0% | 16.46% | 0% | 0% |  | 0 | [5 empty] | 4704
1724 | 2024-02-08 00:29 | P23700 | IPDT Leads | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 15.79% | 0 | 30770 | -30770 |  | 0 | 0 | 41363 | 0 | 84 | 30770 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 22% | 37.79% | 38.46% | 16.46% |  | 61.88 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23458 | Spirit Belfast Tooling Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-08-11 | 0 |  |  | 101.3% | 94.65% | 94.65% | 0 | 8.64% | 30384 | 30785 | -401 |  | 0 | 0 | 0 | 29139 | 1974.96 | 1646 | 0 | 29139 | N/A | N/A | N/A | N/A | 0 | 7% | 15.64% | 0% | -7% |  | 42.2 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23743 | EHM Cloud Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  |  | 3.248% | 258.9% | -0.00101% | 0 | 3.72% | 1016000 | 32995 | 983005 |  | 0 | 0 | 0 | 85408 | 34 | -52413 | 102490 | -0.33333 | 102489.6 | 0 | 0 | 0 | 0 | 28% | 31.72% | 31.72% | 3.72% |  | 49.54 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23365 | GKN 777x Lip Skin Fixture | Steven Lawton | TOO | GKN AEROSPACE SERVICES LTD | MPE | Level 3 | FIX | 2023-10-12 | 1 |  |  | 41.91% | 113.2% | 18.86% | 37544.22 | -9.26% | 79161 | 33176 | 45985 |  | 5110 | 5109.88 | 0 | 37544 | 33175.67 | -4369 | 37544 | 6257.3333 | 0 | 0 | 37544.22 | 0 | 37544.22 | 22% | 12.74% | 0% | -22% |  | 56 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P22768 | MRB Onsite Support - Spirit Belfast | James Montgomery | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2023-07-27 | 0 |  |  |  | 0% | 0% | 0 | -17.07% | 0 | 34614 | -34614 |  | 0 | 0 | 36800 | 0 | 41536.8 | 34614 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 10% | -7.07% | 0% | -10% |  | 36 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23347 | WoT Fixed Leading Edge - Industrial 2023 | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 112.8% | 42.03% | 42.03% | 0 | -0.41% | 31034 | 35002 | -3968 |  | 0 | 0 | 10500 | 14711 | 24349.85 | 20292 | 0 | 14711 | N/A | N/A | N/A | N/A | 0 | 7% | 6.59% | 0% | -7% |  | 32.26 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23051 | Spirit Shorts A350 PAX Door | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 3A | REIM |  |  |  |  | 205.9% | 105.4% | 105.4% | 0 | -0.63% | 18216 | 37513 | -19297 |  | 0 | 0 | 0 | 39537 | 0 | 0 | 0 | 39537 | N/A | N/A | N/A | N/A | 0 | 30% | 29.37% | 0% | -30% |  | 46 | [5 empty] | 2024
1724 | 2024-02-08 00:29 | P23741 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  |  | 7.832% | 108.9% | 0% | 0 | 3.23% | 526262 | 41218 | 485044 |  | 0 | 0 | 0 | 44885 | 34 | -3667 | 53862 | 0 | 53862 | 0 | 0 | 0 | 0 | 28% | 31.23% | 31.23% | 3.23% |  | 38.68 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P22752 | Tooling WoT - 2021 (Spirit) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | REIM | 2023-05-03 | 0 |  |  | 101.1% | 74.02% | 74.02% | 0 | -8.5% | 41525 | 41982 | -457 |  | 0 | 0 | 0 | 31076 | 13087.42 | 10906 | 0 | 31076 | N/A | N/A | N/A | N/A | 0 | 0% | -8.5% | 0% | 0% |  | 39.09 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23339 | Spirit 2023 - Stewart Russell | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 64.51% | 100% | 100% | 0 | 0.62% | 72767 | 46942 | 25825 |  | 0 | 0 | 0 | 46942 | 0 | 0 | 0 | 46942 | N/A | N/A | N/A | N/A | 0 | 7% | 7.62% | 0% | -7% |  | 35.67 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23322 | GKN T Tomblin 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2023-12-31 | 1 |  |  | 83.13% | 100% | 97.01% | 0 | -0.33% | 58952 | 49008 | 9944 |  | 0 | 0 | 0 | 49008 | 34.69 | 0 | 1757 | 47543.8333 | N/A | N/A | N/A | N/A | 0 | 17% | 16.67% | 0% | -17% |  | 48 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P22760 | SA Leading Edge Transport Media ('A' Frames) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-11-15 | 1 |  |  | 85.99% | 110.7% | 116.3% | -3082.8 | 3.97% | 53481 | 45986 | 7495 |  | 42804 | 42804 | 0 | 50912 | 0 | 0 | -3083 | 53481.1667 | 0 | 0 | 0 | -3082.8 | -3082.8 | 6% | 9.97% | 0% | -6% |  | 42 | [5 empty] | 4926
1724 | 2024-02-08 00:29 | P23341 | Spirit 2023 - Tom McFarlane | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 98.58% | 91.46% | 71.9% | 0 | -0.01% | 54282 | 53513 | 769 |  | 0 | 0 | 0 | 48945 | 155.96 | 4568 | 12560 | 38478.3333 | N/A | N/A | N/A | N/A | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23382 | Performance Modelling | Dushan Fernando | BDX | MBDA UK LIMITED | MPE | Level NC | REIM | 2023-07-09 | 1 |  |  | 40.95% | 79.09% | 79.09% | 0 | -16.36% | 170010 | 69626 | 100384 |  | 14560 | 14659.9 | 0 | 55066 | 0 | 0 | 0 | 55066 | N/A | N/A | N/A | N/A | 0 | 20% | 3.64% | 0% | -20% |  | 77.05 | [5 empty] | -14560
1724 | 2024-02-08 00:29 | P23739 | Lifing Services DACs | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  |  | 8.509% | 99.72% | -0.0002983% | 0 | 7.43% | 656508 | 55863 | 600645 |  | 0 | 0 | 0 | 55709 | 34 | 154 | 66851 | -0.16667 | 66850.8 | 0 | 0 | 0 | 0 | 28% | 35.43% | 35.43% | 7.43% |  | 37.91 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23349 | Spirit 2023 - Stress Approve Man Serv (SB) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 58.24% | 80.05% | 80.05% | 0 | -0.29% | 97920 | 57024 | 40896 |  | 0 | 0 | 0 | 45648 | 13651.2 | 11376 | 0 | 45648 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23193 | Spirit Shorts Stephen Greer | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 95.72% | 92.89% | 88.29% | 6199.15 | 2.38% | 61472 | 58838 | 2634 |  | 0 | 0 | 0 | 54656 | 71.39 | 4182 | 3252 | 51946 | N/A | N/A | N/A | N/A | 6199.15 | 29% | 31.38% | 34.03% | 5.03% |  | 34.98 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23106 | ME Support to NPD - Bobby Haggart | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  |  | 95.79% | 97.03% | 97.03% | 0 | 0.3% | 65675 | 62912 | 2763 |  | 0 | 0 | 0 | 61043 | 2243.24 | 1869 | 0 | 61043 | 0 | 0 | 0 | 0 | 0 | 15% | 15.3% | 0% | -15% |  | 35.65 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23561 | SAAB | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  |  | 82.46% | 121.1% | 96.66% | 0 | 3.5% | 67485 | 55649 | 11836 |  | 0 | 0 | 0 | 67399 | 104.63 | -4408 | 16332 | 53789 | N/A | N/A | N/A | N/A | 0 | 16% | 19.5% | 0% | -16% |  | 36.82 | [5 empty] | 7342
1724 | 2024-02-08 00:29 | P22967 | Spirit 2022 - Channapa Laxmeshwar | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2023-01-26 | 2 |  |  | 69.69% | 121.3% | 121.3% | 0 | 9.53% | 75159 | 52376 | 22783 |  | 52376 | 54898.1 | 0 | 63509 | 0.42 | 0 | 0 | 63509 | N/A | N/A | N/A | N/A | 0 | 8% | 17.53% | 0% | -8% |  | 0 | [5 empty] | 11133
1724 | 2024-02-08 00:29 | P23342 | Spirit 2023 - Channapa Laxmeshwar | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 78.75% | 104.3% | 88.16% | 0 | -2.64% | 79348 | 62484 | 16864 |  | 62484 | 63539 | 0 | 65178 | 83.77 | 157 | 12110 | 55086.3333 | N/A | N/A | N/A | N/A | 0 | 7% | 4.36% | 0% | -7% |  | 0 | [5 empty] | 2850
1724 | 2024-02-08 00:29 | P23465 | A220 ToW Design Offload (Wing) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 49.54% | 85.27% | 76.24% | 0 | -3.74% | 132000 | 65398 | 66602 |  | 0 | 0 | 0 | 55768 | 69.69 | 9630 | 7088 | 49861.3333 | N/A | N/A | N/A | N/A | 0 | 20% | 16.26% | 17.66% | -2.34% |  | 42.8 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23560 | NJEWCS TAF202302 SM | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level 2 | FIX |  |  |  |  | 85.19% | 57.61% | 57.61% | 0 | 12.3% | 81500 | 69433 | 12067 |  | 0 | 0 | 0 | 40000 | 111.17 | 29433 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 28% | 40.3% | 41.09% | 13.09% |  | 73.01 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23586 | Project Management Support | Peter Bowen | BDX | MBDA UK LIMITED | MPE | Level NC | REIM |  |  |  |  | 87.58% | 92.03% | 62.06% | 0 | -25.54% | 80000 | 70064 | 9936 |  | 1141 | 1140.6 | 0 | 64480 | 70.76 | 5584 | 25200 | 43480 | N/A | N/A | N/A | N/A | 0 | 49% | 23.46% | 24.63% | -24.37% |  | 80 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23551 | Ian Berry 2023 H2 | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  |  | 92.67% | 95.68% | 39.36% | 0 | 12.82% | 75810 | 70251 | 5559 |  | 0 | 0 | 24259.20 | 67217 | 135.04 | 3034 | 47479 | 27651.1667 | N/A | N/A | N/A | N/A | 0 | 22% | 34.82% | 38.59% | 16.59% |  | 76.65 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23171 | Spirt Shorts Weights Eng | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 81.27% | 126.1% | 117.6% | 7087.68 | -6.62% | 71760 | 58316 | 13444 |  | 58316 | 87405.88 | 0 | 73553 | 2405.3 | -2967 | 5965 | 68582.1667 | N/A | N/A | N/A | N/A | 7087.68 | 24% | 17.38% | 0% | -24% |  | 0 | [5 empty] | 12270
1724 | 2024-02-08 00:29 | P23438 | A220 Spirit Shorts DTC - Stephen Corry | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 151.1% | 56.57% | 56.57% | 0 | -5.46% | 47251 | 71417 | -24166 |  | 0 | 0 | 23745 | 40400 | 163.11 | 31018 | 0 | 40400 | N/A | N/A | N/A | N/A | 0 | 21% | 15.54% | 16.87% | -4.13% |  | 49.7 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23080 | Spirit Shorts DManagement Cairan Cullen | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 48.93% | 98.76% | 93.19% | 7575.6 | -0.8% | 149600 | 73194 | 76406 |  | 0 | 0 | 0 | 72284 | 150.38 | 910 | 4892 | 68207.3333 | N/A | N/A | N/A | N/A | 7575.6 | 24% | 23.2% | 18.05% | -5.95% |  | 44.45 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23340 | Spirit 2023 - John Cole | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 98.04% | 85.4% | 68.54% | 0 | -0.01% | 75065 | 73593 | 1472 |  | 0 | 0 | 0 | 62852 | 126.7 | 10741 | 14894 | 50440.3333 | N/A | N/A | N/A | N/A | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 39.78 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23677 | ME Managed Service - Phase 1 | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  |  | 85.83% | 0% | 0% | 0 | -9.63% | 86400 | 74160 | 12240 |  | 0 | 0 | 0.00 | 0 | 93.09 | 74160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16% | 6.37% | 10.31% | -5.69% |  | 45 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23345 | Spirit 2023- Jonathan Escosio | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 98.99% | 85.71% | 68.15% | 0 | -0.35% | 75971 | 75206 | 765 |  | 0 | 0 | 0 | 64456 | 132.06 | 10749 | 15846 | 51251 | N/A | N/A | N/A | N/A | 0 | 1% | 0.65% | 0.65% | -0.35% |  | 40.26 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23600 | MBDA EXP-EE-023 Bristone Certification | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 59.65% | 100% | 84.61% | 0 | 0.4% | 126600 | 75517 | 51083 |  | 0 | 0 | 0 | 75517 | 52 | 0 | 13942 | 63898.6667 | N/A | N/A | N/A | N/A | 0 | 41% | 41.4% | 0% | -41% |  | 78.5 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23336 | Spirit 2023 - Neil Rampling | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 57.11% | 86.11% | 62.58% | 12687.64 | -0.01% | 133902 | 76477 | 57425 |  | 0 | 0 | 0.00 | 65851 | 159.89 | 10626 | 21586 | 47862.6667 | N/A | N/A | N/A | N/A | 12687.64 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P22505 | Spirit MRB Engineering Support 2021 | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 1 |  |  | 91.17% | 100% | 95.78% | 4020.48 | 21.2% | 87110 | 79415 | 7695 |  | 0 | 0 | 0 | 79415 | 4020.48 | 0 | 4020 | 76065 | 0 | 0 | 0 | 4020.48 | 4020.48 | 0% | 21.2% | 0% | 0% |  | 41.88 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23375 | GKN Jaap Peters NL 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  |  | 84.76% | 115.8% | 80.21% | 0 | -15.19% | 89795 | 76111 | 13684 |  | 76111 | 85308.08 | 5661.24 | 88129 | 95.02 | -8168 | 32497 | 61048.1667 | N/A | N/A | N/A | N/A | 0 | 20% | 4.81% | 0% | -20% |  | 0 | [5 empty] | 3850
1724 | 2024-02-08 00:29 | P22885 | ME Support (Baxi) | James Montgomery | HUV | BAXI HEATING UK LIMITED | ME | Level 3 | FIX | 2023-01-12 | 0 |  |  | 68.78% | 108.7% | 108.7% | 0 | 13.05% | 106633 | 73340 | 33293 |  | 0 | 0 | 0 | 79748 | 1531.35 | 1276 | 0 | 79748 | 0 | 0 | 0 | 0 | 0 | 15% | 28.05% | 0% | -15% |  | 44.37 | [5 empty] | 7684
1724 | 2024-02-08 00:29 | P23079 | Spirit Shorts Nomenclature | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 94.17% | 92.6% | 82.04% | 10554.48 | 1.81% | 88455 | 83302 | 5153 |  | 0 | 0 | 0.00 | 77138 | 182.78 | 6163 | 10554 | 68343 | N/A | N/A | N/A | N/A | 10554.48 | 20% | 21.81% | 25.23% | 5.23% |  | 30.69 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23335 | GKN S McConnell 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2023-12-31 | 3 |  |  | 96.61% | 100% | 75.29% | 0 | 0.74% | 87420 | 84459 | 2961 |  | 0 | 0 | 0 | 84459 | 156 | 0 | 25042 | 63590.6667 | N/A | N/A | N/A | N/A | 0 | 15% | 15.74% | 0% | -15% |  | 47 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23583 | Castalla - Test Rig Design | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 125.5% | 72.29% | 72.29% | 0 | -6.42% | 67520 | 84743 | -17223 |  | 0 | 0 | 22906 | 61258 | 80.93 | 23485 | 0 | 61258 | N/A | N/A | N/A | N/A | 0 | 21% | 14.58% | 19.48% | -1.52% |  | 42.57 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P22965 | Spirit 2022 - Design Man Serv (AH) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 1 |  |  | 106.7% | 96.66% | 92.02% | 4759.75 | 3.14% | 80080 | 85441 | -5361 |  | 0 | 0 | 0 | 82589 | 8182.59 | 2852 | 4760 | 78622.3333 | 0 | 0 | 0 | 4759.75 | 4759.75 | 14% | 17.14% | 0% | -14% |  | 42.44 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23523 | Applique Armour Support | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 0 |  |  | 101.6% | 98.47% | 98.47% | 0 | 3.42% | 84300 | 85607 | -1307 |  | 0 | 0 | 0 | 84300 | 1567.8 | 1307 | 0 | 84300 | 0 | 0 | 0 | 0 | 0 | 25% | 28.42% | 0% | -25% |  | 64.29 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P22964 | Spirit 2022 - MRB Man Serv (JC) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 100.6% | 97.95% | 97.95% | 0 | 1.91% | 85435 | 85960 | -525 |  | 0 | 0 | 0 | 84200 | 2112.62 | 1761 | 0 | 84200 | 0 | 0 | 0 | 0 | 0 | 16% | 17.91% | 0% | -16% |  | 42.69 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23545 | Ultra CSS continuation 2023 H2 | Natalie Sinclair | ULT | ULTRA SONAR SYSTEMS LIMITED | EES | Level NC | REIM |  |  |  |  | 113.9% | 50.78% | 50.78% | 0 | 2.26% | 76000 | 86554 | -10554 |  | 0 | 0 | 24259.20 | 43956 | 132.08 | 42598 | 0 | 43956 | N/A | N/A | N/A | N/A | 0 | 23% | 25.26% | 25% | 2% |  | 80 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P22963 | Spirit 2022 - Design Man Serv (PC) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 1 |  |  | 108.6% | 104% | 94.46% | 9938.48 | 3.18% | 80080 | 86927 | -6847 |  | 0 | 0 | 0 | 90390 | 5782.63 | -3463 | 9938 | 82108.3333 | 0 | 0 | 0 | 9938.48 | 9938.48 | 13% | 16.18% | 0% | -13% |  | 42.39 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23353 | Spirit 2023 - MRB Man Serv (JC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  |  | 97.08% | 76.99% | 76.99% | 0 | -0.22% | 91800 | 89123 | 2677 |  | 0 | 0 | 0 | 68615 | 156.94 | 20507 | 0 | 68615 | 0 | 0 | 0 | 0 | 0 | 18% | 17.78% | 0% | -18% |  | 45 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23588 | BAE Typhoon MRB MC Shop Concessions | Andrew Houghton | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 53.43% | 55.1% | 55.1% | 0 | -4.21% | 175061 | 93536 | 81525 |  | 0 | 0 | 0.00 | 51537 | 102.72 | 41999 | 0 | 51537 | N/A | N/A | N/A | N/A | 0 | 31% | 26.79% | 29.17% | -1.83% |  | 55.52 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23664 | Tempest Composites WP3 | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  |  | 76.95% | 17.53% | 0.0007075% | 0 | -5.14% | 122455 | 94226 | 28229 |  | 0 | 0 | 0.00 | 16519 | 107.5 | 77708 | 19822 | 0.66667 | 0 | 19822.44 | 0 | 0 | 0 | 37% | 31.86% | 35.69% | -1.31% |  | 60.34 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23685 | DAC LUC Support and Recompliance | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  |  | 13.41% | 260.3% | 0.0003452% | 0 | 2.28% | 720000 | 96576 | 623424 |  | 0 | 0 | 0 | 251427 | 34 | -154851 | 301712 | 0.33333 | 301712.4 | 0 | 0 | 0 | 0 | 28% | 30.28% | 30.28% | 2.28% |  | 68.11 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23352 | Spirit 2023 - Stress Approve Man Serv (CC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  |  | 99.63% | 71.66% | 71.66% | 0 | -2.76% | 97920 | 97560 | 360 |  | 0 | 0 | 0 | 69912 | 146.82 | 27648 | 0 | 69912 | 0 | 0 | 0 | 0 | 0 | 18% | 15.24% | 4.69% | -13.31% |  | 48 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P22918 | Spirit Shorts Graduates | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 93.17% | 68.65% | 68.65% | 0 | 9.51% | 110000 | 102486 | 7514 |  | 0 | 0 | 9900 | 70352 | 165.19 | 32134 | 0 | 70352 | N/A | N/A | N/A | N/A | 0 | 7% | 16.51% | 19.11% | 12.11% |  | 23.21 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23282 | Tooling Support (MBDA) | Dushan Fernando | BDV | MBDA UK LIMITED | ME | Level 3 | FIX |  |  |  |  | 102.9% | 96.21% | 85.91% | 0 | -9.63% | 104834 | 107897 | -3063 |  | 0 | 0 | 19964.00 | 103804 | 66.09 | 4093 | 13326 | 92699 | 0 | 13325.98 | 0 | 0 | 0 | 30% | 20.37% | 30.37% | 0.37% |  | 49.69 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23270 | Shorts Project X | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 77.52% | 79.7% | 66.9% | 0 | 0.89% | 142248 | 110276 | 31972 |  | 0 | 0 | 0 | 87889 | 165.34 | 22387 | 16933 | 73778.1667 | N/A | N/A | N/A | N/A | 0 | 13% | 13.89% | 10.99% | -2.01% |  | 45.39 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P22883 | Spirit Shorts Evtol PMO C. Hatton | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 60.08% | 97.6% | 81.73% | 0 | -12.39% | 185800 | 111628 | 74172 |  | 0 | 0 | 0 | 108947 | 140.11 | 2681 | 21252 | 91237 | N/A | N/A | N/A | N/A | 0 | 26% | 13.61% | 26.7% | 0.7% |  | 36.29 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23648 | EXP-032 Delivery of Datalink Eng support - FCAS AP | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 30.26% | 91.62% | 0.0004454% | 0 | 4.53% | 371000 | 112255 | 258745 |  | 1033 | 1032.95 | 0 | 102843 | 117.55 | 9413 | 123411 | 0.5 | N/A | N/A | N/A | N/A | 0 | 22% | 26.53% | 25.96% | 3.96% |  | 104.04 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P22736 | WoT Fixed Leading Edge - Industrial | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 106.7% | 93.42% | 91.32% | 3019.54 | 0.01% | 112196 | 119668 | -7472 |  | 0 | 0 | 0 | 111797 | 12465.69 | 7872 | 3020 | 109280.3333 | 0 | 0 | 0 | 3019.54 | 3019.54 | 7% | 7.01% | 0% | -7% |  | 32.26 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23421 | A220 DTC | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 94.61% | 86.65% | 63.43% | 14911.09 | -11.48% | 130625 | 123587 | 7038 |  | 0 | 0 | 0.00 | 107094 | 101.27 | 16493 | 34447 | 78388.1667 | N/A | N/A | N/A | N/A | 14911.09 | 10% | -1.48% | 4.69% | -5.31% |  | 45.08 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23667 | Safety Systems Engineer | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 31.37% | 96.74% | 0% | 0 | -7.76% | 398000 | 124850 | 273150 |  | 0 | 0 | 0 | 120780 | 157.93 | 4070 | 144936 | 0 | N/A | N/A | N/A | N/A | 0 | 47% | 39.24% | 29.32% | -17.68% |  | 110 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P22861 | WoT FLE Lifting & Handling Tools | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2023-06-14 | 1 |  |  | 65.17% | 101.6% | 101.6% | 0 | 12.01% | 173987 | 113382 | 60605 |  | 50078 | 58423.58 | 0 | 115204 | 12813.9 | 10678 | 0 | 115204 | 0 | 0 | 0 | 0 | 0 | 1% | 13.01% | 0% | -1% |  | 45 | [5 empty] | 12500
1724 | 2024-02-08 00:29 | P23437 | Embedded Software Engineer | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 89.06% | 95.32% | 78.83% | 0 | -6.35% | 150150 | 133717 | 16433 |  | 738 | 737.86 | 0 | 127463 | 75.16 | 6254 | 26470 | 105404.6667 | N/A | N/A | N/A | N/A | 0 | 22% | 15.65% | 16.24% | -5.76% |  | 78.5 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23518 | Systems Engineering support to FCAS | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 70.71% | 94.75% | 73.74% | 0 | -0.34% | 193737 | 136992 | 56745 |  | 3927 | 3927.4 | 0 | 129804 | 93.54 | 7188 | 34537 | 101023.1667 | N/A | N/A | N/A | N/A | 0 | 30% | 29.66% | 3.5% | -26.5% |  | 66.51 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23533 | External Stowage Design and Detail Support | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 0 |  |  | 136.5% | 73.24% | 73.24% | 0 | 6.33% | 105000 | 143369 | -38369 |  | 0 | 0 | 49220 | 105000 | 322.04 | 35000 | 0 | 105000 | 0 | 0 | 0 | 0 | 0 | 24% | 30.33% | 0% | -24% |  | 60.04 | [5 empty] | -3369
1724 | 2024-02-08 00:29 | P23699 | A220 Stress Checkers | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -1.75% | 0 | 143309 | -143309 |  | 0 | 0 | 135880 | 0 | 84 | 143309 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 22% | 20.25% | 20.46% | -1.54% |  | 61.88 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23550 | Tempest Composites | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  |  | 96.18% | 87.89% | 70.07% | 24179.64 | 5.03% | 149495 | 143777 | 5718 |  | 0 | 0 | 0 | 126361 | 200.82 | 17415 | 30735 | 100748.5 | 0 | 6555.8 | 0 | 24179.64 | 24179.64 | 26% | 31.03% | 34.86% | 8.86% |  | 61.81 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P22982 | Spirit 2022 - Hugh Sloan | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 87.06% | 92.56% | 83.7% | 0 | -0.01% | 166046 | 144556 | 21490 |  | 0 | 0 | 0.00 | 133795 | 154.21 | 10761 | 15370 | 120986.6667 | N/A | N/A | N/A | N/A | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 35.42 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23386 | Software Development - BMS | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 96.73% | 97.51% | 82.59% | 0 | 4.3% | 149650 | 144762 | 4888 |  | 0 | 0 | 0 | 141151 | 66.64 | 3611 | 25914 | 119556 | N/A | N/A | N/A | N/A | 0 | 18% | 22.3% | 22.61% | 4.61% |  | 78.5 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23464 | A220 Project X Design Offload | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 81.64% | 90.51% | 67.91% | 0 | -3.72% | 180400 | 147281 | 33119 |  | 0 | 0 | 0.00 | 133307 | 130.29 | 13974 | 39945 | 100019.5 | N/A | N/A | N/A | N/A | 0 | 21% | 17.28% | 17.43% | -3.57% |  | 42.89 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P22954 | Technical Support Step 1 | Owain Jones | HUV | HUARUI SPIRIT AEROSPACE MANUFACT | ME | Level 2 | REIM |  |  |  |  | 94.81% | 58.01% | 58.01% | 0 | 0.31% | 155501 | 147432 | 8069 |  | 23043 | 23043 | 0 | 85525 | 61906.09 | 61906 | 0 | 85525 | N/A | N/A | N/A | N/A | 0 | 30% | 30.31% | 0% | -30% |  | 60.79 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P22440 | Spirit Managed Service - F&DT and Static Approval | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 3 |  |  | 88.56% | 92.56% | 92.56% | 0 | 11.51% | 173500 | 153656 | 19844 |  | 52115 | 55720 | 0 | 142225 | 13717.36 | 11431 | 0 | 142225 | 0 | 0 | 0 | 0 | 0 | 0% | 11.51% | 0% | 0% |  | 44.73 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23629 | F35 FTI | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level NC | REIM | [5 empty] | 79.46% | 79.46% | 0 | -0.06% | 0 | 153833 | -153833 |  | 0 | 0 | 0 | 122231 | 27.61 | 31603 | 0 | 122231 | N/A | N/A | N/A | N/A | 0 | 31% | 30.94% | 29.9% | -1.1% |  | 62.17 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23508 | Verification and Validation | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 74.1% | 96.92% | 72.49% | 0 | 11.31% | 212950 | 157805 | 55145 |  | 0 | 0 | 0 | 152938 | 68.49 | 4867 | 46252 | 114394.6667 | N/A | N/A | N/A | N/A | 0 | 24% | 35.31% | 36.46% | 12.46% |  | 78.5 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23506 | ASTER Mid-Life Refurbishment Project Manager | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 71.98% | 96.15% | 76.58% | 0 | 1.01% | 224900 | 161884 | 63016 |  | 2329 | 2329.13 | 0 | 155656 | 68.29 | 6228 | 38016 | 123976 | N/A | N/A | N/A | N/A | 0 | 25% | 26.01% | 26.59% | 1.59% |  | 110 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23505 | EXP-022 Meteor TBUS T&E support | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 67.85% | 97.65% | 31.51% | 0 | -0.5% | 246744 | 167421 | 79323 |  | 0 | 0 | 0 | 163491 | 244.81 | 3930 | 132886 | 52752.6667 | N/A | N/A | N/A | N/A | 0 | 20% | 19.5% | 15.67% | -4.33% |  | 89.83 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23373 | Raytheon Michael Bellini | Natalie Sinclair | RAS | RAYTHEON UNITED KINGDOM LIMITED | EES | Level NC | REIM |  |  |  |  | 81.91% | 97.45% | 69.75% | 0 | -8.29% | 214367 | 175596 | 38771 |  | 0 | 0 | 0 | 171127 | 99.36 | 4468 | 58374 | 122482 | N/A | N/A | N/A | N/A | 0 | 45% | 36.71% | 37.58% | -7.42% |  | 91.61 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23242 | Physical Architecture & System Engineering Support | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM | 2024-02-28 | 7 |  |  | 58.75% | 97.95% | 88.24% | 0 | 10.21% | 305459 | 179465 | 125994 |  | 776 | 775.55 | 0 | 175794 | 64.81 | 3671 | 20912 | 158367.3333 | N/A | N/A | N/A | N/A | 0 | 15% | 25.21% | 7.68% | -7.32% |  | 78.16 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23524 | Bombardier Regional Jets (BRJ) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 128.6% | 57.84% | 45.06% | 50314.82 | -4.56% | 146288 | 188187 | -41899 |  | 0 | 0 | 46750 | 108838 | 114.92 | 79349 | 28851 | 84795.5 | N/A | N/A | N/A | N/A | 50314.82 | 18% | 13.44% | 16.6% | -1.4% |  | 43.94 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23008 | Spirit Shorts Project Rachel | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 85.87% | 91.32% | 79.5% | 37171.2 | -7.7% | 228880 | 196531 | 32349 |  | 0 | 0 | 0 | 179473 | 238.97 | 17058 | 27878 | 156241.3333 | N/A | N/A | N/A | N/A | 37171.2 | 13% | 5.3% | 0.31% | -12.69% |  | 46.04 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23019 | EXP034-B Actuator Development | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 103% | 90.03% | 90.03% | 0 | -14.62% | 215541 | 221919 | -6378 |  | 12001 | 12092.91 | 0.00 | 199797 | 50.42 | 5145 | 0 | 199797 | N/A | N/A | N/A | N/A | 0 | 34% | 19.38% | 31.68% | -2.32% |  | 58.45 | [5 empty] | -16977
1724 | 2024-02-08 00:29 | P23472 | Tempest Wing Design | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 42.79% | 124.4% | 98.7% | 0 | -19.79% | 483870 | 207042 | 276828 |  | 191163 | 206400 | 0 | 257532 | 4.17 | -50489 | 63812 | 204355.3333 | N/A | N/A | N/A | N/A | 0 | 23% | 3.21% | 16.68% | -6.32% |  | 46.74 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23603 | Typhoon IMDLR | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 189.2% | 0% | 0% | 0 | -2.96% | 119880 | 226784 | -106904 |  | 0 | 0 | 189459 | 0 | 202.2 | 226784 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 34% | 31.04% | 32.25% | -1.75% |  | 57.78 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23316 | Model Factory IL and AW | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX | 2024-01-12 | 1 |  |  | 88.13% | 104.1% | 96.46% | 0 | 2.17% | 250000 | 220328 | 29672 |  | 0 | 0 | 0 | 229409 | 42.48 | -913 | 20249 | 212534.8333 | 0 | 0 | 20248.8 | 0 | 0 | 30% | 32.17% | 32.57% | 2.57% |  | 45.31 | [5 empty] | 8168
1724 | 2024-02-08 00:29 | P23650 | MBDA Recruitment Management costs | Brian Maddrell | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 28.66% | 0 | 237827 | -237827 |  | 0 | 0 | 266000 | 0 | 103.84 | 237827 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 3% | 31.66% | 28.8% | 25.8% |  | 82.27 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23255 | BAE Tempest WP 1 Circuits | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | 2023-10-20 | 0 |  |  | 70.38% | 99.34% | 99.34% | 0 | -2.72% | 355782 | 250395 | 105387 |  | 1654 | 1654.32 | 0 | 248740 | 0.38 | 0 | 0 | 248740 | N/A | N/A | N/A | N/A | 0 | 31% | 28.28% | 100% | 69% |  | 50.3 | [5 empty] | -1654
1724 | 2024-02-08 00:29 | P23007 | EXP-006A - Brimstone 3 | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 94.79% | 97.6% | 84.37% | 17427 | -8.47% | 264150 | 250379 | 13771 |  | 0 | 0 | 0 | 244374 | 116.98 | 5975 | 39752 | 211247.3333 | N/A | N/A | N/A | N/A | 17427 | 30% | 21.53% | 29.94% | -0.06% |  | 69.14 | [5 empty] | -30
1724 | 2024-02-08 00:29 | P23317 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX | 2024-01-12 | 1 |  |  | 95.89% | 104.3% | 98.16% | 0 | 4.05% | 251800 | 241447 | 10353 |  | 0 | 0 | 0 | 251800 | 42.15 | -1177 | 17760 | 237000 | 0 | 0 | 17760 | 0 | 0 | 25% | 29.05% | 40.59% | 15.59% |  | 36.29 | [5 empty] | 9176
1724 | 2024-02-08 00:29 | P22798 | CO2MAP MGSE | Harry James Kellett | DTW | THALES ALENIA SPACE UK (60DAYS) | EES | Level 2 | REIM | 2023-11-08 | 0 |  |  | 85.75% | 105% | 105% | 0 | 3.94% | 252086 | 216158 | 35928 |  | 0 | 0 | 0 | 227053 | 30116.66 | 25097 | 0 | 227053 | N/A | N/A | N/A | N/A | 0 | 29% | 32.94% | 0% | -29% |  | 50.31 | [5 empty] | 35992
1724 | 2024-02-08 00:29 | P21463 | Safety & Monitoring Systems at DM Beith & Gosport | Harry James Kellett | BXW | MOD | EES | Level 2 | FIX |  |  |  |  | 76.7% | 130.4% | 130.4% | 0 | -26.87% | 349405 | 267977 | 81428 |  | 56249 | 66564.38 | 21721 | 349387 | 0 | -81410 | 0 | 349387 | 0 | 0 | 0 | 0 | 0 | 48% | 21.13% | 45.28% | -2.72% |  | 52.82 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23617 | Tempest Composites WP2 | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  |  | 112.9% | 21.26% | 3.694% | 29536.68 | 3.96% | 244405 | 275856 | -31451 |  | 0 | 0 | 50000 | 58643 | 171.55 | 217214 | 58145 | 10188.8333 | 0 | 28608.29 | 0 | 29536.68 | 29536.68 | 30% | 33.96% | 34.83% | 4.83% |  | 62.23 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23308 | NATO JEWCS | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  |  | 78.15% | 98.13% | 84.6% | 0 | -3.18% | 356307 | 278458 | 77849 |  | 614 | 613.89 | 0 | 273254 | 122.88 | 5203 | 45213 | 235576.5 | N/A | N/A | N/A | N/A | 0 | 24% | 20.82% | 12.68% | -11.32% |  | 75.81 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23694 | Systems Portfolio | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 50.3% | 96.15% | 34.11% | 0 | 3.51% | 591943 | 297740 | 294203 |  | 158 | 157.75 | 0 | 286290 | 71.11 | 11451 | 221685 | 101552.5 | N/A | N/A | N/A | N/A | 0 | 21% | 24.51% | 15.98% | -5.02% |  | 90.62 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23045 | Shotgun Adaptors - 10 Sets | Harry James Kellett | BDW | MBDA UK LIMITED | EES | Level 2 | FIX |  |  |  |  | 74.73% | 95.15% | 95.15% | 0 | -19.12% | 399276 | 298392 | 100884 |  | 214430 | 214551.21 | 0 | 283926 | 384.31 | 14467 | 0 | 283926 | 0 | 0 | 0 | 0 | 0 | 29% | 9.88% | 0% | -29% |  | 55.76 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P22515 | Shorts A220 100/300 ALI Phase III | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 77.54% | 95.76% | 91.84% | 0 | 1.11% | 400629 | 310652 | 89977 |  | 3451 | 3450.98 | 0 | 297465 | 115.21 | 13187 | 14584 | 285311.6667 | N/A | N/A | N/A | N/A | 0 | 10% | 11.11% | 14.09% | 4.09% |  | 40.32 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P22953 | Spirit Shorts eVTOL | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 103.1% | 79.36% | 79.36% | 0 | -6.74% | 324272 | 334484 | -10212 |  | 66697 | 67387.9 | 0 | 265432 | 179.02 | 69052 | 0 | 265432 | N/A | N/A | N/A | N/A | 0 | 17% | 10.26% | 0% | -17% |  | 46.19 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P22842 | ME Support (Aim Altitude) | James Montgomery | AVI | AIM ALTITUDE UK LIMITED | ME | Level 3 | FIX | 2023-06-14 | 4 |  |  | 99.31% | 100.5% | 86.63% | 57290.84 | 0.49% | 346294 | 343918 | 2376 |  | 2910 | 2909.86 | 0 | 345673 | 55184.93 | -1755 | 57291 | 297930.5 | 0 | 0 | 0 | 57290.84 | 57290.84 | 13% | 13.49% | 0% | -13% |  | 46.3 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23023 | Spirit Shorts R Foster/M Gourley | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  |  | 81.44% | 107.8% | 100.3% | 15899.32 | -20.01% | 416652 | 339332 | 77320 |  | 188776 | 216366 | 0 | 365804 | 47.11 | -11961 | 30664 | 340250.6667 | N/A | N/A | N/A | N/A | 15899.32 | 27% | 6.99% | 9.9% | -17.1% |  | 29.49 | [5 empty] | 14511
1724 | 2024-02-08 00:29 | P22391 | GE System Engineering support | Vinayakumar Sugur | GEE | EXPERIS LIMITED | EES | Level NC | REIM |  |  |  |  | 82.01% | 96.18% | 95.48% | 0 | 0.13% | 434434 | 356261 | 78173 |  | 0 | 0 | 0 | 342641 | 90.63 | 13620 | 2976 | 340161 | N/A | N/A | N/A | N/A | 0 | 6% | 6.13% | 6.09% | 0.09% |  | 57.33 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23531 | BAe Systems F35 MRB Support | Andrew Houghton | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM | [5 empty] | 73.05% | 73.05% | 0 | 2.54% | 0 | 365866 | -365866 |  | 287 | 287.44 | 0 | 267283 | 65.96 | 98583 | 0 | 267283 | N/A | N/A | N/A | N/A | 0 | 25% | 27.54% | 33.59% | 8.59% |  | 59.03 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23520 | FCAS AP Portfolio Systems | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 46.35% | 96.94% | 76.11% | 0 | -6.83% | 810821 | 375793 | 435028 |  | 320 | 319.5 | 0 | 364294 | 65.12 | 11499 | 93930 | 286019 | N/A | N/A | N/A | N/A | 0 | 22% | 15.17% | 17.36% | -4.64% |  | 79.04 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23554 | Dornier Seawings 328 2023 H2 Support | Steven Lawton | DAX | EXPLEO GERMANY GMBH (EC) | MPE | Level 2 | REIM |  |  |  |  | 92.74% | 90.81% | 90.81% | 0 | 7.75% | 416112 | 385910 | 30202 |  | 3551 | 3550.65 | 25985 | 350449 | 29.07 | 35461 | 0 | 350449 | N/A | N/A | N/A | N/A | 0 | 21% | 28.75% | 32.78% | 11.78% |  | 67.44 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23432 | Spirit Belfast MRB On-Site Support (Mon & Clear) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 65.77% | 125.6% | 96.58% | 77391.6 | -11.53% | 449545 | 295665 | 153880 |  | 295665 | 451827.33 | 0 | 371466 | 37.59 | 36200 | 103100 | 285549.3333 | N/A | N/A | N/A | N/A | 77391.6 | 39% | 27.47% | 0% | -39% |  | 0 | [5 empty] | 112000
1724 | 2024-02-08 00:29 | P23320 | Lifing Services DACs | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX | 2024-01-12 | 1 |  |  | 95.56% | 104.6% | 97.44% | 0 | 2.72% | 413300 | 394956 | 18344 |  | 0 | 0 | 0 | 413300 | 40.63 | -2050 | 34139 | 384850.8333 | 0 | 0 | 34138.8 | 0 | 0 | 26% | 28.72% | 44.21% | 18.21% |  | 33.15 | [5 empty] | 16294
1724 | 2024-02-08 00:29 | P22906 | Spirit Shorts - MRB JD Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  |  | 68.21% | 92.21% | 71.11% | 6156 | -7.57% | 614770 | 419356 | 195414 |  | 0 | 0 | 0.00 | 386688 | 253.08 | 40669 | 106200 | 298188 | N/A | N/A | N/A | N/A | 6156 | 13% | 5.43% | 3.71% | -9.29% |  | 36.82 | [5 empty] | 8000
1724 | 2024-02-08 00:29 | P23473 | Tempest Vertical Tail | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 59.06% | 103.4% | 81.31% | 0 | -2.78% | 723866 | 427497 | 296369 |  | 85150 | 100425 | 0 | 441918 | 49.83 | -14421 | 113181 | 347600.5 | N/A | N/A | N/A | N/A | 0 | 24% | 21.22% | 26.19% | 2.19% |  | 62.43 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23366 | Business Analyst Support | Peter Williams | BDZ | MBDA UK LIMITED | DET | Level NC | REIM |  |  |  |  | 33.09% | 257% | 200.5% | 0 | 11.92% | 583200 | 192994 | 390206 |  | 192993 | 416921.86 | 0 | 496000 | 55.93 | -64871 | 130752 | 387040 | N/A | N/A | N/A | N/A | 0 | 43% | 54.92% | 15.27% | -27.73% |  | 0.01 | [5 empty] | 238135
1724 | 2024-02-08 00:29 | P23140 | Spirit Shorts A220 MLG Stress Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  |  | 70.33% | 88.51% | 78.9% | 48343.2 | -15.24% | 595746 | 418981 | 176765 |  | 20870 | 87811.88 | 0.00 | 370857 | 133.84 | 73124 | 48343 | 330571.1667 | 0 | 0 | 0 | 48343.2 | 48343.2 | 32% | 16.76% | 12.94% | -19.06% |  | 47.32 | [5 empty] | 25000
1724 | 2024-02-08 00:29 | P23372 | BAE Carbon Tooling Off-load | Gary Kempster | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  |  | 165.3% | 56.3% | 56.3% | 0 | -4.12% | 276718 | 457433 | -180715 |  | 0 | 0 | 197460.8 | 257522 | 210.4 | 199912 | 0 | 257522 | N/A | N/A | N/A | N/A | 0 | 27% | 22.88% | 21.55% | -5.45% |  | 53.57 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23602 | EXP-025 Portfolio Software Engineering Support | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 39.7% | 93.3% | 54.28% | 0 | -0.5% | 1221060 | 484751 | 736309 |  | 710 | 901.89 | 0 | 452291 | 69.79 | 32460 | 227007 | 263118.5 | N/A | N/A | N/A | N/A | 0 | 24% | 23.5% | 23.76% | -0.24% |  | 82.56 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23323 | CNC-CMM Programming Support | Andrew Houghton | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  |  | 118.1% | 73.88% | 73.88% | 0 | -3.82% | 416048 | 491422 | -75374 |  | 13662 | 13661.56 | 95785.2 | 363077 | 116.33 | 128346 | 0 | 363077 | N/A | N/A | N/A | N/A | 0 | 32% | 28.18% | 39.22% | 7.22% |  | 56.79 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P22652 | L3 - Saftey Engineering | Sean Simmons | LHW | L3HARRIS MAPPS LIMITED | EES | Level NC | FIX |  |  |  |  | 95.63% | 86.69% | 86.69% | 0 | 5.66% | 523390 | 500498 | 22892 |  | 0 | 0 | 0 | 433883 | 79938 | 66615 | 0 | 433883 | 0 | 0 | 0 | 0 | 0 | 21% | 26.66% | 25.88% | 4.88% |  | 83.05 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23001 | Spirit Shorts A220 Design | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 115% | 72.43% | 69.92% | 15202.56 | -3.8% | 439560 | 505552 | -65992 |  | 0 | 0 | 65953.2 | 366148 | 317.16 | 139404 | 15203 | 353478.8333 | N/A | N/A | N/A | N/A | 15202.56 | 25% | 21.2% | 11.21% | -13.79% |  | 43.63 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23281 | Systems Portfolio | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM | 2024-02-28 | 0 |  |  | 44.43% | 97.19% | 97.19% | 0 | -17.1% | 1177697 | 523237 | 654460 |  | 2133 | 2133.28 | 0 | 508545 | 17523.23 | 14603 | 0 | 508545 | N/A | N/A | N/A | N/A | 0 | 25% | 7.9% | 0% | -25% |  | 70.48 | [5 empty] | -89
1724 | 2024-02-08 00:29 | P23426 | BAE Tempest WP 3 Harness Maturation | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 61.38% | 86.17% | 74.13% | 0 | -5.98% | 884012 | 542632 | 341380 |  | 213 | 213.34 | 0 | 467592 | 67.11 | 75040 | 78397 | 402261.1667 | N/A | N/A | N/A | N/A | 0 | 33% | 27.02% | 29.51% | -3.49% |  | 51.02 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P21138 | D&A Vibration Reduc Damping Struc FOGV Components | Steven Lawton | ATC | AECC SICHUAN GAS TURBINE | MPE | Level 1 | FIX | 2022-09-07 | 0 |  |  | 96.12% | 104% | 104% | 0 | -3.44% | 569346 | 547228 | 22118 |  | 75182 | 75181.75 | 0 | 569346 | 0 | -11 | 0 | 569346 | 0 | 0 | 0 | 0 | 0 | 36% | 32.56% | 0% | -36% |  | 73.95 | [5 empty] | 22107
1724 | 2024-02-08 00:29 | P23219 | Tornado Air 800 Engineering Support | Richard Brook | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 3 | REIM |  |  |  |  | 95.46% | 98.51% | 98.51% | 0 | 1.46% | 615046 | 587098 | 27948 |  | 459 | 459.21 | 314840 | 578373 | 10470.24 | 8725 | 0 | 578373 | N/A | N/A | N/A | N/A | 0 | 31% | 32.46% | 0% | -31% |  | 81.76 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23605 | Typhoon Work Package 2 Continuation | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM |  |  |  |  | 404.5% | 0% | 0% | 0 | 3.19% | 155094 | 627408 | -472314 |  | 4054 | 4054 | 472441.54 | 0 | 172.13 | 627408 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 25% | 28.19% | 29.09% | 4.09% |  | 55.63 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23451 | BAE Tempest - DFM-ASO Planning | Andrew Houghton | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  |  | 67.54% | 63.67% | 23.71% | 0 | -4.01% | 953905 | 644280 | 309625 |  | 0 | 0 | 0 | 410202 | 171.23 | 234078 | 308940 | 152752 | N/A | N/A | N/A | N/A | 0 | 28% | 23.99% | 24.78% | -3.22% |  | 53.18 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P22790 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 2 | REIM |  |  |  |  | 194.5% | 90.44% | 90.44% | 0 | 1.37% | 352240 | 685262 | -333022 |  | 1612 | 1611.52 | 515246 | 619744 | 41098.04 | 34248 | 0 | 619744 | N/A | N/A | N/A | N/A | 0 | 13% | 14.37% | 0% | -13% |  | 45.06 | [5 empty] | -31270
1724 | 2024-02-08 00:29 | P23321 | EHM Cloud Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX | 2024-01-29 | 3 |  |  | 89.76% | 111.4% | 103.8% | 0 | 2.78% | 839969 | 753975 | 85994 |  | 0 | 0 | 24980 | 839969 | 42.98 | -3454 | 69002 | 782467.3333 | 0 | 0 | 69002.4 | 0 | 0 | 28% | 30.78% | 56.85% | 28.85% |  | 49.95 | [5 empty] | 82540
1724 | 2024-02-08 00:29 | P23105 | Raytheon Supply Engineering Support | Natalie Sinclair | RAY | RAYTHEON UNITED KINGDOM LIMITED | MPE | Level 3A | REIM | 2023-07-13 | 2 |  |  | 76.96% | 94.49% | 90.07% | 0 | -1.83% | 1205008 | 927395 | 277613 |  | 0 | 0 | 0 | 876292 | 110481.3 | 51104 | 49157 | 835327.8333 | N/A | N/A | N/A | N/A | 0 | 26% | 24.17% | 0% | -26% |  | 48.97 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P22350 | EMP 2020-2021 | Natalie Sinclair | ARY | GUIDANT GROUP (trading name) | PCPR | Level NC | REIM |  |  |  |  | 100% | 99.19% | 94.5% | 0 | -1.89% | 930212 | 930298 | -86 |  | 400 | 400 | 0.00 | 922738 | 67.35 | 7560 | 52380 | 879088 | N/A | N/A | N/A | N/A | 0 | 32% | 30.11% | 28.89% | -3.11% |  | 44.04 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23117 | BAE Typhoon Eng Support | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 107.6% | 88.52% | 88.52% | 0 | -1.44% | 950772 | 1022826 | -72054 |  | 19090 | 21165.02 | 69773.84 | 905368 | 108434.61 | 90362 | 0 | 905368 | N/A | N/A | N/A | N/A | 0 | 30% | 28.56% | 0% | -30% |  | 52.3 | [5 empty] | -27096
1724 | 2024-02-08 00:29 | P23519 | Mechanical and Electrical Design Eng Support | Dushan Fernando | BAX | SAFRAN SEATS GB LIMITED | MPE | Level 2 | REIM |  |  |  |  | 122.7% | 79.78% | 73.55% | 0 | -1.42% | 839697 | 1030348 | -190651 |  | 727 | 727 | 186282 | 821977 | 64.17 | 208370 | 77014 | 757798.6667 | N/A | N/A | N/A | N/A | 0 | 33% | 31.58% | 32.41% | -0.59% |  | 56.59 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23292 | BAE Tempest WP 4 AV Trays | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 70.54% | 89.32% | 81.26% | 0 | 2.14% | 1498284 | 1056963 | 441321 |  | 0 | 0 | 0 | 944039 | 67.87 | 112925 | 102198 | 858874 | N/A | N/A | N/A | N/A | 0 | 32% | 34.14% | 33.99% | 1.99% |  | 52.98 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23152 | Project Aragon - Design and Stress Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  |  | 90.12% | 61.87% | 61.87% | 0 | -9.4% | 1307861 | 1178663 | 129198 |  | 0 | 0 | 0 | 729296 | 271.35 | 449367 | 0 | 729296 | N/A | N/A | N/A | N/A | 0 | 39% | 29.6% | 31.55% | -7.45% |  | 51.86 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P22671 | Spirit Shorts Pylon and Fairing Package | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX | 2023-05-03 | 4 |  |  | 105% | 95.27% | 95.27% | 0 | -7.21% | 1198495 | 1258028 | -59533 |  | 106451 | 174863.91 | 0 | 1198495 | 2492.21 | 2077 | 0 | 1198495 | 0 | 0 | 0 | 0 | 0 | 20% | 12.79% | 0% | -20% |  | 45.4 | [5 empty] | -57456
1724 | 2024-02-08 00:29 | P23435 | Andy Baker Portfolio | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 44.34% | 90.67% | 75.14% | 0 | -8.85% | 3377457 | 1497703 | 1879754 |  | 2353 | 2352.57 | 0 | 1357991 | 74.37 | 139712 | 279146 | 1125369.3333 | N/A | N/A | N/A | N/A | 0 | 25% | 16.15% | 13.91% | -11.09% |  | 77.99 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23315 | DAC LUC BAU and Service Workbench | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  |  | 83.69% | 119.5% | 107.1% | 0 | 2.62% | 1573630 | 1316976 | 256654 |  | 180 | 180.3 | 0 | 1573630 | 24.34 | -58857 | 195596 | 1410633.3333 | 0 | 0 | 195596.4 | 0 | 0 | 28% | 30.62% | 41.11% | 13.11% |  | 52.33 | [5 empty] | 197797
1724 | 2024-02-08 00:29 | P23411 | Agile & Scrum Delivery Service | Peter Williams | BDZ | MBDA UK LIMITED | DET | Level 2 | REIM | 2023-08-14 | 1 |  |  | 36.3% | 170.5% | 170.5% | 0 | 13.08% | 2487000 | 902904 | 1584096 |  | 894179 | 2337284.55 | 0 | 1539600 | 91 | 16141 | 0 | 1539600 | N/A | N/A | N/A | N/A | 0 | 29% | 42.08% | 0% | -29% |  | 74.57 | [5 empty] | 652837
1724 | 2024-02-08 00:29 | P23006 | Spirit Shorts A350 Freighter Toulouse | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 142.5% | 83.67% | 83.67% | 133600.64 | 18.71% | 1035746 | 1476202 | -440456 |  | 1086670 | 1708220.2 | 0 | 1235101 | 269.93 | 552375 | 0 | 1235101 | N/A | N/A | N/A | N/A | 133600.64 | 5% | 23.71% | 37.65% | 32.65% |  | 47.62 | [5 empty] | 311274
1724 | 2024-02-08 00:29 | P22278 | TAI Supply Engineers to Ankara | Natalie Sinclair | TAI | TUSAS-TURK HAVACILIK VE UZAY | MPE | Level 3A | REIM |  |  |  |  | 19.11% | 474.8% | 468.2% | 16000 | -15.57% | 2105282 | 402400 | 1702882 |  | 49400 | 49400.29 | 0 | 1910696 | 42.25 | -26240 | 32000 | 1884029.3333 | N/A | N/A | N/A | N/A | 16000 | 95% | 79.43% | 52.18% | -42.82% |  | 34.31 | [5 empty] | 1482056
1724 | 2024-02-08 00:29 | P23207 | A350 Approvers - Design and Stress Support | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  |  | 89.59% | 82.62% | 53.04% | 246367.11 | -4.29% | 2183628 | 1956280 | 227348 |  | 17140 | 17602.77 | 0 | 1616237 | 123.02 | 340043 | 694433 | 1037542.8333 | 327329.21 | 105370.2 | 91957.54 | 169776.21 | 246367.11 | 23% | 18.71% | 20.69% | -2.31% |  | 54.71 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23257 | BAE Tempest WP 5 Centre Fuselage | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 94.28% | 96.43% | 91.99% | 0 | -5.82% | 2106861 | 1986436 | 120425 |  | 78100 | 78100 | 0 | 1915593 | 58.13 | 70843 | 105960 | 1827293 | N/A | N/A | N/A | N/A | 0 | 33% | 27.18% | 28.13% | -4.87% |  | 61.05 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23175 | BAe Aero Typhoon Package 2 | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM |  |  |  |  | 103.8% | 96.32% | 96.32% | 0 | -1.63% | 1984265 | 2060012 | -75747 |  | 57678 | 86030.82 | 15444.64 | 1984257 | 84731.75 | 70610 | 0 | 1984257 | N/A | N/A | N/A | N/A | 0 | 29% | 27.37% | 0% | -29% |  | 51.76 | [5 empty] | -5145
1724 | 2024-02-08 00:29 | P19020 | Spirit Concessions - 2018 | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2024-01-23 | 3 |  |  | 90.82% | 111.8% | 107% | 99792.83 | 2.09% | 1914847 | 1739018 | 175829 |  | 44318 | 44317.61 | 15178.88 | 1944711 | 2343.15 | 196987 | 99793 | 1861550.1667 | 0 | 0 | 0 | 99792.83 | 99792.83 | 25% | 27.09% | 10.92% | -14.08% |  | 40.87 | [5 empty] | 402680
1724 | 2024-02-08 00:29 | P23487 | Tornado Air 800 Engineering Support | Richard Brook | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 2 | FIX |  |  |  |  | 98.17% | 88.51% | 82.03% | 0 | -1.53% | 2525468 | 2479187 | 46281 |  | 0 | 0 | 0 | 2194207 | 57.56 | 284980 | 192507 | 2033784.5 | 192507.32 | 0 | 0 | 0 | 0 | 37% | 35.47% | 38.32% | 1.32% |  | 78.71 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P23179 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX |  |  |  |  | 130.6% | 84.37% | 82.88% | 135229.5 | -9.32% | 1921629 | 2510422 | -588793 |  | 155464 | 246717.26 | 492000 | 2118030 | 291.98 | 392391 | 44997 | 2080532.5 | 0 | 9496.08 | 0 | 35500.91 | 135229.5 | 22% | 12.68% | 19.28% | -2.72% |  | 44.4 | [5 empty] | 0
1724 | 2024-02-08 00:29 | P19731 | Hapri HPC Rear Bearing Housing PDR & CDR | Steven Lawton | ATC | AECC Hunan Aviation Powerplant | MPE | Level 1 | FIX |  |  |  |  | 99.37% | 100.6% | 88.05% | 447000 | -15.32% | 2980000 | 2961319 | 18681 |  | 358408 | 512832.98 | 0 | 2980000 | 824.63 | -243681 | 447000 | 2607500 | 0 | 0 | 447000 | 0 | 447000 | 38% | 22.68% | 22.88% | -15.12% |  | 64.86 | [5 empty] | -225000
Extend Table

## AP2-2
|  |  | Projects Overview |  | WIP No.: 1725 | [9 empty] | Report Date: | 2024-02-15 00:34
Project Inclusion Check:
1
185
184
| Project Identification | [12 empty] | Key Indicators | [5 empty] | Current PO Cover | [6 empty] | Current Cash status | [9 empty] | Project Margin | [5 empty] | Quality Metrics | Additional Information | Income Adjustment (If template used for PFR)
| WIP No | Date Created | Project ID | Project Description | Project Manager | Department Id | Client | CBU | Complexity | Type | Stop Booking Hrs | Closing Project: Action(s) to close | RAG | Approx. PO Burndown (weeks) | Turnover vs Contract Value | Invoice To Date vs Turnover | Cash in vs Turnover | Open Amount Overdue | Actual PM% to Baseline PM% delta | Contract Value | Total Project Turnover | Contract Value - Total Turnover | Run Rate (based on total turnover) | Total BOI Spend to Date | Total Committed PO (supplier/best shore) | Current AA in PT3 | Invoiced To Date | DSO | Unbilled (WIP) | Total Open Amount | Cash in (Invoiced - (Open amount -VAT)) | Debt <=30 Days | Debt 31 - 60 Days | Debt 61 - 90 Days | Debt >= 90 Days | Open Amount Overdue2 | Baseline Project Margin | Project To Date (PTD) PM | Year to Date (YTD) PM | YTD Delta Actual PM% to BPM% | Forecast PM at Completion (Manual input from PTT) | Average Sale Rate | CSat score for last quarter (Manual input from PTT) | Comments and Actions | Judged income adjustment at completion | Profit to take now | Provision required now | Fully Traded | Last Months Comments and Actions
| 1725 | 2024-02-15 00:34 | P23641 | Drawing Triage | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM | 2024-01-25 | 0 |  |  |  | 0% | 0% | 0 | 1043368% | 0 | 10756 | -10756 |  | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 1043368% | 100% | 100% |  | 49 | [5 empty] | -10756
| 1725 | 2024-02-15 00:34 | P23637 | MBSE Proposal | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 |  | 0 | 0 | 49980 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23711 | DO NOT USE - RAISED IN ERROR | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23717 | GKN Ted Tomblin 2024 | Matthew Tweed | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 10047.00 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23552 | FCAS AP Product Technology Development | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -25% | 597871 | 0 | 597871 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 25% | 0% | 0% | -25% |  | 0 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23543 | EXP-024 FCAS AP Transformation & Change Enablers | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -26% | 385921 | 0 | 385921 |  | 0 | 0 | 0.00 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 26% | 0% | 0% | -26% |  | 0 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23585 | Systems Design - Missile Systems, Meteor,Brimstone | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 |  | 0 | 0 | 49500.00 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23137 | BAE Management Support Collector | Danny Wilkinson | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3A | REIM | 2024-02-08 | 0 |  |  |  | 0% | 0% | 0 | -44357052% | 0 | 100437 | -100437 |  | 1053 | 1053.38 | 0 | 0 | 0.3 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | -44357052% | 0% | 0% |  | 50 | [5 empty] | -100437
| 1725 | 2024-02-15 00:34 | P23730 | FLE Project | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -17.12% | 0 | 665 | -665 |  | 0 | 0 | 24000.00 | 0 | 41 | 665 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | -17.12% | -17.12% | -17.12% |  | 35 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23463 | A220 Wing MaMo Design Checking | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 7.85% | 0 | 1628 | -1628 |  | 0 | 0 | 15000 | 0 | 1953.6 | 1628 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 3% | 10.85% | 0% | -3% |  | 44 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P21028 | Rebate Collection (BACC) | David Catchpole | TOO | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | [5 empty] | 0% | 0% | 0 | 0% | 0 | 2680 | -2680 |  | 2680 | 2680 | 0 | 0 | 3216 | 2680 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23740 | Phase 2 - EJ200 ESS EHM Platform Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 3 | FIX |  |  |  |  | 1.932% | 739.4% | -0.004902% | 0 | 3.56% | 175971 | 3400 | 172571 |  | 0 | 0 | 0 | 25139 | 41 | -21739 | 30167 | -0.16667 | 30166.8 | 0 | 0 | 0 | 0 | 28% | 31.56% | 31.56% | 3.56% |  | 80 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23578 | ESN Work Package | Hannah Mead | COZ | CHELTON LIMITED | DET | Level 3 | FIX | 2024-01-01 | 0 |  |  | 86.17% | 116.1% | 116.1% | 0 | 35.86% | 4410 | 3800 | 610 |  | 0 | 0 | 0 | 4410 | 0 | -610 | 0 | 4410 | 0 | 0 | 0 | 0 | 0 | 24% | 59.86% | 0% | -24% |  | 95 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23628 | Design Assurance | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -6.67% | 0 | 3909 | -3909 |  | 0 | 0 | 4454.80 | 0 | 4691.09 | 3909 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 7% | 0.33% | 0% | -7% |  | 15.05 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23002 | WoT MAJ Transit Flag Stress | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 30.9% | 323.7% | 323.7% | 0 | 53.84% | 4735 | 1463 | 3272 |  | 0 | 2242.5 | 0 | 4735 | 0.6 | 1 | 0 | 4735 | 0 | 0 | 0 | 0 | 0 | 10% | 63.84% | 0% | -10% |  | 45 | [5 empty] | 3273
| 1725 | 2024-02-15 00:34 | P23718 | Requalification of EJ200 GSS ESS EHM SW module | Vijayakumara Nanjundappa | ARZ | MTU AERO ENGINES AG | DET | Level 3 | FIX |  |  |  |  | 7.508% | 0% | 0% | 0 | -3.61% | 74463 | 5591 | 68872 |  | 881 | 881.46 | 0 | 0 | 41 | 5591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 24.39% | 24.39% | -3.61% |  | 80 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23742 | Cyber Security Support | Hannah Mead | COZ | CHELTON LIMITED | DET | Level 3 | FIX | [5 empty] | 0% | 0% | 0 | 33.55% | 0 | 6600 | -6600 |  | 0 | 0 | 9000.00 | 0 | 63 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 33.55% | 33.55% | 33.55% |  | 100 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23607 | SAFRAN - A330neo Turnover Frame | Gary Kempster | TOO | SAFRAN SEATS GB LIMITED | MPE | Level 3 | FIX |  |  |  |  | 95.68% | 104.5% | 0.001994% | 0 | -19.75% | 8736 | 8359 | 377 |  | 0 | 0 | 0 | 8736 | 10030.8 | -377 | 10483 | 0.16667 | 10483.2 | 0 | 0 | 0 | 0 | 23% | 3.25% | 0% | -23% |  | 52 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23274 | ME Support (Aim Altitude - Cambridge) | James Montgomery | AVI | AVIC CABIN SYSTEMS (UK) LIMITED | ME | Level 3 | FIX | 2023-08-18 | 0 |  |  | 51.88% | 56.29% | 56.29% | 0 | -0.17% | 17280 | 8964 | 8316 |  | 0 | 0 | 0 | 5046 | 4701.24 | 3918 | 0 | 5046 | 0 | 0 | 0 | 0 | 0 | 21% | 20.83% | 0% | -21% |  | 48 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23283 | Spirit Tooling Audit | Charidimos Valadakis | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-05-03 | 0 |  |  | 97.23% | 48.57% | 48.57% | 0 | -7.99% | 9910 | 9635 | 275 |  | 0 | 0 | 0 | 4680 | 5946.05 | 4955 | 0 | 4680 | N/A | N/A | N/A | N/A | 0 | 7% | -0.99% | 0% | -7% |  | 34.41 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23127 | Loft Hall Design Support | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 101% | 99.06% | 99.06% | 0 | -9.55% | 9680 | 9772 | -92 |  | 0 | 0 | 0 | 9680 | 110.4 | 92 | 0 | 9680 | N/A | N/A | N/A | N/A | 0 | 41% | 31.45% | 0% | -41% |  | 44 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23630 | 2Excel CFD Analysis Support | Dushan Fernando | BAX | STIRLING DYNAMICS LTD | MPE | Level NC | FIX |  |  |  |  | 61.2% | 100% | 100% | 0 | -1.87% | 16195 | 9911 | 6284 |  | 0 | 0 | 0 | 9912 | 0 | 0 | 0 | 9912 | 0 | 0 | 0 | 0 | 0 | 26% | 24.13% | 0% | -26% |  | 64.78 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23724 | GKN S McConnell 2024 | Matthew Tweed | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  |  | 21.4% | 65.43% | 0% | 0 | 1.51% | 49820 | 10661 | 39159 |  | 0 | 0 | 0.00 | 6975 | 41 | 3687 | 8370 | 0 | N/A | N/A | N/A | N/A | 0 | 19% | 20.51% | 20.51% | 1.51% |  | 49.82 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23663 | Spirit Tooling Verification and Inspection | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 57.29% | 0% | 0% | 0 | -7.6% | 19820 | 11355 | 8465 |  | 0 | 0 | 7392 | 0 | 116.4 | 11355 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 12% | 4.4% | 4.82% | -7.18% |  | 34.41 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23313 | Laser Trim Fixtures | Gary Kempster | TOO | ALKEN ENGINEERING LIMITED | MPE | Level 3 | FIX | 2023-11-20 | 0 |  |  | 89.87% | 111.3% | 111.3% | 0 | 0.53% | 13770 | 12375 | 1395 |  | 0 | 0 | 0 | 13770 | 0 | -1395 | 0 | 13770 | 0 | 0 | 0 | 0 | 0 | 17% | 17.53% | 0% | -17% |  | 45 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P22761 | Red Bull Chassis Spit | James Montgomery | TOO | MANUFAX ENGINEERING LTD | MPE | Level 3 | FIX | 2022-11-15 | 0 |  |  | 72.19% | 96.98% | 96.98% | 0 | 7.92% | 12961 | 9356 | 3605 |  | 0 | 0 | 0 | 9073 | 4666.39 | 3889 | 0 | 9073 | 0 | 0 | 0 | 0 | 0 | 23% | 30.92% | 0% | -23% |  | 42.19 | [5 empty] | 3606
| 1725 | 2024-02-15 00:34 | P23433 | Cavendish | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 32.81% | 100% | 100% | 0 | -0.34% | 42240 | 13859 | 28381 |  | 0 | 0 | 0 | 13859 | 0 | 0 | 0 | 13859 | N/A | N/A | N/A | N/A | 0 | 7% | 6.66% | 0% | -7% |  | 43.93 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23350 | Spirit 2023 - Stress Approve Man Serv (DH) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 14.15% | 72.64% | 72.64% | 0 | -0.29% | 97920 | 13860 | 84060 |  | 0 | 0 | 0 | 10068 | 4550.4 | 3792 | 0 | 10068 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23344 | Spirit A320 Spoilers Support 2023 | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 38.75% | 100% | 100% | 0 | 5.82% | 35786 | 13867 | 21919 |  | 0 | 0 | 0 | 13867 | 0 | 0 | 0 | 13867 | N/A | N/A | N/A | N/A | 0 | 7% | 12.82% | 0% | -7% |  | 34.41 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23337 | Spirit 2023 - Steve Grimley | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 25.28% | 100% | 100% | 0 | 0.01% | 56813 | 14362 | 42451 |  | 0 | 0 | 0 | 14362 | 0 | 0 | 0 | 14362 | N/A | N/A | N/A | N/A | 0 | 7% | 7.01% | 0% | -7% |  | 30.11 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23598 | MRB Onsite support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -9.65% | 0 | 14389 | -14389 |  | 8736 | 14079.58 | 21700 | 0 | 200.46 | 14389 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 18% | 8.35% | 8.89% | -9.11% |  | 42.5 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23597 | MRB Onsite support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -10.04% | 0 | 15101 | -15101 |  | 9448 | 17381.62 | 24200 | 0 | 187.36 | 15101 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 18% | 7.96% | 8.95% | -9.05% |  | 42.5 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23760 | Land Ceptor V&V Systems Engineer | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 28.98% | 0 | 17584 | -17584 |  | 0 | 0 | 23550 | 0 | 41 | 17584 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 28.98% | 28.98% | 28.98% |  | 78.5 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23635 | Engineering Services: FAI Support | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 47.4% | 0% | 0% | 0 | -3.43% | 37230 | 17647 | 19583 |  | 0 | 0 | 0.00 | 0 | 157.18 | 17647 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 8% | 4.57% | 5.04% | -2.96% |  | 38.7 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23343 | Spirit 2023 - John Agnew | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-08-09 | 0 |  |  | 28.56% | 86.27% | 86.27% | 0 | -0.02% | 65120 | 18601 | 46519 |  | 0 | 0 | 0 | 16047 | 3064.49 | 2554 | 0 | 16047 | N/A | N/A | N/A | N/A | 0 | 7% | 6.98% | 0% | -7% |  | 34.51 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23753 | Tempest Composites Maturation | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | [5 empty] | 0% | 0% | 0 | -26.21% | 0 | 19331 | -19331 |  | 0 | 0 | 54398.40 | 0 | 42 | 19331 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 37% | 10.79% | 10.79% | -26.21% |  | 64.76 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23355 | Spirit Tooling Support 2023 | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-23 | 0 |  |  | 22.93% | 89.03% | 89.03% | 0 | -0.82% | 91800 | 21053 | 70747 |  | 0 | 0 | 0 | 18743 | 2773.01 | 2311 | 0 | 18743 | 0 | 0 | 0 | 0 | 0 | 20% | 19.18% | 0% | -20% |  | 44.46 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23651 | PMO Spirit | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 24.7% | 0 | 21996 | -21996 |  | 0 | 0 | 30800.00 | 0 | 151.5 | 21996 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | 24.7% | 25.06% | 25.06% |  | 36 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23729 | Honda Tooling | Paul Watson | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX | [5 empty] | 0% | 0% | 0 | 6.82% | 0 | 24371 | -24371 |  | 0 | 0 | 33167 | 0 | 35 | 24371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 16.82% | 16.82% | 6.82% |  | 42.2 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23351 | Spirit 2023 - Design Man Serv (KL) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 26.47% | 93.15% | 93.15% | 0 | 0.09% | 93840 | 24840 | 69000 |  | 0 | 0 | 0 | 23138 | 2042.4 | 1702 | 0 | 23138 | 0 | 0 | 0 | 0 | 0 | 26% | 26.09% | 0% | -26% |  | 46 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23356 | Spirit 2023 - Design Man Serv (AH) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX | 2023-08-09 | 1 |  |  |  | 76.66% | 0.001332% | 23018.4 | 0.48% | 0 | 25023 | -25023 |  | 0 | 0 | 25300.00 | 19182 | 30027.7 | 5841 | 23018 | 0.33333 | 0 | 0 | 0 | 23018.4 | 23018.4 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P22884 | Spirit Shorts Config Eng | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 66.3% | 100.1% | 100.1% | 0 | 0.56% | 38976 | 25842 | 13134 |  | 0 | 0 | 0 | 25863 | 0 | 0 | 0 | 25863 | N/A | N/A | N/A | N/A | 0 | 7% | 7.56% | 0% | -7% |  | 20.3 | [5 empty] | 21
| 1725 | 2024-02-15 00:34 | P23354 | Spirit 2023 - Design Man Serv (PC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 27.97% | 99.36% | 99.36% | 0 | 0.48% | 93840 | 26249 | 67591 |  | 0 | 0 | 0 | 26082 | 200.38 | 167 | 0 | 26082 | 0 | 0 | 0 | 0 | 0 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23338 | Spirit 2023 - Blair Hainey | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 78.03% | 67.03% | 67.03% | 0 | 3.77% | 34494 | 26917 | 7577 |  | 0 | 0 | 0 | 18042 | 118.21 | 8875 | 0 | 18042 | N/A | N/A | N/A | N/A | 0 | 7% | 10.77% | 19.31% | 12.31% |  | 18.28 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23744 | Model Factory | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  |  | 10.45% | 83.41% | -0.001216% | 0 | 8.35% | 262300 | 27403 | 234897 |  | 0 | 0 | 0 | 22858 | 41 | 4545 | 27430 | -0.33333 | 27429.6 | 0 | 0 | 0 | 0 | 28% | 36.35% | 36.35% | 8.35% |  | 50.75 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P22756 | A350 FLE Design Checker | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2022-03-23 | 1 |  |  | 68.39% | 119.7% | 119.7% | 0 | 16.46% | 34898 | 23867 | 11031 |  | 23867 | 24342.3 | 0 | 28571 | 0.06 | 0 | 0 | 28571 | N/A | N/A | N/A | N/A | 0 | 0% | 16.46% | 0% | 0% |  | 0 | [5 empty] | 4704
| 1725 | 2024-02-15 00:34 | P23642 | MRB Belfast Support | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -18.13% | 0 | 29783 | -29783 |  | 2170 | 2252.31 | 30800.00 | 0 | 118.14 | 29783 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0% | -18.13% | -18.56% | -18.56% |  | 38.52 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23458 | Spirit Belfast Tooling Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-08-11 | 0 |  |  | 101.3% | 94.65% | 94.65% | 0 | 8.64% | 30384 | 30785 | -401 |  | 0 | 0 | 0 | 29139 | 1974.96 | 1646 | 0 | 29139 | N/A | N/A | N/A | N/A | 0 | 7% | 15.64% | 0% | -7% |  | 42.2 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23754 | Tempest Composites WP4 | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX | [5 empty] | 0% | 0% | 0 | 8.53% | 0 | 32290 | -32290 |  | 0 | 0 | 97140 | 0 | 56 | 32290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 36.53% | 36.53% | 8.53% |  | 65.36 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23365 | GKN 777x Lip Skin Fixture | Steven Lawton | TOO | GKN AEROSPACE SERVICES LTD | MPE | Level 3 | FIX | 2023-10-12 | 0 |  |  | 41.91% | 113.2% | 113.2% | 0 | -9.26% | 79161 | 33176 | 45985 |  | 5110 | 5109.88 | 0 | 37544 | 0 | -4369 | 0 | 37544 | 0 | 0 | 0 | 0 | 0 | 22% | 12.74% | 0% | -22% |  | 56 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P22768 | MRB Onsite Support - Spirit Belfast | James Montgomery | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2023-07-27 | 0 |  |  |  | 0% | 0% | 0 | -17.07% | 0 | 34614 | -34614 |  | 0 | 0 | 36800 | 0 | 41536.8 | 34614 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 10% | -7.07% | 0% | -10% |  | 36 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23347 | WoT Fixed Leading Edge - Industrial 2023 | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 112.8% | 42.03% | 42.03% | 0 | -0.41% | 31034 | 35002 | -3968 |  | 0 | 0 | 10500 | 14711 | 24349.85 | 20292 | 0 | 14711 | N/A | N/A | N/A | N/A | 0 | 7% | 6.59% | 0% | -7% |  | 32.26 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23700 | IPDT Leads | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 15.7% | 0 | 35782 | -35782 |  | 0 | 0 | 41363 | 0 | 91 | 35782 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 22% | 37.7% | 38.22% | 16.22% |  | 61.88 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23784 | Tempest Tooling Offload 2024 | Christopher McCarthy | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -8.88% | 0 | 37272 | -37272 |  | 0 | 0 | 74725 | 0 | 41 | 37272 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 30% | 21.12% | 21.12% | -8.88% |  | 54.61 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23051 | Spirit Shorts A350 PAX Door | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 3A | REIM |  |  |  |  | 205.9% | 105.4% | 105.4% | 0 | -0.63% | 18216 | 37513 | -19297 |  | 0 | 0 | 0 | 39537 | 0 | 0 | 0 | 39537 | N/A | N/A | N/A | N/A | 0 | 30% | 29.37% | 0% | -30% |  | 46 | [5 empty] | 2024
| 1725 | 2024-02-15 00:34 | P22752 | Tooling WoT - 2021 (Spirit) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | REIM | 2023-05-03 | 0 |  |  | 101.1% | 74.02% | 74.02% | 0 | -8.5% | 41525 | 41982 | -457 |  | 0 | 0 | 0 | 31076 | 13087.42 | 10906 | 0 | 31076 | N/A | N/A | N/A | N/A | 0 | 0% | -8.5% | 0% | 0% |  | 39.09 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23339 | Spirit 2023 - Stewart Russell | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 64.51% | 100% | 100% | 0 | 0.62% | 72767 | 46942 | 25825 |  | 0 | 0 | 0 | 46942 | 0 | 0 | 0 | 46942 | N/A | N/A | N/A | N/A | 0 | 7% | 7.62% | 0% | -7% |  | 35.67 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23743 | EHM Cloud Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  |  | 4.91% | 171.2% | -0.0006682% | 0 | 2.99% | 1016000 | 49886 | 966114 |  | 0 | 0 | 0 | 85408 | 41 | -35522 | 102490 | -0.33333 | 102489.6 | 0 | 0 | 0 | 0 | 28% | 30.99% | 30.99% | 2.99% |  | 49.94 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P22760 | SA Leading Edge Transport Media ('A' Frames) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-11-15 | 1 |  |  | 85.99% | 110.7% | 116.3% | -3082.8 | 3.97% | 53481 | 45986 | 7495 |  | 42804 | 42804 | 0 | 50912 | 0 | 0 | -3083 | 53481.1667 | 0 | 0 | 0 | -3082.8 | -3082.8 | 6% | 9.97% | 0% | -6% |  | 42 | [5 empty] | 4926
| 1725 | 2024-02-15 00:34 | P23741 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  |  | 9.819% | 86.86% | 0% | 0 | 3.05% | 526262 | 51674 | 474588 |  | 0 | 0 | 0 | 44885 | 41 | 6789 | 53862 | 0 | 53862 | 0 | 0 | 0 | 0 | 28% | 31.05% | 31.05% | 3.05% |  | 38.59 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23322 | GKN T Tomblin 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  |  | 90.83% | 91.53% | 88.79% | 0 | -0.33% | 58952 | 53544 | 5408 |  | 0 | 0 | 0 | 49008 | 70.87 | 4536 | 1757 | 47543.8333 | N/A | N/A | N/A | N/A | 0 | 17% | 16.67% | 16.67% | -0.33% |  | 48 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23382 | Performance Modelling | Dushan Fernando | BDX | MBDA UK LIMITED | MPE | Level NC | REIM | 2023-07-09 | 1 |  |  | 40.95% | 79.09% | 79.09% | 0 | -16.36% | 170010 | 69626 | 100384 |  | 14560 | 14659.9 | 0 | 55066 | 0 | 0 | 0 | 55066 | N/A | N/A | N/A | N/A | 0 | 20% | 3.64% | 0% | -20% |  | 77.05 | [5 empty] | -14560
| 1725 | 2024-02-15 00:34 | P23341 | Spirit 2023 - Tom McFarlane | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 52.05% | 86.53% | 68.03% | 0 | -0.01% | 108666 | 56564 | 52102 |  | 0 | 0 | 0 | 48945 | 151.96 | 7619 | 12560 | 38478.3333 | N/A | N/A | N/A | N/A | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23349 | Spirit 2023 - Stress Approve Man Serv (SB) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 58.24% | 80.05% | 80.05% | 0 | -0.29% | 97920 | 57024 | 40896 |  | 0 | 0 | 0 | 45648 | 13651.2 | 11376 | 0 | 45648 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23193 | Spirit Shorts Stephen Greer | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 97.08% | 91.59% | 87.05% | 0 | 2.42% | 61472 | 59674 | 1798 |  | 0 | 0 | 0 | 54656 | 80.72 | 5019 | 3252 | 51946 | N/A | N/A | N/A | N/A | 0 | 29% | 31.42% | 34.03% | 5.03% |  | 34.99 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23106 | ME Support to NPD - Bobby Haggart | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  |  | 95.79% | 97.03% | 97.03% | 0 | 0.3% | 65675 | 62912 | 2763 |  | 0 | 0 | 0 | 61043 | 2243.24 | 1869 | 0 | 61043 | 0 | 0 | 0 | 0 | 0 | 15% | 15.3% | 0% | -15% |  | 35.65 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23561 | SAAB | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2024-01-01 | 1 |  |  | 82.46% | 121.1% | 96.66% | 0 | 3.5% | 67485 | 55649 | 11836 |  | 0 | 0 | 0 | 67399 | 134.01 | -4408 | 16332 | 53789 | N/A | N/A | N/A | N/A | 0 | 16% | 19.5% | 0% | -16% |  | 36.82 | [5 empty] | 7342
| 1725 | 2024-02-15 00:34 | P22967 | Spirit 2022 - Channapa Laxmeshwar | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2023-01-26 | 2 |  |  | 69.69% | 121.3% | 121.3% | 0 | 9.53% | 75159 | 52376 | 22783 |  | 52376 | 54898.1 | 0 | 63509 | 0.42 | 0 | 0 | 63509 | N/A | N/A | N/A | N/A | 0 | 8% | 17.53% | 0% | -8% |  | 0 | [5 empty] | 11133
| 1725 | 2024-02-15 00:34 | P23342 | Spirit 2023 - Channapa Laxmeshwar | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 78.75% | 104.3% | 88.16% | 0 | -2.64% | 79348 | 62484 | 16864 |  | 62484 | 63539 | 0 | 65178 | 83.77 | 157 | 12110 | 55086.3333 | N/A | N/A | N/A | N/A | 0 | 7% | 4.36% | 0% | -7% |  | 0 | [5 empty] | 2850
| 1725 | 2024-02-15 00:34 | P23739 | Lifing Services DACs | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  |  | 10.64% | 79.72% | -0.0002385% | 0 | 7.43% | 656508 | 69882 | 586626 |  | 0 | 0 | 0 | 55709 | 41 | 14173 | 66851 | -0.16667 | 66850.8 | 0 | 0 | 0 | 0 | 28% | 35.43% | 35.43% | 7.43% |  | 37.91 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23560 | NJEWCS TAF202302 SM | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level 2 | FIX |  |  |  |  | 88.55% | 55.42% | 55.42% | 0 | 12.33% | 81500 | 72170 | 9330 |  | 0 | 0 | 0 | 40000 | 121.51 | 32170 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 28% | 40.33% | 41.09% | 13.09% |  | 73.01 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23465 | A220 ToW Design Offload (Wing) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 55.25% | 76.47% | 68.37% | 0 | -4.17% | 132000 | 72931 | 59069 |  | 0 | 0 | 0 | 55768 | 80.01 | 17163 | 7088 | 49861.3333 | N/A | N/A | N/A | N/A | 0 | 20% | 15.83% | 15.03% | -4.97% |  | 42.8 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23586 | Project Management Support | Peter Bowen | BDX | MBDA UK LIMITED | MPE | Level NC | REIM |  |  |  |  | 91.28% | 91.89% | 59.54% | 0 | -25.49% | 80000 | 73024 | 6976 |  | 1141 | 1140.6 | 0 | 67104 | 78.64 | 5920 | 28349 | 43479.8333 | N/A | N/A | N/A | N/A | 0 | 49% | 23.51% | 24.63% | -24.37% |  | 80 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23551 | Ian Berry 2023 H2 | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  |  | 96.64% | 91.75% | 37.74% | 0 | 12.98% | 75810 | 73265 | 2545 |  | 0 | 0 | 24259.20 | 67217 | 143.74 | 6047 | 47479 | 27651.1667 | N/A | N/A | N/A | N/A | 0 | 22% | 34.98% | 38.59% | 16.59% |  | 76.8 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23438 | A220 Spirit Shorts DTC - Stephen Corry | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 76.45% | 55.09% | 55.09% | 0 | -7.34% | 95928 | 73340 | 22588 |  | 0 | 0 | 0 | 40400 | 173.73 | 32941 | 0 | 40400 | N/A | N/A | N/A | N/A | 0 | 23% | 15.66% | 18.9% | -4.1% |  | 49.72 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23080 | Spirit Shorts DManagement Cairan Cullen | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 49.07% | 98.47% | 92.92% | 3787.8 | -0.82% | 149600 | 73408 | 76192 |  | 0 | 0 | 0 | 72284 | 166.89 | 1124 | 4892 | 68207.3333 | N/A | N/A | N/A | N/A | 3787.8 | 24% | 23.18% | 18.04% | -5.96% |  | 44.45 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23340 | Spirit 2023 - John Cole | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 100% | 83.73% | 67.2% | 0 | -0.01% | 75065 | 75065 | 0 |  | 0 | 0 | 0 | 62852 | 134.76 | 12212 | 14894 | 50440.3333 | N/A | N/A | N/A | N/A | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 39.78 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23600 | MBDA EXP-EE-023 Bristone Certification | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 59.65% | 100% | 84.61% | 0 | 0.4% | 126600 | 75517 | 51083 |  | 0 | 0 | 0 | 75517 | 60.67 | 0 | 13942 | 63898.6667 | N/A | N/A | N/A | N/A | 0 | 41% | 41.4% | 0% | -41% |  | 78.5 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23345 | Spirit 2023- Jonathan Escosio | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 99.87% | 84.96% | 67.55% | 0 | -0.35% | 75971 | 75870 | 101 |  | 0 | 0 | 0 | 64456 | 142.87 | 11414 | 15846 | 51251 | N/A | N/A | N/A | N/A | 0 | 1% | 0.65% | 0.65% | -0.35% |  | 40.26 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23336 | Spirit 2023 - Neil Rampling | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 58.2% | 84.5% | 61.42% | 6343.82 | -0.01% | 133902 | 77932 | 55970 |  | 0 | 0 | 0.00 | 65851 | 167.84 | 12081 | 21586 | 47862.6667 | N/A | N/A | N/A | N/A | 6343.82 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P22505 | Spirit MRB Engineering Support 2021 | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 1 |  |  | 91.17% | 100% | 95.78% | 4020.48 | 21.2% | 87110 | 79415 | 7695 |  | 0 | 0 | 0 | 79415 | 4020.48 | 0 | 4020 | 76065 | 0 | 0 | 0 | 4020.48 | 4020.48 | 0% | 21.2% | 0% | 0% |  | 41.88 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P22885 | ME Support (Baxi) | James Montgomery | HUV | BAXI HEATING UK LIMITED | ME | Level 3 | FIX | 2023-01-12 | 0 |  |  | 68.78% | 108.7% | 108.7% | 0 | 13.05% | 106633 | 73340 | 33293 |  | 0 | 0 | 0 | 79748 | 1531.35 | 1276 | 0 | 79748 | 0 | 0 | 0 | 0 | 0 | 15% | 28.05% | 0% | -15% |  | 44.37 | [5 empty] | 7684
| 1725 | 2024-02-15 00:34 | P23171 | Spirt Shorts Weights Eng | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 99.4% | 103.1% | 96.15% | 0 | -9.32% | 71760 | 71329 | 431 |  | 71329 | 90419.91 | 0 | 73553 | 18020.95 | 10046 | 5965 | 68582.1667 | N/A | N/A | N/A | N/A | 0 | 24% | 14.68% | 0% | -24% |  | 0 | [5 empty] | 12270
| 1725 | 2024-02-15 00:34 | P23079 | Spirit Shorts Nomenclature | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 94.9% | 91.89% | 81.41% | 10554.48 | 1.83% | 88455 | 83944 | 4511 |  | 0 | 0 | 0.00 | 77138 | 190.63 | 6805 | 10554 | 68343 | N/A | N/A | N/A | N/A | 10554.48 | 20% | 21.83% | 25.23% | 5.23% |  | 30.7 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23335 | GKN S McConnell 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2023-12-31 | 3 |  |  | 96.61% | 100% | 75.29% | 0 | 0.74% | 87420 | 84459 | 2961 |  | 0 | 0 | 0 | 84459 | 182 | 0 | 25042 | 63590.6667 | N/A | N/A | N/A | N/A | 0 | 15% | 15.74% | 0% | -15% |  | 47 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P22965 | Spirit 2022 - Design Man Serv (AH) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 1 |  |  | 106.7% | 96.66% | 92.02% | 4759.75 | 3.14% | 80080 | 85441 | -5361 |  | 0 | 0 | 0 | 82589 | 8182.59 | 2852 | 4760 | 78622.3333 | 0 | 0 | 0 | 4759.75 | 4759.75 | 14% | 17.14% | 0% | -14% |  | 42.44 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23523 | Applique Armour Support | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 0 |  |  | 101.6% | 98.47% | 98.47% | 0 | 3.42% | 84300 | 85607 | -1307 |  | 0 | 0 | 0 | 84300 | 1567.8 | 1307 | 0 | 84300 | 0 | 0 | 0 | 0 | 0 | 25% | 28.42% | 0% | -25% |  | 64.29 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P22964 | Spirit 2022 - MRB Man Serv (JC) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 100.6% | 97.95% | 97.95% | 0 | 1.91% | 85435 | 85960 | -525 |  | 0 | 0 | 0 | 84200 | 2112.62 | 1761 | 0 | 84200 | 0 | 0 | 0 | 0 | 0 | 16% | 17.91% | 0% | -16% |  | 42.69 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23677 | ME Managed Service - Phase 1 | Paul Watson | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  |  | 99.74% | 0% | 0% | 0 | -9.22% | 86400 | 86175 | 225 |  | 0 | 0 | 0.00 | 0 | 100.73 | 86175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16% | 6.78% | 10.04% | -5.96% |  | 45 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P22963 | Spirit 2022 - Design Man Serv (PC) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 1 |  |  | 108.6% | 104% | 94.46% | 9938.48 | 3.18% | 80080 | 86927 | -6847 |  | 0 | 0 | 0 | 90390 | 5782.63 | -3463 | 9938 | 82108.3333 | 0 | 0 | 0 | 9938.48 | 9938.48 | 13% | 16.18% | 0% | -13% |  | 42.39 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23583 | Castalla - Test Rig Design | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 130.4% | 69.58% | 69.58% | 0 | -6.16% | 67520 | 88043 | -20523 |  | 0 | 0 | 22906 | 61258 | 86.6 | 26785 | 0 | 61258 | N/A | N/A | N/A | N/A | 0 | 21% | 14.84% | 19.92% | -1.08% |  | 42.63 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23353 | Spirit 2023 - MRB Man Serv (JC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  |  | 99.04% | 75.46% | 75.46% | 0 | -0.22% | 91800 | 90923 | 877 |  | 0 | 0 | 0 | 68615 | 157.32 | 22307 | 0 | 68615 | 0 | 0 | 0 | 0 | 0 | 18% | 17.78% | 17.78% | -0.22% |  | 45 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23545 | Ultra CSS continuation 2023 H2 | Natalie Sinclair | ULT | ULTRA SONAR SYSTEMS LIMITED | EES | Level NC | REIM |  |  |  |  | 121.5% | 47.59% | 47.59% | 0 | 2.24% | 76000 | 92370 | -16370 |  | 0 | 0 | 24259.20 | 43956 | 138.21 | 48414 | 0 | 43956 | N/A | N/A | N/A | N/A | 0 | 23% | 25.24% | 25% | 2% |  | 80 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23375 | GKN Jaap Peters NL 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  |  | 93.37% | 105.3% | 67.32% | 0 | -15.93% | 97123 | 90686 | 6437 |  | 90686 | 92269.6 | 5661.24 | 95457 | 168.24 | -920 | 41290 | 61048.6667 | N/A | N/A | N/A | N/A | 0 | 20% | 4.07% | 0% | -20% |  | 0 | [5 empty] | 3850
| 1725 | 2024-02-15 00:34 | P23588 | BAE Typhoon MRB MC Shop Concessions | Andrew Houghton | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 54.87% | 96.09% | 53.65% | 0 | -4.13% | 175061 | 96055 | 79006 |  | 0 | 0 | 0.00 | 92296 | 114.01 | 3759 | 48910 | 51537.6667 | N/A | N/A | N/A | N/A | 0 | 31% | 26.87% | 29.25% | -1.75% |  | 55.5 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23352 | Spirit 2023 - Stress Approve Man Serv (CC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  |  | 99.63% | 71.66% | 71.66% | 0 | -2.76% | 97920 | 97560 | 360 |  | 0 | 0 | 0 | 69912 | 165.35 | 27648 | 0 | 69912 | 0 | 0 | 0 | 0 | 0 | 18% | 15.24% | 4.69% | -13.31% |  | 48 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23664 | Tempest Composites WP3 | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  |  | 80.46% | 16.77% | 0.0006766% | 0 | -5.01% | 122455 | 98525 | 23930 |  | 0 | 0 | 0.00 | 16519 | 117.4 | 82006 | 19822 | 0.66667 | 0 | 19822.44 | 0 | 0 | 0 | 37% | 31.99% | 35.53% | -1.47% |  | 60.33 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P22918 | Spirit Shorts Graduates | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 95.34% | 67.08% | 67.08% | 0 | 9.57% | 110000 | 104872 | 5128 |  | 0 | 0 | 9900 | 70352 | 168.07 | 34520 | 0 | 70352 | N/A | N/A | N/A | N/A | 0 | 7% | 16.57% | 19.08% | 12.08% |  | 23.23 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23282 | Tooling Support (MBDA) | Dushan Fernando | BDV | MBDA UK LIMITED | ME | Level 3 | FIX |  |  |  |  | 104.8% | 94.5% | 84.39% | 0 | -9.45% | 104834 | 109843 | -5009 |  | 0 | 0 | 19964.00 | 103804 | 74.56 | 6039 | 13326 | 92699 | 0 | 13325.98 | 0 | 0 | 0 | 30% | 20.55% | 30.37% | 0.37% |  | 49.69 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P22883 | Spirit Shorts Evtol PMO C. Hatton | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 60.08% | 97.6% | 81.73% | 0 | -12.39% | 185800 | 111628 | 74172 |  | 0 | 0 | 0 | 108947 | 159.75 | 2681 | 21252 | 91237 | N/A | N/A | N/A | N/A | 0 | 26% | 13.61% | 26.7% | 0.7% |  | 36.29 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23270 | Shorts Project X | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 78.69% | 78.52% | 65.91% | 0 | 0.85% | 142248 | 111939 | 30309 |  | 0 | 0 | 0 | 87889 | 172.87 | 24050 | 16933 | 73778.1667 | N/A | N/A | N/A | N/A | 0 | 13% | 13.85% | 10.99% | -2.01% |  | 45.38 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23685 | DAC LUC Support and Recompliance | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  |  | 16.29% | 214.4% | 0.0002843% | 0 | 2.25% | 720000 | 117252 | 602748 |  | 0 | 0 | 0 | 251427 | 41 | -134176 | 301712 | 0.33333 | 301712.4 | 0 | 0 | 0 | 0 | 28% | 30.25% | 30.25% | 2.25% |  | 67.68 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P22736 | WoT Fixed Leading Edge - Industrial | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 106.7% | 93.42% | 91.32% | 3019.54 | 0.01% | 112196 | 119668 | -7472 |  | 0 | 0 | 0 | 111797 | 12465.69 | 7872 | 3020 | 109280.3333 | 0 | 0 | 0 | 3019.54 | 3019.54 | 7% | 7.01% | 0% | -7% |  | 32.26 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23648 | EXP-032 Delivery of Datalink Eng support - FCAS AP | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 32.38% | 85.61% | 0.0004162% | 0 | 4.66% | 371000 | 120125 | 250875 |  | 1033 | 1032.95 | 0 | 102843 | 120.52 | 17283 | 123411 | 0.5 | N/A | N/A | N/A | N/A | 0 | 22% | 26.66% | 26.28% | 4.28% |  | 103.92 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P22861 | WoT FLE Lifting & Handling Tools | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2023-06-14 | 1 |  |  | 65.17% | 101.6% | 101.6% | 0 | 12.01% | 173987 | 113382 | 60605 |  | 50078 | 58423.58 | 0 | 115204 | 12813.9 | 10678 | 0 | 115204 | 0 | 0 | 0 | 0 | 0 | 1% | 13.01% | 0% | -1% |  | 45 | [5 empty] | 12500
| 1725 | 2024-02-15 00:34 | P23667 | Safety Systems Engineer | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 32.39% | 93.69% | 0% | 0 | -8.08% | 398000 | 128920 | 269080 |  | 0 | 0 | 0 | 120780 | 172.86 | 8140 | 144936 | 0 | N/A | N/A | N/A | N/A | 0 | 47% | 38.92% | 29.32% | -17.68% |  | 110 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23421 | A220 DTC | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 98.71% | 83.06% | 60.8% | 0 | -11.46% | 130625 | 128935 | 1690 |  | 0 | 0 | 0.00 | 107094 | 110.17 | 21841 | 34447 | 78388.1667 | N/A | N/A | N/A | N/A | 0 | 10% | -1.46% | 3.19% | -6.81% |  | 45.08 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23437 | Embedded Software Engineer | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 90.99% | 95.75% | 85.25% | 0 | -6.34% | 150150 | 136621 | 13529 |  | 738 | 737.86 | 0 | 130812 | 53.49 | 5809 | 17207 | 116472.8333 | N/A | N/A | N/A | N/A | 0 | 22% | 15.66% | 16.24% | -5.76% |  | 78.5 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23518 | Systems Engineering support to FCAS | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 72.21% | 92.79% | 84.73% | 0 | -0.88% | 193737 | 139896 | 53841 |  | 3927 | 3927.4 | 0 | 129804 | 55.83 | 10092 | 13518 | 118539 | N/A | N/A | N/A | N/A | 0 | 30% | 29.12% | 3.5% | -26.5% |  | 66.73 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23533 | External Stowage Design and Detail Support | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 0 |  |  | 136.5% | 73.24% | 73.24% | 0 | 6.33% | 105000 | 143369 | -38369 |  | 0 | 0 | 49220 | 105000 | 615.57 | 35000 | 0 | 105000 | 0 | 0 | 0 | 0 | 0 | 24% | 30.33% | 0% | -24% |  | 60.04 | [5 empty] | -3369
| 1725 | 2024-02-15 00:34 | P23699 | A220 Stress Checkers | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -1.75% | 0 | 143309 | -143309 |  | 0 | 0 | 135880 | 0 | 91 | 143309 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 22% | 20.25% | 20.46% | -1.54% |  | 61.88 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P22982 | Spirit 2022 - Hugh Sloan | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 87.64% | 91.94% | 83.13% | 0 | -0.01% | 166046 | 145531 | 20515 |  | 0 | 0 | 0.00 | 133795 | 168.1 | 11736 | 15370 | 120986.6667 | N/A | N/A | N/A | N/A | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 35.42 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23550 | Tempest Composites | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  |  | 98.09% | 101.9% | 68.7% | 24179.64 | 5.16% | 149495 | 146641 | 2854 |  | 0 | 0 | 0 | 149495 | 187.13 | -2854 | 58496 | 100748.3333 | 27760.26 | 6555.8 | 0 | 24179.64 | 24179.64 | 26% | 31.16% | 35.4% | 9.4% |  | 61.72 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P22954 | Technical Support Step 1 | Owain Jones | HUV | HUARUI SPIRIT AEROSPACE MANUFACT | ME | Level 2 | REIM |  |  |  |  | 94.81% | 58.01% | 58.01% | 0 | 0.31% | 155501 | 147432 | 8069 |  | 23043 | 23043 | 0 | 85525 | 61906.09 | 61906 | 0 | 85525 | N/A | N/A | N/A | N/A | 0 | 30% | 30.31% | 0% | -30% |  | 60.79 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23386 | Software Development - BMS | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 98.78% | 95.49% | 88.63% | 0 | 4.31% | 149650 | 147823 | 1827 |  | 0 | 0 | 0 | 141151 | 44.63 | 6673 | 12161 | 131016.8333 | N/A | N/A | N/A | N/A | 0 | 18% | 22.31% | 22.61% | 4.61% |  | 78.5 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23464 | A220 Project X Design Offload | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 83.4% | 88.61% | 66.48% | 0 | -3.74% | 180400 | 150449 | 29951 |  | 0 | 0 | 0.00 | 133307 | 139.02 | 17141 | 39945 | 100019.5 | N/A | N/A | N/A | N/A | 0 | 21% | 17.26% | 17.29% | -3.71% |  | 42.89 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P22440 | Spirit Managed Service - F&DT and Static Approval | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 3 |  |  | 88.56% | 92.56% | 92.56% | 0 | 11.51% | 173500 | 153656 | 19844 |  | 52115 | 55720 | 0 | 142225 | 13717.36 | 11431 | 0 | 142225 | 0 | 0 | 0 | 0 | 0 | 0% | 11.51% | 0% | 0% |  | 44.73 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23508 | Verification and Validation | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 75.03% | 95.71% | 83.92% | 0 | 11.23% | 212950 | 159787 | 53163 |  | 0 | 0 | 0 | 152938 | 42.59 | 6849 | 22608 | 134098 | N/A | N/A | N/A | N/A | 0 | 24% | 35.23% | 35.89% | 11.89% |  | 78.5 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23629 | F35 FTI | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level NC | REIM | [5 empty] | 92.38% | 76.29% | 0 | 0.2% | 0 | 160223 | -160223 |  | 0 | 0 | 0 | 148010 | 34.19 | 12213 | 30935 | 122230.8333 | N/A | N/A | N/A | N/A | 0 | 31% | 31.2% | 30.83% | -0.17% |  | 62.13 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23506 | ASTER Mid-Life Refurbishment Project Manager | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 73.81% | 95.03% | 84.12% | 0 | 1.03% | 224900 | 166009 | 58891 |  | 2329 | 2329.13 | 0 | 157759 | 47.48 | 8250 | 21730 | 139650.6667 | N/A | N/A | N/A | N/A | 0 | 25% | 26.03% | 26.59% | 1.59% |  | 110 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23505 | EXP-022 Meteor TBUS T&E support | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 69.49% | 95.35% | 30.77% | 0 | -0.59% | 246744 | 171463 | 75281 |  | 0 | 0 | 0 | 163491 | 250.53 | 7972 | 132886 | 52752.6667 | N/A | N/A | N/A | N/A | 0 | 20% | 19.41% | 15.67% | -4.33% |  | 89.83 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23242 | Physical Architecture & System Engineering Support | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM | 2024-02-28 | 6 |  |  | 58.75% | 97.95% | 93.1% | 0 | 10.21% | 305459 | 179465 | 125994 |  | 776 | 775.55 | 0 | 175794 | 42.18 | 3671 | 10456 | 167080.6667 | N/A | N/A | N/A | N/A | 0 | 15% | 25.21% | 7.68% | -7.32% |  | 78.16 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23373 | Raytheon Michael Bellini | Natalie Sinclair | RAS | RAYTHEON UNITED KINGDOM LIMITED | EES | Level NC | REIM |  |  |  |  | 83.84% | 95.22% | 68.15% | 0 | -8.26% | 214367 | 179718 | 34649 |  | 0 | 0 | 0 | 171127 | 107.07 | 8591 | 58374 | 122482 | N/A | N/A | N/A | N/A | 0 | 45% | 36.74% | 37.63% | -7.37% |  | 91.61 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23524 | Bombardier Regional Jets (BRJ) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 130.8% | 56.89% | 44.32% | 25157.41 | -4.43% | 146288 | 191312 | -45024 |  | 0 | 0 | 46750 | 108838 | 128.42 | 82473 | 28851 | 84795.5 | N/A | N/A | N/A | N/A | 25157.41 | 18% | 13.57% | 17.17% | -0.83% |  | 43.92 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23008 | Spirit Shorts Project Rachel | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 85.87% | 91.32% | 79.5% | 18585.6 | -7.7% | 228880 | 196531 | 32349 |  | 0 | 0 | 0 | 179473 | 275.46 | 17058 | 27878 | 156241.3333 | N/A | N/A | N/A | N/A | 18585.6 | 13% | 5.3% | 0.31% | -12.69% |  | 46.04 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23019 | EXP034-B Actuator Development | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 103% | 90.03% | 90.03% | 0 | -14.62% | 215541 | 221919 | -6378 |  | 12001 | 12297.9 | 0.00 | 199797 | 71.97 | 5145 | 0 | 199797 | N/A | N/A | N/A | N/A | 0 | 34% | 19.38% | 31.68% | -2.32% |  | 58.45 | [5 empty] | -16977
| 1725 | 2024-02-15 00:34 | P23472 | Tempest Wing Design | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 43.68% | 121.8% | 96.68% | 0 | -19.86% | 483870 | 211367 | 272503 |  | 195488 | 206400 | 0 | 257532 | 10.88 | -46164 | 63812 | 204355.3333 | N/A | N/A | N/A | N/A | 0 | 23% | 3.14% | 14.72% | -8.28% |  | 46.74 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23316 | Model Factory IL and AW | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX | 2024-01-12 | 1 |  |  | 88.13% | 104.1% | 96.46% | 0 | 2.17% | 250000 | 220328 | 29672 |  | 0 | 0 | 0 | 229409 | 49.68 | -913 | 20249 | 212534.8333 | 0 | 0 | 20248.8 | 0 | 0 | 30% | 32.17% | 32.57% | 2.57% |  | 45.31 | [5 empty] | 8168
| 1725 | 2024-02-15 00:34 | P23603 | Typhoon IMDLR | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 193.6% | 0% | 0% | 0 | -2.84% | 119880 | 232074 | -112194 |  | 0 | 0 | 189459 | 0 | 224.19 | 232074 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 34% | 31.16% | 32.77% | -1.23% |  | 57.67 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23650 | MBDA Recruitment Management costs | Brian Maddrell | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 28.54% | 0 | 240972 | -240972 |  | 0 | 0 | 266000 | 0 | 110.23 | 240972 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 3% | 31.54% | 28.64% | 25.64% |  | 82.3 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23255 | BAE Tempest WP 1 Circuits | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | 2023-10-20 | 0 |  |  | 70.38% | 99.34% | 99.34% | 0 | -2.72% | 355782 | 250395 | 105387 |  | 1654 | 1654.32 | 0 | 248740 | 0.38 | 0 | 0 | 248740 | N/A | N/A | N/A | N/A | 0 | 31% | 28.28% | 100% | 69% |  | 50.3 | [5 empty] | -1654
| 1725 | 2024-02-15 00:34 | P23317 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX | 2024-01-12 | 1 |  |  | 95.89% | 104.3% | 98.16% | 0 | 4.05% | 251800 | 241447 | 10353 |  | 0 | 0 | 0 | 251800 | 51.06 | -1177 | 17760 | 237000 | 0 | 0 | 17760 | 0 | 0 | 25% | 29.05% | 40.59% | 15.59% |  | 36.29 | [5 empty] | 9176
| 1725 | 2024-02-15 00:34 | P22798 | CO2MAP MGSE | Harry James Kellett | DTW | THALES ALENIA SPACE UK (60DAYS) | EES | Level 2 | REIM | 2023-11-08 | 0 |  |  | 85.75% | 105% | 105% | 0 | 3.94% | 252086 | 216158 | 35928 |  | 0 | 0 | 0 | 227053 | 30116.66 | 25097 | 0 | 227053 | N/A | N/A | N/A | N/A | 0 | 29% | 32.94% | 0% | -29% |  | 50.31 | [5 empty] | 35992
| 1725 | 2024-02-15 00:34 | P23007 | EXP-006A - Brimstone 3 | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 62.37% | 97.54% | 93.17% | 0 | -3.37% | 406450 | 253519 | 152931 |  | 0 | 0 | 0 | 247278 | 51.3 | 6211 | 13282 | 236209.6667 | N/A | N/A | N/A | N/A | 0 | 25% | 21.63% | 29.94% | 4.94% |  | 69.24 | [5 empty] | -30
| 1725 | 2024-02-15 00:34 | P21463 | Safety & Monitoring Systems at DM Beith & Gosport | Harry James Kellett | BXW | MOD | EES | Level 2 | FIX |  |  |  |  | 77.23% | 129.5% | 129.5% | 0 | -26.79% | 349405 | 269829 | 79576 |  | 56249 | 66564.38 | 21721 | 349387 | 0 | -79558 | 0 | 349387 | 0 | 0 | 0 | 0 | 0 | 48% | 21.21% | 43.81% | -4.19% |  | 52.91 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23308 | NATO JEWCS | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  |  | 78.94% | 97.15% | 83.76% | 0 | -3.26% | 356307 | 281263 | 75044 |  | 614 | 613.89 | 0 | 273254 | 130.92 | 8008 | 45213 | 235576.5 | N/A | N/A | N/A | N/A | 0 | 24% | 20.74% | 12.72% | -11.28% |  | 75.81 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23617 | Tempest Composites WP2 | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  |  | 117.8% | 25.88% | 3.539% | 29536.68 | 3.92% | 244405 | 287895 | -43490 |  | 0 | 0 | 50000 | 74512 | 187.32 | 213382 | 77189 | 10187.8333 | 19043.96 | 28608.29 | 0 | 29536.68 | 29536.68 | 30% | 33.92% | 34.41% | 4.41% |  | 62.31 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23045 | Shotgun Adaptors - 10 Sets | Harry James Kellett | BDW | MBDA UK LIMITED | EES | Level 2 | FIX |  |  |  |  | 74.73% | 95.15% | 95.15% | 0 | -19.12% | 399276 | 298392 | 100884 |  | 214430 | 214551.21 | 0 | 283926 | 480.44 | 14467 | 0 | 283926 | 0 | 0 | 0 | 0 | 0 | 29% | 9.88% | 0% | -29% |  | 55.76 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P22515 | Shorts A220 100/300 ALI Phase III | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 78.12% | 95.05% | 91.16% | 0 | 1.12% | 400629 | 312972 | 87657 |  | 3451 | 3450.98 | 0 | 297465 | 121.97 | 15506 | 14584 | 285311.6667 | N/A | N/A | N/A | N/A | 0 | 10% | 11.12% | 13.74% | 3.74% |  | 40.35 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23694 | Systems Portfolio | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 54.32% | 85.94% | 64.03% | 0 | 3.27% | 591943 | 321573 | 270370 |  | 158 | 157.75 | 0 | 276367 | 41.28 | 45205 | 84550 | 205908.6667 | N/A | N/A | N/A | N/A | 0 | 21% | 24.27% | 17.07% | -3.93% |  | 90.35 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P22953 | Spirit Shorts eVTOL | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-05-08 | 1 |  |  | 103.1% | 79.36% | 79.36% | 0 | -6.74% | 324272 | 334484 | -10212 |  | 66697 | 67387.9 | 0 | 265432 | 179.02 | 69052 | 0 | 265432 | N/A | N/A | N/A | N/A | 0 | 17% | 10.26% | 0% | -17% |  | 46.19 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P22842 | ME Support (Aim Altitude) | James Montgomery | AVI | AIM ALTITUDE UK LIMITED | ME | Level 3 | FIX | 2023-06-14 | 4 |  |  | 99.31% | 100.5% | 86.63% | 57290.84 | 0.49% | 346294 | 343918 | 2376 |  | 2910 | 2909.86 | 0 | 345673 | 55184.93 | -1755 | 57291 | 297930.5 | 0 | 0 | 0 | 57290.84 | 57290.84 | 13% | 13.49% | 0% | -13% |  | 46.3 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23023 | Spirit Shorts R Foster/M Gourley | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  |  | 82.02% | 107% | 100.2% | 0 | -19.99% | 416652 | 341737 | 74915 |  | 188776 | 216366 | 0 | 365804 | 48.12 | -9555 | 28129 | 342363.1667 | N/A | N/A | N/A | N/A | 0 | 27% | 7.01% | 9.9% | -17.1% |  | 29.51 | [5 empty] | 14511
| 1725 | 2024-02-15 00:34 | P22391 | GE System Engineering support | Vinayakumar Sugur | GEE | EXPERIS LIMITED | EES | Level NC | REIM |  |  |  |  | 82.01% | 96.86% | 96.17% | 0 | 0.13% | 434434 | 356261 | 78173 |  | 0 | 0 | 0 | 345090 | 90.57 | 11171 | 2976 | 342610 | N/A | N/A | N/A | N/A | 0 | 6% | 6.13% | 6.09% | 0.09% |  | 57.33 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23531 | BAe Systems F35 MRB Support | Andrew Houghton | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM | [5 empty] | 77.91% | 70.61% | 0 | 2.74% | 0 | 378551 | -378551 |  | 287 | 287.44 | 0 | 294944 | 74.9 | 83607 | 33194 | 267282.3333 | N/A | N/A | N/A | N/A | 0 | 25% | 27.74% | 33.57% | 8.57% |  | 59.16 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23520 | FCAS AP Portfolio Systems | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 47.43% | 94.79% | 85.53% | 0 | -6.83% | 810821 | 384546 | 426275 |  | 320 | 319.5 | 0 | 364501 | 41.24 | 20045 | 42698 | 328919.3333 | N/A | N/A | N/A | N/A | 0 | 22% | 15.17% | 17.05% | -4.95% |  | 79.03 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23554 | Dornier Seawings 328 2023 H2 Support | Steven Lawton | DAX | EXPLEO GERMANY GMBH (EC) | MPE | Level 2 | REIM |  |  |  |  | 83.11% | 96.02% | 90.05% | 0 | 7.8% | 474542 | 394387 | 80155 |  | 3551 | 3550.65 | 0.00 | 378685 | 38.73 | 15702 | 28236 | 355155 | N/A | N/A | N/A | N/A | 0 | 21% | 28.8% | 32.45% | 11.45% |  | 67.47 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23432 | Spirit Belfast MRB On-Site Support (Mon & Clear) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 65.77% | 125.6% | 96.58% | 77391.6 | -11.53% | 449545 | 295665 | 153880 |  | 295665 | 451827.33 | 0 | 371466 | 37.59 | 36200 | 103100 | 285549.3333 | N/A | N/A | N/A | N/A | 77391.6 | 39% | 27.47% | 0% | -39% |  | 0 | [5 empty] | 112000
| 1725 | 2024-02-15 00:34 | P23320 | Lifing Services DACs | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX | 2024-01-12 | 1 |  |  | 95.56% | 104.6% | 97.44% | 0 | 2.72% | 413300 | 394956 | 18344 |  | 0 | 0 | 0 | 413300 | 46.81 | -2050 | 34139 | 384850.8333 | 0 | 0 | 34138.8 | 0 | 0 | 26% | 28.72% | 44.21% | 18.21% |  | 33.15 | [5 empty] | 16294
| 1725 | 2024-02-15 00:34 | P23366 | Business Analyst Support | Peter Williams | BDZ | MBDA UK LIMITED | DET | Level NC | REIM |  |  |  |  | 33.09% | 257% | 200.5% | 0 | 11.92% | 583200 | 192994 | 390206 |  | 192993 | 416921.86 | 0 | 496000 | 55.93 | -64871 | 130752 | 387040 | N/A | N/A | N/A | N/A | 0 | 43% | 54.92% | 15.27% | -27.73% |  | 0.01 | [5 empty] | 238135
| 1725 | 2024-02-15 00:34 | P22906 | Spirit Shorts - MRB JD Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  |  | 68.9% | 91.3% | 70.4% | 0 | -7.59% | 614770 | 423554 | 191216 |  | 0 | 0 | 0.00 | 386688 | 257.71 | 44867 | 106200 | 298188 | N/A | N/A | N/A | N/A | 0 | 13% | 5.41% | 3.71% | -9.29% |  | 36.83 | [5 empty] | 8000
| 1725 | 2024-02-15 00:34 | P23473 | Tempest Vertical Tail | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 61.07% | 99.96% | 78.63% | 0 | -2.79% | 723866 | 442083 | 281783 |  | 88725 | 100425 | 0 | 441918 | 58.93 | 165 | 113181 | 347600.5 | N/A | N/A | N/A | N/A | 0 | 24% | 21.21% | 25% | 1% |  | 62.43 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23140 | Spirit Shorts A220 MLG Stress Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  |  | 71.26% | 87.36% | 77.87% | 48343.2 | -15.32% | 595746 | 424535 | 171211 |  | 20870 | 87811.88 | 0.00 | 370857 | 143.2 | 78677 | 48343 | 330571.1667 | 0 | 0 | 0 | 48343.2 | 48343.2 | 32% | 16.68% | 12.45% | -19.55% |  | 47.29 | [5 empty] | 25000
| 1725 | 2024-02-15 00:34 | P23372 | BAE Carbon Tooling Off-load | Gary Kempster | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  |  | 165.3% | 56.3% | 56.3% | 0 | -4.12% | 276718 | 457433 | -180715 |  | 0 | 0 | 197460.8 | 257522 | 244.67 | 199912 | 0 | 257522 | N/A | N/A | N/A | N/A | 0 | 27% | 22.88% | 21.55% | -5.45% |  | 53.57 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23323 | CNC-CMM Programming Support | Andrew Houghton | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  |  | 119.3% | 86.06% | 73.14% | 0 | -3.67% | 416048 | 496413 | -80365 |  | 13662 | 13661.56 | 95785.2 | 427206 | 123.8 | 69207 | 76956 | 363076 | N/A | N/A | N/A | N/A | 0 | 32% | 28.33% | 39.58% | 7.58% |  | 56.82 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P22652 | L3 - Saftey Engineering | Sean Simmons | LHW | L3HARRIS MAPPS LIMITED | EES | Level NC | FIX |  |  |  |  | 95.63% | 86.69% | 86.69% | 0 | 5.66% | 523390 | 500498 | 22892 |  | 0 | 0 | 0 | 433883 | 79938 | 66615 | 0 | 433883 | 0 | 0 | 0 | 0 | 0 | 21% | 26.66% | 25.88% | 4.88% |  | 83.05 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23602 | EXP-025 Portfolio Software Engineering Support | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 41.77% | 89.68% | 51.59% | 0 | -0.49% | 1221060 | 510054 | 711006 |  | 824 | 1015.89 | 0 | 457393 | 77.56 | 52661 | 233130 | 263118 | N/A | N/A | N/A | N/A | 0 | 24% | 23.51% | 23.77% | -0.23% |  | 82.61 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23001 | Spirit Shorts A220 Design | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 116.2% | 71.69% | 69.21% | 0 | -3.86% | 439560 | 510743 | -71183 |  | 0 | 0 | 65953.2 | 366148 | 313.45 | 144595 | 15203 | 353478.8333 | N/A | N/A | N/A | N/A | 0 | 25% | 21.14% | 12.5% | -12.5% |  | 43.62 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23281 | Systems Portfolio | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM | 2024-02-28 | 1 |  |  | 44.43% | 97.31% | 97.19% | 0 | -17.1% | 1177697 | 523237 | 654460 |  | 2133 | 2133.28 | 0 | 509180 | 17523.23 | 13968 | 762 | 508545 | N/A | N/A | N/A | N/A | 0 | 25% | 7.9% | 0% | -25% |  | 70.48 | [5 empty] | -89
| 1725 | 2024-02-15 00:34 | P23426 | BAE Tempest WP 3 Harness Maturation | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 63.21% | 93.6% | 71.98% | 0 | -5.88% | 884012 | 558828 | 325184 |  | 213 | 213.34 | 0 | 523063 | 74.75 | 35765 | 144962 | 402261.3333 | N/A | N/A | N/A | N/A | 0 | 33% | 27.12% | 29.71% | -3.29% |  | 51.06 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P21138 | D&A Vibration Reduc Damping Struc FOGV Components | Steven Lawton | ATC | AECC SICHUAN GAS TURBINE | MPE | Level 1 | FIX | 2022-09-07 | 0 |  |  | 96.12% | 104% | 104% | 0 | -3.44% | 569346 | 547228 | 22118 |  | 75182 | 75181.75 | 0 | 569346 | 0 | -11 | 0 | 569346 | 0 | 0 | 0 | 0 | 0 | 36% | 32.56% | 0% | -36% |  | 73.95 | [5 empty] | 22107
| 1725 | 2024-02-15 00:34 | P23219 | Tornado Air 800 Engineering Support | Richard Brook | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 3 | REIM |  |  |  |  | 95.46% | 98.51% | 98.51% | 0 | 1.46% | 615046 | 587098 | 27948 |  | 459 | 459.21 | 0 | 578373 | 10470.24 | 8725 | 0 | 578373 | N/A | N/A | N/A | N/A | 0 | 31% | 32.46% | 0% | -31% |  | 81.76 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23605 | Typhoon Work Package 2 Continuation | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM |  |  |  |  | 186.1% | 0% | 0% | 0 | 0.21% | 350520 | 652386 | -301866 |  | 4054 | 4054 | 277015 | 0 | 179.68 | 652386 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 28% | 28.21% | 29.04% | 1.04% |  | 55.72 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P22790 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 2 | REIM |  |  |  |  | 194.5% | 90.44% | 90.44% | 0 | 1.37% | 352240 | 685262 | -333022 |  | 1612 | 1611.52 | 515246 | 619744 | 41098.04 | 34248 | 0 | 619744 | N/A | N/A | N/A | N/A | 0 | 13% | 14.37% | 0% | -13% |  | 45.06 | [5 empty] | -31270
| 1725 | 2024-02-15 00:34 | P23451 | BAE Tempest - DFM-ASO Planning | Andrew Houghton | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  |  | 69.73% | 61.67% | 22.97% | 0 | -3.99% | 953905 | 665131 | 288774 |  | 0 | 0 | 0 | 410202 | 179.88 | 254930 | 308940 | 152752 | N/A | N/A | N/A | N/A | 0 | 28% | 24.01% | 24.79% | -3.21% |  | 53.15 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23321 | EHM Cloud Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX | 2024-01-29 | 3 |  |  | 89.76% | 111.4% | 103.8% | 0 | 2.78% | 839969 | 753975 | 85994 |  | 0 | 0 | 0 | 839969 | 50.04 | -3454 | 69002 | 782467.3333 | 0 | 0 | 69002.4 | 0 | 0 | 28% | 30.78% | 56.85% | 28.85% |  | 49.95 | [5 empty] | 82540
| 1725 | 2024-02-15 00:34 | P23105 | Raytheon Supply Engineering Support | Natalie Sinclair | RAY | RAYTHEON UNITED KINGDOM LIMITED | MPE | Level 3A | REIM | 2023-07-13 | 2 |  |  | 76.96% | 94.49% | 90.07% | 0 | -1.83% | 1205008 | 927395 | 277613 |  | 0 | 0 | 0 | 876292 | 110481.3 | 51104 | 49157 | 835327.8333 | N/A | N/A | N/A | N/A | 0 | 26% | 24.17% | 0% | -26% |  | 48.97 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P22350 | EMP 2020-2021 | Natalie Sinclair | ARY | GUIDANT GROUP (trading name) | PCPR | Level NC | REIM |  |  |  |  | 100.9% | 98.31% | 94.33% | 0 | -1.88% | 930212 | 938574 | -8362 |  | 400 | 400 | 0.00 | 922738 | 67.52 | 15836 | 44888 | 885331.3333 | N/A | N/A | N/A | N/A | 0 | 32% | 30.12% | 29.25% | -2.75% |  | 44.05 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23117 | BAE Typhoon Eng Support | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 107.6% | 88.52% | 88.52% | 0 | -1.44% | 950772 | 1022826 | -72054 |  | 19090 | 21165.02 | 69773.84 | 905368 | 108434.61 | 90362 | 0 | 905368 | N/A | N/A | N/A | N/A | 0 | 30% | 28.56% | 0% | -30% |  | 52.3 | [5 empty] | -27096
| 1725 | 2024-02-15 00:34 | P23519 | Mechanical and Electrical Design Eng Support | Dushan Fernando | BAX | SAFRAN SEATS GB LIMITED | MPE | Level 2 | REIM |  |  |  |  | 123.1% | 79.49% | 73.29% | 0 | -1.46% | 839697 | 1034032 | -194335 |  | 727 | 727 | 186282 | 821977 | 70.99 | 212054 | 77014 | 757798.6667 | N/A | N/A | N/A | N/A | 0 | 33% | 31.54% | 32.17% | -0.83% |  | 56.6 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23292 | BAE Tempest WP 4 AV Trays | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 72.2% | 95.29% | 79.4% | 0 | 2.15% | 1498284 | 1081698 | 416586 |  | 0 | 0 | 0 | 1030718 | 75.97 | 50981 | 206213 | 858873.8333 | N/A | N/A | N/A | N/A | 0 | 32% | 34.15% | 34.11% | 2.11% |  | 53.05 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23152 | Project Aragon - Design and Stress Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  |  | 91.14% | 61.19% | 61.19% | 0 | -9.38% | 1307861 | 1191932 | 115929 |  | 0 | 0 | 0 | 729296 | 277.88 | 462636 | 0 | 729296 | N/A | N/A | N/A | N/A | 0 | 39% | 29.62% | 31.48% | -7.52% |  | 51.87 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P22671 | Spirit Shorts Pylon and Fairing Package | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX | 2023-05-03 | 4 |  |  | 105% | 95.27% | 95.27% | 0 | -7.21% | 1198495 | 1258028 | -59533 |  | 106451 | 174863.91 | 0 | 1198495 | 2492.21 | 2077 | 0 | 1198495 | 0 | 0 | 0 | 0 | 0 | 20% | 12.79% | 0% | -20% |  | 45.4 | [5 empty] | -57456
| 1725 | 2024-02-15 00:34 | P23315 | DAC LUC BAU and Service Workbench | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  |  | 84.95% | 117.7% | 105.5% | 0 | 2.52% | 1573630 | 1336842 | 236788 |  | 180 | 180.3 | 0 | 1573630 | 30.13 | -38991 | 195596 | 1410633.3333 | 0 | 0 | 195596.4 | 0 | 0 | 28% | 30.52% | 39.03% | 11.03% |  | 52.28 | [5 empty] | 197797
| 1725 | 2024-02-15 00:34 | P23435 | Andy Baker Portfolio | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 45.81% | 88.03% | 80.42% | 0 | -8.84% | 3377457 | 1547106 | 1830351 |  | 2353 | 2352.57 | 0 | 1361987 | 58.68 | 185119 | 141345 | 1244199.5 | N/A | N/A | N/A | N/A | 0 | 25% | 16.16% | 14.35% | -10.65% |  | 78.08 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23411 | Agile & Scrum Delivery Service | Peter Williams | BDZ | MBDA UK LIMITED | DET | Level 2 | REIM | 2023-08-14 | 1 |  |  | 36.3% | 170.5% | 170.5% | 0 | 13.08% | 2487000 | 902904 | 1584096 |  | 894179 | 2337284.55 | 0 | 1539600 | 91 | 16141 | 0 | 1539600 | N/A | N/A | N/A | N/A | 0 | 29% | 42.08% | 0% | -29% |  | 74.57 | [5 empty] | 652837
| 1725 | 2024-02-15 00:34 | P23006 | Spirit Shorts A350 Freighter Toulouse | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 144.2% | 82.71% | 82.71% | 0 | 18.83% | 1035746 | 1493209 | -457463 |  | 1086670 | 1708220.2 | 0 | 1235101 | 278.22 | 569382 | 0 | 1235101 | N/A | N/A | N/A | N/A | 0 | 5% | 23.83% | 37.5% | 32.5% |  | 47.7 | [5 empty] | 311274
| 1725 | 2024-02-15 00:34 | P22278 | TAI Supply Engineers to Ankara | Natalie Sinclair | TAI | TUSAS-TURK HAVACILIK VE UZAY | MPE | Level 3A | REIM |  |  |  |  | 19.17% | 473.5% | 466.9% | 0 | -15.61% | 2105282 | 403510 | 1701772 |  | 49400 | 49400.29 | 0 | 1910696 | 50.4 | -25130 | 32000 | 1884029.3333 | N/A | N/A | N/A | N/A | 0 | 95% | 79.39% | 49.04% | -45.96% |  | 34.3 | [5 empty] | 1482056
| 1725 | 2024-02-15 00:34 | P23257 | BAE Tempest WP 5 Centre Fuselage | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 95.22% | 99.17% | 91.08% | 0 | -5.79% | 2106861 | 2006189 | 100672 |  | 78100 | 78100 | 0 | 1989561 | 65.52 | 16628 | 194722 | 1827292.6667 | N/A | N/A | N/A | N/A | 0 | 33% | 27.21% | 28.53% | -4.47% |  | 61.05 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23207 | A350 Approvers - Design and Stress Support | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  |  | 92.14% | 80.33% | 51.57% | 261733.75 | -4.27% | 2183628 | 2012061 | 171567 |  | 17140 | 17602.77 | 0 | 1616237 | 130.06 | 395824 | 694433 | 1037542.8333 | 327329.21 | 105370.2 | 91957.54 | 169776.21 | 261733.75 | 23% | 18.73% | 20.49% | -2.51% |  | 54.72 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23175 | BAe Aero Typhoon Package 2 | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM |  |  |  |  | 103.8% | 96.32% | 96.32% | 0 | -1.63% | 1984265 | 2060012 | -75747 |  | 57678 | 86030.82 | 15444.64 | 1984257 | 84731.75 | 70610 | 0 | 1984257 | N/A | N/A | N/A | N/A | 0 | 29% | 27.37% | 0% | -29% |  | 51.76 | [5 empty] | -5145
| 1725 | 2024-02-15 00:34 | P19020 | Spirit Concessions - 2018 | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2024-01-23 | 3 |  |  | 90.82% | 111.8% | 107% | 99792.83 | 2.09% | 1914847 | 1739018 | 175829 |  | 44318 | 44317.61 | 15178.88 | 1944711 | 2729.49 | 196987 | 99793 | 1861550.1667 | 0 | 0 | 0 | 99792.83 | 99792.83 | 25% | 27.09% | 10.92% | -14.08% |  | 40.87 | [5 empty] | 402680
| 1725 | 2024-02-15 00:34 | P23179 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX |  |  |  |  | 128.6% | 84.22% | 82.73% | 35500.91 | -9.33% | 1955411 | 2514731 | -559320 |  | 155464 | 246717.26 | 492000 | 2118030 | 311.51 | 396701 | 44997 | 2080532.5 | 0 | 9496.08 | 0 | 35500.91 | 35500.91 | 22% | 12.67% | 18.65% | -3.35% |  | 44.4 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P23487 | Tornado Air 800 Engineering Support | Richard Brook | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 2 | FIX |  |  |  |  | 100.5% | 86.42% | 80.1% | 0 | -4.51% | 2525468 | 2538948 | -13480 |  | 0 | 0 | 196775.00 | 2194207 | 65.25 | 344740 | 192507 | 2033784.5 | 192507.32 | 0 | 0 | 0 | 0 | 40% | 35.49% | 38% | -2% |  | 78.71 | [5 empty] | 0
| 1725 | 2024-02-15 00:34 | P19731 | Hapri HPC Rear Bearing Housing PDR & CDR | Steven Lawton | ATC | AECC Hunan Aviation Powerplant | MPE | Level 1 | FIX |  |  |  |  | 99.49% | 100.5% | 87.94% | 447000 | -15.32% | 2980000 | 2964940 | 15060 |  | 358408 | 512832.98 | 0 | 2980000 | 845.31 | -240060 | 447000 | 2607500 | 0 | 0 | 447000 | 0 | 447000 | 38% | 22.68% | 23.47% | -14.53% |  | 64.86 | [5 empty] | -225000
Extend Table

## AP2-3
WIP No | Date Created | Project ID | Project Description | Project Manager | Department Id | Client | CBU | Complexity | Type | Stop Booking Hrs | Closing Project: Action(s) to close | RAG | Approx. PO Burndown (weeks) | Turnover vs Contract Value | Invoice To Date vs Turnover | Cash in vs Turnover | Open Amount Overdue | Actual PM% to Baseline PM% delta | Contract Value | Total Project Turnover | Contract Value - Total Turnover | Run Rate (based on total turnover) | Total BOI Spend to Date | Total Committed PO (supplier/best shore) | Current AA in PT3 | Invoiced To Date | DSO | Unbilled (WIP) | Total Open Amount | Cash in (Invoiced - (Open amount -VAT)) | Debt <=30 Days | Debt 31 - 60 Days | Debt 61 - 90 Days | Debt >= 90 Days | Open Amount Overdue2 | Baseline Project Margin | Project To Date (PTD) PM | Year to Date (YTD) PM | YTD Delta Actual PM% to BPM% | Forecast PM at Completion (Manual input from PTT) | Average Sale Rate | CSat score for last quarter (Manual input from PTT) | Comments and Actions | Judged income adjustment at completion | Profit to take now | Provision required now | Fully Traded | Last Months Comments and Actions
1726 | 2024-02-22 00:34 | P23811 | Spirit T300 MRB Concessions | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [7 empty] | 0 | -21% | 0 | 0 | 0 | 0 | 0 | 0 | 34639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21% | 0% | 0% | -21% |  | 0
1726 | 2024-02-22 00:34 | P23637 | MBSE Proposal | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 | 0 | 0 | 0 | 49980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35% | 0% | 0% | -35% |  | 0
1726 | 2024-02-22 00:34 | P23711 | DO NOT USE - RAISED IN ERROR | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0
1726 | 2024-02-22 00:34 | P23717 | GKN Ted Tomblin 2024 | Matthew Tweed | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 10047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0
1726 | 2024-02-22 00:34 | P23543 | EXP-024 FCAS AP Transformation & Change Enablers | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -26% | 385921 | 0 | 385921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26% | 0% | 0% | -26% |  | 0
1726 | 2024-02-22 00:34 | P23585 | Systems Design - Missile Systems, Meteor,Brimstone | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 | 0 | 0 | 0 | 49500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35% | 0% | 0% | -35% |  | 0
1726 | 2024-02-22 00:34 | P23552 | FCAS AP Product Technology Development | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -25% | 597871 | 0 | 597871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0% | -25% |  | 0
1726 | 2024-02-22 00:34 | P23137 | BAE Management Support Collector | Danny Wilkinson | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3A | REIM | 2024-02-08 | 0 |  |  |  | 0% | 0% | 0 | -44357052% | 0 | 100437 | -100437 | 0 | 1053 | 1053.38 | 0 | 0 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | -44357052% | 0% | 0% |  | 50
1726 | 2024-02-22 00:34 | P23641 | Drawing Triage | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM | 2024-01-25 | 1 |  |  |  | 0% | 0% | 0 | -1043168% | 0 | 10756 | -10756 | 0 | 0 | 0 | 0 | 0 | 0.01 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | -1043168% | 100% | 100% |  | 49
1726 | 2024-02-22 00:34 | P23730 | FLE Project | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -15.64% | 0 | 1120 | -1120 | 0 | 0 | 0 | 24000 | 0 | 48 | 1120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | -15.64% | -15.64% | -15.64% |  | 35
1726 | 2024-02-22 00:34 | P23463 | A220 Wing MaMo Design Checking | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 7.85% | 0 | 1628 | -1628 | 0 | 0 | 0 | 15000 | 0 | 1953.6 | 1628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | 10.85% | 0% | -3% |  | 44
1726 | 2024-02-22 00:34 | P21028 | Rebate Collection (BACC) | David Catchpole | TOO | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | [5 empty] | 0% | 0% | 0 | 0% | 0 | 2680 | -2680 | 0 | 2680 | 2680 | 0 | 0 | 3216 | 2680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0
1726 | 2024-02-22 00:34 | P23740 | Phase 2 - EJ200 ESS EHM Platform Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 3 | FIX |  |  |  |  | 1.932% | 739.4% | -0.004902% | 0 | 3.56% | 175971 | 3400 | 172571 | 0 | 0 | 0 | 0 | 25139 | 48 | -21739 | 30167 | -0.16667 | 30166.8 | 0 | 0 | 0 | 0 | 28% | 31.56% | 31.56% | 3.56% |  | 80
1726 | 2024-02-22 00:34 | P23578 | ESN Work Package | Hannah Mead | COZ | CHELTON LIMITED | DET | Level 3 | FIX | 2024-01-01 | 0 |  |  | 86.17% | 116.1% | 116.1% | 0 | 35.86% | 4410 | 3800 | 610 | 0 | 0 | 0 | 0 | 4410 | 0 | -610 | 0 | 4410 | 0 | 0 | 0 | 0 | 0 | 24% | 59.86% | 0% | -24% |  | 95
1726 | 2024-02-22 00:34 | P23628 | Design Assurance | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -6.67% | 0 | 3909 | -3909 | 0 | 0 | 0 | 4454.8 | 0 | 4691.09 | 3909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 0.33% | 0% | -7% |  | 15.05
1726 | 2024-02-22 00:34 | P23002 | WoT MAJ Transit Flag Stress | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 30.9% | 323.7% | 323.7% | 0 | 53.84% | 4735 | 1463 | 3272 | 0 | 0 | 2242.5 | 0 | 4735 | 0.6 | 1 | 0 | 4735 | 0 | 0 | 0 | 0 | 0 | 10% | 63.84% | 0% | -10% |  | 45
1726 | 2024-02-22 00:34 | P23718 | Requalification of EJ200 GSS ESS EHM SW module | Vijayakumara Nanjundappa | ARZ | MTU AERO ENGINES AG | DET | Level 3 | FIX |  |  |  |  | 7.508% | 0% | 0% | 0 | -3.61% | 74463 | 5591 | 68872 | 0 | 881 | 881.46 | 0 | 0 | 48 | 5591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 24.39% | 24.39% | -3.61% |  | 80
1726 | 2024-02-22 00:34 | P23742 | Cyber Security Support | Hannah Mead | COZ | CHELTON LIMITED | DET | Level 3 | FIX | [5 empty] | 0% | 0% | 0 | 33.55% | 0 | 8100 | -8100 | 0 | 0 | 0 | 9000 | 0 | 70 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 33.55% | 33.55% | 33.55% |  | 100
1726 | 2024-02-22 00:34 | P23607 | SAFRAN - A330neo Turnover Frame | Gary Kempster | TOO | SAFRAN SEATS GB LIMITED | MPE | Level 3 | FIX |  |  |  |  | 95.68% | 104.5% | 0.001994% | 0 | -19.75% | 8736 | 8359 | 377 | 0 | 0 | 0 | 0 | 8736 | 10030.8 | -377 | 10483 | 0.16667 | 10483.2 | 0 | 0 | 0 | 0 | 23% | 3.25% | 0% | -23% |  | 52
1726 | 2024-02-22 00:34 | P23274 | ME Support (Aim Altitude - Cambridge) | James Montgomery | AVI | AVIC CABIN SYSTEMS (UK) LIMITED | ME | Level 3 | FIX | 2023-08-18 | 0 |  |  | 51.88% | 56.29% | 56.29% | 0 | -0.17% | 17280 | 8964 | 8316 | 0 | 0 | 0 | 0 | 5046 | 4701.24 | 3918 | 0 | 5046 | 0 | 0 | 0 | 0 | 0 | 21% | 20.83% | 0% | -21% |  | 48
1726 | 2024-02-22 00:34 | P23283 | Spirit Tooling Audit | Charidimos Valadakis | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-05-03 | 0 |  |  | 97.23% | 48.57% | 48.57% | 0 | -7.99% | 9910 | 9635 | 275 | 0 | 0 | 0 | 0 | 4680 | 5946.05 | 4955 | 0 | 4680 | 0 | 0 | 0 | 0 | 0 | 7% | -0.99% | 0% | -7% |  | 34.41
1726 | 2024-02-22 00:34 | P23127 | Loft Hall Design Support | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 101% | 99.06% | 99.06% | 0 | -9.55% | 9680 | 9772 | -92 | 0 | 0 | 0 | 0 | 9680 | 110.4 | 92 | 0 | 9680 | 0 | 0 | 0 | 0 | 0 | 41% | 31.45% | 0% | -41% |  | 44
1726 | 2024-02-22 00:34 | P23630 | 2Excel CFD Analysis Support | Dushan Fernando | BAX | STIRLING DYNAMICS LTD | MPE | Level NC | FIX |  |  |  |  | 61.2% | 100% | 100% | 0 | -1.87% | 16195 | 9911 | 6284 | 0 | 0 | 0 | 0 | 9912 | 0 | 0 | 0 | 9912 | 0 | 0 | 0 | 0 | 0 | 26% | 24.13% | 0% | -26% |  | 64.78
1726 | 2024-02-22 00:34 | P23663 | Spirit Tooling Verification and Inspection | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 61.46% | 0% | 0% | 0 | -7.57% | 19820 | 12181 | 7639 | 0 | 0 | 0 | 7392 | 0 | 124.86 | 12181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12% | 4.43% | 4.82% | -7.18% |  | 34.41
1726 | 2024-02-22 00:34 | P23313 | Laser Trim Fixtures | Gary Kempster | TOO | ALKEN ENGINEERING LIMITED | MPE | Level 3 | FIX | 2023-11-20 | 0 |  |  | 89.87% | 111.3% | 111.3% | 0 | 0.53% | 13770 | 12375 | 1395 | 0 | 0 | 0 | 0 | 13770 | 0 | -1395 | 0 | 13770 | 0 | 0 | 0 | 0 | 0 | 17% | 17.53% | 0% | -17% |  | 45
1726 | 2024-02-22 00:34 | P23724 | GKN S McConnell 2024 | Matthew Tweed | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  |  | 25.1% | 55.78% | 0% | 0 | 1.51% | 49820 | 12505 | 37315 | 0 | 0 | 0 | 0 | 6975 | 48 | 5530 | 8370 | 0 | 8369.76 | 0 | 0 | 0 | 0 | 19% | 20.51% | 20.51% | 1.51% |  | 49.82
1726 | 2024-02-22 00:34 | P22761 | Red Bull Chassis Spit | James Montgomery | TOO | MANUFAX ENGINEERING LTD | MPE | Level 3 | FIX | 2022-11-15 | 0 |  |  | 72.19% | 96.98% | 96.98% | 0 | 7.92% | 12961 | 9356 | 3605 | 0 | 0 | 0 | 0 | 9073 | 4666.39 | 3889 | 0 | 9073 | 0 | 0 | 0 | 0 | 0 | 23% | 30.92% | 0% | -23% |  | 42.19
1726 | 2024-02-22 00:34 | P23433 | Cavendish | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 32.81% | 100% | 100% | 0 | -0.34% | 42240 | 13859 | 28381 | 0 | 0 | 0 | 0 | 13859 | 0 | 0 | 0 | 13859 | 0 | 0 | 0 | 0 | 0 | 7% | 6.66% | 0% | -7% |  | 43.93
1726 | 2024-02-22 00:34 | P23350 | Spirit 2023 - Stress Approve Man Serv (DH) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 14.15% | 72.64% | 72.64% | 0 | -0.29% | 97920 | 13860 | 84060 | 0 | 0 | 0 | 0 | 10068 | 4550.4 | 3792 | 0 | 10068 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48
1726 | 2024-02-22 00:34 | P23344 | Spirit A320 Spoilers Support 2023 | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 38.75% | 100% | 100% | 0 | 5.82% | 35786 | 13867 | 21919 | 0 | 0 | 0 | 0 | 13867 | 0 | 0 | 0 | 13867 | 0 | 0 | 0 | 0 | 0 | 7% | 12.82% | 0% | -7% |  | 34.41
1726 | 2024-02-22 00:34 | P23337 | Spirit 2023 - Steve Grimley | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 25.28% | 100% | 100% | 0 | 0.01% | 56813 | 14362 | 42451 | 0 | 0 | 0 | 0 | 14362 | 0 | 0 | 0 | 14362 | 0 | 0 | 0 | 0 | 0 | 7% | 7.01% | 0% | -7% |  | 30.11
1726 | 2024-02-22 00:34 | P23598 | MRB Onsite support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -9.65% | 0 | 14389 | -14389 | 0 | 8736 | 14079.58 | 21700 | 0 | 91 | 14389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 8.35% | 8.89% | -9.11% |  | 42.5
1726 | 2024-02-22 00:34 | P23597 | MRB Onsite support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -10.04% | 0 | 15101 | -15101 | 0 | 9448 | 17381.62 | 24200 | 0 | 91 | 15101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 7.96% | 8.95% | -9.05% |  | 42.5
1726 | 2024-02-22 00:34 | P23760 | Land Ceptor V&V Systems Engineer | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 28.98% | 0 | 17584 | -17584 | 0 | 0 | 0 | 23550 | 0 | 48 | 17584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 28.98% | 28.98% | 28.98% |  | 78.5
1726 | 2024-02-22 00:34 | P23635 | Engineering Services: FAI Support | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 49.9% | 0% | 0% | 0 | -3.4% | 37230 | 18576 | 18654 | 0 | 0 | 0 | 0 | 0 | 165.45 | 18576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8% | 4.6% | 5.04% | -2.96% |  | 38.7
1726 | 2024-02-22 00:34 | P23343 | Spirit 2023 - John Agnew | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-08-09 | 0 |  |  | 28.56% | 86.27% | 86.27% | 0 | -0.02% | 65120 | 18601 | 46519 | 0 | 0 | 0 | 0 | 16047 | 3064.49 | 2554 | 0 | 16047 | 0 | 0 | 0 | 0 | 0 | 7% | 6.98% | 0% | -7% |  | 34.51
1726 | 2024-02-22 00:34 | P23355 | Spirit Tooling Support 2023 | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-23 | 0 |  |  | 22.93% | 89.03% | 89.03% | 0 | -0.82% | 91800 | 21053 | 70747 | 0 | 0 | 0 | 0 | 18743 | 2773.01 | 2311 | 0 | 18743 | 0 | 0 | 0 | 0 | 0 | 20% | 19.18% | 0% | -20% |  | 44.46
1726 | 2024-02-22 00:34 | P23651 | PMO Spirit | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 24.7% | 0 | 21996 | -21996 | 0 | 0 | 0 | 30800 | 0 | 164.74 | 21996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 24.7% | 25.06% | 25.06% |  | 36
1726 | 2024-02-22 00:34 | P23351 | Spirit 2023 - Design Man Serv (KL) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 26.47% | 93.15% | 93.15% | 0 | 0.09% | 93840 | 24840 | 69000 | 0 | 0 | 0 | 0 | 23138 | 2042.4 | 1702 | 0 | 23138 | 0 | 0 | 0 | 0 | 0 | 26% | 26.09% | 0% | -26% |  | 46
1726 | 2024-02-22 00:34 | P23356 | Spirit 2023 - Design Man Serv (AH) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX | 2023-08-09 | 1 |  |  |  | 76.66% | 0.001332% | 23018.4 | 0.48% | 0 | 25023 | -25023 | 0 | 0 | 0 | 25300 | 19182 | 30027.7 | 5841 | 23018 | 0.33333 | 0 | 0 | 0 | 23018.4 | 23018.4 | 18% | 18.48% | 0% | -18% |  | 46
1726 | 2024-02-22 00:34 | P23753 | Tempest Composites Maturation | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | [5 empty] | 0% | 0% | 0 | -23.04% | 0 | 25451 | -25451 | 0 | 0 | 0 | 54398.4 | 0 | 49 | 25451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37% | 13.96% | 13.96% | -23.04% |  | 64.76
1726 | 2024-02-22 00:34 | P22884 | Spirit Shorts Config Eng | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 66.3% | 100.1% | 100.1% | 0 | 0.56% | 38976 | 25842 | 13134 | 0 | 0 | 0 | 0 | 25863 | 0 | 0 | 0 | 25863 | 0 | 0 | 0 | 0 | 0 | 7% | 7.56% | 0% | -7% |  | 20.3
1726 | 2024-02-22 00:34 | P23354 | Spirit 2023 - Design Man Serv (PC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 27.97% | 99.36% | 99.36% | 0 | 0.48% | 93840 | 26249 | 67591 | 0 | 0 | 0 | 0 | 26082 | 200.38 | 167 | 0 | 26082 | 0 | 0 | 0 | 0 | 0 | 18% | 18.48% | 0% | -18% |  | 46
1726 | 2024-02-22 00:34 | P23338 | Spirit 2023 - Blair Hainey | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 81.16% | 64.44% | 64.44% | 0 | 4.1% | 34494 | 27996 | 6498 | 0 | 0 | 0 | 0 | 18042 | 125.36 | 9953 | 0 | 18042 | 0 | 0 | 0 | 0 | 0 | 7% | 11.1% | 19.31% | 12.31% |  | 18.28
1726 | 2024-02-22 00:34 | P22756 | A350 FLE Design Checker | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2022-03-23 | 1 |  |  | 68.39% | 119.7% | 119.7% | 0 | 16.46% | 34898 | 23867 | 11031 | 0 | 23867 | 24342.3 | 0 | 28571 | 0.06 | 0 | 0 | 28571 | 0 | 0 | 0 | 0 | 0 | 0% | 16.46% | 0% | 0% |  | 0
1726 | 2024-02-22 00:34 | P23729 | Honda Tooling | Paul Watson | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX | [5 empty] | 0% | 0% | 0 | 6.81% | 0 | 29171 | -29171 | 0 | 0 | 0 | 33167 | 0 | 42 | 29171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 16.81% | 16.81% | 6.81% |  | 42.2
1726 | 2024-02-22 00:34 | P23458 | Spirit Belfast Tooling Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-08-11 | 0 |  |  | 101.3% | 94.65% | 94.65% | 0 | 8.64% | 30384 | 30785 | -401 | 0 | 0 | 0 | 0 | 29139 | 1974.96 | 1646 | 0 | 29139 | 0 | 0 | 0 | 0 | 0 | 7% | 15.64% | 0% | -7% |  | 42.2
1726 | 2024-02-22 00:34 | P23642 | MRB Belfast Support | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -18.27% | 0 | 31632 | -31632 | 0 | 2170 | 2252.31 | 30800 | 0 | 128.23 | 31632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | -18.27% | -18.84% | -18.84% |  | 38.52
1726 | 2024-02-22 00:34 | P23744 | Model Factory | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  |  | 12.6% | 69.17% | -0.001009% | 0 | 8.34% | 262300 | 33045 | 229255 | 0 | 0 | 0 | 0 | 22858 | 48 | 10187 | 27430 | -0.33333 | 27429.6 | 0 | 0 | 0 | 0 | 28% | 36.34% | 36.34% | 8.34% |  | 50.76
1726 | 2024-02-22 00:34 | P23365 | GKN 777x Lip Skin Fixture | Steven Lawton | TOO | GKN AEROSPACE SERVICES LTD | MPE | Level 3 | FIX | 2023-10-12 | 0 |  |  | 41.91% | 113.2% | 113.2% | 0 | -9.26% | 79161 | 33176 | 45985 | 0 | 5110 | 5109.88 | 0 | 37544 | 0 | -4369 | 0 | 37544 | 0 | 0 | 0 | 0 | 0 | 22% | 12.74% | 0% | -22% |  | 56
1726 | 2024-02-22 00:34 | P22768 | MRB Onsite Support - Spirit Belfast | James Montgomery | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2023-07-27 | 0 |  |  |  | 0% | 0% | 0 | -17.07% | 0 | 34614 | -34614 | 0 | 0 | 0 | 36800 | 0 | 41536.8 | 34614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | -7.07% | 0% | -10% |  | 36
1726 | 2024-02-22 00:34 | P23347 | WoT Fixed Leading Edge - Industrial 2023 | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 112.8% | 42.03% | 42.03% | 0 | -0.41% | 31034 | 35002 | -3968 | 0 | 0 | 0 | 10500 | 14711 | 24349.85 | 20292 | 0 | 14711 | 0 | 0 | 0 | 0 | 0 | 7% | 6.59% | 0% | -7% |  | 32.26
1726 | 2024-02-22 00:34 | P23051 | Spirit Shorts A350 PAX Door | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 3A | REIM |  |  |  |  | 205.9% | 105.4% | 105.4% | 0 | -0.63% | 18216 | 37513 | -19297 | 0 | 0 | 0 | 0 | 39537 | 0 | 0 | 0 | 39537 | 0 | 0 | 0 | 0 | 0 | 30% | 29.37% | 0% | -30% |  | 46
1726 | 2024-02-22 00:34 | P23754 | Tempest Composites WP4 | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX | [5 empty] | 0% | 0% | 0 | 8.66% | 0 | 39584 | -39584 | 0 | 0 | 0 | 97140 | 0 | 63 | 39584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 36.66% | 36.66% | 8.66% |  | 65
1726 | 2024-02-22 00:34 | P23700 | IPDT Leads | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 23.53% | 0% | 0% | 0 | 11.6% | 169264 | 39835 | 129429 | 0 | 0 | 0 | 0 | 0 | 91 | 39835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26% | 37.6% | 38.02% | 12.02% |  | 61.88
1726 | 2024-02-22 00:34 | P22752 | Tooling WoT - 2021 (Spirit) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | REIM | 2023-05-03 | 0 |  |  | 101.1% | 74.02% | 74.02% | 0 | -8.5% | 41525 | 41982 | -457 | 0 | 0 | 0 | 0 | 31076 | 13087.42 | 10906 | 0 | 31076 | 0 | 0 | 0 | 0 | 0 | 0% | -8.5% | 0% | 0% |  | 39.09
1726 | 2024-02-22 00:34 | P23784 | Tempest Tooling Offload 2024 | Christopher McCarthy | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -9.15% | 0 | 43319 | -43319 | 0 | 0 | 0 | 74725 | 0 | 48 | 43319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 20.85% | 20.85% | -9.15% |  | 54.77
1726 | 2024-02-22 00:34 | P23339 | Spirit 2023 - Stewart Russell | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 64.51% | 100% | 100% | 0 | 0.62% | 72767 | 46942 | 25825 | 0 | 0 | 0 | 0 | 46942 | 0 | 0 | 0 | 46942 | 0 | 0 | 0 | 0 | 0 | 7% | 7.62% | 0% | -7% |  | 35.67
1726 | 2024-02-22 00:34 | P23810 | Strategic Enablement | Owain Jones | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -19.66% | 0 | 49098 | -49098 | 0 | 0 | 0 | 50000 | 0 | 49 | 49098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | -1.66% | -1.66% | -19.66% |  | 42
1726 | 2024-02-22 00:34 | P22760 | SA Leading Edge Transport Media ('A' Frames) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-11-15 | 1 |  |  | 85.99% | 110.7% | 116.3% | -3082.8 | 3.97% | 53481 | 45986 | 7495 | 0 | 42804 | 42804 | 0 | 50912 | 0 | 0 | -3083 | 53481.1667 | 0 | 0 | 0 | -3082.8 | -3082.8 | 6% | 9.97% | 0% | -6% |  | 42
1726 | 2024-02-22 00:34 | P23322 | GKN T Tomblin 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  |  | 90.83% | 97.09% | 88.79% | 0 | -0.33% | 58952 | 53544 | 5408 | 0 | 0 | 0 | 0 | 51984 | 80.96 | 1560 | 5328 | 47544 | 3571.2 | 1756.8 | 0 | 0 | 0 | 17% | 16.67% | 16.67% | -0.33% |  | 48
1726 | 2024-02-22 00:34 | P23382 | Performance Modelling | Dushan Fernando | BDX | MBDA UK LIMITED | MPE | Level NC | REIM | 2023-07-09 | 1 |  |  | 40.95% | 79.09% | 79.09% | 0 | -16.36% | 170010 | 69626 | 100384 | 0 | 14560 | 14659.9 | 0 | 55066 | 0 | 0 | 0 | 55066 | 0 | 0 | 0 | 0 | 0 | 20% | 3.64% | 0% | -20% |  | 77.05
1726 | 2024-02-22 00:34 | P23349 | Spirit 2023 - Stress Approve Man Serv (SB) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 58.24% | 80.05% | 80.05% | 0 | -0.29% | 97920 | 57024 | 40896 | 0 | 0 | 0 | 0 | 45648 | 13651.2 | 11376 | 0 | 45648 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48
1726 | 2024-02-22 00:34 | P23341 | Spirit 2023 - Tom McFarlane | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 52.93% | 85.09% | 66.89% | 0 | -0.01% | 108666 | 57522 | 51144 | 0 | 0 | 0 | 0 | 48945 | 159.75 | 8577 | 12560 | 38478.3333 | 0 | 0 | 7110.19 | 5449.73 | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48
1726 | 2024-02-22 00:34 | P23193 | Spirit Shorts Stephen Greer | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 98.32% | 90.43% | 85.95% | 0 | 2.45% | 61472 | 60438 | 1034 | 0 | 0 | 0 | 0 | 54656 | 88.33 | 5783 | 3252 | 51946 | 0 | 3252.37 | 0 | 0 | 0 | 29% | 31.45% | 34.03% | 5.03% |  | 35.01
1726 | 2024-02-22 00:34 | P23106 | ME Support to NPD - Bobby Haggart | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  |  | 95.79% | 97.03% | 97.03% | 0 | 0.3% | 65675 | 62912 | 2763 | 0 | 0 | 0 | 0 | 61043 | 2243.24 | 1869 | 0 | 61043 | 0 | 0 | 0 | 0 | 0 | 15% | 15.3% | 0% | -15% |  | 35.65
1726 | 2024-02-22 00:34 | P23561 | SAAB | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2024-01-01 | 1 |  |  | 82.46% | 121.1% | 96.66% | 0 | 3.5% | 67485 | 55649 | 11836 | 0 | 0 | 0 | 0 | 67399 | 184.58 | -4408 | 16332 | 53789 | 0 | 16332.48 | 0 | 0 | 0 | 16% | 19.5% | 0% | -16% |  | 36.82
1726 | 2024-02-22 00:34 | P23741 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  |  | 11.99% | 71.14% | 0% | 0 | 2.96% | 526262 | 63092 | 463170 | 0 | 0 | 0 | 0 | 44885 | 48 | 18207 | 53862 | 0 | 53862 | 0 | 0 | 0 | 0 | 28% | 30.96% | 30.96% | 2.96% |  | 38.59
1726 | 2024-02-22 00:34 | P22967 | Spirit 2022 - Channapa Laxmeshwar | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2023-01-26 | 2 |  |  | 69.69% | 121.3% | 121.3% | 0 | 9.53% | 75159 | 52376 | 22783 | 0 | 52376 | 54898.1 | 0 | 63509 | 0.42 | 0 | 0 | 63509 | 0 | 0 | 0 | 0 | 0 | 8% | 17.53% | 0% | -8% |  | 0
1726 | 2024-02-22 00:34 | P23342 | Spirit 2023 - Channapa Laxmeshwar | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 78.75% | 104.3% | 88.16% | 0 | -2.64% | 79348 | 62484 | 16864 | 0 | 62484 | 63539 | 0 | 65178 | 12298.5 | 157 | 12110 | 55086.3333 | 0 | 0 | 4036.8 | 8073.6 | 0 | 7% | 4.36% | 0% | -7% |  | 0
1726 | 2024-02-22 00:34 | P23743 | EHM Cloud Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  |  | 6.839% | 122.9% | -0.0004797% | 0 | 2.27% | 1016000 | 69487 | 946513 | 0 | 0 | 0 | 0 | 85408 | 48 | -15921 | 102490 | -0.33333 | 102489.6 | 0 | 0 | 0 | 0 | 28% | 30.27% | 30.27% | 2.27% |  | 50.68
1726 | 2024-02-22 00:34 | P23080 | Spirit Shorts DManagement Cairan Cullen | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 49.07% | 98.47% | 92.92% | 3787.8 | -0.82% | 149600 | 73408 | 76192 | 0 | 0 | 0 | 0 | 72284 | 189.81 | 1124 | 4892 | 68207.3333 | 0 | 1104.24 | 0 | 3787.8 | 3787.8 | 24% | 23.18% | 18.04% | -5.96% |  | 44.45
1726 | 2024-02-22 00:34 | P23465 | A220 ToW Design Offload (Wing) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 56.55% | 74.71% | 66.8% | 0 | -4.16% | 132000 | 74643 | 57357 | 0 | 0 | 0 | 0 | 55768 | 85.53 | 18875 | 7088 | 49861.3333 | 0 | 7087.68 | 0 | 0 | 0 | 20% | 15.84% | 15.17% | -4.83% |  | 42.8
1726 | 2024-02-22 00:34 | P23560 | NJEWCS TAF202302 SM | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level 2 | FIX |  |  |  |  | 91.91% | 53.4% | 53.4% | 0 | 12.36% | 81500 | 74908 | 6592 | 0 | 0 | 0 | 0 | 40000 | 131.85 | 34908 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 28% | 40.36% | 41.09% | 13.09% |  | 73.01
1726 | 2024-02-22 00:34 | P23600 | MBDA EXP-EE-023 Bristone Certification | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 59.65% | 100% | 84.61% | 0 | 0.4% | 126600 | 75517 | 51083 | 0 | 0 | 0 | 0 | 75517 | 72.8 | 0 | 13942 | 63898.6667 | 0 | 13941.6 | 0 | 0 | 0 | 41% | 41.4% | 0% | -41% |  | 78.5
1726 | 2024-02-22 00:34 | P23586 | Project Management Support | Peter Bowen | BDX | MBDA UK LIMITED | MPE | Level NC | REIM |  |  |  |  | 94.98% | 88.31% | 57.22% | 0 | -25.44% | 80000 | 75984 | 4016 | 0 | 1141 | 1140.6 | 16000 | 67104 | 86.51 | 8880 | 28349 | 43479.8333 | 3148.63 | 25200 | 0 | 0 | 0 | 49% | 23.56% | 24.63% | -24.37% |  | 80
1726 | 2024-02-22 00:34 | P23551 | Ian Berry 2023 H2 | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  |  | 100.6% | 88.12% | 36.25% | 0 | 13.12% | 75810 | 76278 | -468 | 0 | 0 | 0 | 24259.2 | 67217 | 156.2 | 9061 | 47479 | 27651.1667 | 47478.96 | 0 | 0 | 0 | 0 | 22% | 35.12% | 38.59% | 16.59% |  | 76.93
1726 | 2024-02-22 00:34 | P23340 | Spirit 2023 - John Cole | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 102% | 82.12% | 65.9% | 0 | -0.01% | 75065 | 76537 | -1472 | 0 | 0 | 0 | 8831 | 62852 | 142.81 | 13684 | 14894 | 50440.3333 | 0 | 0 | 8831.16 | 6062.47 | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 39.78
1726 | 2024-02-22 00:34 | P23345 | Spirit 2023- Jonathan Escosio | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 102.9% | 82.44% | 65.55% | 0 | -6.35% | 75971 | 78185 | -2214 | 0 | 0 | 0 | 8938 | 64456 | 148.49 | 13729 | 15846 | 51251 | 0 | 0 | 8696.16 | 7150.18 | 0 | 7% | 0.65% | 0.65% | -6.35% |  | 40.26
1726 | 2024-02-22 00:34 | P22505 | Spirit MRB Engineering Support 2021 | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 1 |  |  | 91.17% | 100% | 95.78% | 4020.48 | 21.2% | 87110 | 79415 | 7695 | 0 | 0 | 0 | 0 | 79415 | 4020.48 | 0 | 4020 | 76065 | 0 | 0 | 0 | 4020.48 | 4020.48 | 0% | 21.2% | 0% | 0% |  | 41.88
1726 | 2024-02-22 00:34 | P23336 | Spirit 2023 - Neil Rampling | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 59.31% | 82.91% | 60.26% | 6343.82 | -0.01% | 133902 | 79422 | 54480 | 0 | 0 | 0 | 0 | 65851 | 175.78 | 13571 | 21586 | 47862.6667 | 0 | 0 | 8515.2 | 13070.83 | 6343.82 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48
1726 | 2024-02-22 00:34 | P22885 | ME Support (Baxi) | James Montgomery | HUV | BAXI HEATING UK LIMITED | ME | Level 3 | FIX | 2023-01-12 | 0 |  |  | 68.78% | 108.7% | 108.7% | 0 | 13.05% | 106633 | 73340 | 33293 | 0 | 0 | 0 | 0 | 79748 | 1531.35 | 1276 | 0 | 79748 | 0 | 0 | 0 | 0 | 0 | 15% | 28.05% | 0% | -15% |  | 44.37
1726 | 2024-02-22 00:34 | P23739 | Lifing Services DACs | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  |  | 12.58% | 67.45% | -0.0002018% | 0 | 7.4% | 656508 | 82592 | 573916 | 0 | 0 | 0 | 0 | 55709 | 48 | 26883 | 66851 | -0.16667 | 66850.8 | 0 | 0 | 0 | 0 | 28% | 35.4% | 35.4% | 7.4% |  | 37.88
1726 | 2024-02-22 00:34 | P23171 | Spirt Shorts Weights Eng | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 69.18% | 112.2% | 96.15% | 0 | 2.68% | 103113 | 71329 | 31784 | 0 | 71329 | 90419.91 | 0 | 80050 | 105.02 | 3549 | 13762 | 68581.6667 | 7796.45 | 5965.46 | 0 | 0 | 0 | 12% | 14.68% | 0% | -12% |  | 0
1726 | 2024-02-22 00:34 | P23335 | GKN S McConnell 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2023-12-31 | 3 |  |  | 96.61% | 100% | 75.29% | 0 | 0.74% | 87420 | 84459 | 2961 | 0 | 0 | 0 | 0 | 84459 | 218.4 | 0 | 25042 | 63590.6667 | 0 | 8347.2 | 0 | 16694.4 | 0 | 15% | 15.74% | 0% | -15% |  | 47
1726 | 2024-02-22 00:34 | P23079 | Spirit Shorts Nomenclature | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 95.63% | 91.19% | 80.8% | 10554.48 | 1.86% | 88455 | 84586 | 3869 | 0 | 0 | 0 | 0 | 77138 | 198.47 | 7447 | 10554 | 68343 | 0 | 0 | 0 | 10554.48 | 10554.48 | 20% | 21.86% | 25.23% | 5.23% |  | 30.71
1726 | 2024-02-22 00:34 | P22965 | Spirit 2022 - Design Man Serv (AH) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 1 |  |  | 106.7% | 96.66% | 92.02% | 4759.75 | 3.14% | 80080 | 85441 | -5361 | 0 | 0 | 0 | 0 | 82589 | 8182.59 | 2852 | 4760 | 78622.3333 | 0 | 0 | 0 | 4759.75 | 4759.75 | 14% | 17.14% | 0% | -14% |  | 42.44
1726 | 2024-02-22 00:34 | P23523 | Applique Armour Support | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 0 |  |  | 72.43% | 98.47% | 98.47% | 0 | 3.42% | 118200 | 85607 | 32593 | 0 | 0 | 0 | 0 | 84300 | 1567.8 | 1307 | 0 | 84300 | 0 | 0 | 0 | 0 | 0 | 25% | 28.42% | 0% | -25% |  | 64.29
1726 | 2024-02-22 00:34 | P23438 | A220 Spirit Shorts DTC - Stephen Corry | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 89.43% | 47.09% | 47.09% | 0 | -6.65% | 95928 | 85788 | 10140 | 0 | 0 | 0 | 0 | 40400 | 148.95 | 45388 | 0 | 40400 | 0 | 0 | 0 | 0 | 0 | 23% | 16.35% | 20.15% | -2.85% |  | 49.85
1726 | 2024-02-22 00:34 | P22964 | Spirit 2022 - MRB Man Serv (JC) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 100.6% | 97.95% | 97.95% | 0 | 1.91% | 85435 | 85960 | -525 | 0 | 0 | 0 | 0 | 84200 | 2112.62 | 1761 | 0 | 84200 | 0 | 0 | 0 | 0 | 0 | 16% | 17.91% | 0% | -16% |  | 42.69
1726 | 2024-02-22 00:34 | P22963 | Spirit 2022 - Design Man Serv (PC) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 1 |  |  | 108.6% | 104% | 94.46% | 9938.48 | 3.18% | 80080 | 86927 | -6847 | 0 | 0 | 0 | 0 | 90390 | 5782.63 | -3463 | 9938 | 82108.3333 | 0 | 0 | 0 | 9938.48 | 9938.48 | 13% | 16.18% | 0% | -13% |  | 42.39
1726 | 2024-02-22 00:34 | P23583 | Castalla - Test Rig Design | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 132.8% | 68.31% | 68.31% | 0 | -6.13% | 67520 | 89671 | -22151 | 0 | 0 | 0 | 22906 | 61258 | 97.01 | 28413 | 0 | 61258 | 0 | 0 | 0 | 0 | 0 | 21% | 14.87% | 19.58% | -1.42% |  | 42.65
1726 | 2024-02-22 00:34 | P23353 | Spirit 2023 - MRB Man Serv (JC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  |  | 99.04% | 75.46% | 75.46% | 0 | -0.27% | 91800 | 90923 | 877 | 0 | 0 | 0 | 0 | 68615 | 179.01 | 22307 | 0 | 68615 | 0 | 0 | 0 | 0 | 0 | 18% | 17.73% | 15.49% | -2.51% |  | 45
1726 | 2024-02-22 00:34 | P23375 | GKN Jaap Peters NL 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  |  | 93.37% | 105.3% | 67.32% | 0 | -15.93% | 97123 | 90686 | 6437 | 0 | 90686 | 92269.6 | 0 | 95457 | 124.66 | -920 | 41290 | 61048.6667 | 8793.29 | 13234.06 | 0 | 19262.9 | 0 | 20% | 4.07% | 0% | -20% |  | 0
1726 | 2024-02-22 00:34 | P23545 | Ultra CSS continuation 2023 H2 | Natalie Sinclair | ULT | ULTRA SONAR SYSTEMS LIMITED | EES | Level NC | REIM |  |  |  |  | 125.3% | 79.24% | 46.16% | 0 | 2.24% | 76000 | 95219 | -19219 | 0 | 0 | 0 | 24259.2 | 75451 | 146.98 | 19768 | 37794 | 43956 | 37794.24 | 0 | 0 | 0 | 0 | 23% | 25.24% | 25% | 2% |  | 80
1726 | 2024-02-22 00:34 | P23588 | BAE Typhoon MRB MC Shop Concessions | Andrew Houghton | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 56.39% | 93.49% | 52.21% | 0 | -4.08% | 175061 | 98719 | 76342 | 0 | 0 | 0 | 0 | 92296 | 128.33 | 6423 | 48910 | 51537.6667 | 48910.43 | 0 | 0 | 0 | 0 | 31% | 26.92% | 29.18% | -1.82% |  | 55.53
1726 | 2024-02-22 00:34 | P23664 | Tempest Composites WP3 | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  |  | 83.16% | 16.22% | 0.0006546% | 0 | -4.91% | 122455 | 101838 | 20617 | 0 | 0 | 0 | 0 | 16519 | 131.49 | 85320 | 19822 | 0.66667 | 0 | 19822.44 | 0 | 0 | 0 | 37% | 32.09% | 35.46% | -1.54% |  | 60.38
1726 | 2024-02-22 00:34 | P23677 | ME Managed Service - Phase 1 | Paul Watson | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  |  | 18.49% | 0% | 0% | 0 | -25.59% | 554400 | 102533 | 451867 | 0 | 0 | 0 | 0 | 0 | 106.58 | 102533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33% | 7.41% | 10.22% | -22.78% |  | 45
1726 | 2024-02-22 00:34 | P22918 | Spirit Shorts Graduates | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 81.75% | 66.2% | 66.2% | 0 | -2.4% | 130000 | 106270 | 23730 | 0 | 0 | 0 | 0 | 70352 | 178.92 | 35918 | 0 | 70352 | 0 | 0 | 0 | 0 | 0 | 19% | 16.6% | 19.08% | 0.08% |  | 23.24
1726 | 2024-02-22 00:34 | P23352 | Spirit 2023 - Stress Approve Man Serv (CC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  |  | 109.4% | 65.24% | 65.24% | 0 | 7.29% | 97920 | 107160 | -9240 | 0 | 0 | 0 | 10656 | 69912 | 148.04 | 37248 | 0 | 69912 | 0 | 0 | 0 | 0 | 0 | 7% | 14.29% | 4.69% | -2.31% |  | 48
1726 | 2024-02-22 00:34 | P23282 | Tooling Support (MBDA) | Dushan Fernando | BDV | MBDA UK LIMITED | ME | Level 3 | FIX |  |  |  |  | 106.6% | 92.85% | 82.91% | 0 | -9.28% | 104834 | 111802 | -6968 | 0 | 0 | 0 | 19964 | 103804 | 82.83 | 7998 | 13326 | 92699 | 0 | 13325.98 | 0 | 0 | 0 | 30% | 20.72% | 30.37% | 0.37% |  | 49.7
1726 | 2024-02-22 00:34 | P22883 | Spirit Shorts Evtol PMO C. Hatton | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 60.96% | 96.2% | 80.56% | 14784 | -12.2% | 185800 | 113256 | 72544 | 0 | 0 | 0 | 0 | 108947 | 172.5 | 4309 | 21252 | 91237 | 0 | 6468 | 14784 | 0 | 14784 | 26% | 13.8% | 26.7% | 0.7% |  | 36.38
1726 | 2024-02-22 00:34 | P23270 | Shorts Project X | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 79.93% | 77.3% | 71.45% | 0 | 0.81% | 142248 | 113692 | 28556 | 0 | 0 | 0 | 0 | 87889 | 148.34 | 25802 | 7981 | 81238.1667 | 0 | 7981.34 | 0 | 0 | 0 | 13% | 13.81% | 10.99% | -2.01% |  | 45.38
1726 | 2024-02-22 00:34 | P22736 | WoT Fixed Leading Edge - Industrial | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 106.7% | 93.42% | 91.32% | 3019.54 | 0.01% | 112196 | 119668 | -7472 | 0 | 0 | 0 | 0 | 111797 | 12465.69 | 7872 | 3020 | 109280.3333 | 0 | 0 | 0 | 3019.54 | 3019.54 | 7% | 7.01% | 0% | -7% |  | 32.26
1726 | 2024-02-22 00:34 | P22861 | WoT FLE Lifting & Handling Tools | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2023-06-14 | 1 |  |  | 65.17% | 101.6% | 101.6% | 0 | 12.01% | 173987 | 113382 | 60605 | 0 | 50078 | 58423.58 | 0 | 115204 | 12813.9 | 10678 | 0 | 115204 | 0 | 0 | 0 | 0 | 0 | 1% | 13.01% | 0% | -1% |  | 45
1726 | 2024-02-22 00:34 | P23648 | EXP-032 Delivery of Datalink Eng support - FCAS AP | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 34.49% | 80.38% | 0.0003908% | 0 | 4.78% | 371000 | 127948 | 243052 | 0 | 1033 | 1032.95 | 0 | 102843 | 128.44 | 25105 | 123411 | 0.5 | 0 | 123411 | 0 | 0 | 0 | 22% | 26.78% | 26.52% | 4.52% |  | 103.82
1726 | 2024-02-22 00:34 | P23421 | A220 DTC | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 101.5% | 80.81% | 59.15% | 0 | -11.32% | 130625 | 132530 | -1905 | 0 | 0 | 0 | 0 | 107094 | 118.43 | 25436 | 34447 | 78388.1667 | 0 | 34446.52 | 0 | 0 | 0 | 10% | -1.32% | 3.24% | -6.76% |  | 45.07
1726 | 2024-02-22 00:34 | P23667 | Safety Systems Engineer | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 33.41% | 90.82% | 0% | 0 | -8.37% | 398000 | 132990 | 265010 | 0 | 0 | 0 | 0 | 120780 | 189.69 | 12210 | 144936 | 0 | 0 | 144936 | 0 | 0 | 0 | 47% | 38.63% | 29.32% | -17.68% |  | 110
1726 | 2024-02-22 00:34 | P23437 | Embedded Software Engineer | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 92.92% | 93.75% | 83.48% | 0 | -6.33% | 150150 | 139526 | 10624 | 0 | 738 | 737.86 | 0 | 130812 | 61.48 | 8714 | 17207 | 116472.8333 | 4019.1 | 13188 | 0 | 0 | 0 | 22% | 15.67% | 16.24% | -5.76% |  | 78.5
1726 | 2024-02-22 00:34 | P23533 | External Stowage Design and Detail Support | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 0 |  |  | 102.4% | 73.24% | 73.24% | 0 | 3.33% | 140000 | 143369 | -3369 | 0 | 0 | 0 | 12936 | 105000 | 24882.63 | 35000 | 0 | 105000 | 0 | 0 | 0 | 0 | 0 | 27% | 30.33% | 0% | -27% |  | 60.04
1726 | 2024-02-22 00:34 | P23518 | Systems Engineering support to FCAS | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 73.71% | 90.9% | 83.01% | 0 | -1.4% | 193737 | 142801 | 50936 | 0 | 3927 | 3927.4 | 0 | 129804 | 66.6 | 12997 | 13518 | 118539 | 0 | 13517.7 | 0 | 0 | 0 | 30% | 28.6% | 3.5% | -26.5% |  | 66.94
1726 | 2024-02-22 00:34 | P23699 | A220 Stress Checkers | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -2.17% | 0 | 143309 | -143309 | 0 | 0 | 0 | 135880 | 0 | 91 | 143309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22% | 19.83% | 19.84% | -2.16% |  | 61.88
1726 | 2024-02-22 00:34 | P22982 | Spirit 2022 - Hugh Sloan | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 88.16% | 91.4% | 82.65% | 0 | -0.01% | 166046 | 146383 | 19663 | 0 | 0 | 0 | 0 | 133795 | 183.74 | 12588 | 15370 | 120986.6667 | 0 | 0 | 8217.17 | 7152.77 | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 35.42
1726 | 2024-02-22 00:34 | P23685 | DAC LUC Support and Recompliance | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  |  | 20.34% | 171.7% | 0.0002276% | 0 | 1.54% | 720000 | 146429 | 573571 | 0 | 0 | 0 | 0 | 251427 | 48 | -104998 | 301712 | 0.33333 | 301712.4 | 0 | 0 | 0 | 0 | 28% | 29.54% | 29.54% | 1.54% |  | 63.2
1726 | 2024-02-22 00:34 | P22954 | Technical Support Step 1 | Owain Jones | HUV | HUARUI SPIRIT AEROSPACE MANUFACT | ME | Level 2 | REIM |  |  |  |  | 94.81% | 58.01% | 58.01% | 0 | 0.31% | 155501 | 147432 | 8069 | 0 | 23043 | 23043 | 0 | 85525 | 61906.09 | 61906 | 0 | 85525 | 0 | 0 | 0 | 0 | 0 | 30% | 30.31% | 0% | -30% |  | 60.79
1726 | 2024-02-22 00:34 | P23386 | Software Development - BMS | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 98.78% | 95.49% | 88.63% | 0 | 4.31% | 149650 | 147823 | 1827 | 0 | 0 | 0 | 0 | 141151 | 48.87 | 6673 | 12161 | 131016.8333 | 0 | 12161.22 | 0 | 0 | 0 | 18% | 22.31% | 22.61% | 4.61% |  | 78.5
1726 | 2024-02-22 00:34 | P23550 | Tempest Composites | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  |  | 100.2% | 99.83% | 67.28% | 24179.64 | 5.26% | 149495 | 149755 | -260 | 0 | 0 | 0 | 0 | 149495 | 176.04 | 260 | 58496 | 100748.3333 | 27760.26 | 6555.8 | 0 | 24179.64 | 24179.64 | 26% | 31.26% | 35.49% | 9.49% |  | 61.6
1726 | 2024-02-22 00:34 | P23464 | A220 Project X Design Offload | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 84.98% | 86.96% | 65.25% | 27862.8 | -3.73% | 180400 | 153295 | 27105 | 0 | 0 | 0 | 0 | 133307 | 148.31 | 19988 | 39945 | 100019.5 | 0 | 12082.44 | 27862.8 | 0 | 27862.8 | 21% | 17.27% | 17.34% | -3.66% |  | 42.89
1726 | 2024-02-22 00:34 | P22440 | Spirit Managed Service - F&DT and Static Approval | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 3 |  |  | 88.56% | 92.56% | 92.56% | 0 | 11.51% | 173500 | 153656 | 19844 | 0 | 52115 | 55720 | 0 | 142225 | 13717.36 | 11431 | 0 | 142225 | 0 | 0 | 0 | 0 | 0 | 0% | 11.51% | 0% | 0% |  | 44.73
1726 | 2024-02-22 00:34 | P23508 | Verification and Validation | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 77.47% | 92.71% | 81.29% | 0 | 11.26% | 212950 | 164968 | 47982 | 0 | 0 | 0 | 0 | 152938 | 50.96 | 12030 | 22608 | 134098 | 0 | 22608 | 0 | 0 | 0 | 24% | 35.26% | 35.93% | 11.93% |  | 78.5
1726 | 2024-02-22 00:34 | P23506 | ASTER Mid-Life Refurbishment Project Manager | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 74.03% | 94.76% | 83.88% | 0 | 0.95% | 224900 | 166486 | 58414 | 0 | 2806 | 2806.41 | 0 | 157759 | 53.58 | 8727 | 21730 | 139650.6667 | 2523.88 | 19206 | 0 | 0 | 0 | 25% | 25.95% | 26.08% | 1.08% |  | 110
1726 | 2024-02-22 00:34 | P23629 | F35 FTI | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level NC | REIM | [5 empty] | 87.32% | 72.12% | 0 | -0.35% | 0 | 169494 | -169494 | 0 | 0 | 0 | 0 | 148010 | 42.07 | 21484 | 30935 | 122230.8333 | 30934.91 | 0 | 0 | 0 | 0 | 31% | 30.65% | 29.34% | -1.66% |  | 62.01
1726 | 2024-02-22 00:34 | P23505 | EXP-022 Meteor TBUS T&E support | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 71.13% | 93.15% | 30.06% | 0 | -0.67% | 246744 | 175505 | 71239 | 0 | 0 | 0 | 0 | 163491 | 256.39 | 12015 | 132886 | 52752.6667 | 0 | 132885.54 | 0 | 0 | 0 | 20% | 19.33% | 15.67% | -4.33% |  | 89.83
1726 | 2024-02-22 00:34 | P23373 | Raytheon Michael Bellini | Natalie Sinclair | RAS | RAYTHEON UNITED KINGDOM LIMITED | EES | Level NC | REIM |  |  |  |  | 83.84% | 95.22% | 86.5% | 0 | -8.26% | 214367 | 179718 | 34649 | 0 | 0 | 0 | 0 | 171127 | 49.58 | 8591 | 18798 | 155462 | 18798.37 | 0 | 0 | 0 | 0 | 45% | 36.74% | 37.63% | -7.37% |  | 91.61
1726 | 2024-02-22 00:34 | P23242 | Physical Architecture & System Engineering Support | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM | 2024-02-28 | 16 |  |  | 60.65% | 94.88% | 90.18% | 0 | 9.67% | 305459 | 185274 | 120185 | 0 | 776 | 775.55 | 0 | 175794 | 55.89 | 9480 | 10456 | 167080.6667 | 0 | 10456.2 | 0 | 0 | 0 | 15% | 24.67% | 7.77% | -7.23% |  | 78.17
1726 | 2024-02-22 00:34 | P23524 | Bombardier Regional Jets (BRJ) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 130.8% | 56.89% | 44.32% | 25157.41 | -4.43% | 146288 | 191312 | -45024 | 0 | 0 | 0 | 46750 | 108838 | 148.45 | 82473 | 28851 | 84795.5 | 0 | 3694.07 | 25157.41 | 0 | 25157.41 | 18% | 13.57% | 17.17% | -0.83% |  | 43.92
1726 | 2024-02-22 00:34 | P23008 | Spirit Shorts Project Rachel | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 85.87% | 91.32% | 87.38% | 0 | -7.7% | 228880 | 196531 | 32349 | 0 | 0 | 0 | 0 | 179473 | 200.14 | 17058 | 9293 | 171728.8333 | 0 | 9292.8 | 0 | 0 | 0 | 13% | 5.3% | 0.31% | -12.69% |  | 46.04
1726 | 2024-02-22 00:34 | P23019 | EXP034-B Actuator Development | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 103.1% | 89.91% | 89.91% | 0 | -14.64% | 215541 | 222216 | -6675 | 0 | 12298 | 12297.9 | 0 | 199797 | 126.7 | 5442 | 0 | 199797 | 0 | 0 | 0 | 0 | 0 | 34% | 19.36% | 35.7% | 1.7% |  | 58.45
1726 | 2024-02-22 00:34 | P23472 | Tempest Wing Design | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 43.68% | 121.8% | 96.68% | 0 | -19.86% | 483870 | 211367 | 272503 | 0 | 195488 | 206400 | 0 | 257532 | 12 | -46164 | 63812 | 204355.3333 | 32753.16 | 31059.04 | 0 | 0 | 0 | 23% | 3.14% | 14.72% | -8.28% |  | 46.74
1726 | 2024-02-22 00:34 | P22798 | CO2MAP MGSE | Harry James Kellett | DTW | THALES ALENIA SPACE UK (60DAYS) | EES | Level 2 | REIM | 2023-11-08 | 1 |  |  | 85.75% | 105% | 105% | 0 | -3.47% | 252086 | 216158 | 35928 | 0 | 0 | 0 | 0 | 227053 | 0.26 | 0 | 0 | 227053 | 0 | 0 | 0 | 0 | 0 | 29% | 25.53% | 100% | 71% |  | 50.31
1726 | 2024-02-22 00:34 | P23316 | Model Factory IL and AW | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX | 2024-01-12 | 2 |  |  | 88.13% | 104.1% | 96.46% | 0 | 2.44% | 250000 | 220328 | 29672 | 0 | 0 | 0 | 0 | 229409 | 62.28 | 0 | 20249 | 212534.8333 | 0 | 0 | 20248.8 | 0 | 0 | 30% | 32.44% | 44.5% | 14.5% |  | 45.31
1726 | 2024-02-22 00:34 | P23603 | Typhoon IMDLR | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 76.07% | 0% | 0% | 0 | 2.16% | 305067 | 232074 | 72993 | 0 | 0 | 0 | 4271.91 | 0 | 258.99 | 232074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29% | 31.16% | 32.77% | 3.77% |  | 57.67
1726 | 2024-02-22 00:34 | P23650 | MBDA Recruitment Management costs | Brian Maddrell | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 28.54% | 0 | 240972 | -240972 | 0 | 0 | 0 | 266000 | 0 | 116.06 | 240972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | 31.54% | 28.64% | 25.64% |  | 82.3
1726 | 2024-02-22 00:34 | P23255 | BAE Tempest WP 1 Circuits | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | 2023-10-20 | 0 |  |  | 70.38% | 99.34% | 99.34% | 0 | -2.72% | 355782 | 250395 | 105387 | 0 | 1654 | 1654.32 | 0 | 248740 | 0.38 | 0 | 0 | 248740 | 0 | 0 | 0 | 0 | 0 | 31% | 28.28% | 100% | 69% |  | 50.3
1726 | 2024-02-22 00:34 | P23317 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX | 2024-01-12 | 2 |  |  | 95.89% | 104.3% | 98.16% | 0 | 4.38% | 251800 | 241447 | 10353 | 0 | 0 | 0 | 0 | 251800 | 65.31 | 0 | 17760 | 237000 | 0 | 0 | 17760 | 0 | 0 | 25% | 29.38% | 52.32% | 27.32% |  | 36.29
1726 | 2024-02-22 00:34 | P23007 | EXP-006A - Brimstone 3 | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 63.14% | 96.36% | 92.05% | 0 | -3.27% | 406450 | 256620 | 149830 | 0 | 0 | 0 | 0 | 247278 | 60.12 | 9312 | 13282 | 236209.6667 | 3485.4 | 9796.8 | 0 | 0 | 0 | 25% | 21.73% | 29.94% | 4.94% |  | 69.34
1726 | 2024-02-22 00:34 | P21463 | Safety & Monitoring Systems at DM Beith & Gosport | Harry James Kellett | BXW | MOD | EES | Level 2 | FIX |  |  |  |  | 77.26% | 129.4% | 129.4% | 0 | -26.8% | 349405 | 269966 | 79439 | 0 | 56284 | 66687.57 | 21721 | 349387 | 0 | -79421 | 0 | 349387 | 0 | 0 | 0 | 0 | 0 | 48% | 21.2% | 43.42% | -4.58% |  | 52.91
1726 | 2024-02-22 00:34 | P23308 | NATO JEWCS | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  |  | 79.59% | 96.35% | 83.07% | 0 | -3.32% | 356307 | 283594 | 72713 | 0 | 614 | 613.89 | 0 | 273254 | 136.38 | 10340 | 45213 | 235576.5 | 45213.08 | 0 | 0 | 0 | 0 | 24% | 20.68% | 12.75% | -11.25% |  | 75.81
1726 | 2024-02-22 00:34 | P23617 | Tempest Composites WP2 | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  |  | 120.8% | 27.93% | 3.451% | 29536.68 | 3.85% | 244405 | 295179 | -50774 | 0 | 0 | 0 | 50000 | 82447 | 204.64 | 212732 | 86711 | 10187.8333 | 28565.94 | 28608.29 | 0 | 29536.68 | 29536.68 | 30% | 33.85% | 34.04% | 4.04% |  | 62.32
1726 | 2024-02-22 00:34 | P23045 | Shotgun Adaptors - 10 Sets | Harry James Kellett | BDW | MBDA UK LIMITED | EES | Level 2 | FIX |  |  |  |  | 74.73% | 133.8% | 95.15% | 0 | -19.12% | 399276 | 298392 | 100884 | 0 | 214430 | 214551.21 | 0 | 399276 | 664.47 | -100884 | 138421 | 283925.1667 | 138420.73 | 0 | 0 | 0 | 0 | 29% | 9.88% | 0% | -29% |  | 55.76
1726 | 2024-02-22 00:34 | P22515 | Shorts A220 100/300 ALI Phase III | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 78.51% | 94.57% | 90.71% | 0 | 1.15% | 400629 | 314540 | 86089 | 0 | 3451 | 3450.98 | 0 | 297465 | 130.54 | 17074 | 14584 | 285311.6667 | 0 | 14583.89 | 0 | 0 | 0 | 10% | 11.15% | 14.11% | 4.11% |  | 40.36
1726 | 2024-02-22 00:34 | P22953 | Spirit Shorts eVTOL | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-05-08 | 1 |  |  | 103.1% | 79.36% | 79.36% | 0 | -6.74% | 324272 | 334484 | -10212 | 0 | 66697 | 67387.9 | 0 | 265432 | 179.02 | 69052 | 0 | 265432 | 0 | 0 | 0 | 0 | 0 | 17% | 10.26% | 0% | -17% |  | 46.19
1726 | 2024-02-22 00:34 | P22842 | ME Support (Aim Altitude) | James Montgomery | AVI | AIM ALTITUDE UK LIMITED | ME | Level 3 | FIX | 2023-06-14 | 4 |  |  | 99.31% | 100.5% | 86.63% | 57290.84 | 0.49% | 346294 | 343918 | 2376 | 0 | 2910 | 2909.86 | 0 | 345673 | 55184.93 | -1755 | 57291 | 297930.5 | 0 | 0 | 0 | 57290.84 | 57290.84 | 13% | 13.49% | 0% | -13% |  | 46.3
1726 | 2024-02-22 00:34 | P23694 | Systems Portfolio EXP-011a | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 53.39% | 79.82% | 59.47% | 0 | 3.06% | 648493 | 346256 | 302237 | 0 | 158 | 157.75 | 0 | 276367 | 49.21 | 69889 | 84550 | 205908.6667 | -11906.7 | 96456.46 | 0 | 0 | 0 | 21% | 24.06% | 17.84% | -3.16% |  | 90.08
1726 | 2024-02-22 00:34 | P22391 | GE System Engineering support | Vinayakumar Sugur | GEE | EXPERIS LIMITED | EES | Level NC | REIM |  |  |  |  | 82.01% | 98.14% | 97.5% | 0 | 0.13% | 434434 | 356261 | 78173 | 0 | 0 | 0 | 0 | 349621 | 70.77 | 6640 | 2719 | 347355.1667 | 2718.61 | 0 | 0 | 0 | 0 | 6% | 6.13% | 6.09% | 0.09% |  | 57.33
1726 | 2024-02-22 00:34 | P23023 | Spirit Shorts R Foster/M Gourley | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  |  | 82.61% | 106.3% | 99.47% | 0 | -19.98% | 416652 | 344187 | 72465 | 0 | 188776 | 216366 | 0 | 365804 | 56.32 | -7106 | 28129 | 342363.1667 | 11919.83 | 16209.44 | 0 | 0 | 0 | 27% | 7.02% | 9.88% | -17.12% |  | 29.53
1726 | 2024-02-22 00:34 | P23531 | BAe Systems F35 MRB Support | Andrew Houghton | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM | [5 empty] | 77.01% | 69.79% | 0 | 2.78% | 0 | 382974 | -382974 | 0 | 287 | 287.44 | 0 | 294944 | 83.48 | 88029 | 33194 | 267282.3333 | 33193.82 | 0 | 0 | 0 | 0 | 25% | 27.78% | 33.44% | 8.44% |  | 59.16
1726 | 2024-02-22 00:34 | P23520 | FCAS AP Portfolio Systems | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 49.39% | 91.01% | 82.13% | 0 | -6.65% | 810821 | 400504 | 410317 | 0 | 320 | 319.5 | 0 | 364501 | 51.49 | 36003 | 42698 | 328919.3333 | 248.4 | 42449.86 | 0 | 0 | 0 | 22% | 15.35% | 17.61% | -4.39% |  | 79.43
1726 | 2024-02-22 00:34 | P23432 | Spirit Belfast MRB On-Site Support (Mon & Clear) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 65.77% | 125.6% | 96.58% | 89754.6 | -11.53% | 449545 | 295665 | 153880 | 0 | 295665 | 451827.33 | 0 | 371466 | 92.07 | 36200 | 103100 | 285549.3333 | 0 | 13345.8 | 12363 | 77391.6 | 89754.6 | 39% | 27.47% | 0% | -39% |  | 0
1726 | 2024-02-22 00:34 | P23554 | Dornier Seawings 328 2023 H2 Support | Steven Lawton | DAX | EXPLEO GERMANY GMBH (EC) | MPE | Level 2 | REIM |  |  |  |  | 86.16% | 92.62% | 86.87% | 0 | 7.9% | 474542 | 408843 | 65699 | 0 | 3551 | 3550.65 | 0 | 378685 | 51.61 | 30158 | 28236 | 355155 | 28236.25 | 0 | 0 | 0 | 0 | 21% | 28.9% | 32.28% | 11.28% |  | 67.57
1726 | 2024-02-22 00:34 | P23320 | Lifing Services DACs | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX | 2024-01-12 | 2 |  |  | 95.56% | 104.6% | 97.44% | 0 | 3.07% | 413300 | 394956 | 18344 | 0 | 0 | 0 | 0 | 413300 | 59.49 | -1 | 34139 | 384850.8333 | 0 | 0 | 34138.8 | 0 | 0 | 26% | 29.07% | 55.77% | 29.77% |  | 33.15
1726 | 2024-02-22 00:34 | P22906 | Spirit Shorts - MRB JD Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  |  | 69.35% | 90.7% | 69.94% | 13497.6 | -7.59% | 614770 | 426346 | 188424 | 0 | 0 | 0 | 0 | 386688 | 271.88 | 47659 | 106200 | 298188 | 0 | 92702.52 | 13497.6 | 0 | 13497.6 | 13% | 5.41% | 3.87% | -9.13% |  | 36.84
1726 | 2024-02-22 00:34 | P23366 | Business Analyst Support | Peter Williams | BDZ | MBDA UK LIMITED | DET | Level NC | REIM |  |  |  |  | 33.09% | 257% | 200.5% | 0 | 13.44% | 583200 | 192994 | 390206 | 0 | 192993 | 416921.86 | 0 | 496000 | 54.45 | -49871 | 130752 | 387040 | 80064 | 50688 | 0 | 0 | 0 | 43% | 56.44% | 31.06% | -11.94% |  | 0.01
1726 | 2024-02-22 00:34 | P23473 | Tempest Vertical Tail | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 62.51% | 97.67% | 76.82% | 0 | -2.66% | 723866 | 452458 | 271408 | 0 | 88725 | 100425 | 0 | 441918 | 68.93 | 10540 | 113181 | 347600.5 | 58489.72 | 54691.04 | 0 | 0 | 0 | 24% | 21.34% | 25.3% | 1.3% |  | 62.42
1726 | 2024-02-22 00:34 | P23140 | Spirit Shorts A220 MLG Stress Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  |  | 71.95% | 86.52% | 77.12% | 48343.2 | -15.3% | 595746 | 428632 | 167114 | 0 | 20870 | 87811.88 | 0 | 370857 | 155.41 | 82774 | 48343 | 330571.1667 | 0 | 0 | 0 | 48343.2 | 48343.2 | 32% | 16.7% | 13.29% | -18.71% |  | 47.31
1726 | 2024-02-22 00:34 | P23372 | BAE Carbon Tooling Off-load | Gary Kempster | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  |  | 165.3% | 56.3% | 56.3% | 0 | -4.12% | 276718 | 457433 | -180715 | 0 | 0 | 0 | 197460.8 | 257522 | 293.02 | 199912 | 0 | 257522 | 0 | 0 | 0 | 0 | 0 | 27% | 22.88% | 21.55% | -5.45% |  | 53.57
1726 | 2024-02-22 00:34 | P22652 | L3 - Saftey Engineering | Sean Simmons | LHW | L3HARRIS MAPPS LIMITED | EES | Level NC | FIX |  |  |  |  | 95.63% | 86.69% | 86.69% | 0 | 5.66% | 523390 | 500498 | 22892 | 0 | 0 | 0 | 0 | 433883 | 79938 | 66615 | 0 | 433883 | 0 | 0 | 0 | 0 | 0 | 21% | 26.66% | 25.88% | 4.88% |  | 83.05
1726 | 2024-02-22 00:34 | P23323 | CNC-CMM Programming Support | Andrew Houghton | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  |  | 82.43% | 83.88% | 71.29% | 0 | -3.49% | 617810 | 509276 | 108534 | 0 | 13662 | 13661.56 | 0 | 427206 | 130.38 | 82069 | 76956 | 363076 | 76955.66 | 0 | 0 | 0 | 0 | 32% | 28.51% | 38.77% | 6.77% |  | 56.91
1726 | 2024-02-22 00:34 | P23001 | Spirit Shorts A220 Design | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 116.9% | 71.25% | 68.78% | 0 | -3.92% | 439560 | 513910 | -74350 | 0 | 0 | 0 | 65953.2 | 366148 | 319.76 | 147762 | 15203 | 353478.8333 | 0 | 15202.56 | 0 | 0 | 0 | 25% | 21.08% | 12.33% | -12.67% |  | 43.62
1726 | 2024-02-22 00:34 | P23281 | Systems Portfolio | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM | 2024-02-28 | 1 |  |  | 44.43% | 97.31% | 97.19% | 0 | -17.1% | 1177697 | 523237 | 654460 | 0 | 2133 | 2133.28 | 0 | 509180 | 17523.23 | 13968 | 762 | 508545 | 761.53 | 0 | 0 | 0 | 0 | 25% | 7.9% | 0% | -25% |  | 70.48
1726 | 2024-02-22 00:34 | P23602 | EXP-025 Portfolio Software Engineering Support | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 41.03% | 84% | 48.32% | 0 | -0.47% | 1327080 | 544530 | 782550 | 0 | 824 | 1015.89 | 0 | 457393 | 85.24 | 87137 | 233130 | 263118 | 6122.76 | 227007.26 | 0 | 0 | 0 | 24% | 23.53% | 23.77% | -0.23% |  | 82.65
1726 | 2024-02-22 00:34 | P21138 | D&A Vibration Reduc Damping Struc FOGV Components | Steven Lawton | ATC | AECC SICHUAN GAS TURBINE | MPE | Level 1 | FIX | 2022-09-07 | 1 |  |  | 96.12% | 104% | 104% | 0 | -3.44% | 569346 | 547228 | 22118 | 0 | 75182 | 75181.75 | 0 | 569346 | 0 | 0 | 0 | 569346 | 0 | 0 | 0 | 0 | 0 | 36% | 32.56% | 0.08% | -35.92% |  | 73.95
1726 | 2024-02-22 00:34 | P23426 | BAE Tempest WP 3 Harness Maturation | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 65.39% | 90.48% | 69.58% | 0 | -5.8% | 884012 | 578096 | 305916 | 0 | 213 | 213.34 | 0 | 523063 | 83.3 | 55033 | 144962 | 402261.3333 | 66565.09 | 78396.7 | 0 | 0 | 0 | 33% | 27.2% | 29.63% | -3.37% |  | 51.12
1726 | 2024-02-22 00:34 | P23219 | Tornado Air 800 Engineering Support | Richard Brook | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 3 | REIM |  |  |  |  | 95.46% | 98.51% | 98.51% | 0 | 1.46% | 615046 | 587098 | 27948 | 0 | 459 | 459.21 | 0 | 578373 | 10470.24 | 8725 | 0 | 578373 | 0 | 0 | 0 | 0 | 0 | 31% | 32.46% | 0% | -31% |  | 81.76
1726 | 2024-02-22 00:34 | P23605 | Typhoon Work Package 2 Continuation | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM |  |  |  |  | 186.1% | 0% | 0% | 0 | 0.21% | 350520 | 652386 | -301866 | 0 | 4054 | 4054 | 277015 | 0 | 195.4 | 652386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 28.21% | 29.04% | 1.04% |  | 55.72
1726 | 2024-02-22 00:34 | P22790 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 2 | REIM |  |  |  |  | 194.5% | 90.44% | 90.44% | 0 | 1.37% | 352240 | 685262 | -333022 | 0 | 1612 | 1611.52 | 515246 | 619744 | 41098.04 | 34248 | 0 | 619744 | 0 | 0 | 0 | 0 | 0 | 13% | 14.37% | 0% | -13% |  | 45.06
1726 | 2024-02-22 00:34 | P23451 | BAE Tempest - DFM-ASO Planning | Andrew Houghton | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  |  | 72.61% | 59.23% | 22.05% | 0 | -3.41% | 953905 | 692596 | 261309 | 0 | 0 | 0 | 0 | 410202 | 185.33 | 282395 | 308940 | 152752 | 0 | 308939.76 | 0 | 0 | 0 | 28% | 24.59% | 27.2% | -0.8% |  | 53.56
1726 | 2024-02-22 00:34 | P23321 | EHM Cloud Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX | 2024-01-29 | 4 |  |  | 89.76% | 111.4% | 103.8% | 0 | 3.07% | 839969 | 753975 | 85994 | 0 | 0 | 0 | 0 | 839969 | 62.83 | 0 | 69002 | 782467.3333 | 0 | 0 | 69002.4 | 0 | 0 | 28% | 31.07% | 60.18% | 32.18% |  | 49.95
1726 | 2024-02-22 00:34 | P23105 | Raytheon Supply Engineering Support | Natalie Sinclair | RAY | RAYTHEON UNITED KINGDOM LIMITED | MPE | Level 3A | REIM | 2023-07-13 | 3 |  |  | 76.96% | 94.49% | 90.07% | 0 | -2.02% | 1205008 | 927395 | 277613 | 0 | 0 | 0 | 0 | 876292 | 107644.5 | 48740 | 49157 | 835327.8333 | 49156.8 | 0 | 0 | 0 | 0 | 26% | 23.98% | 100% | 74% |  | 48.97
1726 | 2024-02-22 00:34 | P22350 | EMP 2020-2021 | Natalie Sinclair | ARY | GUIDANT GROUP (trading name) | PCPR | Level NC | REIM |  |  |  |  | 100.9% | 99.54% | 95.01% | 0 | -1.88% | 930212 | 938574 | -8362 | 0 | 400 | 400 | 0 | 934216 | 63.71 | 4358 | 50977 | 891735.1667 | 39833.59 | 11143.64 | 0 | 0 | 0 | 32% | 30.12% | 29.25% | -2.75% |  | 44.05
1726 | 2024-02-22 00:34 | P23117 | BAE Typhoon Eng Support | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 107.6% | 88.52% | 88.52% | 0 | -1.44% | 950772 | 1022826 | -72054 | 0 | 19090 | 21165.02 | 69773.84 | 905368 | 108434.61 | 90362 | 0 | 905368 | 0 | 0 | 0 | 0 | 0 | 30% | 28.56% | 0% | -30% |  | 52.3
1726 | 2024-02-22 00:34 | P23519 | Mechanical and Electrical Design Eng Support | Dushan Fernando | BAX | SAFRAN SEATS GB LIMITED | MPE | Level 2 | REIM |  |  |  |  | 60.9% | 74.68% | 74.68% | 0 | -1.39% | 1807261 | 1100621 | 706640 | 0 | 727 | 727 | 0 | 821977 | 65.48 | 278644 | 0 | 821977 | 0 | 0 | 0 | 0 | 0 | 33% | 31.61% | 32.32% | -0.68% |  | 56.61
1726 | 2024-02-22 00:34 | P23292 | BAE Tempest WP 4 AV Trays | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 73.65% | 93.4% | 77.83% | 0 | 2.17% | 1498284 | 1103532 | 394752 | 0 | 0 | 0 | 0 | 1030718 | 83.52 | 72814 | 206213 | 858873.8333 | 104014.85 | 102197.8 | 0 | 0 | 0 | 32% | 34.17% | 34.23% | 2.23% |  | 53.13
1726 | 2024-02-22 00:34 | P22671 | Spirit Shorts Pylon and Fairing Package | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX | 2023-05-03 | 4 |  |  | 105% | 95.26% | 95.26% | 0 | -7.21% | 1198495 | 1258071 | -59576 | 0 | 106495 | 174907.39 | 0 | 1198495 | 2544.39 | 2120 | 0 | 1198495 | 0 | 0 | 0 | 0 | 0 | 20% | 12.79% | 0% | -20% |  | 45.4
1726 | 2024-02-22 00:34 | P23152 | Project Aragon - Design and Stress Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  |  | 92.22% | 60.47% | 60.47% | 0 | -9.37% | 1307861 | 1206072 | 101789 | 0 | 0 | 0 | 0 | 729296 | 287.95 | 476776 | 0 | 729296 | 0 | 0 | 0 | 0 | 0 | 39% | 29.63% | 31.33% | -7.67% |  | 51.88
1726 | 2024-02-22 00:34 | P23411 | Agile & Scrum Delivery Service | Peter Williams | BDZ | MBDA UK LIMITED | DET | Level 2 | REIM | 2023-08-14 | 1 |  |  | 36.3% | 170.5% | 170.5% | 0 | 13.08% | 2487000 | 902904 | 1584096 | 0 | 894179 | 2337284.55 | 0 | 1539600 | 19368.95 | 16141 | 0 | 1539600 | 0 | 0 | 0 | 0 | 0 | 29% | 42.08% | 0% | -29% |  | 74.57
1726 | 2024-02-22 00:34 | P23315 | DAC LUC BAU and Service Workbench | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX | 2024-02-16 | 125 |  |  | 85.17% | 117.4% | 105.3% | 0 | 3.51% | 1573630 | 1340192 | 233438 | 0 | 180 | 180.3 | 0 | 1573630 | 40.11 | -13236 | 195596 | 1410633.3333 | 0 | 0 | 195596.4 | 0 | 0 | 28% | 31.51% | 45.71% | 17.71% |  | 52.35
1726 | 2024-02-22 00:34 | P23435 | Andy Baker Portfolio | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 48.03% | 83.95% | 76.69% | 0 | -7.51% | 3377457 | 1622322 | 1755135 | 0 | 2353 | 2352.57 | 0 | 1361987 | 68.43 | 260336 | 141345 | 1244199.5 | 4794.7 | 136550.72 | 0 | 0 | 0 | 25% | 17.49% | 20.85% | -4.15% |  | 79.45
1726 | 2024-02-22 00:34 | P23006 | Spirit Shorts A350 Freighter Toulouse | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 145.6% | 81.88% | 81.88% | 0 | 18.92% | 1035746 | 1508361 | -472615 | 0 | 1086670 | 1708220.2 | 0 | 1235101 | 288.37 | 584534 | 0 | 1235101 | 0 | 0 | 0 | 0 | 0 | 5% | 23.92% | 37.12% | 32.12% |  | 47.76
1726 | 2024-02-22 00:34 | P22278 | TAI Supply Engineers to Ankara | Natalie Sinclair | TAI | TUSAS-TURK HAVACILIK VE UZAY | MPE | Level 3A | REIM |  |  |  |  | 19.23% | 472.1% | 465.5% | 0 | -15.52% | 2105282 | 404751 | 1700531 | 0 | 49400 | 49400.29 | 0 | 1910696 | 143.67 | -12539 | 32000 | 1884029.3333 | 16000 | 16000 | 0 | 0 | 0 | 95% | 79.48% | 72.55% | -22.45% |  | 34.28
1726 | 2024-02-22 00:34 | P23257 | BAE Tempest WP 5 Centre Fuselage | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 95.98% | 98.38% | 90.36% | 0 | -5.76% | 2106861 | 2022262 | 84599 | 0 | 78100 | 78100 | 0 | 1989561 | 73.69 | 32701 | 194722 | 1827292.6667 | 88762 | 105959.8 | 0 | 0 | 0 | 33% | 27.24% | 28.72% | -4.28% |  | 61.05
1726 | 2024-02-22 00:34 | P23175 | BAe Aero Typhoon Package 2 | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM |  |  |  |  | 103.8% | 96.32% | 96.32% | 0 | -1.63% | 1984265 | 2060012 | -75747 | 0 | 57678 | 86030.82 | 15444.64 | 1984257 | 84731.75 | 70610 | 0 | 1984257 | 0 | 0 | 0 | 0 | 0 | 29% | 27.37% | 0% | -29% |  | 51.76
1726 | 2024-02-22 00:34 | P23207 | A350 Approvers - Design and Stress Support | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  |  | 94.73% | 78.23% | 53.86% | 169776.21 | -4.27% | 2183628 | 2068562 | 115066 | 0 | 18126 | 18233.03 | 0 | 1618138 | 127.02 | 450424 | 604757 | 1114173.8333 | 329610.17 | 105370.2 | 0 | 169776.21 | 169776.21 | 23% | 18.73% | 20.27% | -2.73% |  | 54.73
1726 | 2024-02-22 00:34 | P19020 | Spirit Concessions - 2018 | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2024-01-23 | 3 |  |  | 90.82% | 111.8% | 107% | 99792.83 | 2.09% | 1914847 | 1739018 | 175829 | 0 | 44318 | 44317.61 | 15178.88 | 1944711 | 3178.74 | 196987 | 99793 | 1861550.1667 | 0 | 0 | 0 | 99792.83 | 99792.83 | 25% | 27.09% | 10.92% | -14.08% |  | 40.87
1726 | 2024-02-22 00:34 | P23179 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX |  |  |  |  | 129.2% | 85.15% | 82.33% | 35500.91 | -9.31% | 1955411 | 2527164 | -571753 | 0 | 156991 | 248243.92 | 492000 | 2151812 | 320.41 | 375352 | 85535 | 2080532.8333 | 40538.4 | 9496.08 | 0 | 35500.91 | 35500.91 | 22% | 12.69% | 18.29% | -3.71% |  | 44.4
1726 | 2024-02-22 00:34 | P23487 | Tornado Air 800 Engineering Support | Richard Brook | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 2 | FIX |  |  |  |  | 103.1% | 84.24% | 78.08% | 0 | -4.4% | 2525468 | 2604848 | -79380 | 0 | 0 | 0 | 196775 | 2194207 | 73.07 | 410640 | 192507 | 2033784.5 | 192507.32 | 0 | 0 | 0 | 0 | 40% | 35.6% | 38.27% | -1.73% |  | 78.71
1726 | 2024-02-22 00:34 | P19731 | Hapri HPC Rear Bearing Housing PDR & CDR | Steven Lawton | ATC | AECC Hunan Aviation Powerplant | MPE | Level 1 | FIX |  |  |  |  | 99.53% | 100.5% | 87.91% | 447000 | -15.32% | 2980000 | 2965957 | 14043 | 0 | 358408 | 512832.98 | 0 | 2980000 | 959.85 | -239043 | 447000 | 2607500 | 0 | 0 | 447000 | 0 | 447000 | 38% | 22.68% | 22.06% | -15.94% |  | 64.86
Extend Table

## AP2-4
WIP No | Date Created | Project ID | Project Description | Project Manager | Department Id | Client | CBU | Complexity | Type | Stop Booking Hrs | Closing Project: Action(s) to close | RAG | Approx. PO Burndown (weeks) | Turnover vs Contract Value | Invoice To Date vs Turnover | Cash in vs Turnover | Open Amount Overdue | Actual PM% to Baseline PM% delta | Contract Value | Total Project Turnover | Contract Value - Total Turnover | Run Rate (based on total turnover) | Total BOI Spend to Date | Total Committed PO (supplier/best shore) | Current AA in PT3 | Invoiced To Date | DSO | Unbilled (WIP) | Total Open Amount | Cash in (Invoiced - (Open amount -VAT)) | Debt <=30 Days | Debt 31 - 60 Days | Debt 61 - 90 Days | Debt >= 90 Days | Open Amount Overdue2 | Baseline Project Margin | Project To Date (PTD) PM | Year to Date (YTD) PM | YTD Delta Actual PM% to BPM% | Forecast PM at Completion (Manual input from PTT) | Average Sale Rate | CSat score for last quarter (Manual input from PTT) | Comments and Actions | Judged income adjustment at completion | Profit to take now | Provision required now | Fully Traded | Last Months Comments and Actions
1727 | 2024-02-29 00:36 | P23811 | Spirit T300 MRB Concessions | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [7 empty] | 0 | -21% | 0 | 0 | 0 | 0 | 0 | 0 | 34639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21% | 0% | 0% | -21% |  | 0
1727 | 2024-02-29 00:36 | P23822 | FCASW Requirements Management | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 3 | REIM | [7 empty] | 0 | -16% | 0 | 0 | 0 | 0 | 0 | 0 | 35930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16% | 0% | 0% | -16% |  | 0
1727 | 2024-02-29 00:36 | P23637 | MBSE Proposal | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 | 0 | 0 | 0 | 49980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35% | 0% | 0% | -35% |  | 0
1727 | 2024-02-29 00:36 | P23823 | EXP-034 Spear 3 Test Equip Requirement Authority | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -14% | 85825 | 0 | 85825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14% | 0% | 0% | -14% |  | 0
1727 | 2024-02-29 00:36 | P23711 | DO NOT USE - RAISED IN ERROR | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0
1727 | 2024-02-29 00:36 | P23717 | GKN Ted Tomblin 2024 | Matthew Tweed | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 10047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0
1727 | 2024-02-29 00:36 | P23552 | FCAS AP Product Technology Development | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -25% | 597871 | 0 | 597871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0% | -25% |  | 0
1727 | 2024-02-29 00:36 | P23585 | Systems Design - Missile Systems, Meteor,Brimstone | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 | 0 | 0 | 0 | 49500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35% | 0% | 0% | -35% |  | 0
1727 | 2024-02-29 00:36 | P23543 | EXP-024 FCAS AP Transformation & Change Enablers | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -26% | 385921 | 0 | 385921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26% | 0% | 0% | -26% |  | 0
1727 | 2024-02-29 00:36 | P23641 | Drawing Triage | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM | 2024-01-25 | 1 |  |  |  | 0% | 0% | 0 | -1043168% | 0 | 10756 | -10756 | 0 | 0 | 0 | 0 | 0 | 0.02 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | -1043168% | 100% | 100% |  | 49
1727 | 2024-02-29 00:36 | P23730 | FLE Project | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -16.79% | 0 | 1120 | -1120 | 0 | 0 | 0 | 24000 | 0 | 55 | 1120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | -16.79% | -16.79% | -16.79% |  | 35
1727 | 2024-02-29 00:36 | P23463 | A220 Wing MaMo Design Checking | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 7.85% | 0 | 1628 | -1628 | 0 | 0 | 0 | 15000 | 0 | 1953.6 | 1628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | 10.85% | 0% | -3% |  | 44
1727 | 2024-02-29 00:36 | P21028 | Rebate Collection (BACC) | David Catchpole | TOO | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | [5 empty] | 0% | 0% | 0 | 0% | 0 | 2680 | -2680 | 0 | 2680 | 2680 | 0 | 0 | 3216 | 2680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0
1727 | 2024-02-29 00:36 | P23578 | ESN Work Package | Hannah Mead | COZ | CHELTON LIMITED | DET | Level 3 | FIX | 2024-01-01 | 0 |  |  | 86.17% | 116.1% | 116.1% | 0 | 35.86% | 4410 | 3800 | 610 | 0 | 0 | 0 | 0 | 4410 | 0 | -610 | 0 | 4410 | 0 | 0 | 0 | 0 | 0 | 24% | 59.86% | 0% | -24% |  | 95
1727 | 2024-02-29 00:36 | P23628 | Design Assurance | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -6.67% | 0 | 3909 | -3909 | 0 | 0 | 0 | 4454.8 | 0 | 4691.09 | 3909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 0.33% | 0% | -7% |  | 15.05
1727 | 2024-02-29 00:36 | P23002 | WoT MAJ Transit Flag Stress | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 30.9% | 323.7% | 323.7% | 0 | 53.84% | 4735 | 1463 | 3272 | 0 | 0 | 2242.5 | 0 | 4735 | 0.6 | 1 | 0 | 4735 | 0 | 0 | 0 | 0 | 0 | 10% | 63.84% | 0% | -10% |  | 45
1727 | 2024-02-29 00:36 | P23740 | Phase 2 - EJ200 ESS EHM Platform Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 3 | FIX |  |  |  |  | 3.214% | 444.5% | -0.002947% | 0 | 0.87% | 175971 | 5655 | 170316 | 0 | 0 | 0 | 0 | 25139 | 55 | -19484 | 30167 | -0.16667 | 30166.8 | 0 | 0 | 0 | 0 | 28% | 28.87% | 28.87% | 0.87% |  | 61.8
1727 | 2024-02-29 00:36 | P23718 | Requalification of EJ200 GSS ESS EHM SW module | Vijayakumara Nanjundappa | ARZ | MTU AERO ENGINES AG | DET | Level 3 | FIX |  |  |  |  | 7.938% | 306.6% | 51.11% | 0 | -3.22% | 74463 | 5911 | 68552 | 0 | 881 | 881.46 | 0 | 18125 | 55 | -12214 | 18125 | 3020.8333 | 18125 | 0 | 0 | 0 | 0 | 28% | 24.78% | 24.78% | -3.22% |  | 80
1727 | 2024-02-29 00:36 | P23742 | Cyber Security Support | Hannah Mead | COZ | CHELTON LIMITED | DET | Level 3 | FIX | [5 empty] | 0% | 0% | 0 | 31.67% | 0 | 8100 | -8100 | 0 | 0 | 0 | 9000 | 0 | 77 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 31.67% | 31.67% | 31.67% |  | 100
1727 | 2024-02-29 00:36 | P23607 | SAFRAN - A330neo Turnover Frame | Gary Kempster | TOO | SAFRAN SEATS GB LIMITED | MPE | Level 3 | FIX |  |  |  |  | 95.68% | 104.5% | 0.001994% | 0 | -19.75% | 8736 | 8359 | 377 | 0 | 0 | 0 | 0 | 8736 | 10030.8 | -377 | 10483 | 0.16667 | 10483.2 | 0 | 0 | 0 | 0 | 23% | 3.25% | 0% | -23% |  | 52
1727 | 2024-02-29 00:36 | P23274 | ME Support (Aim Altitude - Cambridge) | James Montgomery | AVI | AVIC CABIN SYSTEMS (UK) LIMITED | ME | Level 3 | FIX | 2023-08-18 | 0 |  |  | 51.88% | 56.29% | 56.29% | 0 | -0.17% | 17280 | 8964 | 8316 | 0 | 0 | 0 | 0 | 5046 | 4701.24 | 3918 | 0 | 5046 | 0 | 0 | 0 | 0 | 0 | 21% | 20.83% | 0% | -21% |  | 48
1727 | 2024-02-29 00:36 | P23283 | Spirit Tooling Audit | Charidimos Valadakis | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-05-03 | 0 |  |  | 97.23% | 48.57% | 48.57% | 0 | -7.99% | 9910 | 9635 | 275 | 0 | 0 | 0 | 0 | 4680 | 5946.05 | 4955 | 0 | 4680 | 0 | 0 | 0 | 0 | 0 | 7% | -0.99% | 0% | -7% |  | 34.41
1727 | 2024-02-29 00:36 | P23127 | Loft Hall Design Support | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 101% | 99.06% | 99.06% | 0 | -9.55% | 9680 | 9772 | -92 | 0 | 0 | 0 | 0 | 9680 | 110.4 | 92 | 0 | 9680 | 0 | 0 | 0 | 0 | 0 | 41% | 31.45% | 0% | -41% |  | 44
1727 | 2024-02-29 00:36 | P23630 | 2Excel CFD Analysis Support | Dushan Fernando | BAX | STIRLING DYNAMICS LTD | MPE | Level NC | FIX |  |  |  |  | 61.2% | 100% | 100% | 0 | -1.87% | 16195 | 9911 | 6284 | 0 | 0 | 0 | 0 | 9912 | 0 | 0 | 0 | 9912 | 0 | 0 | 0 | 0 | 0 | 26% | 24.13% | 0% | -26% |  | 64.78
1727 | 2024-02-29 00:36 | P23313 | Laser Trim Fixtures | Gary Kempster | TOO | ALKEN ENGINEERING LIMITED | MPE | Level 3 | FIX | 2023-11-20 | 0 |  |  | 89.87% | 111.3% | 111.3% | 0 | 0.53% | 13770 | 12375 | 1395 | 0 | 0 | 0 | 0 | 13770 | 0 | -1395 | 0 | 13770 | 0 | 0 | 0 | 0 | 0 | 17% | 17.53% | 0% | -17% |  | 45
1727 | 2024-02-29 00:36 | P22761 | Red Bull Chassis Spit | James Montgomery | TOO | MANUFAX ENGINEERING LTD | MPE | Level 3 | FIX | 2022-11-15 | 0 |  |  | 72.19% | 96.98% | 96.98% | 0 | 7.92% | 12961 | 9356 | 3605 | 0 | 0 | 0 | 0 | 9073 | 4666.39 | 3889 | 0 | 9073 | 0 | 0 | 0 | 0 | 0 | 23% | 30.92% | 0% | -23% |  | 42.19
1727 | 2024-02-29 00:36 | P23663 | Spirit Tooling Verification and Inspection | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 65.63% | 0% | 0% | 0 | -7.54% | 19820 | 13007 | 6813 | 0 | 0 | 0 | 7392 | 0 | 121.98 | 13007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12% | 4.46% | 4.82% | -7.18% |  | 34.41
1727 | 2024-02-29 00:36 | P23821 | Supply of Safety Engineer | Dinna Elkhalifa | BXW | STIRLING DYNAMICS LTD | EES | Level NC | REIM |  |  |  |  | 38.34% | 100% | 0.003835% | 0 | 20.48% | 34006 | 13038 | 20968 | 0 | 0 | 0 | 0 | 13038 | 73 | 0 | 15645 | 0.5 | 15645.36 | 0 | 0 | 0 | 0 | 0% | 20.48% | 20.48% | 20.48% |  | 55.48
1727 | 2024-02-29 00:36 | P23433 | Cavendish | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 32.81% | 100% | 100% | 0 | -0.34% | 42240 | 13859 | 28381 | 0 | 0 | 0 | 0 | 13859 | 0 | 0 | 0 | 13859 | 0 | 0 | 0 | 0 | 0 | 7% | 6.66% | 0% | -7% |  | 43.93
1727 | 2024-02-29 00:36 | P23350 | Spirit 2023 - Stress Approve Man Serv (DH) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 14.15% | 72.64% | 72.64% | 0 | -0.29% | 97920 | 13860 | 84060 | 0 | 0 | 0 | 0 | 10068 | 4550.4 | 3792 | 0 | 10068 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48
1727 | 2024-02-29 00:36 | P23344 | Spirit A320 Spoilers Support 2023 | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 38.75% | 100% | 100% | 0 | 5.82% | 35786 | 13867 | 21919 | 0 | 0 | 0 | 0 | 13867 | 0 | 0 | 0 | 13867 | 0 | 0 | 0 | 0 | 0 | 7% | 12.82% | 0% | -7% |  | 34.41
1727 | 2024-02-29 00:36 | P23724 | GKN S McConnell 2024 | Matthew Tweed | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  |  | 28.8% | 48.61% | 0% | 0 | 1.51% | 49820 | 14348 | 35472 | 0 | 0 | 0 | 0 | 6975 | 55 | 7373 | 8370 | 0 | 8369.76 | 0 | 0 | 0 | 0 | 19% | 20.51% | 20.51% | 1.51% |  | 49.82
1727 | 2024-02-29 00:36 | P23337 | Spirit 2023 - Steve Grimley | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 25.28% | 100% | 100% | 0 | 0.01% | 56813 | 14362 | 42451 | 0 | 0 | 0 | 0 | 14362 | 0 | 0 | 0 | 14362 | 0 | 0 | 0 | 0 | 0 | 7% | 7.01% | 0% | -7% |  | 30.11
1727 | 2024-02-29 00:36 | P23597 | MRB Onsite support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -10.04% | 0 | 15101 | -15101 | 0 | 9448 | 17381.62 | 24200 | 0 | 91 | 15101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 7.96% | 8.95% | -9.05% |  | 42.5
1727 | 2024-02-29 00:36 | P23598 | MRB Onsite support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -8.38% | 0 | 15961 | -15961 | 0 | 8736 | 14079.58 | 21700 | 0 | 91 | 15961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 9.62% | 10.18% | -7.82% |  | 42.5
1727 | 2024-02-29 00:36 | P23635 | Engineering Services: FAI Support | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 49.9% | 0% | 0% | 0 | -3.4% | 37230 | 18576 | 18654 | 0 | 0 | 0 | 0 | 0 | 182 | 18576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8% | 4.6% | 5.04% | -2.96% |  | 38.7
1727 | 2024-02-29 00:36 | P23343 | Spirit 2023 - John Agnew | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-08-09 | 0 |  |  | 28.56% | 86.27% | 86.27% | 0 | -0.02% | 65120 | 18601 | 46519 | 0 | 0 | 0 | 0 | 16047 | 3064.49 | 2554 | 0 | 16047 | 0 | 0 | 0 | 0 | 0 | 7% | 6.98% | 0% | -7% |  | 34.51
1727 | 2024-02-29 00:36 | P23355 | Spirit Tooling Support 2023 | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-23 | 0 |  |  | 22.93% | 89.03% | 89.03% | 0 | -0.82% | 91800 | 21053 | 70747 | 0 | 0 | 0 | 0 | 18743 | 2773.01 | 2311 | 0 | 18743 | 0 | 0 | 0 | 0 | 0 | 20% | 19.18% | 0% | -20% |  | 44.46
1727 | 2024-02-29 00:36 | P23651 | PMO Spirit | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 24.02% | 0 | 23454 | -23454 | 0 | 0 | 0 | 42680 | 0 | 173.86 | 23454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 24.02% | 23.26% | 23.26% |  | 36
1727 | 2024-02-29 00:36 | P23760 | EXP-033 Systems Engineering Support | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 16.74% | 0% | 0% | 0 | -0.02% | 142300 | 23825 | 118475 | 0 | 0 | 0 | 0 | 0 | 55 | 23825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29% | 28.98% | 28.98% | -0.02% |  | 78.5
1727 | 2024-02-29 00:36 | P23351 | Spirit 2023 - Design Man Serv (KL) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 26.47% | 93.15% | 93.15% | 0 | 0.09% | 93840 | 24840 | 69000 | 0 | 0 | 0 | 0 | 23138 | 2042.4 | 1702 | 0 | 23138 | 0 | 0 | 0 | 0 | 0 | 26% | 26.09% | 0% | -26% |  | 46
1727 | 2024-02-29 00:36 | P23356 | Spirit 2023 - Design Man Serv (AH) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX | 2023-08-09 | 1 |  |  |  | 76.66% | 0.001332% | 23018.4 | 0.48% | 0 | 25023 | -25023 | 0 | 0 | 0 | 25300 | 19182 | 30027.7 | 5841 | 23018 | 0.33333 | 0 | 0 | 0 | 23018.4 | 23018.4 | 18% | 18.48% | 0% | -18% |  | 46
1727 | 2024-02-29 00:36 | P22884 | Spirit Shorts Config Eng | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 66.3% | 100.1% | 100.1% | 0 | 0.56% | 38976 | 25842 | 13134 | 0 | 0 | 0 | 0 | 25863 | 0 | 0 | 0 | 25863 | 0 | 0 | 0 | 0 | 0 | 7% | 7.56% | 0% | -7% |  | 20.3
1727 | 2024-02-29 00:36 | P23354 | Spirit 2023 - Design Man Serv (PC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 27.97% | 99.36% | 99.36% | 0 | 0.48% | 93840 | 26249 | 67591 | 0 | 0 | 0 | 0 | 26082 | 200.38 | 167 | 0 | 26082 | 0 | 0 | 0 | 0 | 0 | 18% | 18.48% | 0% | -18% |  | 46
1727 | 2024-02-29 00:36 | P22756 | A350 FLE Design Checker | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2022-03-23 | 1 |  |  | 68.39% | 119.7% | 119.7% | 0 | 16.46% | 34898 | 23867 | 11031 | 0 | 23867 | 24342.3 | 0 | 28571 | 0.06 | 0 | 0 | 28571 | 0 | 0 | 0 | 0 | 0 | 0% | 16.46% | 0% | 0% |  | 0
1727 | 2024-02-29 00:36 | P23338 | Spirit 2023 - Blair Hainey | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 83.12% | 62.93% | 62.93% | 0 | 4.29% | 34494 | 28672 | 5822 | 0 | 0 | 0 | 0 | 18042 | 132.87 | 10630 | 0 | 18042 | 0 | 0 | 0 | 0 | 0 | 7% | 11.29% | 19.31% | 12.31% |  | 18.28
1727 | 2024-02-29 00:36 | P23458 | Spirit Belfast Tooling Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-08-11 | 0 |  |  | 101.3% | 94.65% | 94.65% | 0 | 8.64% | 30384 | 30785 | -401 | 0 | 0 | 0 | 0 | 29139 | 1974.96 | 1646 | 0 | 29139 | 0 | 0 | 0 | 0 | 0 | 7% | 15.64% | 0% | -7% |  | 42.2
1727 | 2024-02-29 00:36 | P23753 | Tempest Composites Maturation | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | [5 empty] | 0% | 0% | 0 | -24.68% | 0 | 31085 | -31085 | 0 | 0 | 0 | 54398.4 | 0 | 56 | 31085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37% | 12.32% | 12.32% | -24.68% |  | 64.76
1727 | 2024-02-29 00:36 | P23729 | Honda Tooling | Paul Watson | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX | [5 empty] | 0% | 0% | 0 | 5.78% | 0 | 32610 | -32610 | 0 | 0 | 0 | 33167 | 0 | 49 | 32610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 15.78% | 15.78% | 5.78% |  | 42.2
1727 | 2024-02-29 00:36 | P23365 | GKN 777x Lip Skin Fixture | Steven Lawton | TOO | GKN AEROSPACE SERVICES LTD | MPE | Level 3 | FIX | 2023-10-12 | 0 |  |  | 41.91% | 113.2% | 113.2% | 0 | -9.26% | 79161 | 33176 | 45985 | 0 | 5110 | 5109.88 | 0 | 37544 | 0 | -4369 | 0 | 37544 | 0 | 0 | 0 | 0 | 0 | 22% | 12.74% | 0% | -22% |  | 56
1727 | 2024-02-29 00:36 | P23642 | MRB Belfast Support | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -20.2% | 0 | 34423 | -34423 | 0 | 2948 | 2947.65 | 30800 | 0 | 134.37 | 34423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | -20.2% | -22.85% | -22.85% |  | 38.52
1727 | 2024-02-29 00:36 | P22768 | MRB Onsite Support - Spirit Belfast | James Montgomery | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2023-07-27 | 0 |  |  |  | 0% | 0% | 0 | -17.07% | 0 | 34614 | -34614 | 0 | 0 | 0 | 36800 | 0 | 41536.8 | 34614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | -7.07% | 0% | -10% |  | 36
1727 | 2024-02-29 00:36 | P23347 | WoT Fixed Leading Edge - Industrial 2023 | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 112.8% | 42.03% | 42.03% | 0 | -0.41% | 31034 | 35002 | -3968 | 0 | 0 | 0 | 10500 | 14711 | 24349.85 | 20292 | 0 | 14711 | 0 | 0 | 0 | 0 | 0 | 7% | 6.59% | 0% | -7% |  | 32.26
1727 | 2024-02-29 00:36 | P23744 | Model Factory | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  |  | 14.75% | 115.6% | 0.0004308% | 0 | 6.4% | 262300 | 38688 | 223612 | 0 | 0 | 0 | 0 | 44716 | 55 | -6029 | 53659 | 0.16667 | 53659.2 | 0 | 0 | 0 | 0 | 28% | 34.4% | 34.4% | 6.4% |  | 50.77
1727 | 2024-02-29 00:36 | P23051 | Spirit Shorts A350 PAX Door | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 3A | REIM |  |  |  |  | 205.9% | 105.4% | 105.4% | 0 | -0.63% | 18216 | 37513 | -19297 | 0 | 0 | 0 | 0 | 39537 | 0 | 0 | 0 | 39537 | 0 | 0 | 0 | 0 | 0 | 30% | 29.37% | 0% | -30% |  | 46
1727 | 2024-02-29 00:36 | P22752 | Tooling WoT - 2021 (Spirit) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | REIM | 2023-05-03 | 0 |  |  | 101.1% | 74.02% | 74.02% | 0 | -8.5% | 41525 | 41982 | -457 | 0 | 0 | 0 | 0 | 31076 | 13087.42 | 10906 | 0 | 31076 | 0 | 0 | 0 | 0 | 0 | 0% | -8.5% | 0% | 0% |  | 39.09
1727 | 2024-02-29 00:36 | P23700 | IPDT Leads | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 25.51% | 0% | 0% | 0 | 12.01% | 169264 | 43177 | 126087 | 0 | 0 | 0 | 0 | 0 | 91 | 43177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26% | 38.01% | 38.5% | 12.5% |  | 61.88
1727 | 2024-02-29 00:36 | P23754 | Tempest Composites WP4 | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX | [5 empty] | 0% | 0% | 0 | 7.94% | 0 | 44621 | -44621 | 0 | 149 | 149.25 | 97140 | 0 | 70 | 44621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 35.94% | 35.94% | 7.94% |  | 64.69
1727 | 2024-02-29 00:36 | P23339 | Spirit 2023 - Stewart Russell | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 64.51% | 100% | 100% | 0 | 0.62% | 72767 | 46942 | 25825 | 0 | 0 | 0 | 0 | 46942 | 0 | 0 | 0 | 46942 | 0 | 0 | 0 | 0 | 0 | 7% | 7.62% | 0% | -7% |  | 35.67
1727 | 2024-02-29 00:36 | P22760 | SA Leading Edge Transport Media ('A' Frames) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-11-15 | 1 |  |  | 85.99% | 110.7% | 116.3% | -3082.8 | 3.97% | 53481 | 45986 | 7495 | 0 | 42804 | 42804 | 0 | 50912 | 0 | 0 | -3083 | 53481.1667 | 0 | 0 | 0 | -3082.8 | -3082.8 | 6% | 9.97% | 0% | -6% |  | 42
1727 | 2024-02-29 00:36 | P23784 | Tempest Tooling Offload 2024 | Christopher McCarthy | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -10.88% | 0 | 51737 | -51737 | 0 | 0 | 0 | 74725 | 0 | 55 | 51737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 19.12% | 19.12% | -10.88% |  | 54.82
1727 | 2024-02-29 00:36 | P23382 | Performance Modelling | Dushan Fernando | BDX | MBDA UK LIMITED | MPE | Level NC | REIM | 2023-07-09 | 1 |  |  | 40.95% | 79.09% | 79.09% | 0 | -16.36% | 170010 | 69626 | 100384 | 0 | 14560 | 14659.9 | 0 | 55066 | 0 | 0 | 0 | 55066 | 0 | 0 | 0 | 0 | 0 | 20% | 3.64% | 0% | -20% |  | 77.05
1727 | 2024-02-29 00:36 | P23322 | GKN T Tomblin 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  |  | 94.73% | 93.08% | 87.75% | 0 | -0.33% | 58952 | 55848 | 3104 | 0 | 0 | 0 | 0 | 51984 | 74.96 | 3864 | 3571 | 49008.1667 | 3571.2 | 0 | 0 | 0 | 0 | 17% | 16.67% | 16.67% | -0.33% |  | 48
1727 | 2024-02-29 00:36 | P23349 | Spirit 2023 - Stress Approve Man Serv (SB) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 58.24% | 80.05% | 80.05% | 0 | -0.29% | 97920 | 57024 | 40896 | 0 | 0 | 0 | 0 | 45648 | 13651.2 | 11376 | 0 | 45648 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48
1727 | 2024-02-29 00:36 | P23341 | Spirit 2023 - Tom McFarlane | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 53.83% | 83.67% | 73.54% | 0 | -0.01% | 108666 | 58498 | 50168 | 0 | 0 | 0 | 0 | 48945 | 129.84 | 9553 | 7110 | 43020 | 0 | 0 | 7110.19 | 0 | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48
1727 | 2024-02-29 00:36 | P23816 | Typhoon FTI Works - 2024 Fixed Price Element | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX | [5 empty] | 0% | 0% | 0 | -2.41% | 0 | 59831 | -59831 | 0 | 0 | 0 | 146328 | 0 | 21 | 59831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29% | 26.59% | 26.59% | -2.41% |  | 54.35
1727 | 2024-02-29 00:36 | P23193 | Spirit Shorts Stephen Greer | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 99.65% | 89.22% | 84.8% | 3252.37 | 2.49% | 61472 | 61257 | 215 | 0 | 0 | 0 | 0 | 54656 | 96.65 | 6601 | 3252 | 51946 | 0 | 3252.37 | 0 | 0 | 3252.37 | 29% | 31.49% | 34.03% | 5.03% |  | 35.03
1727 | 2024-02-29 00:36 | P23106 | ME Support to NPD - Bobby Haggart | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  |  | 95.79% | 97.03% | 97.03% | 0 | 0.3% | 65675 | 62912 | 2763 | 0 | 0 | 0 | 0 | 61043 | 2243.24 | 1869 | 0 | 61043 | 0 | 0 | 0 | 0 | 0 | 15% | 15.3% | 0% | -15% |  | 35.65
1727 | 2024-02-29 00:36 | P23561 | SAAB | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2024-01-01 | 1 |  |  | 82.46% | 121.1% | 96.66% | 16332.48 | 3.5% | 67485 | 55649 | 11836 | 0 | 0 | 0 | 0 | 67399 | 264.4 | -4408 | 16332 | 53789 | 0 | 16332.48 | 0 | 0 | 16332.48 | 16% | 19.5% | 0% | -16% |  | 36.82
1727 | 2024-02-29 00:36 | P22967 | Spirit 2022 - Channapa Laxmeshwar | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2023-01-26 | 2 |  |  | 69.69% | 121.3% | 121.3% | 0 | 9.53% | 75159 | 52376 | 22783 | 0 | 52376 | 54898.1 | 0 | 63509 | 0.42 | 0 | 0 | 63509 | 0 | 0 | 0 | 0 | 0 | 8% | 17.53% | 0% | -8% |  | 0
1727 | 2024-02-29 00:36 | P23342 | Spirit 2023 - Channapa Laxmeshwar | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 78.75% | 104.3% | 98.93% | 0 | -2.64% | 79348 | 62484 | 16864 | 0 | 62484 | 63539 | 0 | 65178 | 4224.9 | 157 | 4037 | 61813.8333 | 0 | 0 | 4036.8 | 0 | 0 | 7% | 4.36% | 0% | -7% |  | 0
1727 | 2024-02-29 00:36 | P23080 | Spirit Shorts DManagement Cairan Cullen | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 49.07% | 98.47% | 92.92% | 4892.04 | -0.89% | 149600 | 73408 | 76192 | 0 | 0 | 0 | 0 | 72284 | 231.55 | 1124 | 4892 | 68207.3333 | 0 | 1104.24 | 0 | 3787.8 | 4892.04 | 24% | 23.11% | 13.22% | -10.78% |  | 44.45
1727 | 2024-02-29 00:36 | P23741 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  |  | 11.59% | 119.5% | 0% | 0 | -0.7% | 640812 | 74263 | 566549 | 0 | 0 | 0 | 0 | 88770 | 55 | -14508 | 106524 | 0 | 106524 | 0 | 0 | 0 | 0 | 28% | 27.3% | 27.3% | -0.7% |  | 38.61
1727 | 2024-02-29 00:36 | P23600 | MBDA EXP-EE-023 Bristone Certification | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 59.65% | 100% | 84.61% | 0 | 0.4% | 126600 | 75517 | 51083 | 0 | 0 | 0 | 0 | 75517 | 91 | 0 | 13942 | 63898.6667 | 0 | 13941.6 | 0 | 0 | 0 | 41% | 41.4% | 0% | -41% |  | 78.5
1727 | 2024-02-29 00:36 | P23438 | A220 Spirit Shorts DTC - Stephen Corry | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 79.99% | 52.65% | 52.65% | 0 | -7.37% | 95928 | 76730 | 19198 | 0 | 0 | 0 | 0 | 40400 | 202.6 | 36331 | 0 | 40400 | 0 | 0 | 0 | 0 | 0 | 23% | 15.63% | 16.89% | -6.11% |  | 49.76
1727 | 2024-02-29 00:36 | P23560 | NJEWCS TAF202302 SM | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level 2 | FIX |  |  |  |  | 95.27% | 51.52% | 51.52% | 0 | 11.78% | 81500 | 77646 | 3854 | 0 | 0 | 0 | 0 | 40000 | 142.19 | 37646 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 28% | 39.78% | 38.83% | 10.83% |  | 73.01
1727 | 2024-02-29 00:36 | P23340 | Spirit 2023 - John Cole | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 103.5% | 80.9% | 71.43% | 0 | -0.01% | 75065 | 77690 | -2625 | 0 | 0 | 0 | 8831 | 62852 | 123.85 | 14838 | 8831 | 55492.8333 | 0 | 0 | 8831.16 | 0 | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 39.78
1727 | 2024-02-29 00:36 | P23586 | Project Management Support | Peter Bowen | BDX | MBDA UK LIMITED | MPE | Level NC | REIM |  |  |  |  | 97.93% | 85.65% | 55.5% | 0 | -25.99% | 80000 | 78344 | 1656 | 0 | 1141 | 1140.6 | 16000 | 67104 | 94.45 | 11240 | 28349 | 43479.8333 | 3148.63 | 25200 | 0 | 0 | 0 | 49% | 23.01% | 22.41% | -26.59% |  | 80
1727 | 2024-02-29 00:36 | P23551 | Ian Berry 2023 H2 | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  |  | 104.6% | 84.77% | 84.77% | 0 | 12.75% | 75810 | 79292 | -3482 | 0 | 0 | 0 | 24259.2 | 67217 | 35.75 | 12074 | 0 | 67217 | 0 | 0 | 0 | 0 | 0 | 22% | 34.75% | 36.83% | 14.83% |  | 77.06
1727 | 2024-02-29 00:36 | P23465 | A220 ToW Design Offload (Wing) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 60.15% | 70.24% | 62.8% | 7087.68 | -4.33% | 132000 | 79394 | 52606 | 0 | 0 | 0 | 0 | 55768 | 91 | 23626 | 7088 | 49861.3333 | 0 | 7087.68 | 0 | 0 | 7087.68 | 20% | 15.67% | 14.71% | -5.29% |  | 42.8
1727 | 2024-02-29 00:36 | P22505 | Spirit MRB Engineering Support 2021 | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 1 |  |  | 91.17% | 100% | 95.78% | 4020.48 | 21.2% | 87110 | 79415 | 7695 | 0 | 0 | 0 | 0 | 79415 | 4020.48 | 0 | 4020 | 76065 | 0 | 0 | 0 | 4020.48 | 4020.48 | 0% | 21.2% | 0% | 0% |  | 41.88
1727 | 2024-02-29 00:36 | P23345 | Spirit 2023- Jonathan Escosio | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 104.9% | 80.9% | 64.33% | 7150.18 | -6.35% | 75971 | 79675 | -3704 | 0 | 0 | 0 | 8938 | 64456 | 156.7 | 15218 | 15846 | 51251 | 0 | 0 | 8696.16 | 7150.18 | 7150.18 | 7% | 0.65% | 0.65% | -6.35% |  | 40.26
1727 | 2024-02-29 00:36 | P23336 | Spirit 2023 - Neil Rampling | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 60.43% | 81.39% | 59.15% | 13070.83 | -0.01% | 133902 | 80912 | 52990 | 0 | 0 | 0 | 0 | 65851 | 183.48 | 15061 | 21586 | 47862.6667 | 0 | 0 | 8515.2 | 13070.83 | 13070.83 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48
1727 | 2024-02-29 00:36 | P22885 | ME Support (Baxi) | James Montgomery | HUV | BAXI HEATING UK LIMITED | ME | Level 3 | FIX | 2023-01-12 | 0 |  |  | 68.78% | 108.7% | 108.7% | 0 | 13.05% | 106633 | 73340 | 33293 | 0 | 0 | 0 | 0 | 79748 | 1531.35 | 1276 | 0 | 79748 | 0 | 0 | 0 | 0 | 0 | 15% | 28.05% | 0% | -15% |  | 44.37
1727 | 2024-02-29 00:36 | P23171 | Spirt Shorts Weights Eng | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 69.18% | 122.7% | 96.15% | 0 | 2.68% | 103113 | 71329 | 31784 | 0 | 71329 | 90419.91 | 0 | 87532 | 105.02 | -3932 | 22740 | 68582 | 16774.18 | 5965.46 | 0 | 0 | 0 | 12% | 14.68% | 0% | -12% |  | 0
1727 | 2024-02-29 00:36 | P23335 | GKN S McConnell 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2023-12-31 | 3 |  |  | 96.61% | 100% | 75.29% | 8347.2 | 0.74% | 87420 | 84459 | 2961 | 0 | 0 | 0 | 0 | 84459 | 273 | 0 | 25042 | 63590.6667 | 0 | 8347.2 | 0 | 16694.4 | 8347.2 | 15% | 15.74% | 0% | -15% |  | 47
1727 | 2024-02-29 00:36 | P23079 | Spirit Shorts Nomenclature | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 96.35% | 90.51% | 80.19% | 10554.48 | 1.88% | 88455 | 85228 | 3227 | 0 | 0 | 0 | 0 | 77138 | 206.32 | 8089 | 10554 | 68343 | 0 | 0 | 0 | 10554.48 | 10554.48 | 20% | 21.88% | 25.23% | 5.23% |  | 30.72
1727 | 2024-02-29 00:36 | P22965 | Spirit 2022 - Design Man Serv (AH) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 1 |  |  | 106.7% | 96.66% | 92.02% | 4759.75 | 3.14% | 80080 | 85441 | -5361 | 0 | 0 | 0 | 0 | 82589 | 8182.59 | 2852 | 4760 | 78622.3333 | 0 | 0 | 0 | 4759.75 | 4759.75 | 14% | 17.14% | 0% | -14% |  | 42.44
1727 | 2024-02-29 00:36 | P23523 | Applique Armour Support | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 0 |  |  | 72.43% | 98.47% | 98.47% | 0 | 3.42% | 118200 | 85607 | 32593 | 0 | 0 | 0 | 0 | 84300 | 1567.8 | 1307 | 0 | 84300 | 0 | 0 | 0 | 0 | 0 | 25% | 28.42% | 0% | -25% |  | 64.29
1727 | 2024-02-29 00:36 | P22964 | Spirit 2022 - MRB Man Serv (JC) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 100.6% | 97.95% | 97.95% | 0 | 1.91% | 85435 | 85960 | -525 | 0 | 0 | 0 | 0 | 84200 | 2112.62 | 1761 | 0 | 84200 | 0 | 0 | 0 | 0 | 0 | 16% | 17.91% | 0% | -16% |  | 42.69
1727 | 2024-02-29 00:36 | P22963 | Spirit 2022 - Design Man Serv (PC) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 1 |  |  | 108.6% | 104% | 94.46% | 9938.48 | 3.18% | 80080 | 86927 | -6847 | 0 | 0 | 0 | 0 | 90390 | 5782.63 | -3463 | 9938 | 82108.3333 | 0 | 0 | 0 | 9938.48 | 9938.48 | 13% | 16.18% | 0% | -13% |  | 42.39
1727 | 2024-02-29 00:36 | P23743 | EHM Cloud Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  |  | 8.754% | 192% | 0.0003748% | 0 | -1.5% | 1016000 | 88943 | 927057 | 0 | 0 | 0 | 0 | 170752 | 55 | -81809 | 204902 | 0.33333 | 204902.4 | 0 | 0 | 0 | 0 | 28% | 26.5% | 26.5% | -1.5% |  | 51.31
1727 | 2024-02-29 00:36 | P23583 | Castalla - Test Rig Design | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 135.2% | 67.1% | 67.1% | 0 | -6.46% | 67520 | 91299 | -23779 | 0 | 0 | 0 | 36106 | 61258 | 108.67 | 30041 | 0 | 61258 | 0 | 0 | 0 | 0 | 0 | 21% | 14.54% | 17.59% | -3.41% |  | 42.67
1727 | 2024-02-29 00:36 | P23375 | GKN Jaap Peters NL 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  |  | 93.37% | 105.3% | 67.32% | 10410.79 | -15.93% | 97123 | 90686 | 6437 | 0 | 90686 | 92269.6 | 0 | 95457 | 124.66 | -920 | 41290 | 61048.6667 | 8793.29 | 13234.06 | 0 | 19262.9 | 10410.79 | 20% | 4.07% | 0% | -20% |  | 0
1727 | 2024-02-29 00:36 | P23739 | Lifing Services DACs | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  |  | 14.5% | 116% | -0.0003502% | 0 | 2.92% | 656508 | 95180 | 561328 | 0 | 0 | 0 | 0 | 110418 | 55 | -15238 | 132502 | -0.33333 | 132501.6 | 0 | 0 | 0 | 0 | 28% | 30.92% | 30.92% | 2.92% |  | 37.76
1727 | 2024-02-29 00:36 | P23545 | Ultra CSS continuation 2023 H2 | Natalie Sinclair | ULT | ULTRA SONAR SYSTEMS LIMITED | EES | Level NC | REIM |  |  |  |  | 125.3% | 79.24% | 46.16% | 0 | 2.24% | 76000 | 95219 | -19219 | 0 | 0 | 0 | 24259.2 | 75451 | 161.57 | 19768 | 37794 | 43956 | 37794.24 | 0 | 0 | 0 | 0 | 23% | 25.24% | 25% | 2% |  | 80
1727 | 2024-02-29 00:36 | P23353 | Spirit 2023 - MRB Man Serv (JC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  |  | 104.8% | 71.33% | 71.33% | 0 | 10.37% | 91800 | 96188 | -4388 | 0 | 0 | 0 | 13320 | 68615 | 173.16 | 27572 | 0 | 68615 | 0 | 0 | 0 | 0 | 0 | 7% | 17.37% | 12.23% | 5.23% |  | 45
1727 | 2024-02-29 00:36 | P23588 | BAE Typhoon MRB MC Shop Concessions | Andrew Houghton | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 57.86% | 91.13% | 50.88% | 0 | -4.02% | 175061 | 101283 | 73778 | 0 | 0 | 0 | 0 | 92296 | 136.72 | 8987 | 48910 | 51537.6667 | 48910.43 | 0 | 0 | 0 | 0 | 31% | 26.98% | 29.18% | -1.82% |  | 55.54
1727 | 2024-02-29 00:36 | P23664 | Tempest Composites WP3 | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  |  | 85.04% | 15.86% | 0.0006402% | 0 | -5.19% | 122455 | 104137 | 18318 | 0 | 0 | 0 | 0 | 16519 | 149.97 | 87619 | 19822 | 0.66667 | 0 | 19822.44 | 0 | 0 | 0 | 37% | 31.81% | 34.14% | -2.86% |  | 60.47
1727 | 2024-02-29 00:36 | P23810 | Strategic Enablement | Owain Jones | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -19.69% | 0 | 104471 | -104471 | 0 | 0 | 0 | 134000 | 0 | 56 | 104471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | -1.69% | -1.69% | -19.69% |  | 42
1727 | 2024-02-29 00:36 | P23352 | Spirit 2023 - Stress Approve Man Serv (CC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  |  | 109.4% | 65.24% | 65.24% | 0 | 7.29% | 97920 | 107160 | -9240 | 0 | 0 | 0 | 10656 | 69912 | 161.59 | 37248 | 0 | 69912 | 0 | 0 | 0 | 0 | 0 | 7% | 14.29% | 4.69% | -2.31% |  | 48
1727 | 2024-02-29 00:36 | P22918 | Spirit Shorts Graduates | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 83.04% | 98.87% | 65.17% | 0 | -2.36% | 130000 | 107957 | 22043 | 0 | 0 | 0 | 0 | 106735 | 188.32 | 1222 | 43660 | 70351.6667 | 43659.95 | 0 | 0 | 0 | 0 | 19% | 16.64% | 19.09% | 0.09% |  | 23.25
1727 | 2024-02-29 00:36 | P23282 | Tooling Support (MBDA) | Dushan Fernando | BDV | MBDA UK LIMITED | ME | Level 3 | FIX |  |  |  |  | 108.5% | 91.28% | 81.51% | 0 | -9.11% | 104834 | 113724 | -8890 | 0 | 0 | 0 | 19964 | 103804 | 91.11 | 9920 | 13326 | 92699 | 0 | 13325.98 | 0 | 0 | 0 | 30% | 20.89% | 30.37% | 0.37% |  | 49.7
1727 | 2024-02-29 00:36 | P22883 | Spirit Shorts Evtol PMO C. Hatton | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 61.83% | 94.83% | 79.42% | 21252 | -12.15% | 185800 | 114884 | 70916 | 0 | 0 | 0 | 0 | 108947 | 185.25 | 5937 | 21252 | 91237 | 0 | 6468 | 14784 | 0 | 21252 | 26% | 13.85% | 24.2% | -1.8% |  | 36.47
1727 | 2024-02-29 00:36 | P23270 | Shorts Project X | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 81.13% | 76.16% | 70.4% | 7981.34 | 0.76% | 142248 | 115399 | 26849 | 0 | 0 | 0 | 0 | 87889 | 155.8 | 27510 | 7981 | 81238.1667 | 0 | 7981.34 | 0 | 0 | 7981.34 | 13% | 13.76% | 10.99% | -2.01% |  | 45.37
1727 | 2024-02-29 00:36 | P23677 | ME Managed Service - Phase 1 | Paul Watson | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  |  | 21.19% | 0% | 0% | 0 | -24.66% | 554400 | 117450 | 436950 | 0 | 0 | 0 | 0 | 0 | 110.37 | 117450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33% | 8.34% | 11.11% | -21.89% |  | 45
1727 | 2024-02-29 00:36 | P22736 | WoT Fixed Leading Edge - Industrial | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 106.7% | 93.42% | 91.32% | 3019.54 | 0.01% | 112196 | 119668 | -7472 | 0 | 0 | 0 | 0 | 111797 | 12465.69 | 7872 | 3020 | 109280.3333 | 0 | 0 | 0 | 3019.54 | 3019.54 | 7% | 7.01% | 0% | -7% |  | 32.26
1727 | 2024-02-29 00:36 | P22861 | WoT FLE Lifting & Handling Tools | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2023-06-14 | 1 |  |  | 65.17% | 101.6% | 101.6% | 0 | 12.01% | 173987 | 113382 | 60605 | 0 | 50078 | 58423.58 | 0 | 115204 | 12813.9 | 10678 | 0 | 115204 | 0 | 0 | 0 | 0 | 0 | 1% | 13.01% | 0% | -1% |  | 45
1727 | 2024-02-29 00:36 | P23421 | A220 DTC | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 61.92% | 79.67% | 58.32% | 34446.52 | -30.07% | 217089 | 134418 | 82671 | 0 | 0 | 0 | 0 | 107094 | 127.84 | 27324 | 34447 | 78388.1667 | 0 | 34446.52 | 0 | 0 | 34446.52 | 29% | -1.07% | 4.21% | -24.79% |  | 45.07
1727 | 2024-02-29 00:36 | P23648 | EXP-032 Delivery of Datalink Eng support - FCAS AP | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 36.63% | 75.67% | 0.0003679% | 0 | 4.89% | 371000 | 135913 | 235087 | 0 | 1033 | 1032.95 | 0 | 102843 | 136.22 | 33070 | 123411 | 0.5 | 0 | 123411 | 0 | 0 | 0 | 22% | 26.89% | 26.74% | 4.74% |  | 103.71
1727 | 2024-02-29 00:36 | P23667 | Safety Systems Engineer | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 34.44% | 88.12% | 76.89% | 0 | -8.65% | 398000 | 137060 | 260940 | 0 | 0 | 0 | 0 | 120780 | 48.27 | 16280 | 18480 | 105380 | 0 | 18480 | 0 | 0 | 0 | 47% | 38.35% | 29.32% | -17.68% |  | 110
1727 | 2024-02-29 00:36 | P23533 | External Stowage Design and Detail Support | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 0 |  |  | 102.4% | 73.24% | 73.24% | 0 | 3.33% | 140000 | 143369 | -3369 | 0 | 0 | 0 | 12936 | 105000 | 41999.7 | 35000 | 0 | 105000 | 0 | 0 | 0 | 0 | 0 | 27% | 30.33% | 0% | -27% |  | 60.04
1727 | 2024-02-29 00:36 | P23437 | Embedded Software Engineer | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 94.86% | 91.84% | 81.78% | 0 | -6.32% | 150150 | 142430 | 7720 | 0 | 738 | 737.86 | 0 | 130812 | 69.23 | 11618 | 17207 | 116472.8333 | 4019.1 | 13188 | 0 | 0 | 0 | 22% | 15.68% | 16.24% | -5.76% |  | 78.5
1727 | 2024-02-29 00:36 | P23518 | Systems Engineering support to FCAS | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 75.21% | 89.09% | 81.36% | 0 | -1.9% | 193737 | 145705 | 48032 | 0 | 3927 | 3927.4 | 0 | 129804 | 71.18 | 15901 | 13518 | 118539 | 0 | 13517.7 | 0 | 0 | 0 | 30% | 28.1% | 3.5% | -26.5% |  | 67.15
1727 | 2024-02-29 00:36 | P22982 | Spirit 2022 - Hugh Sloan | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 88.74% | 90.81% | 86.16% | 0 | -0.01% | 166046 | 147341 | 18705 | 0 | 0 | 0 | 0 | 133795 | 145.9 | 13546 | 8217 | 126947.5 | 0 | 0 | 8217.17 | 0 | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 35.42
1727 | 2024-02-29 00:36 | P22954 | Technical Support Step 1 | Owain Jones | HUV | HUARUI SPIRIT AEROSPACE MANUFACT | ME | Level 2 | REIM |  |  |  |  | 94.81% | 58.01% | 58.01% | 0 | 0.31% | 155501 | 147432 | 8069 | 0 | 23043 | 23043 | 0 | 85525 | 61906.09 | 61906 | 0 | 85525 | 0 | 0 | 0 | 0 | 0 | 30% | 30.31% | 0% | -30% |  | 60.79
1727 | 2024-02-29 00:36 | P23386 | Software Development - BMS | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 98.78% | 100% | 88.63% | 0 | 4.31% | 149650 | 147823 | 1827 | 0 | 0 | 0 | 0 | 147823 | 54.1 | 0 | 20168 | 131016.3333 | 8007 | 12161.22 | 0 | 0 | 0 | 18% | 22.31% | 22.61% | 4.61% |  | 78.5
1727 | 2024-02-29 00:36 | P23550 | Tempest Composites | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  |  | 100.2% | 99.83% | 67.28% | 24179.64 | 5.13% | 149495 | 149755 | -260 | 0 | 0 | 0 | 2396.12 | 149495 | 193.87 | 260 | 58496 | 100748.3333 | 27760.26 | 6555.8 | 0 | 24179.64 | 24179.64 | 26% | 31.13% | 34.44% | 8.44% |  | 61.6
1727 | 2024-02-29 00:36 | P22440 | Spirit Managed Service - F&DT and Static Approval | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 3 |  |  | 88.56% | 92.56% | 92.56% | 0 | 11.51% | 173500 | 153656 | 19844 | 0 | 52115 | 55720 | 0 | 142225 | 13717.36 | 11431 | 0 | 142225 | 0 | 0 | 0 | 0 | 0 | 0% | 11.51% | 0% | 0% |  | 44.73
1727 | 2024-02-29 00:36 | P23464 | A220 Project X Design Offload | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 47.08% | 85.2% | 63.93% | 39945.24 | -9.03% | 332340 | 156462 | 175878 | 0 | 0 | 0 | 0 | 133307 | 154.6 | 23155 | 39945 | 100019.5 | 0 | 12082.44 | 27862.8 | 0 | 39945.24 | 26% | 16.97% | 15.33% | -10.67% |  | 42.89
1727 | 2024-02-29 00:36 | P23508 | Verification and Validation | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 78.39% | 91.62% | 80.33% | 0 | 10.98% | 212950 | 166930 | 46020 | 0 | 0 | 0 | 0 | 152938 | 56.87 | 13993 | 22608 | 134098 | 0 | 22608 | 0 | 0 | 0 | 24% | 34.98% | 34.49% | 10.49% |  | 78.5
1727 | 2024-02-29 00:36 | P23506 | ASTER Mid-Life Refurbishment Project Manager | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 77.69% | 90.28% | 79.92% | 0 | 0.98% | 224900 | 174736 | 50164 | 0 | 2806 | 2806.41 | 0 | 157759 | 64.23 | 16977 | 21730 | 139650.6667 | 2523.88 | 19206 | 0 | 0 | 0 | 25% | 25.98% | 26.21% | 1.21% |  | 110
1727 | 2024-02-29 00:36 | P23629 | F35 FTI | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level NC | REIM | [5 empty] | 92.99% | 68.92% | 0 | -1% | 0 | 177347 | -177347 | 0 | 0 | 0 | 0 | 164921 | 49.68 | 12426 | 51228 | 122231 | 51227.95 | 0 | 0 | 0 | 0 | 31% | 30% | 27.81% | -3.19% |  | 62.06
1727 | 2024-02-29 00:36 | P23505 | EXP-022 Meteor TBUS T&E support | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 72.77% | 91.06% | 29.38% | 0 | -0.76% | 246744 | 179548 | 67196 | 0 | 0 | 0 | 0 | 163491 | 262.14 | 16057 | 132886 | 52752.6667 | 0 | 132885.54 | 0 | 0 | 0 | 20% | 19.24% | 15.67% | -4.33% |  | 89.83
1727 | 2024-02-29 00:36 | P23685 | DAC LUC Support and Recompliance | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  |  | 25.48% | 267.8% | -0.0001817% | 0 | -1.28% | 720000 | 183476 | 536524 | 0 | 0 | 0 | 0 | 491428 | 55 | -307952 | 589714 | -0.33333 | 589713.6 | 0 | 0 | 0 | 0 | 28% | 26.72% | 26.72% | -1.28% |  | 61.37
1727 | 2024-02-29 00:36 | P23373 | Raytheon Michael Bellini | Natalie Sinclair | RAS | RAYTHEON UNITED KINGDOM LIMITED | EES | Level NC | REIM |  |  |  |  | 85.76% | 93.08% | 84.56% | 0 | -8.54% | 214367 | 183841 | 30526 | 0 | 0 | 0 | 0 | 171127 | 58 | 12713 | 18798 | 155462 | 18798.37 | 0 | 0 | 0 | 0 | 45% | 36.46% | 36.11% | -8.89% |  | 91.61
1727 | 2024-02-29 00:36 | P23242 | Physical Architecture & System Engineering Support | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM | 2024-02-28 | 21 |  |  | 61.61% | 93.42% | 88.79% | 0 | 9.42% | 305459 | 188179 | 117280 | 0 | 776 | 775.55 | 0 | 175794 | 65.16 | 12385 | 10456 | 167080.6667 | 0 | 10456.2 | 0 | 0 | 0 | 15% | 24.42% | 7.8% | -7.2% |  | 78.17
1727 | 2024-02-29 00:36 | P23524 | Bombardier Regional Jets (BRJ) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 130.8% | 56.89% | 44.32% | 28851.48 | -4.69% | 146288 | 191312 | -45024 | 0 | 0 | 0 | 46750 | 108838 | 170.58 | 82473 | 28851 | 84795.5 | 0 | 3694.07 | 25157.41 | 0 | 28851.48 | 18% | 13.31% | 15.43% | -2.57% |  | 43.92
1727 | 2024-02-29 00:36 | P23008 | Spirit Shorts Project Rachel | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 85.87% | 91.32% | 87.38% | 9292.8 | -7.7% | 228880 | 196531 | 32349 | 0 | 0 | 0 | 0 | 179473 | 244.15 | 17058 | 9293 | 171728.8333 | 0 | 9292.8 | 0 | 0 | 9292.8 | 13% | 5.3% | 0.31% | -12.69% |  | 46.04
1727 | 2024-02-29 00:36 | P23019 | EXP034-B Actuator Development | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 103.1% | 89.91% | 89.91% | 0 | -14.64% | 215541 | 222216 | -6675 | 0 | 12298 | 12297.9 | 0 | 199797 | 395.05 | 5442 | 0 | 199797 | 0 | 0 | 0 | 0 | 0 | 34% | 19.36% | 35.7% | 1.7% |  | 58.45
1727 | 2024-02-29 00:36 | P23472 | Tempest Wing Design | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 45.03% | 118.2% | 93.8% | 0 | -19.95% | 483870 | 217867 | 266003 | 0 | 201988 | 356900 | 0 | 257532 | 20.6 | -39664 | 63812 | 204355.3333 | 32753.16 | 31059.04 | 0 | 0 | 0 | 23% | 3.05% | 12.51% | -10.49% |  | 46.74
1727 | 2024-02-29 00:36 | P22798 | CO2MAP MGSE | Harry James Kellett | DTW | THALES ALENIA SPACE UK (60DAYS) | EES | Level 2 | REIM | 2023-11-08 | 1 |  |  | 85.75% | 105% | 105% | 0 | -3.47% | 252086 | 216158 | 35928 | 0 | 0 | 0 | 0 | 227053 | 0.26 | 0 | 0 | 227053 | 0 | 0 | 0 | 0 | 0 | 29% | 25.53% | 100% | 71% |  | 50.31
1727 | 2024-02-29 00:36 | P23316 | Model Factory IL and AW | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX | 2024-01-12 | 2 |  |  | 88.13% | 104.1% | 96.46% | 0 | 2.41% | 250000 | 220328 | 29672 | 0 | 0 | 0 | 0 | 229409 | 78.91 | 0 | 20249 | 212534.8333 | 0 | 0 | 20248.8 | 0 | 0 | 30% | 32.41% | 42.82% | 12.82% |  | 45.31
1727 | 2024-02-29 00:36 | P23699 | A220 Stress Checkers | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -2.09% | 0 | 232656 | -232656 | 0 | 7000 | 7000 | 321520 | 0 | 91 | 232656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22% | 19.91% | 19.93% | -2.07% |  | 61.88
1727 | 2024-02-29 00:36 | P23650 | MBDA Recruitment Management costs | Brian Maddrell | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 28.46% | 0 | 240972 | -240972 | 0 | 0 | 0 | 266000 | 0 | 127.1 | 240972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | 31.46% | 28.48% | 25.48% |  | 82.3
1727 | 2024-02-29 00:36 | P23603 | Typhoon IMDLR | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 79.93% | 0% | 0% | 0 | 2.12% | 305067 | 243849 | 61218 | 0 | 0 | 0 | 4271.91 | 0 | 271.11 | 243849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29% | 31.12% | 32.21% | 3.21% |  | 57.52
1727 | 2024-02-29 00:36 | P23317 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX | 2024-01-12 | 2 |  |  | 95.89% | 104.3% | 98.16% | 0 | 4.31% | 251800 | 241447 | 10353 | 0 | 0 | 0 | 0 | 251800 | 88.27 | 0 | 17760 | 237000 | 0 | 0 | 17760 | 0 | 0 | 25% | 29.31% | 49.38% | 24.38% |  | 36.29
1727 | 2024-02-29 00:36 | P23007 | EXP-006A - Brimstone 3 | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 63.91% | 95.19% | 90.93% | 0 | -3.17% | 406450 | 259760 | 146690 | 0 | 0 | 0 | 0 | 247278 | 68.85 | 12452 | 13282 | 236209.6667 | 3485.4 | 9796.8 | 0 | 0 | 0 | 25% | 21.83% | 29.94% | 4.94% |  | 69.44
1727 | 2024-02-29 00:36 | P21463 | Safety & Monitoring Systems at DM Beith & Gosport | Harry James Kellett | BXW | MOD | EES | Level 2 | FIX |  |  |  |  | 77.42% | 129.2% | 129.2% | 0 | -26.91% | 349405 | 270510 | 78895 | 0 | 56389 | 69642.23 | 21721 | 349387 | 0 | -78877 | 0 | 349387 | 0 | 0 | 0 | 0 | 0 | 48% | 21.09% | 40.79% | -7.21% |  | 52.91
1727 | 2024-02-29 00:36 | P23308 | NATO JEWCS | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  |  | 80.16% | 95.67% | 82.48% | 45213.08 | -3.38% | 356307 | 285622 | 70685 | 0 | 614 | 613.89 | 0 | 273254 | 145.67 | 12368 | 45213 | 235576.5 | 45213.08 | 0 | 0 | 0 | 45213.08 | 24% | 20.62% | 12.77% | -11.23% |  | 75.81
1727 | 2024-02-29 00:36 | P23045 | Shotgun Adaptors - 10 Sets | Harry James Kellett | BDW | MBDA UK LIMITED | EES | Level 2 | FIX | 2024-02-27 | 6 |  |  | 74.76% | 133.8% | 95.11% | 0 | -19.12% | 399276 | 298513 | 100763 | 0 | 214550 | 214550.47 | 0 | 399276 | 2385.79 | -100763 | 138421 | 283925.1667 | 138420.73 | 0 | 0 | 0 | 0 | 29% | 9.88% | 0% | -29% |  | 55.76
1727 | 2024-02-29 00:36 | P23617 | Tempest Composites WP2 | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  |  | 123.8% | 27.25% | 3.367% | 29536.68 | 2.77% | 244405 | 302596 | -58191 | 0 | 0 | 0 | 57651.28 | 82447 | 222.21 | 220148 | 86711 | 10187.8333 | 28565.94 | 28608.29 | 0 | 29536.68 | 29536.68 | 31% | 33.77% | 33.63% | 2.63% |  | 62.31
1727 | 2024-02-29 00:36 | P22515 | Shorts A220 100/300 ALI Phase III | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 79.07% | 93.91% | 90.07% | 14583.89 | 1.16% | 400629 | 316761 | 83868 | 0 | 3451 | 3450.98 | 0 | 297465 | 134.98 | 19296 | 14584 | 285311.6667 | 0 | 14583.89 | 0 | 0 | 14583.89 | 10% | 11.16% | 13.91% | 3.91% |  | 40.38
1727 | 2024-02-29 00:36 | P22953 | Spirit Shorts eVTOL | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-05-08 | 1 |  |  | 103.1% | 79.36% | 79.36% | 0 | -6.74% | 324272 | 334484 | -10212 | 0 | 66697 | 67387.9 | 0 | 265432 | 179.02 | 69052 | 0 | 265432 | 0 | 0 | 0 | 0 | 0 | 17% | 10.26% | 0% | -17% |  | 46.19
1727 | 2024-02-29 00:36 | P22842 | ME Support (Aim Altitude) | James Montgomery | AVI | AIM ALTITUDE UK LIMITED | ME | Level 3 | FIX | 2023-06-14 | 4 |  |  | 99.31% | 100.5% | 86.63% | 57290.84 | 0.49% | 346294 | 343918 | 2376 | 0 | 2910 | 2909.86 | 0 | 345673 | 55184.93 | -1755 | 57291 | 297930.5 | 0 | 0 | 0 | 57290.84 | 57290.84 | 13% | 13.49% | 0% | -13% |  | 46.3
1727 | 2024-02-29 00:36 | P22391 | GE System Engineering support | Vinayakumar Sugur | GEE | EXPERIS LIMITED | EES | Level NC | REIM |  |  |  |  | 82.01% | 98.14% | 98.14% | 0 | 0.13% | 434434 | 356261 | 78173 | 0 | 0 | 0 | 0 | 349621 | 65.78 | 6640 | 0 | 349621 | 0 | 0 | 0 | 0 | 0 | 6% | 6.13% | 6.09% | 0.09% |  | 57.33
1727 | 2024-02-29 00:36 | P23694 | Systems Portfolio EXP-011a | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 56.1% | 75.96% | 56.6% | 0 | 2.89% | 648493 | 363828 | 284665 | 0 | 158 | 157.75 | 0 | 276367 | 56.15 | 87461 | 84550 | 205908.6667 | -11906.7 | 96456.46 | 0 | 0 | 0 | 21% | 23.89% | 18.13% | -2.87% |  | 89.77
1727 | 2024-02-29 00:36 | P23023 | Spirit Shorts R Foster/M Gourley | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  |  | 91.62% | 100.5% | 89.68% | 0 | -20.66% | 416652 | 381747 | 34905 | 0 | 223872 | 267726 | 0 | 383474 | 79.51 | 12784 | 49334 | 342362.3333 | 33124.42 | 16209.44 | 0 | 0 | 0 | 27% | 6.34% | 2.88% | -24.12% |  | 29.54
1727 | 2024-02-29 00:36 | P23531 | BAe Systems F35 MRB Support | Andrew Houghton | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM | [5 empty] | 77.8% | 66.37% | 0 | 2.72% | 0 | 402690 | -402690 | 0 | 287 | 287.44 | 0 | 313284 | 91.9 | 89406 | 55201 | 267283.1667 | 55201.11 | 0 | 0 | 0 | 0 | 25% | 27.72% | 32.02% | 7.02% |  | 59.37
1727 | 2024-02-29 00:36 | P23432 | Spirit Belfast MRB On-Site Support (Mon & Clear) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 65.77% | 125.6% | 100.1% | 90737.4 | -11.53% | 449545 | 295665 | 153880 | 0 | 295665 | 451827.33 | 0 | 371466 | 84.3 | 36200 | 90737 | 295851.8333 | 0 | 13345.8 | 0 | 77391.6 | 90737.4 | 39% | 27.47% | 0% | -39% |  | 0
1727 | 2024-02-29 00:36 | P23320 | Lifing Services DACs | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX | 2024-01-12 | 2 |  |  | 95.56% | 104.6% | 97.44% | 0 | 2.98% | 413300 | 394956 | 18344 | 0 | 0 | 0 | 0 | 413300 | 74.03 | -1 | 34139 | 384850.8333 | 0 | 0 | 34138.8 | 0 | 0 | 26% | 28.98% | 52.05% | 26.05% |  | 33.15
1727 | 2024-02-29 00:36 | P23520 | FCAS AP Portfolio Systems | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 51.01% | 88.14% | 79.53% | 0 | -6.56% | 810821 | 413562 | 397259 | 0 | 320 | 319.5 | 0 | 364501 | 60.39 | 49061 | 42698 | 328919.3333 | 248.4 | 42449.86 | 0 | 0 | 0 | 22% | 15.44% | 17.7% | -4.3% |  | 79.63
1727 | 2024-02-29 00:36 | P23554 | Dornier Seawings 328 2023 H2 Support | Steven Lawton | DAX | EXPLEO GERMANY GMBH (EC) | MPE | Level 2 | REIM |  |  |  |  | 88.54% | 90.13% | 90.13% | 0 | 7.84% | 474542 | 420172 | 54370 | 0 | 4046 | 4046.44 | 0 | 378685 | 36.75 | 41487 | 0 | 378685 | 0 | 0 | 0 | 0 | 0 | 21% | 28.84% | 31.36% | 10.36% |  | 67.59
1727 | 2024-02-29 00:36 | P22906 | Spirit Shorts - MRB JD Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  |  | 70.22% | 89.58% | 69.08% | 20246.4 | -7.66% | 614770 | 431665 | 183105 | 0 | 0 | 0 | 0 | 386688 | 276.64 | 52977 | 106200 | 298188 | 0 | 92702.52 | 13497.6 | 0 | 20246.4 | 13% | 5.34% | 3.06% | -9.94% |  | 36.86
1727 | 2024-02-29 00:36 | P23366 | Business Analyst Support | Peter Williams | BDZ | MBDA UK LIMITED | DET | Level NC | REIM |  |  |  |  | 33.09% | 257% | 200.5% | 0 | 13.44% | 583200 | 192994 | 390206 | 0 | 192993 | 416921.86 | 0 | 496000 | 54.45 | -49871 | 130752 | 387040 | 80064 | 50688 | 0 | 0 | 0 | 43% | 56.44% | 31.06% | -11.94% |  | 0.01
1727 | 2024-02-29 00:36 | P23372 | BAE Carbon Tooling Off-load | Gary Kempster | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  |  | 165.3% | 56.3% | 56.3% | 0 | -4.13% | 276718 | 457433 | -180715 | 0 | 0 | 0 | 197460.8 | 257522 | 364.18 | 199912 | 0 | 257522 | 0 | 0 | 0 | 0 | 0 | 27% | 22.87% | 20.94% | -6.06% |  | 53.57
1727 | 2024-02-29 00:36 | P23140 | Spirit Shorts A220 MLG Stress Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  |  | 72.7% | 85.63% | 76.32% | 48343.2 | -15.31% | 595746 | 433117 | 162629 | 0 | 20870 | 87811.88 | 0 | 370857 | 171.64 | 87259 | 48343 | 330571.1667 | 0 | 0 | 0 | 48343.2 | 48343.2 | 32% | 16.69% | 13.54% | -18.46% |  | 47.33
1727 | 2024-02-29 00:36 | P23473 | Tempest Vertical Tail | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 64.38% | 94.82% | 74.58% | 0 | -2.9% | 723866 | 466061 | 257805 | 0 | 91875 | 100425 | 0 | 441918 | 77.25 | 24143 | 113181 | 347600.5 | 58489.72 | 54691.04 | 0 | 0 | 0 | 24% | 21.1% | 23.45% | -0.55% |  | 62.41
1727 | 2024-02-29 00:36 | P22652 | L3 - Saftey Engineering | Sean Simmons | LHW | L3HARRIS MAPPS LIMITED | EES | Level NC | FIX |  |  |  |  | 95.63% | 86.69% | 86.69% | 0 | 5.66% | 523390 | 500498 | 22892 | 0 | 0 | 0 | 0 | 433883 | 79938 | 66615 | 0 | 433883 | 0 | 0 | 0 | 0 | 0 | 21% | 26.66% | 25.88% | 4.88% |  | 83.05
1727 | 2024-02-29 00:36 | P23001 | Spirit Shorts A220 Design | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 117.6% | 70.81% | 68.36% | 15202.56 | -3.99% | 439560 | 517077 | -77517 | 0 | 0 | 0 | 65953.2 | 366148 | 342.58 | 150929 | 15203 | 353478.8333 | 0 | 15202.56 | 0 | 0 | 15202.56 | 25% | 21.01% | 11.94% | -13.06% |  | 43.61
1727 | 2024-02-29 00:36 | P23323 | CNC-CMM Programming Support | Andrew Houghton | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  |  | 84.54% | 81.8% | 69.52% | 0 | -3.32% | 617810 | 522286 | 95524 | 0 | 13662 | 15941.56 | 0 | 427206 | 135.87 | 95080 | 76956 | 363076 | 76955.66 | 0 | 0 | 0 | 0 | 32% | 28.68% | 38.21% | 6.21% |  | 56.99
1727 | 2024-02-29 00:36 | P23281 | Systems Portfolio | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM | 2024-02-28 | 1 |  |  | 44.43% | 97.31% | 97.19% | 0 | -17.1% | 1177697 | 523237 | 654460 | 0 | 2133 | 2133.28 | 0 | 509180 | 17523.23 | 13968 | 762 | 508545 | 761.53 | 0 | 0 | 0 | 0 | 25% | 7.9% | 0% | -25% |  | 70.48
1727 | 2024-02-29 00:36 | P21138 | D&A Vibration Reduc Damping Struc FOGV Components | Steven Lawton | ATC | AECC SICHUAN GAS TURBINE | MPE | Level 1 | FIX | 2022-09-07 | 1 |  |  | 96.12% | 104% | 104% | 0 | -3.44% | 569346 | 547228 | 22118 | 0 | 75182 | 75181.75 | 0 | 569346 | 0 | 0 | 0 | 569346 | 0 | 0 | 0 | 0 | 0 | 36% | 32.56% | 0.08% | -35.92% |  | 73.95
1727 | 2024-02-29 00:36 | P23602 | EXP-025 Portfolio Software Engineering Support | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 43.38% | 79.46% | 45.71% | 0 | -0.62% | 1327080 | 575651 | 751429 | 0 | 1024 | 1216.09 | 0 | 457393 | 92.51 | 118258 | 233130 | 263118 | 6122.76 | 227007.26 | 0 | 0 | 0 | 24% | 23.38% | 23.34% | -0.66% |  | 82.72
1727 | 2024-02-29 00:36 | P23219 | Tornado Air 800 Engineering Support | Richard Brook | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 3 | REIM |  |  |  |  | 95.46% | 98.51% | 98.51% | 0 | 1.46% | 615046 | 587098 | 27948 | 0 | 459 | 459.21 | 0 | 578373 | 10470.24 | 8725 | 0 | 578373 | 0 | 0 | 0 | 0 | 0 | 31% | 32.46% | 0% | -31% |  | 81.76
1727 | 2024-02-29 00:36 | P23426 | BAE Tempest WP 3 Harness Maturation | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 67.5% | 87.66% | 67.42% | 0 | -5.98% | 884012 | 596667 | 287345 | 0 | 213 | 213.34 | 0 | 523063 | 90.92 | 73604 | 144962 | 402261.3333 | 66565.09 | 78396.7 | 0 | 0 | 0 | 33% | 27.02% | 28.47% | -4.53% |  | 51.23
1727 | 2024-02-29 00:36 | P23605 | Typhoon Work Package 2 Continuation | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM |  |  |  |  | 119.7% | 4.183% | -0.0001021% | 0 | 5.16% | 545536 | 652893 | -107357 | 0 | 4054 | 4054 | 81999.09 | 27311 | 213.48 | 625582 | 32774 | -0.66667 | 32773.76 | 0 | 0 | 0 | 0 | 23% | 28.16% | 28.83% | 5.83% |  | 55.72
1727 | 2024-02-29 00:36 | P22790 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 2 | REIM |  |  |  |  | 194.5% | 90.44% | 90.44% | 0 | 1.37% | 352240 | 685262 | -333022 | 0 | 1612 | 1611.52 | 515246 | 619744 | 41098.04 | 34248 | 0 | 619744 | 0 | 0 | 0 | 0 | 0 | 13% | 14.37% | 0% | -13% |  | 45.06
1727 | 2024-02-29 00:36 | P23451 | BAE Tempest - DFM-ASO Planning | Andrew Houghton | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  |  | 74.8% | 57.49% | 21.41% | 0 | -3.35% | 953905 | 713489 | 240416 | 0 | 0 | 0 | 0 | 410202 | 194.04 | 303287 | 308940 | 152752 | 0 | 308939.76 | 0 | 0 | 0 | 28% | 24.65% | 27.12% | -0.88% |  | 53.58
1727 | 2024-02-29 00:36 | P23321 | EHM Cloud Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX | 2024-01-29 | 4 |  |  | 89.76% | 111.4% | 103.8% | 0 | 2.93% | 839969 | 753975 | 85994 | 0 | 0 | 0 | 0 | 839969 | 78.32 | 0 | 69002 | 782467.3333 | 0 | 0 | 69002.4 | 0 | 0 | 28% | 30.93% | 57.58% | 29.58% |  | 49.95
1727 | 2024-02-29 00:36 | P23105 | Raytheon Supply Engineering Support | Natalie Sinclair | RAY | RAYTHEON UNITED KINGDOM LIMITED | MPE | Level 3A | REIM | 2023-07-13 | 3 |  |  | 76.96% | 94.49% | 90.07% | 0 | -2.02% | 1205008 | 927395 | 277613 | 0 | 0 | 0 | 0 | 876292 | 107644.5 | 48740 | 49157 | 835327.8333 | 49156.8 | 0 | 0 | 0 | 0 | 26% | 23.98% | 100% | 74% |  | 48.97
1727 | 2024-02-29 00:36 | P22350 | EMP 2020-2021 | Natalie Sinclair | ARY | GUIDANT GROUP (trading name) | PCPR | Level NC | REIM |  |  |  |  | 93.55% | 98.14% | 94.23% | 0 | -2.02% | 1017580 | 951925 | 65655 | 0 | 400 | 400 | 0 | 934216 | 65.88 | 17709 | 44656 | 897002.6667 | 39833.59 | 4822.56 | 0 | 0 | 0 | 32% | 29.98% | 26.97% | -5.03% |  | 44.07
1727 | 2024-02-29 00:36 | P23117 | BAE Typhoon Eng Support | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 107.6% | 88.52% | 88.52% | 0 | -1.44% | 950772 | 1022826 | -72054 | 0 | 19090 | 21165.02 | 69773.84 | 905368 | 108434.61 | 90362 | 0 | 905368 | 0 | 0 | 0 | 0 | 0 | 30% | 28.56% | 0% | -30% |  | 52.3
1727 | 2024-02-29 00:36 | P23292 | BAE Tempest WP 4 AV Trays | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 75.01% | 91.71% | 76.42% | 0 | 2.06% | 1498284 | 1123917 | 374367 | 0 | 0 | 0 | 0 | 1030718 | 91 | 93199 | 206213 | 858873.8333 | 104014.85 | 102197.8 | 0 | 0 | 0 | 32% | 34.06% | 33.58% | 1.58% |  | 53.14
1727 | 2024-02-29 00:36 | P23519 | Mechanical and Electrical Design Eng Support | Dushan Fernando | BAX | SAFRAN SEATS GB LIMITED | MPE | Level 2 | REIM |  |  |  |  | 62.81% | 98.07% | 72.41% | 0 | -1.53% | 1807261 | 1135204 | 672057 | 0 | 727 | 727 | 0 | 1113290 | 73.3 | 21914 | 349575 | 821977.5 | 349574.52 | 0 | 0 | 0 | 0 | 33% | 31.47% | 31.64% | -1.36% |  | 56.62
1727 | 2024-02-29 00:36 | P22671 | Spirit Shorts Pylon and Fairing Package | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX | 2023-05-03 | 4 |  |  | 105% | 95.26% | 95.26% | 0 | -7.21% | 1198495 | 1258071 | -59576 | 0 | 106495 | 174907.39 | 0 | 1198495 | 2544.39 | 2120 | 0 | 1198495 | 0 | 0 | 0 | 0 | 0 | 20% | 12.79% | 0% | -20% |  | 45.4
1727 | 2024-02-29 00:36 | P23152 | Project Aragon - Design and Stress Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  |  | 93.24% | 59.81% | 59.81% | 0 | -9.54% | 1307861 | 1219418 | 88443 | 0 | 0 | 0 | 0 | 729296 | 298.72 | 490122 | 0 | 729296 | 0 | 0 | 0 | 0 | 0 | 39% | 29.46% | 29.11% | -9.89% |  | 51.89
1727 | 2024-02-29 00:36 | P23411 | Agile & Scrum Delivery Service | Peter Williams | BDZ | MBDA UK LIMITED | DET | Level 2 | REIM | 2023-08-14 | 1 |  |  | 36.3% | 170.5% | 170.5% | 0 | 13.08% | 2487000 | 902904 | 1584096 | 0 | 894179 | 2337284.55 | 0 | 1539600 | 19368.95 | 16141 | 0 | 1539600 | 0 | 0 | 0 | 0 | 0 | 29% | 42.08% | 0% | -29% |  | 74.57
1727 | 2024-02-29 00:36 | P23315 | DAC LUC BAU and Service Workbench | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX | 2024-02-16 | 125 |  |  | 85.17% | 117.4% | 105.3% | 0 | 3.24% | 1573630 | 1340192 | 233438 | 0 | 180 | 180.3 | 0 | 1573630 | 45.31 | -13236 | 195596 | 1410633.3333 | 0 | 0 | 195596.4 | 0 | 0 | 28% | 31.24% | 43.62% | 15.62% |  | 52.35
1727 | 2024-02-29 00:36 | P23435 | Andy Baker Portfolio | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 49.79% | 80.99% | 73.99% | 0 | -7.38% | 3377457 | 1681671 | 1695786 | 0 | 2353 | 2352.57 | 0 | 1361987 | 76.1 | 319684 | 141345 | 1244199.5 | 4794.7 | 136550.72 | 0 | 0 | 0 | 25% | 17.62% | 20.9% | -4.1% |  | 79.64
1727 | 2024-02-29 00:36 | P23006 | Spirit Shorts A350 Freighter Toulouse | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 147.2% | 81% | 81% | 0 | 18.97% | 1035746 | 1524765 | -489019 | 0 | 1086670 | 1708220.2 | 0 | 1235101 | 297.88 | 600938 | 0 | 1235101 | 0 | 0 | 0 | 0 | 0 | 5% | 23.97% | 36.11% | 31.11% |  | 47.8
1727 | 2024-02-29 00:36 | P22278 | TAI Supply Engineers to Ankara | Natalie Sinclair | TAI | TUSAS-TURK HAVACILIK VE UZAY | MPE | Level 3A | REIM |  |  |  |  | 19.27% | 471% | 464.5% | 0 | -15.58% | 2105282 | 405636 | 1699646 | 0 | 49400 | 49400.29 | 0 | 1910696 | 153 | -11654 | 32000 | 1884029.3333 | 16000 | 16000 | 0 | 0 | 0 | 95% | 79.42% | 67.85% | -27.15% |  | 34.27
1727 | 2024-02-29 00:36 | P23257 | BAE Tempest WP 5 Centre Fuselage | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 96.9% | 97.45% | 89.51% | 0 | -5.79% | 2106861 | 2041532 | 65329 | 0 | 78100 | 78100 | 0 | 1989561 | 82.16 | 51970 | 194722 | 1827292.6667 | 88762 | 105959.8 | 0 | 0 | 0 | 33% | 27.21% | 28.15% | -4.85% |  | 61.06
1727 | 2024-02-29 00:36 | P23175 | BAe Aero Typhoon Package 2 | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM |  |  |  |  | 103.8% | 96.32% | 96.32% | 0 | -1.63% | 1984265 | 2060012 | -75747 | 0 | 57678 | 86030.82 | 15444.64 | 1984257 | 84731.75 | 70610 | 0 | 1984257 | 0 | 0 | 0 | 0 | 0 | 29% | 27.37% | 0% | -29% |  | 51.76
1727 | 2024-02-29 00:36 | P23207 | A350 Approvers - Design and Stress Support | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  |  | 97.71% | 91.97% | 52.22% | 169776.21 | -4.5% | 2183628 | 2133598 | 50030 | 0 | 24625 | 24977.09 | 0 | 1962284 | 133.72 | 171314 | 1017732 | 1114174 | 742585.21 | 105370.2 | 0 | 169776.21 | 169776.21 | 23% | 18.5% | 19% | -4% |  | 54.7
1727 | 2024-02-29 00:36 | P19020 | Spirit Concessions - 2018 | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2024-01-23 | 3 |  |  | 90.82% | 111.8% | 107% | 99792.83 | 2.09% | 1914847 | 1739018 | 175829 | 0 | 44318 | 44317.61 | 15178.88 | 1944711 | 3782.41 | 196987 | 99793 | 1861550.1667 | 0 | 0 | 0 | 99792.83 | 99792.83 | 25% | 27.09% | 9.32% | -15.68% |  | 40.87
1727 | 2024-02-29 00:36 | P23179 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX |  |  |  |  | 129.4% | 88.3% | 82.2% | 35500.91 | -9.35% | 1955411 | 2530997 | -575586 | 0 | 156991 | 248243.92 | 492000 | 2234920 | 346.81 | 296077 | 185264 | 2080533.3333 | 140266.99 | 9496.08 | 0 | 35500.91 | 35500.91 | 22% | 12.65% | 16.63% | -5.37% |  | 44.4
1727 | 2024-02-29 00:36 | P23487 | Tornado Air 800 Engineering Support | Richard Brook | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 2 | FIX |  |  |  |  | 105.5% | 84.99% | 76.32% | 0 | -4.38% | 2525468 | 2664884 | -139416 | 0 | 0 | 0 | 196775 | 2264958 | 81.14 | 399926 | 277408 | 2033784.6667 | 277408.04 | 0 | 0 | 0 | 0 | 40% | 35.62% | 38.04% | -1.96% |  | 78.71
1727 | 2024-02-29 00:36 | P19731 | Hapri HPC Rear Bearing Housing PDR & CDR | Steven Lawton | ATC | AECC Hunan Aviation Powerplant | MPE | Level 1 | FIX |  |  |  |  | 99.76% | 100.2% | 87.71% | 447000 | -15.38% | 2980000 | 2972816 | 7184 | 0 | 363828 | 518253.56 | 0 | 2980000 | 808.41 | -232184 | 447000 | 2607500 | 0 | 0 | 447000 | 0 | 447000 | 38% | 22.62% | 12.85% | -25.15% |  | 64.86
Extend Table

## AP3-1
WIP No | Date Created | Project ID | Project Description | Project Manager | Department Id | Client | CBU | Complexity | Type | Stop Booking Hrs | Closing Project: Action(s) to close | RAG | Approx. PO Burndown (weeks) | Turnover vs Contract Value | Invoice To Date vs Turnover | Cash in vs Turnover | Open Amount Overdue | Actual PM% to Baseline PM% delta | Contract Value | Total Project Turnover | Contract Value - Total Turnover | Run Rate (based on total turnover) | Total BOI Spend to Date | Total Committed PO (supplier/best shore) | Current AA in PT3 | Invoiced To Date | DSO | Unbilled (WIP) | Total Open Amount | Cash in (Invoiced - (Open amount -VAT)) | Debt <=30 Days | Debt 31 - 60 Days | Debt 61 - 90 Days | Debt >= 90 Days | Open Amount Overdue2 | Baseline Project Margin | Project To Date (PTD) PM | Year to Date (YTD) PM | YTD Delta Actual PM% to BPM% | Forecast PM at Completion (Manual input from PTT) | Average Sale Rate | CSat score for last quarter (Manual input from PTT) | Comments and Actions | Judged income adjustment at completion | Profit to take now | Provision required now | Fully Traded | Last Months Comments and Actions
1728 | 2024-03-07 00:30 | P23637 | MBSE Proposal | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 | 0 | 0 | 0 | 49980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23822 | FCASW Requirements Management | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 3 | REIM | [7 empty] | 0 | -16% | 0 | 0 | 0 | 0 | 0 | 0 | 35930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16% | 0% | 0% | -16% |  | 0 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23711 | DO NOT USE - RAISED IN ERROR | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23717 | GKN Ted Tomblin 2024 | Matthew Tweed | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  | 0 |  |  |  | 0 | 0% | 0 | 0 | 0 | -1090.13 | 0 | 0 | 10047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23585 | Systems Design - Missile Systems, Meteor,Brimstone | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 | 0 | 0 | 0 | 49500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23552 | FCAS AP Product Technology Development | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -25% | 597871 | 0 | 597871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0% | -25% |  | 0 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23543 | EXP-024 FCAS AP Transformation & Change Enablers | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -26% | 385921 | 0 | 385921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26% | 0% | 0% | -26% |  | 0 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23641 | Drawing Triage | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM | 2024-01-25 | 0 |  | -43024 |  | 0% | 0% | 0 | -1043168% | 0 | 10756 | -10756 | 0.25 | 0 | 0 | 0 | 0 | 0.04 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | -1043168% | 100% | 100% |  | 49 | [5 empty] | -10755
1728 | 2024-03-07 00:30 | P23730 | FLE Project | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -8.5333 |  | 0% | 0% | 0 | -16.79% | 0 | 1120 | -1120 | 131.25 | 0 | 0 | 24000 | 0 | 62 | 1120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | -16.79% | -16.79% | -16.79% |  | 35 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23463 | A220 Wing MaMo Design Checking | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | 7.85% | 0 | 1628 | -1628 | 0 | 0 | 0 | 15000 | 0 | 1953.6 | 1628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | 10.85% | 0% | -3% |  | 44 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P21028 | Rebate Collection (BACC) | David Catchpole | TOO | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | [5 empty] | 0% | 0% | 0 | 0% | 0 | 2680 | -2680 | 0 | 2680 | 2680 | 0 | 0 | 3216 | 2680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23578 | ESN Work Package | Hannah Mead | COZ | CHELTON LIMITED | DET | Level 3 | FIX | 2024-01-01 | 0 |  |  | 86.17% | 116.1% | 116.1% | 0 | 35.86% | 4410 | 3800 | 610 | 0 | 0 | 0 | 0 | 4410 | 0 | -610 | 0 | 4410 | 0 | 0 | 0 | 0 | 0 | 24% | 59.86% | 0% | -24% |  | 95 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23628 | Design Assurance | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -6.67% | 0 | 3909 | -3909 | 0 | 0 | 0 | 4454.8 | 0 | 4691.09 | 3909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 0.33% | 0% | -7% |  | 15.05 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23002 | WoT MAJ Transit Flag Stress | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 30.9% | 323.7% | 323.7% | 0 | 53.84% | 4735 | 1463 | 3272 | 0 | 0 | 2242.5 | 0 | 4735 | 0.6 | 1 | 0 | 4735 | 0 | 0 | 0 | 0 | 0 | 10% | 63.84% | 0% | -10% |  | 45 | [5 empty] | 3273
1728 | 2024-03-07 00:30 | P23718 | Requalification of EJ200 GSS ESS EHM SW module | Vijayakumara Nanjundappa | ARZ | MTU AERO ENGINES AG | DET | Level 3 | FIX |  |  |  | 325.1048 | 8.314% | 292.8% | 48.79% | 0 | -2.92% | 74463 | 6191 | 68272 | 210 | 881 | 881.46 | 0 | 18125 | 62 | -11934 | 18125 | 3020.8333 | 0 | 18125 | 0 | 0 | 0 | 28% | 25.08% | 25.08% | -2.92% |  | 80 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23823 | EXP-034 Spear 3 Test Equip Requirement Authority | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 20.4842 | 8.895% | 48.15% | 0.002183% | 0 | 0.32% | 85825 | 7634 | 78191 | 3817.13 | 0 | 0 | 0 | 3676 | 21 | 3959 | 4411 | 0.16667 | 4410.9 | 0 | 0 | 0 | 0 | 14% | 14.32% | 14.32% | 0.32% |  | 94.25 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23742 | Cyber Security Support | Hannah Mead | COZ | CHELTON LIMITED | DET | Level 3 | FIX |  |  |  | -10.8 |  | 0% | 0% | 0 | 31.67% | 0 | 8100 | -8100 | 750 | 0 | 0 | 9000 | 0 | 84 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 31.67% | 31.67% | 31.67% |  | 100 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23740 | Phase 2 - EJ200 ESS EHM Platform Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 3 | FIX |  |  |  | 120.9719 | 4.719% | 302.7% | -0.002007% | 0 | 0.51% | 175971 | 8304 | 167667 | 1386 | 0 | 0 | 0 | 25139 | 62 | -16835 | 30167 | -0.16667 | 0 | 0 | 30166.8 | 0 | 0 | 28% | 28.51% | 28.51% | 0.51% |  | 57.47 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23607 | SAFRAN - A330neo Turnover Frame | Gary Kempster | TOO | SAFRAN SEATS GB LIMITED | MPE | Level 3 | FIX |  |  |  |  | 95.68% | 104.5% | 0.001994% | 0 | -19.75% | 8736 | 8359 | 377 | 0 | 0 | 0 | 0 | 8736 | 10030.8 | -377 | 10483 | 0.16667 | 0 | 0 | 10483.2 | 0 | 0 | 23% | 3.25% | 0% | -23% |  | 52 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23811 | Spirit T300 MRB Concessions | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -3.0001 |  | 0% | 0% | 0 | -7.24% | 0 | 8824 | -8824 | 2941.23 | 0 | 0 | 34639 | 0 | 21 | 8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21% | 13.76% | 13.76% | -7.24% |  | 46.81 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23274 | ME Support (Aim Altitude - Cambridge) | James Montgomery | AVI | AVIC CABIN SYSTEMS (UK) LIMITED | ME | Level 3 | FIX | 2023-08-18 | 0 |  |  | 51.88% | 56.29% | 56.29% | 0 | -0.17% | 17280 | 8964 | 8316 | 0 | 0 | 0 | 0 | 5046 | 4701.24 | 3918 | 0 | 5046 | 0 | 0 | 0 | 0 | 0 | 21% | 20.83% | 0% | -21% |  | 48 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23283 | Spirit Tooling Audit | Charidimos Valadakis | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-05-03 | 0 |  |  | 97.23% | 48.57% | 48.57% | 0 | -7.99% | 9910 | 9635 | 275 | 0 | 0 | 0 | 0 | 4680 | 5946.05 | 4955 | 0 | 4680 | 0 | 0 | 0 | 0 | 0 | 7% | -0.99% | 0% | -7% |  | 34.41 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23127 | Loft Hall Design Support | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 101% | 99.06% | 99.06% | 0 | -9.55% | 9680 | 9772 | -92 | 0 | 0 | 0 | 0 | 9680 | 110.4 | 92 | 0 | 9680 | 0 | 0 | 0 | 0 | 0 | 41% | 31.45% | 0% | -41% |  | 44 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23630 | 2Excel CFD Analysis Support | Dushan Fernando | BAX | STIRLING DYNAMICS LTD | MPE | Level NC | FIX |  |  |  |  | 61.2% | 100% | 100% | 0 | -1.87% | 16195 | 9911 | 6284 | 0 | 0 | 0 | 0 | 9912 | 0 | 0 | 0 | 9912 | 0 | 0 | 0 | 0 | 0 | 26% | 24.13% | 0% | -26% |  | 64.78 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23313 | Laser Trim Fixtures | Gary Kempster | TOO | ALKEN ENGINEERING LIMITED | MPE | Level 3 | FIX | 2023-11-20 | 0 |  |  | 89.87% | 111.3% | 111.3% | 0 | 0.53% | 13770 | 12375 | 1395 | 0 | 0 | 0 | 0 | 13770 | 0 | -1395 | 0 | 13770 | 0 | 0 | 0 | 0 | 0 | 17% | 17.53% | 0% | -17% |  | 45 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P22761 | Red Bull Chassis Spit | James Montgomery | TOO | MANUFAX ENGINEERING LTD | MPE | Level 3 | FIX | 2022-11-15 | 0 |  |  | 72.19% | 96.98% | 96.98% | 0 | 7.92% | 12961 | 9356 | 3605 | 0 | 0 | 0 | 0 | 9073 | 4666.39 | 3889 | 0 | 9073 | 0 | 0 | 0 | 0 | 0 | 23% | 30.92% | 0% | -23% |  | 42.19 | [5 empty] | 3606
1728 | 2024-03-07 00:30 | P23821 | Supply of Safety Engineer | Dinna Elkhalifa | BXW | STIRLING DYNAMICS LTD | EES | Level NC | REIM |  |  |  | 3.2165 | 38.34% | 100% | 0.003835% | 0 | 20.48% | 34006 | 13038 | 20968 | 6518.9 | 0 | 0 | 0 | 13038 | 80 | 0 | 15645 | 0.5 | 0 | 15645.36 | 0 | 0 | 0 | 0% | 20.48% | 20.48% | 20.48% |  | 55.48 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23663 | Spirit Tooling Verification and Inspection | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 7.4835 | 69.79% | 0% | 0% | 0 | -7.52% | 19820 | 13833 | 5987 | 800.03 | 0 | 0 | 7392 | 0 | 129.72 | 13833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12% | 4.48% | 4.82% | -7.18% |  | 34.41 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23433 | Cavendish | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 32.81% | 100% | 100% | 0 | -0.34% | 42240 | 13859 | 28381 | 0 | 0 | 0 | 0 | 13859 | 0 | 0 | 0 | 13859 | 0 | 0 | 0 | 0 | 0 | 7% | 6.66% | 0% | -7% |  | 43.93 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23350 | Spirit 2023 - Stress Approve Man Serv (DH) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 14.15% | 72.64% | 72.64% | 0 | -0.29% | 97920 | 13860 | 84060 | 0 | 0 | 0 | 0 | 10068 | 4550.4 | 3792 | 0 | 10068 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23344 | Spirit A320 Spoilers Support 2023 | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 38.75% | 100% | 100% | 0 | 5.82% | 35786 | 13867 | 21919 | 0 | 0 | 0 | 0 | 13867 | 0 | 0 | 0 | 13867 | 0 | 0 | 0 | 0 | 0 | 7% | 12.82% | 0% | -7% |  | 34.41 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23337 | Spirit 2023 - Steve Grimley | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 25.28% | 100% | 100% | 0 | 0.01% | 56813 | 14362 | 42451 | 0 | 0 | 0 | 0 | 14362 | 0 | 0 | 0 | 14362 | 0 | 0 | 0 | 0 | 0 | 7% | 7.01% | 0% | -7% |  | 30.11 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23597 | MRB Onsite support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-02-16 | 1 |  | -5.8793 |  | 0% | 0% | 0 | -10.04% | 0 | 15101 | -15101 | 2568.49 | 9448 | 17381.62 | 24200 | 0 | 91 | 15101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 7.96% | 8.95% | -9.05% |  | 42.5 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23724 | GKN S McConnell 2024 | Matthew Tweed | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  | 18.243 | 32.5% | 88.61% | -0.002059% | 0 | 1.51% | 49820 | 16192 | 33628 | 1843.34 | 0 | 0 | 0 | 14348 | 62 | 1843 | 17218 | -0.33333 | 0 | 17217.79 | 0 | 0 | 0 | 19% | 20.51% | 20.51% | 1.51% |  | 49.82 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23598 | MRB Onsite support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -5.2183 |  | 0% | 0% | 0 | -7.52% | 0 | 17236 | -17236 | 3302.96 | 8736 | 14079.58 | 21700 | 0 | 91 | 17236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 10.48% | 11.05% | -6.95% |  | 42.5 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23635 | Engineering Services: FAI Support | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 40.168 | 49.9% | 0% | 0% | 0 | -3.4% | 37230 | 18576 | 18654 | 464.4 | 0 | 0 | 0 | 0 | 202.22 | 18576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8% | 4.6% | 5.04% | -2.96% |  | 38.7 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23343 | Spirit 2023 - John Agnew | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-08-09 | 0 |  |  | 28.56% | 86.27% | 86.27% | 0 | -0.02% | 65120 | 18601 | 46519 | 0 | 0 | 0 | 0 | 16047 | 3064.49 | 2554 | 0 | 16047 | 0 | 0 | 0 | 0 | 0 | 7% | 6.98% | 0% | -7% |  | 34.51 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23355 | Spirit Tooling Support 2023 | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-23 | 0 |  |  | 22.93% | 89.03% | 89.03% | 0 | -0.82% | 91800 | 21053 | 70747 | 0 | 0 | 0 | 0 | 18743 | 2773.01 | 2311 | 0 | 18743 | 0 | 0 | 0 | 0 | 0 | 20% | 19.18% | 0% | -20% |  | 44.46 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23651 | PMO Spirit | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -24.0524 |  | 0% | 0% | 0 | 23.97% | 0 | 24786 | -24786 | 1030.5 | 0 | 0 | 42680 | 0 | 180.04 | 24786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 23.97% | 23.23% | 23.23% |  | 36 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23351 | Spirit 2023 - Design Man Serv (KL) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 26.47% | 93.15% | 93.15% | 0 | 0.09% | 93840 | 24840 | 69000 | 0 | 0 | 0 | 0 | 23138 | 2042.4 | 1702 | 0 | 23138 | 0 | 0 | 0 | 0 | 0 | 26% | 26.09% | 0% | -26% |  | 46 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23356 | Spirit 2023 - Design Man Serv (AH) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX | 2023-08-09 | 1 |  |  |  | 76.66% | 0.001332% | 23018.4 | 0.48% | 0 | 25023 | -25023 | 0 | 0 | 0 | 25300 | 19182 | 30027.7 | 5841 | 23018 | 0.33333 | 0 | 0 | 0 | 23018.4 | 23018.4 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P22884 | Spirit Shorts Config Eng | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 66.3% | 100.1% | 100.1% | 0 | 0.56% | 38976 | 25842 | 13134 | 0 | 0 | 0 | 0 | 25863 | 0 | 0 | 0 | 25863 | 0 | 0 | 0 | 0 | 0 | 7% | 7.56% | 0% | -7% |  | 20.3 | [5 empty] | 21
1728 | 2024-03-07 00:30 | P23760 | EXP-033 Systems Engineering Support | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 40.2512 | 18.4% | 91% | 0% | 0 | -0.02% | 142300 | 26180 | 116120 | 2884.88 | 0 | 0 | 0 | 23825 | 62 | 2355 | 28590 | 0 | 0 | 28589.7 | 0 | 0 | 0 | 29% | 28.98% | 28.98% | -0.02% |  | 78.5 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23354 | Spirit 2023 - Design Man Serv (PC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 27.97% | 99.36% | 99.36% | 0 | 0.48% | 93840 | 26249 | 67591 | 0 | 0 | 0 | 0 | 26082 | 200.38 | 167 | 0 | 26082 | 0 | 0 | 0 | 0 | 0 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P22756 | A350 FLE Design Checker | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2022-03-23 | 1 |  |  | 68.39% | 119.7% | 119.7% | 0 | 16.46% | 34898 | 23867 | 11031 | 0 | 23867 | 24342.3 | 0 | 28571 | 0.06 | 0 | 0 | 28571 | 0 | 0 | 0 | 0 | 0 | 0% | 16.46% | 0% | 0% |  | 0 | [5 empty] | 4704
1728 | 2024-03-07 00:30 | P23338 | Spirit 2023 - Blair Hainey | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 8.4648 | 85.08% | 61.47% | 61.47% | 0 | 4.48% | 34494 | 29349 | 5145 | 607.81 | 0 | 0 | 0 | 18042 | 139.23 | 11306 | 0 | 18042 | 0 | 0 | 0 | 0 | 0 | 7% | 11.48% | 19.31% | 12.31% |  | 18.28 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23458 | Spirit Belfast Tooling Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-08-11 | 0 |  |  | 101.3% | 94.65% | 94.65% | 0 | 8.64% | 30384 | 30785 | -401 | 0 | 0 | 0 | 0 | 29139 | 1974.96 | 1646 | 0 | 29139 | 0 | 0 | 0 | 0 | 0 | 7% | 15.64% | 0% | -7% |  | 42.2 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23365 | GKN 777x Lip Skin Fixture | Steven Lawton | TOO | GKN AEROSPACE SERVICES LTD | MPE | Level 3 | FIX | 2023-10-12 | 0 |  |  | 41.91% | 113.2% | 113.2% | 0 | -9.26% | 79161 | 33176 | 45985 | 0 | 5110 | 5109.88 | 0 | 37544 | 0 | -4369 | 0 | 37544 | 0 | 0 | 0 | 0 | 0 | 22% | 12.74% | 0% | -22% |  | 56 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P22768 | MRB Onsite Support - Spirit Belfast | James Montgomery | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2023-07-27 | 0 |  |  |  | 0% | 0% | 0 | -17.07% | 0 | 34614 | -34614 | 0 | 0 | 0 | 36800 | 0 | 41536.8 | 34614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | -7.07% | 0% | -10% |  | 36 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23642 | MRB Belfast Support | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -20.5309 |  | 0% | 0% | 0 | -42.02% | 0 | 34742 | -34742 | 1692.18 | 2948 | 2947.65 | 42350 | 0 | 147.82 | 34742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22% | -20.02% | -22.41% | -44.41% |  | 38.52 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23347 | WoT Fixed Leading Edge - Industrial 2023 | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 112.8% | 42.03% | 42.03% | 0 | -0.41% | 31034 | 35002 | -3968 | 0 | 0 | 0 | 10500 | 14711 | 24349.85 | 20292 | 0 | 14711 | 0 | 0 | 0 | 0 | 0 | 7% | 6.59% | 0% | -7% |  | 32.26 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23729 | Honda Tooling | Paul Watson | STX | SHORT BROTHERS PLC | MPE | Level NC | FIX |  |  |  | 8.3831 | 48.07% | 89.28% | 0% | 0 | 5.02% | 75600 | 36341 | 39259 | 4683.14 | 0 | 0 | 0 | 32445 | 56 | 3896 | 38934 | 0 | 38934 | 0 | 0 | 0 | 0 | 10% | 15.02% | 15.02% | 5.02% |  | 42 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23753 | Tempest Composites Maturation | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | -6.7497 |  | 0% | 0% | 0 | -21.99% | 0 | 39504 | -39504 | 5852.69 | 0 | 0 | 54398.4 | 0 | 63 | 39504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37% | 15.01% | 15.01% | -21.99% |  | 64.76 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23051 | Spirit Shorts A350 PAX Door | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 3A | REIM |  |  |  |  | 205.9% | 105.4% | 105.4% | 0 | -0.63% | 18216 | 37513 | -19297 | 0 | 0 | 0 | 0 | 39537 | 0 | 0 | 0 | 39537 | 0 | 0 | 0 | 0 | 0 | 30% | 29.37% | 0% | -30% |  | 46 | [5 empty] | 2024
1728 | 2024-03-07 00:30 | P22752 | Tooling WoT - 2021 (Spirit) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | REIM | 2023-05-03 | 0 |  |  | 101.1% | 74.02% | 74.02% | 0 | -8.5% | 41525 | 41982 | -457 | 0 | 0 | 0 | 0 | 31076 | 13087.42 | 10906 | 0 | 31076 | 0 | 0 | 0 | 0 | 0 | 0% | -8.5% | 0% | 0% |  | 39.09 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23744 | Model Factory | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 39.3562 | 16.76% | 101.7% | 0.0003792% | 0 | 6.4% | 262300 | 43952 | 218348 | 5548 | 0 | 0 | 0 | 44716 | 62 | -764 | 53659 | 0.16667 | 0 | 26229.6 | 27429.6 | 0 | 0 | 28% | 34.4% | 34.4% | 6.4% |  | 50.75 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23700 | IPDT Leads | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 34.5466 | 26.67% | 0% | 0% | 0 | 11.51% | 169264 | 45141 | 124123 | 3592.91 | 0 | 0 | 0 | 0 | 91 | 45141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26% | 37.51% | 37.85% | 11.85% |  | 61.88 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23339 | Spirit 2023 - Stewart Russell | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 64.51% | 100% | 100% | 0 | 0.62% | 72767 | 46942 | 25825 | 0 | 0 | 0 | 0 | 46942 | 0 | 0 | 0 | 46942 | 0 | 0 | 0 | 0 | 0 | 7% | 7.62% | 0% | -7% |  | 35.67 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P22760 | SA Leading Edge Transport Media ('A' Frames) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-11-15 | 1 |  |  | 85.99% | 110.7% | 116.3% | -3082.8 | 3.97% | 53481 | 45986 | 7495 | 0 | 42804 | 42804 | 0 | 50912 | 0 | 0 | -3083 | 53481.1667 | 0 | 0 | 0 | -3082.8 | -3082.8 | 6% | 9.97% | 0% | -6% |  | 42 | [5 empty] | 4926
1728 | 2024-03-07 00:30 | P23754 | Tempest Composites WP4 | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -8.5406 |  | 0% | 0% | 0 | 7.75% | 0 | 51771 | -51771 | 6061.74 | 149 | 149.25 | 97140 | 0 | 77 | 51771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 35.75% | 35.75% | 7.75% |  | 64.89 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23382 | Performance Modelling | Dushan Fernando | BDX | MBDA UK LIMITED | MPE | Level NC | REIM | 2023-07-09 | 0 |  |  | 40.95% | 79.09% | 79.09% | 0 | -16.36% | 170010 | 69626 | 100384 | 0 | 14560 | 14559.9 | 0 | 55066 | 0 | 0 | 0 | 55066 | 0 | 0 | 0 | 0 | 0 | 20% | 3.64% | 0% | -20% |  | 77.05 | [5 empty] | -14560
1728 | 2024-03-07 00:30 | P23349 | Spirit 2023 - Stress Approve Man Serv (SB) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 58.24% | 80.05% | 80.05% | 0 | -0.29% | 97920 | 57024 | 40896 | 0 | 0 | 0 | 0 | 45648 | 13651.2 | 11376 | 0 | 45648 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23322 | GKN T Tomblin 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  | 0.9179 | 96.85% | 97.81% | 85.83% | 0 | -0.33% | 58952 | 57096 | 1856 | 2022 | 0 | 0 | 0 | 55848 | 77.05 | 1248 | 8208 | 49008 | 0 | 8208 | 0 | 0 | 0 | 17% | 16.67% | 16.67% | -0.33% |  | 48 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23784 | Tempest Tooling Offload 2024 | Christopher McCarthy | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  | -6.0234 |  | 0% | 0% | 0 | -11.1% | 0 | 59651 | -59651 | 9903.22 | 0 | 0 | 74725 | 0 | 62 | 59651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 18.9% | 18.9% | -11.1% |  | 54.86 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23341 | Spirit 2023 - Tom McFarlane | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 28.1758 | 55.55% | 81.08% | 71.26% | 0 | -0.01% | 108666 | 60369 | 48297 | 1714.13 | 0 | 0 | 0 | 48945 | 138.2 | 11425 | 7110 | 43020 | 0 | 0 | 0 | 7110.19 | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23193 | Spirit Shorts Stephen Greer | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -0.0045497 | 100% | 88.91% | 88.91% | 0 | 8.49% | 61472 | 61475 | -3 | 659.39 | 0 | 0 | 10878 | 54656 | 75.31 | 6820 | 0 | 54656 | 0 | 0 | 0 | 0 | 0 | 23% | 31.49% | 34.03% | 11.03% |  | 35.03 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23106 | ME Support to NPD - Bobby Haggart | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  |  | 95.79% | 97.03% | 97.03% | 0 | 0.3% | 65675 | 62912 | 2763 | 0 | 0 | 0 | 0 | 61043 | 2243.24 | 1869 | 0 | 61043 | 0 | 0 | 0 | 0 | 0 | 15% | 15.3% | 0% | -15% |  | 35.65 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23561 | SAAB | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2024-01-01 | 0 |  |  | 82.46% | 121.1% | 121.1% | 0 | 3.5% | 67485 | 55649 | 11836 | 0 | 0 | 0 | 0 | 67399 | 0 | -4408 | 0 | 67399 | 0 | 0 | 0 | 0 | 0 | 16% | 19.5% | 0% | -16% |  | 36.82 | [5 empty] | 7342
1728 | 2024-03-07 00:30 | P22967 | Spirit 2022 - Channapa Laxmeshwar | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2023-01-26 | 2 |  |  | 69.69% | 121.3% | 121.3% | 0 | 9.53% | 75159 | 52376 | 22783 | 0 | 52376 | 54898.1 | 0 | 63509 | 0.42 | 0 | 0 | 63509 | 0 | 0 | 0 | 0 | 0 | 8% | 17.53% | 0% | -8% |  | 0 | [5 empty] | 11133
1728 | 2024-03-07 00:30 | P23342 | Spirit 2023 - Channapa Laxmeshwar | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 78.75% | 104.3% | 98.93% | 0 | -2.64% | 79348 | 62484 | 16864 | 0 | 62484 | 94827 | 0 | 65178 | 4224.9 | 157 | 4037 | 61813.8333 | 0 | 0 | 0 | 4036.8 | 0 | 7% | 4.36% | 0% | -7% |  | 0 | [5 empty] | 2850
1728 | 2024-03-07 00:30 | P23080 | Spirit Shorts DManagement Cairan Cullen | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 506.0547 | 49.33% | 97.96% | 93.68% | 3787.8 | -0.95% | 149600 | 73793 | 75807 | 149.8 | 0 | 0 | 0 | 72284 | 212.17 | 1509 | 3788 | 69127.3333 | 0 | 0 | 0 | 3787.8 | 3787.8 | 24% | 23.05% | 13.22% | -10.78% |  | 44.44 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23600 | MBDA EXP-EE-023 Bristone Certification | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 59.65% | 100% | 100% | 0 | 0.4% | 126600 | 75517 | 51083 | 0 | 0 | 0 | 0 | 75517 | 0 | 0 | 0 | 75517 | 0 | 0 | 0 | 0 | 0 | 41% | 41.4% | 0% | -41% |  | 78.5 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23438 | A220 Spirit Shorts DTC - Stephen Corry | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 9.5497 | 81.99% | 51.36% | 51.36% | 0 | -7.31% | 95928 | 78653 | 17275 | 1808.95 | 0 | 0 | 0 | 40400 | 214.65 | 38254 | 0 | 40400 | 0 | 0 | 0 | 0 | 0 | 23% | 15.69% | 17.14% | -5.86% |  | 49.78 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23340 | Spirit 2023 - John Cole | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -2.9426 | 105.5% | 79.4% | 70.1% | 0 | -0.01% | 75065 | 79162 | -4097 | 1392.3 | 0 | 0 | 8831 | 62852 | 132.06 | 16310 | 8831 | 55492.8333 | 0 | 0 | 0 | 8831.16 | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 39.78 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P22505 | Spirit MRB Engineering Support 2021 | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 1 |  |  | 91.17% | 100% | 95.78% | 4020.48 | 21.2% | 87110 | 79415 | 7695 | 0 | 0 | 0 | 0 | 79415 | 4020.48 | 0 | 4020 | 76065 | 0 | 0 | 0 | 4020.48 | 4020.48 | 0% | 21.2% | 0% | 0% |  | 41.88 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23560 | NJEWCS TAF202302 SM | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level 2 | FIX |  |  |  | 0.63976 | 97.96% | 50.1% | 50.1% | 0 | 11.75% | 81500 | 79836 | 1664 | 2600.98 | 0 | 0 | 0 | 40000 | 153.96 | 39836 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 28% | 39.75% | 38.83% | 10.83% |  | 73.01 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23586 | Project Management Support | Peter Bowen | BDX | MBDA UK LIMITED | MPE | Level NC | REIM |  |  |  | -0.26466 | 100.9% | 83.15% | 79.9% | 0 | -26.01% | 80000 | 80704 | -704 | 2660 | 1141 | 1140.6 | 16000 | 67104 | 44.75 | 13600 | 3149 | 64479.8333 | 0 | 3148.63 | 0 | 0 | 0 | 49% | 22.99% | 22.4% | -26.6% |  | 80 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P22885 | ME Support (Baxi) | James Montgomery | HUV | BAXI HEATING UK LIMITED | ME | Level 3 | FIX | 2023-01-12 | 0 |  |  | 68.78% | 108.7% | 108.7% | 0 | 13.05% | 106633 | 73340 | 33293 | 0 | 0 | 0 | 0 | 79748 | 1531.35 | 1276 | 0 | 79748 | 0 | 0 | 0 | 0 | 0 | 15% | 28.05% | 0% | -15% |  | 44.37 | [5 empty] | 7684
1728 | 2024-03-07 00:30 | P23345 | Spirit 2023- Jonathan Escosio | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | -3.4861 | 106.8% | 79.41% | 63.14% | 7150.18 | -6.35% | 75971 | 81164 | -5193 | 1489.62 | 0 | 0 | 8938 | 64456 | 162.92 | 16708 | 15846 | 51251 | 0 | 0 | 0 | 15846.34 | 7150.18 | 7% | 0.65% | 0.65% | -6.35% |  | 40.26 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23465 | A220 ToW Design Offload (Wing) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 11.9194 | 62.22% | 67.9% | 67.9% | 0 | -4.41% | 132000 | 82133 | 49867 | 4183.7 | 0 | 0 | 0 | 55768 | 77.64 | 26365 | 0 | 55768 | 0 | 0 | 0 | 0 | 0 | 20% | 15.59% | 14.57% | -5.43% |  | 42.8 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23551 | Ian Berry 2023 H2 | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  | -2.1553 | 108.6% | 81.67% | 81.67% | 0 | 12.82% | 75810 | 82305 | -6495 | 3013.5 | 0 | 0 | 24259.2 | 67217 | 44.05 | 15088 | 0 | 67217 | 0 | 0 | 0 | 0 | 0 | 22% | 34.82% | 36.83% | 14.83% |  | 77.17 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23336 | Spirit 2023 - Neil Rampling | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 34.3082 | 61.59% | 79.85% | 58.03% | 13070.83 | -0.01% | 133902 | 82473 | 51429 | 1499.03 | 0 | 0 | 0 | 65851 | 189.48 | 16622 | 21586 | 47862.6667 | 0 | 0 | 0 | 21586.03 | 13070.83 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23171 | Spirt Shorts Weights Eng | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 9.7699 | 69.18% | 122.7% | 96.15% | 0 | 2.68% | 103113 | 71329 | 31784 | 3253.26 | 71329 | 85975.13 | 0 | 87532 | 105.02 | -3932 | 22740 | 68582 | 0 | 16774.18 | 5965.46 | 0 | 0 | 12% | 14.68% | 0% | -12% |  | 0 | [5 empty] | 12270
1728 | 2024-03-07 00:30 | P23335 | GKN S McConnell 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2023-12-31 | 2 |  |  | 96.61% | 100% | 83.53% | 0 | 0.74% | 87420 | 84459 | 2961 | 0 | 0 | 0 | 0 | 84459 | 242.67 | 0 | 16694 | 70547.3333 | 0 | 0 | 0 | 16694.4 | 0 | 15% | 15.74% | 0% | -15% |  | 47 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P22965 | Spirit 2022 - Design Man Serv (AH) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 1 |  |  | 106.7% | 96.66% | 92.02% | 4759.75 | 3.14% | 80080 | 85441 | -5361 | 0 | 0 | 0 | 0 | 82589 | 8182.59 | 2852 | 4760 | 78622.3333 | 0 | 0 | 0 | 4759.75 | 4759.75 | 14% | 17.14% | 0% | -14% |  | 42.44 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23523 | Applique Armour Support | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 1 |  |  | 72.43% | 138.1% | 98.47% | 0 | 3.42% | 118200 | 85607 | 32593 | 0 | 0 | 0 | 0 | 118200 | 1567.8 | -32594 | 40680 | 84300 | 40680 | 0 | 0 | 0 | 0 | 25% | 28.42% | 0% | -25% |  | 64.29 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23079 | Spirit Shorts Nomenclature | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 4.0265 | 97.08% | 79.59% | 79.59% | 10554.48 | 1.91% | 88455 | 85870 | 2585 | 642 | 0 | 0 | 0 | 68343 | 214.16 | 17527 | 0 | 68343 | -10554.48 | 0 | 0 | 10554.48 | 10554.48 | 20% | 21.91% | 25.23% | 5.23% |  | 30.73 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P22964 | Spirit 2022 - MRB Man Serv (JC) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 100.6% | 97.95% | 97.95% | 0 | 1.91% | 85435 | 85960 | -525 | 0 | 0 | 0 | 0 | 84200 | 2112.62 | 1761 | 0 | 84200 | 0 | 0 | 0 | 0 | 0 | 16% | 17.91% | 0% | -16% |  | 42.69 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P22963 | Spirit 2022 - Design Man Serv (PC) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 1 |  |  | 108.6% | 104% | 94.46% | 9938.48 | 3.18% | 80080 | 86927 | -6847 | 0 | 0 | 0 | 0 | 90390 | 5782.63 | -3463 | 9938 | 82108.3333 | 0 | 0 | 0 | 9938.48 | 9938.48 | 13% | 16.18% | 0% | -13% |  | 42.39 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23741 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  | 48.2251 | 13.6% | 101.9% | 0% | 0 | 0.65% | 640812 | 87142 | 553670 | 11480.95 | 0 | 0 | 0 | 88770 | 62 | -1628 | 106524 | 0 | 0 | 52662 | 53862 | 0 | 0 | 28% | 28.65% | 28.65% | 0.65% |  | 38.62 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23816 | Typhoon FTI Works - 2024 Fixed Price Element | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -2 |  | 0% | 0% | 0 | -3.36% | 0 | 88374 | -88374 | 44186.89 | 0 | 0 | 146328 | 0 | 28 | 88374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29% | 25.64% | 25.64% | -3.36% |  | 53.77 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23583 | Castalla - Test Rig Design | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -12.4179 | 137.6% | 65.92% | 65.92% | 0 | -6.46% | 67520 | 92927 | -25407 | 2046 | 0 | 0 | 36106 | 61258 | 118.83 | 31669 | 0 | 61258 | 0 | 0 | 0 | 0 | 0 | 21% | 14.54% | 17.36% | -3.64% |  | 42.7 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23375 | GKN Jaap Peters NL 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2024-03-01 | 5 |  | 1.7666 | 93.37% | 105.3% | 76.89% | 0 | -15.93% | 97123 | 90686 | 6437 | 3643.74 | 90686 | 92269.6 | 0 | 95457 | 92.36 | -920 | 30879 | 69724.5 | 0 | 8793.29 | 0 | 22086.17 | 0 | 20% | 4.07% | 0% | -20% |  | 0 | [5 empty] | 3850
1728 | 2024-03-07 00:30 | P23545 | Ultra CSS continuation 2023 H2 | Natalie Sinclair | ULT | ULTRA SONAR SYSTEMS LIMITED | EES | Level NC | REIM |  |  |  | -7.6807 | 129% | 76.97% | 44.84% | 0 | 2.23% | 76000 | 98022 | -22022 | 2867.2 | 0 | 0 | 24259.2 | 75451 | 170.19 | 22571 | 37794 | 43956 | 0 | 37794.24 | 0 | 0 | 0 | 23% | 25.23% | 25% | 2% |  | 80 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23588 | BAE Typhoon MRB MC Shop Concessions | Andrew Houghton | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 37.2667 | 57.94% | 90.99% | 50.81% | 0 | -4.03% | 175061 | 101438 | 73623 | 1975.57 | 0 | 0 | 0 | 92296 | 151.19 | 9142 | 48910 | 51537.6667 | 0 | 48910.43 | 0 | 0 | 0 | 31% | 26.97% | 29.13% | -1.87% |  | 55.56 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23664 | Tempest Composites WP3 | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 7.3932 | 85.04% | 15.86% | 15.86% | 0 | -5.19% | 122455 | 104137 | 18318 | 2477.69 | 0 | 0 | 0 | 16519 | 144.53 | 87619 | 0 | 16519 | 0 | 0 | 0 | 0 | 0 | 37% | 31.81% | 34.14% | -2.86% |  | 60.47 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23353 | Spirit 2023 - MRB Man Serv (JC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  | -3.3022 | 113.8% | 65.68% | 65.68% | 0 | 10.29% | 91800 | 104468 | -12668 | 3836.25 | 0 | 0 | 13320 | 68615 | 155.58 | 35852 | 0 | 68615 | 0 | 0 | 0 | 0 | 0 | 7% | 17.29% | 14.44% | 7.44% |  | 45 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23739 | Lifing Services DACs | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  | 42.972 | 16.3% | 103.2% | -0.0003115% | 0 | 2.98% | 656508 | 107012 | 549496 | 12787.3 | 0 | 0 | 0 | 110418 | 62 | -3406 | 132502 | -0.33333 | 0 | 65650.8 | 66850.8 | 0 | 0 | 28% | 30.98% | 30.98% | 2.98% |  | 37.79 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23352 | Spirit 2023 - Stress Approve Man Serv (CC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  | -3.85 | 109.4% | 65.24% | 65.24% | 0 | 7.29% | 97920 | 107160 | -9240 | 2400 | 0 | 0 | 10656 | 69912 | 177.87 | 37248 | 0 | 69912 | 0 | 0 | 0 | 0 | 0 | 7% | 14.29% | 4.69% | -2.31% |  | 48 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P22918 | Spirit Shorts Graduates | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 13.2981 | 83.73% | 98.06% | 64.63% | 0 | 9.66% | 130000 | 108848 | 21152 | 1590.6 | 0 | 0 | 9900 | 106735 | 202.74 | 2113 | 43660 | 70351.6667 | 0 | 43659.95 | 0 | 0 | 0 | 7% | 16.66% | 19.09% | 12.09% |  | 23.26 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23743 | EHM Cloud Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 47.511 | 10.76% | 156.2% | 0.0003049% | 0 | -0.88% | 1016000 | 109329 | 906671 | 19083.38 | 0 | 0 | 0 | 170752 | 62 | -61423 | 204902 | 0.33333 | 0 | 102412.8 | 102489.6 | 0 | 0 | 28% | 27.12% | 27.12% | -0.88% |  | 52.16 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23282 | Tooling Support (MBDA) | Dushan Fernando | BDV | MBDA UK LIMITED | ME | Level NC | REIM |  |  |  | -5.6695 | 109.9% | 90.08% | 90.08% | 0 | -8.99% | 104834 | 115233 | -10399 | 1834.19 | 0 | 0 | 19964 | 103804 | 50.58 | 11429 | 0 | 103804 | 0 | 0 | 0 | 0 | 0 | 30% | 21.01% | 30.37% | 0.37% |  | 49.7 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P22883 | Spirit Shorts Evtol PMO C. Hatton | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 56.7469 | 62.71% | 93.51% | 82.93% | 14784 | -12.01% | 185800 | 116512 | 69288 | 1221 | 0 | 0 | 0 | 108947 | 155.78 | 7565 | 14784 | 96627 | 0 | 0 | 0 | 14784 | 14784 | 26% | 13.99% | 24.2% | -1.8% |  | 36.56 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23270 | Shorts Project X | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 14.722 | 82.33% | 75.05% | 75.05% | 0 | 0.72% | 142248 | 117107 | 25141 | 1707.72 | 0 | 0 | 0 | 87889 | 132.95 | 29218 | 0 | 87889 | 0 | 0 | 0 | 0 | 0 | 13% | 13.72% | 10.99% | -2.01% |  | 45.36 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P22736 | WoT Fixed Leading Edge - Industrial | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 106.7% | 93.42% | 91.32% | 3019.54 | 0.01% | 112196 | 119668 | -7472 | 0 | 0 | 0 | 0 | 111797 | 12465.69 | 7872 | 3020 | 109280.3333 | 0 | 0 | 0 | 3019.54 | 3019.54 | 7% | 7.01% | 0% | -7% |  | 32.26 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P22861 | WoT FLE Lifting & Handling Tools | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2023-06-14 | 1 |  |  | 65.17% | 101.6% | 101.6% | 0 | 12.01% | 173987 | 113382 | 60605 | 0 | 50078 | 58423.58 | 0 | 115204 | 12813.9 | 10678 | 0 | 115204 | 0 | 0 | 0 | 0 | 0 | 1% | 13.01% | 0% | -1% |  | 45 | [5 empty] | 12500
1728 | 2024-03-07 00:30 | P23810 | Strategic Enablement | Owain Jones | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -3 |  | 0% | 0% | 0 | -20.58% | 0 | 133060 | -133060 | 44353.4 | 0 | 0 | 134000 | 0 | 63 | 133060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | -2.58% | -2.58% | -20.58% |  | 42 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23677 | ME Managed Service - Phase 1 | Paul Watson | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  | 26.8662 | 24.6% | 0% | 0% | 0 | -23.71% | 554400 | 136395 | 418005 | 15558.75 | 0 | 0 | 0 | 0 | 112.3 | 136395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33% | 9.29% | 11.91% | -21.09% |  | 45 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23421 | A220 DTC | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 19.182 | 64.36% | 76.65% | 76.65% | 0 | -30.08% | 217089 | 139721 | 77368 | 4033.37 | 0 | 0 | 0 | 107094 | 71.42 | 32626 | 0 | 107094 | 0 | 0 | 0 | 0 | 0 | 29% | -1.08% | 3.29% | -25.71% |  | 45.07 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23533 | External Stowage Design and Detail Support | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 1 |  |  | 102.4% | 97.65% | 73.24% | 0 | 3.33% | 140000 | 143369 | -3369 | 0 | 0 | 0 | 12936 | 140000 | 41999.7 | 0 | 42000 | 105000 | 42000 | 0 | 0 | 0 | 0 | 27% | 30.33% | 0% | -27% |  | 60.04 | [5 empty] | -3369
1728 | 2024-03-07 00:30 | P23667 | Safety Systems Engineer | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 63.113 | 35.46% | 97.12% | 74.67% | 0 | -8.91% | 398000 | 141130 | 256870 | 4070 | 0 | 0 | 0 | 137060 | 59.75 | 4070 | 38016 | 105380 | 0 | 19536 | 18480 | 0 | 0 | 47% | 38.09% | 29.32% | -17.68% |  | 110 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23648 | EXP-032 Delivery of Datalink Eng support - FCAS AP | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 28.8278 | 38.76% | 94.53% | 71.53% | 0 | 4.98% | 371000 | 143783 | 227217 | 7881.88 | 1033 | 1032.95 | 0 | 135913 | 41.31 | 7870 | 39685 | 102842.1667 | 0 | 39684.54 | 0 | 0 | 0 | 22% | 26.98% | 26.9% | 4.9% |  | 103.63 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23437 | Embedded Software Engineer | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 1.6578 | 96.79% | 98% | 87.7% | 0 | -6.31% | 150150 | 145335 | 4815 | 2904.5 | 738 | 737.86 | 0 | 142430 | 47.66 | 2905 | 17961 | 127462.5 | 0 | 17960.7 | 0 | 0 | 0 | 22% | 15.69% | 16.24% | -5.76% |  | 78.5 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P22954 | Technical Support Step 1 | Owain Jones | HUV | HUARUI SPIRIT AEROSPACE MANUFACT | ME | Level 2 | REIM |  |  |  |  | 94.81% | 58.01% | 58.01% | 0 | 0.31% | 155501 | 147432 | 8069 | 0 | 23043 | 23043 | 0 | 85525 | 61906.09 | 61906 | 0 | 85525 | 0 | 0 | 0 | 0 | 0 | 30% | 30.31% | 0% | -30% |  | 60.79 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23386 | Software Development - BMS | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 2.387 | 98.78% | 100% | 95.49% | 0 | 4.31% | 149650 | 147823 | 1827 | 765.38 | 0 | 0 | 0 | 147823 | 24.49 | 0 | 8007 | 141150.5 | 0 | 8007 | 0 | 0 | 0 | 18% | 22.31% | 22.61% | 4.61% |  | 78.5 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P22982 | Spirit 2022 - Hugh Sloan | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 105.9789 | 59.93% | 90.22% | 85.6% | 0 | -0.01% | 247473 | 148299 | 99174 | 935.79 | 0 | 0 | 0 | 133795 | 160.36 | 14504 | 8217 | 126947.5 | 0 | 0 | 0 | 8217.17 | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 35.42 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23518 | Systems Engineering support to FCAS | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 15.4712 | 76.73% | 95.14% | 87.32% | 0 | -2.39% | 193737 | 148649 | 45088 | 2914.31 | 3927 | 3927.4 | 0 | 141422 | 46.75 | 7227 | 13942 | 129803.6667 | 0 | 13941.6 | 0 | 0 | 0 | 30% | 27.61% | 3.5% | -26.5% |  | 67.35 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23550 | Tempest Composites | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -0.17396 | 100.2% | 99.83% | 84.38% | 0 | 5.13% | 149495 | 149755 | -260 | 1494.56 | 0 | 0 | 2396.12 | 149495 | 95.99 | 260 | 27760 | 126361.6667 | 0 | 27760.26 | 0 | 0 | 0 | 26% | 31.13% | 34.44% | 8.44% |  | 61.6 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P22440 | Spirit Managed Service - F&DT and Static Approval | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 3 |  |  | 88.56% | 92.56% | 92.56% | 0 | 11.51% | 173500 | 153656 | 19844 | 0 | 52115 | 55720 | 0 | 142225 | 13717.36 | 11431 | 0 | 142225 | 0 | 0 | 0 | 0 | 0 | 0% | 11.51% | 0% | 0% |  | 44.73 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23464 | A220 Project X Design Offload | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 57.5488 | 47.94% | 83.68% | 69.1% | 27862.8 | -9.05% | 332340 | 159308 | 173032 | 3006.7 | 0 | 0 | 0 | 133307 | 132.26 | 26001 | 27863 | 110087.8333 | 0 | 0 | 0 | 27862.8 | 27862.8 | 26% | 16.95% | 15.38% | -10.62% |  | 42.89 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23508 | Verification and Validation | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 16.1432 | 79.25% | 98.92% | 90.63% | 0 | 10.92% | 212950 | 168755 | 44195 | 2737.69 | 0 | 0 | 0 | 166930 | 28.57 | 1825 | 16791 | 152937.5 | 0 | 16791.16 | 0 | 0 | 0 | 24% | 34.92% | 34.2% | 10.2% |  | 78.5 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23506 | ASTER Mid-Life Refurbishment Project Manager | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 10.8472 | 79.53% | 97.69% | 87.03% | 0 | 1% | 224900 | 178861 | 46039 | 4244.32 | 2806 | 2806.41 | 0 | 174736 | 42.48 | 4125 | 22897 | 155655.1667 | 0 | 22896.62 | 0 | 0 | 0 | 25% | 26% | 26.25% | 1.25% |  | 110 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23505 | EXP-022 Meteor TBUS T&E support | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 15.6231 | 74.41% | 97.8% | 89.05% | 0 | -0.83% | 246744 | 183590 | 63154 | 4042.35 | 0 | 0 | 0 | 179548 | 41.53 | 4042 | 19269 | 163490.5 | 0 | 19268.53 | 0 | 0 | 0 | 20% | 19.17% | 15.67% | -4.33% |  | 89.83 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23629 | F35 FTI | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level NC | REIM |  |  |  | -23.6422 |  | 89.07% | 79.94% | 0 | -1.32% | 0 | 185161 | -185161 | 7831.81 | 0 | 0 | 0 | 164921 | 33.87 | 20240 | 20293 | 148010.1667 | 0 | 20293.04 | 0 | 0 | 0 | 31% | 29.68% | 27.25% | -3.75% |  | 62.09 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23242 | Physical Architecture & System Engineering Support | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 39.9731 | 62.5% | 98.16% | 87.51% | 0 | 9.18% | 305459 | 190926 | 114533 | 2865.25 | 776 | 775.55 | 0 | 187412 | 74.04 | 3514 | 24398 | 167080.3333 | 0 | 13941.6 | 10456.2 | 0 | 0 | 15% | 24.18% | 7.82% | -7.18% |  | 78.18 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23524 | Bombardier Regional Jets (BRJ) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -57.6418 | 130.8% | 56.89% | 44.32% | 28851.48 | -4.69% | 146288 | 191312 | -45024 | 781.1 | 0 | 0 | 46750 | 108838 | 190.47 | 82473 | 28851 | 84795.5 | 0 | 0 | 0 | 28851.48 | 28851.48 | 18% | 13.31% | 15.43% | -2.57% |  | 43.92 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23373 | Raytheon Michael Bellini | Natalie Sinclair | RAS | RAYTHEON UNITED KINGDOM LIMITED | EES | Level NC | REIM |  |  |  | 5.4048 | 89.61% | 89.09% | 89.09% | 0 | -8.56% | 214367 | 192086 | 22281 | 4122.45 | 0 | 0 | 0 | 171127 | 39.21 | 20958 | 0 | 171127 | 0 | 0 | 0 | 0 | 0 | 45% | 36.44% | 36.08% | -8.92% |  | 91.61 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23008 | Spirit Shorts Project Rachel | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 85.87% | 91.32% | 91.32% | 0 | -7.7% | 228880 | 196531 | 32349 | 0 | 0 | 0 | 0 | 179473 | 212.4 | 17058 | 0 | 179473 | 0 | 0 | 0 | 0 | 0 | 13% | 5.3% | 0.31% | -12.69% |  | 46.04 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23019 | EXP034-B Actuator Development | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | -90.0081 | 103.1% | 89.91% | 89.91% | 0 | -14.64% | 215541 | 222216 | -6675 | 74.16 | 12298 | 12297.9 | 0 | 199797 | 395.05 | 5442 | 0 | 199797 | 0 | 0 | 0 | 0 | 0 | 34% | 19.36% | 35.7% | 1.7% |  | 58.45 | [5 empty] | -16977
1728 | 2024-03-07 00:30 | P23472 | Tempest Wing Design | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 98.2921 | 45.03% | 118.2% | 105.7% | 0 | -19.95% | 483870 | 217867 | 266003 | 2706.25 | 201988 | 356900 | 0 | 257532 | 0 | -39664 | 32753 | 230237.8333 | 0 | 32753.16 | 0 | 0 | 0 | 23% | 3.05% | 12.51% | -10.49% |  | 46.74 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23685 | DAC LUC Support and Recompliance | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 15.5569 | 31.12% | 219.3% | -0.0001488% | 0 | -1.23% | 720000 | 224086 | 495914 | 31877.46 | 0 | 0 | 0 | 491428 | 62 | -267342 | 589714 | -0.33333 | 0 | 288001.2 | 301712.4 | 0 | 0 | 28% | 26.77% | 26.77% | -1.23% |  | 60.5 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P22798 | CO2MAP MGSE | Harry James Kellett | DTW | THALES ALENIA SPACE UK (60DAYS) | EES | Level 2 | REIM | 2023-11-08 | 0 |  | -5.7263 | 85.75% | 105% | 105% | 0 | -3.47% | 252086 | 216158 | 35928 | -6274.25 | 0 | 0 | 0 | 227053 | 0.26 | 0 | 0 | 227053 | 0 | 0 | 0 | 0 | 0 | 29% | 25.53% | 100% | 71% |  | 50.31 | [5 empty] | 10895
1728 | 2024-03-07 00:30 | P23316 | Model Factory IL and AW | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX | 2024-01-12 | 1 |  | 129.9978 | 88.13% | 104.1% | 96.46% | 20248.8 | 2.41% | 250000 | 220328 | 29672 | 228.25 | 0 | 0 | 0 | 229409 | 104.58 | 0 | 20249 | 212534.8333 | 0 | 0 | 0 | 20248.8 | 20248.8 | 30% | 32.41% | 42.82% | 12.82% |  | 45.31 | [5 empty] | 9081
1728 | 2024-03-07 00:30 | P23650 | MBDA Recruitment Management costs | Brian Maddrell | BDW | MBDA UK LIMITED | EES | Level NC | REIM | 2024-02-01 | 0 |  | -306.4827 |  | 0% | 0% | 0 | 28.46% | 0 | 240972 | -240972 | 786.25 | 0 | 0 | 266000 | 0 | 140.3 | 240972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | 31.46% | 28.48% | 25.48% |  | 82.3 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23603 | Typhoon IMDLR | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 10.7821 | 81.28% | 0% | 0% | 0 | 2.19% | 305067 | 247967 | 57100 | 5295.83 | 0 | 0 | 4271.91 | 0 | 290.03 | 247967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29% | 31.19% | 32.45% | 3.45% |  | 57.42 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23317 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX | 2024-01-12 | 1 |  | 35.1844 | 95.89% | 104.3% | 98.16% | 17760 | 4.31% | 251800 | 241447 | 10353 | 294.25 | 0 | 0 | 0 | 251800 | 113.29 | 0 | 17760 | 237000 | 0 | 0 | 0 | 17760 | 17760 | 25% | 29.31% | 49.38% | 24.38% |  | 36.29 | [5 empty] | 10353
1728 | 2024-03-07 00:30 | P23699 | A220 Stress Checkers | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -9.1224 |  | 0% | 0% | 0 | -2.07% | 0 | 255217 | -255217 | 27977.07 | 7000 | 7000 | 321520 | 0 | 94.79 | 255217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22% | 19.93% | 19.95% | -2.05% |  | 61.88 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23007 | EXP-006A - Brimstone 3 | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 49.0177 | 64.5% | 99.09% | 93.22% | 0 | -3.09% | 406450 | 262154 | 144296 | 2943.75 | 0 | 0 | 0 | 259760 | 52.83 | 2364 | 18463 | 244374.1667 | 0 | 18463.2 | 0 | 0 | 0 | 25% | 21.91% | 29.94% | 4.94% |  | 69.51 | [5 empty] | -30
1728 | 2024-03-07 00:30 | P21463 | Safety & Monitoring Systems at DM Beith & Gosport | Harry James Kellett | BXW | MOD | EES | Level 2 | FIX |  |  |  | 124.5835 | 77.42% | 129.2% | 129.2% | 0 | -26.91% | 349405 | 270510 | 78895 | 633.27 | 56389 | 69642.23 | 21721 | 349387 | 0 | -78877 | 0 | 349387 | 0 | 0 | 0 | 0 | 0 | 48% | 21.09% | 40.79% | -7.21% |  | 52.91 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23308 | NATO JEWCS | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  | 28.9927 | 80.8% | 94.91% | 81.83% | 45213.08 | -3.44% | 356307 | 287896 | 68411 | 2359.59 | 614 | 613.89 | 0 | 273254 | 154.92 | 14642 | 45213 | 235576.5 | 0 | 0 | 45213.08 | 0 | 45213.08 | 24% | 20.56% | 12.78% | -11.22% |  | 75.81 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23045 | Shotgun Adaptors - 10 Sets | Harry James Kellett | BDW | MBDA UK LIMITED | EES | Level 2 | FIX | 2024-02-27 | 6 |  | 3347.608 | 74.76% | 133.8% | 95.11% | 0 | -19.12% | 399276 | 298513 | 100763 | 30.1 | 214550 | 214550.47 | 0 | 399276 | 5744.55 | -100763 | 138421 | 283925.1667 | 0 | 138420.73 | 0 | 0 | 0 | 29% | 9.88% | 0% | -29% |  | 55.76 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23617 | Tempest Composites WP2 | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -8.7048 | 123.8% | 27.25% | 11.25% | 29536.68 | 2.77% | 244405 | 302596 | -58191 | 6684.93 | 0 | 0 | 57651.28 | 82447 | 234.58 | 220148 | 58103 | 34027.8333 | 0 | 28565.94 | 0 | 29536.68 | 29536.68 | 31% | 33.77% | 33.63% | 2.63% |  | 62.31 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P22515 | Shorts A220 100/300 ALI Phase III | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 38.9774 | 79.63% | 93.24% | 93.24% | 0 | 1.17% | 400629 | 319026 | 81603 | 2093.6 | 3451 | 3450.98 | 0 | 297465 | 88.89 | 21561 | 0 | 297465 | 0 | 0 | 0 | 0 | 0 | 10% | 11.17% | 13.78% | 3.78% |  | 40.4 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P22953 | Spirit Shorts eVTOL | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-05-08 | 1 |  |  | 103.1% | 79.36% | 79.36% | 0 | -6.74% | 324272 | 334484 | -10212 | 0 | 66697 | 67387.9 | 0 | 265432 | 179.02 | 69052 | 0 | 265432 | 0 | 0 | 0 | 0 | 0 | 17% | 10.26% | 0% | -17% |  | 46.19 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P22842 | ME Support (Aim Altitude) | James Montgomery | AVI | AIM ALTITUDE UK LIMITED | ME | Level 3 | FIX | 2023-06-14 | 4 |  |  | 99.31% | 100.5% | 86.63% | 57290.84 | 0.49% | 346294 | 343918 | 2376 | 0 | 2910 | 2909.86 | 0 | 345673 | 55184.93 | -1755 | 57291 | 297930.5 | 0 | 0 | 0 | 57290.84 | 57290.84 | 13% | 13.49% | 0% | -13% |  | 46.3 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P22391 | GE System Engineering support | Vinayakumar Sugur | GEE | EXPERIS LIMITED | EES | Level NC | REIM |  |  |  |  | 82.01% | 98.82% | 98.14% | 0 | 0.13% | 434434 | 356261 | 78173 | 0 | 0 | 0 | 0 | 352070 | 89.71 | 4190 | 2939 | 349620.8333 | 0 | 2939.04 | 0 | 0 | 0 | 6% | 6.13% | 6.09% | 0.09% |  | 57.33 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23694 | Systems Portfolio EXP-011a | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 11.4665 | 59.9% | 93.39% | 73.7% | 0 | 2.72% | 648493 | 388453 | 260040 | 22678.28 | 158 | 157.75 | 0 | 362779 | 35.78 | 25675 | 91787 | 286289.8333 | 0 | 91786.96 | 0 | 0 | 0 | 21% | 23.72% | 18.56% | -2.44% |  | 89.57 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23023 | Spirit Shorts R Foster/M Gourley | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 8.5737 | 79.99% | 99.82% | 89.12% | 0 | -20.64% | 480221 | 384152 | 96069 | 11205.1 | 223872 | 267726 | 0 | 383474 | 82.94 | 15189 | 49334 | 342362.3333 | 0 | 21204.59 | 28129.27 | 0 | 0 | 27% | 6.36% | 3.11% | -23.89% |  | 29.56 | [5 empty] | 14511
1728 | 2024-03-07 00:30 | P23432 | Spirit Belfast MRB On-Site Support (Mon & Clear) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 65.77% | 125.6% | 103.8% | 77391.6 | -11.53% | 449545 | 295665 | 153880 | 0 | 295665 | 451827.33 | 0 | 371466 | 75.91 | 36200 | 77392 | 306972.6667 | 0 | 0 | 0 | 77391.6 | 77391.6 | 39% | 27.47% | 0% | -39% |  | 0 | [5 empty] | 112000
1728 | 2024-03-07 00:30 | P23320 | Lifing Services DACs | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX | 2024-01-12 | 1 |  | 35.8106 | 95.56% | 104.6% | 97.44% | 34138.8 | 2.98% | 413300 | 394956 | 18344 | 512.25 | 0 | 0 | 0 | 413300 | 97.07 | -1 | 34139 | 384850.8333 | 0 | 0 | 0 | 34138.8 | 34138.8 | 26% | 28.98% | 52.05% | 26.05% |  | 33.15 | [5 empty] | 18343
1728 | 2024-03-07 00:30 | P23531 | BAe Systems F35 MRB Support | Andrew Houghton | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | -33.6916 |  | 75.46% | 71.04% | 0 | 2.85% | 0 | 415155 | -415155 | 12322.2 | 287 | 287.44 | 0 | 313284 | 80.77 | 101871 | 22007 | 294944.8333 | 0 | 22007.29 | 0 | 0 | 0 | 25% | 27.85% | 32.01% | 7.01% |  | 59.47 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23520 | FCAS AP Portfolio Systems | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 30.2623 | 52.61% | 96.98% | 85.4% | 0 | -6.48% | 810821 | 426581 | 384240 | 12697 | 320 | 319.5 | 0 | 413678 | 43.77 | 12903 | 59261 | 364293.8333 | 0 | 59261.4 | 0 | 0 | 0 | 22% | 15.52% | 17.76% | -4.24% |  | 79.82 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23554 | Dornier Seawings 328 2023 H2 Support | Steven Lawton | DAX | EXPLEO GERMANY GMBH (EC) | MPE | Level 2 | REIM |  |  |  | 3.8188 | 90.88% | 87.81% | 87.81% | 0 | 7.89% | 474542 | 431253 | 43289 | 11335.86 | 4046 | 4046.44 | 0 | 378685 | 45.54 | 52568 | 0 | 378685 | 0 | 0 | 0 | 0 | 0 | 21% | 28.89% | 31.3% | 10.3% |  | 67.62 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P22906 | Spirit Shorts - MRB JD Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 43.5733 | 70.89% | 88.73% | 69.72% | 13497.6 | -7.68% | 614770 | 435787 | 178983 | 4107.63 | 0 | 0 | 0 | 386688 | 274.15 | 57099 | 99451 | 303812.1667 | 0 | 0 | 85953.72 | 13497.6 | 13497.6 | 13% | 5.32% | 3.06% | -9.94% |  | 36.87 | [5 empty] | 8000
1728 | 2024-03-07 00:30 | P23366 | Business Analyst Support | Peter Williams | BDZ | MBDA UK LIMITED | DET | Level NC | REIM |  |  |  | 104.0549 | 33.09% | 292.3% | 222.4% | 0 | 13.44% | 583200 | 192994 | 390206 | 3750 | 192993 | 416921.86 | 0 | 564160 | 15.53 | -118031 | 161856 | 429280 | 81792 | 80064 | 0 | 0 | 0 | 43% | 56.44% | 31.06% | -11.94% |  | 0.01 | [5 empty] | 253135
1728 | 2024-03-07 00:30 | P23372 | BAE Carbon Tooling Off-load | Gary Kempster | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  |  | 165.3% | 56.3% | 56.3% | 0 | -4.13% | 276718 | 457433 | -180715 | 0 | 0 | 0 | 197460.8 | 257522 | 475.07 | 199912 | 0 | 257522 | 0 | 0 | 0 | 0 | 0 | 27% | 22.87% | 20.94% | -6.06% |  | 53.57 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23140 | Spirit Shorts A220 MLG Stress Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  | 42.2835 | 68.82% | 84.72% | 75.52% | 48343.2 | -8.36% | 636032 | 437740 | 198292 | 4689.58 | 20870 | 87811.88 | 0 | 370857 | 193.91 | 91882 | 48343 | 330571.1667 | 0 | 0 | 0 | 48343.2 | 48343.2 | 25% | 16.64% | 13.29% | -11.71% |  | 47.35 | [5 empty] | 25000
1728 | 2024-03-07 00:30 | P23473 | Tempest Vertical Tail | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 20.3037 | 65.8% | 92.79% | 82.55% | 0 | -2.81% | 723866 | 476274 | 247592 | 12194.41 | 91875 | 100425 | 0 | 441918 | 54.55 | 34356 | 58490 | 393176.3333 | 0 | 58489.72 | 0 | 0 | 0 | 24% | 21.19% | 23.67% | -0.33% |  | 62.4 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P22652 | L3 - Saftey Engineering | Sean Simmons | LHW | L3HARRIS MAPPS LIMITED | EES | Level NC | FIX |  |  |  |  | 95.63% | 86.69% | 86.69% | 0 | 5.66% | 523390 | 500498 | 22892 | 0 | 0 | 0 | 0 | 433883 | 79938 | 66615 | 0 | 433883 | 0 | 0 | 0 | 0 | 0 | 21% | 26.66% | 25.88% | 4.88% |  | 83.05 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23001 | Spirit Shorts A220 Design | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -15.557 | 112.3% | 70.38% | 70.38% | 0 | -4.05% | 463100 | 520244 | -57144 | 3673.2 | 0 | 0 | 65953.2 | 366148 | 339.89 | 154097 | 0 | 366148 | 0 | 0 | 0 | 0 | 0 | 25% | 20.95% | 11.86% | -13.14% |  | 43.61 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23281 | Systems Portfolio | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM | 2024-02-28 | 1 |  |  | 44.43% | 97.31% | 97.19% | 0 | -17.1% | 1177697 | 523237 | 654460 | 0 | 2133 | 2133.28 | 0 | 509180 | 17523.23 | 13968 | 762 | 508545 | 0 | 761.53 | 0 | 0 | 0 | 25% | 7.9% | 0% | -25% |  | 70.48 | [5 empty] | -89
1728 | 2024-03-07 00:30 | P23323 | CNC-CMM Programming Support | Andrew Houghton | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | 8.2589 | 86.22% | 80.2% | 68.16% | 0 | -3.15% | 617810 | 532662 | 85148 | 10309.83 | 13662 | 15941.56 | 0 | 427206 | 143.1 | 105455 | 76956 | 363076 | 0 | 76955.66 | 0 | 0 | 0 | 32% | 28.85% | 38.11% | 6.11% |  | 57.05 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P21138 | D&A Vibration Reduc Damping Struc FOGV Components | Steven Lawton | ATC | AECC SICHUAN GAS TURBINE | MPE | Level 1 | FIX | 2022-09-07 | 0 |  | 8042.9091 | 96.12% | 104% | 104% | 0 | -3.44% | 569346 | 547228 | 22118 | 2.75 | 75182 | 75181.75 | 0 | 569346 | 0 | 0 | 0 | 569346 | 0 | 0 | 0 | 0 | 0 | 36% | 32.56% | 0.08% | -35.92% |  | 73.95 | [5 empty] | 22118
1728 | 2024-03-07 00:30 | P23602 | EXP-025 Portfolio Software Engineering Support | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 23.8448 | 45.65% | 95.04% | 59.13% | 112950.72 | -0.65% | 1327080 | 605755 | 721325 | 30250.86 | 1837 | 2251.8 | 0 | 575686 | 72.7 | 30069 | 261025 | 358165.1667 | 0 | 148074.11 | 0 | 112950.72 | 112950.72 | 24% | 23.35% | 23.27% | -0.73% |  | 82.83 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23426 | BAE Tempest WP 3 Harness Maturation | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 14.6225 | 69.68% | 84.92% | 75.91% | 0 | -5.98% | 884012 | 615958 | 268054 | 18331.55 | 213 | 213.34 | 0 | 523063 | 69.29 | 92895 | 66565 | 467592.1667 | 0 | 66565.09 | 0 | 0 | 0 | 33% | 27.02% | 28.29% | -4.71% |  | 51.21 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23219 | Tornado Air 800 Engineering Support | Richard Brook | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 3 | REIM |  |  |  | -1.1861 | 101.9% | 92.27% | 92.27% | 0 | 1.44% | 615046 | 626827 | -11781 | 9932.22 | 459 | 459.21 | 0 | 578373 | 110.99 | 48454 | 0 | 578373 | 0 | 0 | 0 | 0 | 0 | 31% | 32.44% | 32.13% | 1.13% |  | 81.56 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23605 | Typhoon Work Package 2 Continuation | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM |  |  |  | -17.0571 | 119.6% | 29.87% | 0.0001022% | 0 | 5.21% | 545536 | 652490 | -106954 | 6270.35 | 4054 | 4054 | 81999.09 | 194929 | 239.29 | 457561 | 233914 | 0.66667 | 0 | 233914.28 | 0 | 0 | 0 | 23% | 28.21% | 29.02% | 6.02% |  | 55.81 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P22790 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 2 | REIM |  |  |  |  | 194.5% | 90.44% | 90.44% | 0 | 1.37% | 352240 | 685262 | -333022 | 0 | 1612 | 1611.52 | 515246 | 619744 | 41098.04 | 34248 | 0 | 619744 | 0 | 0 | 0 | 0 | 0 | 13% | 14.37% | 0% | -13% |  | 45.06 | [5 empty] | -31270
1728 | 2024-03-07 00:30 | P23451 | BAE Tempest - DFM-ASO Planning | Andrew Houghton | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | 9.9765 | 76.83% | 55.97% | 52.87% | 27224.9 | -3.3% | 953905 | 732893 | 221012 | 22153.21 | 0 | 0 | 0 | 410202 | 119.87 | 322691 | 27225 | 387514.5 | 0 | 0 | 27224.9 | 0 | 27224.9 | 28% | 24.7% | 27.06% | -0.94% |  | 53.6 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23321 | EHM Cloud Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX | 2024-01-29 | 3 |  | 99.5877 | 89.76% | 111.4% | 103.8% | 69002.4 | 2.93% | 839969 | 753975 | 85994 | 863.5 | 0 | 0 | 0 | 839969 | 101.36 | 0 | 69002 | 782467.3333 | 0 | 0 | 0 | 69002.4 | 69002.4 | 28% | 30.93% | 57.58% | 29.58% |  | 49.95 | [5 empty] | 85994
1728 | 2024-03-07 00:30 | P23105 | Raytheon Supply Engineering Support | Natalie Sinclair | RAY | RAYTHEON UNITED KINGDOM LIMITED | MPE | Level 3A | REIM | 2023-07-13 | 2 |  | -469.7343 | 76.96% | 94.49% | 90.07% | 49156.8 | -2.02% | 1205008 | 927395 | 277613 | -591 | 0 | 0 | 0 | 876292 | 107644.5 | 48740 | 49157 | 835327.8333 | 0 | 0 | 49156.8 | 0 | 49156.8 | 26% | 23.98% | 100% | 74% |  | 48.97 | [5 empty] | -2364
1728 | 2024-03-07 00:30 | P22350 | EMP 2020-2021 | Natalie Sinclair | ARY | GUIDANT GROUP (trading name) | PCPR | Level NC | REIM |  |  |  | 8.4659 | 94.17% | 98.35% | 94.02% | 0 | -2.05% | 1017580 | 958305 | 59275 | 7001.65 | 400 | 400 | 0 | 942526 | 68.29 | 15779 | 49806 | 901021 | 0 | 31809.66 | 17995.95 | 0 | 0 | 32% | 29.95% | 26.92% | -5.08% |  | 44.08 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23117 | BAE Typhoon Eng Support | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  |  | 107.6% | 88.52% | 88.52% | 0 | -1.44% | 950772 | 1022826 | -72054 | 0 | 19090 | 21165.02 | 69773.84 | 905368 | 108434.61 | 90362 | 0 | 905368 | 0 | 0 | 0 | 0 | 0 | 30% | 28.56% | 0% | -30% |  | 52.3 | [5 empty] | -27096
1728 | 2024-03-07 00:30 | P23292 | BAE Tempest WP 4 AV Trays | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 15.7274 | 76.52% | 89.91% | 82.34% | 0 | 2.04% | 1498284 | 1146447 | 351837 | 22370.89 | 0 | 0 | 0 | 1030718 | 68.41 | 115729 | 104015 | 944038.8333 | 0 | 104014.85 | 0 | 0 | 0 | 32% | 34.04% | 33.47% | 1.47% |  | 53.12 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23519 | Mechanical and Electrical Design Eng Support | Dushan Fernando | BAX | SAFRAN SEATS GB LIMITED | MPE | Level 2 | REIM |  |  |  | 18.5474 | 64.64% | 95.3% | 70.36% | 0 | -1.52% | 1807261 | 1168175 | 639086 | 34456.85 | 727 | 727 | 0 | 1113290 | 80.85 | 54886 | 349575 | 821977.5 | 0 | 349574.52 | 0 | 0 | 0 | 33% | 31.48% | 31.64% | -1.36% |  | 56.62 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P22671 | Spirit Shorts Pylon and Fairing Package | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX | 2023-05-03 | 4 |  | -5480.7728 | 105% | 95.26% | 95.26% | 0 | -7.21% | 1198495 | 1258071 | -59576 | 10.87 | 106495 | 174907.39 | 0 | 1198495 | 2544.39 | 2120 | 0 | 1198495 | 0 | 0 | 0 | 0 | 0 | 20% | 12.79% | 0% | -20% |  | 45.4 | [5 empty] | -57456
1728 | 2024-03-07 00:30 | P23152 | Project Aragon - Design and Stress Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 7.5214 | 92.42% | 59.18% | 59.18% | 0 | -9.54% | 1333452 | 1232403 | 101049 | 13434.87 | 0 | 0 | 0 | 729296 | 306.73 | 503107 | 0 | 729296 | 0 | 0 | 0 | 0 | 0 | 39% | 29.46% | 29.16% | -9.84% |  | 51.9 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23411 | Agile & Scrum Delivery Service | Peter Williams | BDZ | MBDA UK LIMITED | DET | Level 2 | REIM | 2023-08-14 | 0 |  |  | 36.3% | 170.5% | 170.5% | 0 | 13.08% | 2487000 | 902904 | 1584096 | 0 | 894179 | 894178.59 | 0 | 1539600 | 19368.95 | 16141 | 0 | 1539600 | 0 | 0 | 0 | 0 | 0 | 29% | 42.08% | 0% | -29% |  | 74.57 | [5 empty] | 652837
1728 | 2024-03-07 00:30 | P23315 | DAC LUC BAU and Service Workbench | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX | 2024-02-16 | 3 |  | 20.4674 | 85.17% | 117.4% | 105.3% | 195596.4 | 3.28% | 1573630 | 1340192 | 233438 | 11405.38 | 180 | 180.3 | 0 | 1573630 | 53.27 | -13236 | 195596 | 1410633.3333 | 0 | 0 | 0 | 195596.4 | 195596.4 | 28% | 31.28% | 43.91% | 15.91% |  | 52.35 | [5 empty] | 220202
1728 | 2024-03-07 00:30 | P23435 | Andy Baker Portfolio | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 27.2383 | 51.47% | 85.53% | 78.12% | 0 | -7.31% | 3377457 | 1738402 | 1639055 | 60174.65 | 2353 | 2352.57 | 0 | 1486941 | 63.9 | 251460 | 154740 | 1357991 | 0 | 154740.27 | 0 | 0 | 0 | 25% | 17.69% | 20.76% | -4.24% |  | 79.8 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23006 | Spirit Shorts A350 Freighter Toulouse | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -30.5915 | 148.9% | 80.07% | 80.07% | 0 | 19.08% | 1035746 | 1542457 | -506711 | 16563.79 | 1086670 | 1708220.2 | 0 | 1235101 | 299.58 | 618630 | 0 | 1235101 | 0 | 0 | 0 | 0 | 0 | 5% | 24.08% | 36% | 31% |  | 47.84 | [5 empty] | 311274
1728 | 2024-03-07 00:30 | P22278 | TAI Supply Engineers to Ankara | Natalie Sinclair | TAI | TUSAS-TURK HAVACILIK VE UZAY | MPE | Level 3A | REIM |  |  |  | 432.8583 | 19.32% | 469.8% | 466.5% | 0 | -15.62% | 2105282 | 406746 | 1698536 | 3924 | 49400 | 49400.29 | 0 | 1910696 | 41.03 | -10544 | 16000 | 1897362.6667 | 0 | 0 | 16000 | 0 | 0 | 95% | 79.38% | 65.48% | -29.52% |  | 34.25 | [5 empty] | 1493406
1728 | 2024-03-07 00:30 | P23175 | BAe Aero Typhoon Package 2 | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM |  |  |  |  | 103.8% | 96.32% | 96.32% | 0 | -1.63% | 1984265 | 2060012 | -75747 | 0 | 57678 | 86030.82 | 15444.64 | 1984257 | 84731.75 | 70610 | 0 | 1984257 | 0 | 0 | 0 | 0 | 0 | 29% | 27.37% | 0% | -29% |  | 51.76 | [5 empty] | -5145
1728 | 2024-03-07 00:30 | P23257 | BAE Tempest WP 5 Centre Fuselage | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 2.4616 | 97.82% | 96.53% | 92.95% | 0 | -5.77% | 2106861 | 2060984 | 45877 | 18637.22 | 78100 | 78100 | 0 | 1989561 | 56.36 | 71423 | 88762 | 1915592.6667 | 0 | 88762 | 0 | 0 | 0 | 33% | 27.23% | 28.3% | -4.7% |  | 61.06 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P19020 | Spirit Concessions - 2018 | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2024-01-23 | 3 |  |  | 90.82% | 111.8% | 107% | 99792.83 | 2.09% | 1914847 | 1739018 | 175829 | 0 | 44318 | 44317.61 | 15178.88 | 1944711 | 4635.18 | 196987 | 99793 | 1861550.1667 | 0 | 0 | 0 | 99792.83 | 99792.83 | 25% | 27.09% | 9.32% | -15.68% |  | 40.87 | [5 empty] | 402680
1728 | 2024-03-07 00:30 | P23207 | A350 Approvers - Design and Stress Support | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  | -0.15349 | 100.4% | 91.91% | 50.81% | 169776.21 | -4.54% | 2183628 | 2192700 | -9072 | 59104.94 | 24625 | 24977.09 | 0 | 2015419 | 140.68 | 177281 | 1081494 | 1114174 | 0 | 570705.26 | 341012.63 | 169776.21 | 169776.21 | 23% | 18.46% | 18.75% | -4.25% |  | 54.7 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23179 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX |  |  |  | -108.6678 | 129.5% | 88.28% | 82.18% | 35500.91 | -9.35% | 1955411 | 2531632 | -576221 | 5302.59 | 156991 | 248243.92 | 492000 | 2234920 | 392.57 | 296713 | 185264 | 2080533.3333 | 0 | 140266.99 | 9496.08 | 35500.91 | 35500.91 | 22% | 12.65% | 16.51% | -5.49% |  | 44.4 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P23487 | Tornado Air 800 Engineering Support | Richard Brook | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 2 | FIX |  |  |  | -3.0638 | 106% | 85.87% | 81.03% | 30074.38 | -4.39% | 2525468 | 2676926 | -151458 | 49434.8 | 0 | 0 | 196775 | 2298725 | 70.67 | 378202 | 155495 | 2169145.8333 | 0 | 125420.63 | 30074.38 | 0 | 30074.38 | 40% | 35.61% | 37.92% | -2.08% |  | 78.71 | [5 empty] | 0
1728 | 2024-03-07 00:30 | P19731 | Hapri HPC Rear Bearing Housing PDR & CDR | Steven Lawton | ATC | AECC Hunan Aviation Powerplant | MPE | Level 1 | FIX |  |  |  | 1.5956 | 99.82% | 100.2% | 87.66% | 447000 | -15.38% | 2980000 | 2974673 | 5327 | 3338.66 | 363828 | 518253.56 | 0 | 2980000 | 845.72 | -230327 | 447000 | 2607500 | 0 | 0 | 0 | 447000 | 447000 | 38% | 22.62% | 13.84% | -24.16% |  | 64.86 | [5 empty] | -225000
Extend Table

## AP3-2
WIP No | Date Created | Project ID | Project Description | Project Manager | Department Id | Client | CBU | Complexity | Type | Stop Booking Hrs | Closing Project: Action(s) to close | RAG | Approx. PO Burndown (weeks) | Turnover vs Contract Value | Invoice To Date vs Turnover | Cash in vs Turnover | Open Amount Overdue | Actual PM% to Baseline PM% delta | Contract Value | Total Project Turnover | Contract Value - Total Turnover | Run Rate (based on total turnover) | Total BOI Spend to Date | Total Committed PO (supplier/best shore) | Current AA in PT3 | Invoiced To Date | DSO | Unbilled (WIP) | Total Open Amount | Cash in (Invoiced - (Open amount -VAT)) | Debt <=30 Days | Debt 31 - 60 Days | Debt 61 - 90 Days | Debt >= 90 Days | Open Amount Overdue2 | Baseline Project Margin | Project To Date (PTD) PM | Year to Date (YTD) PM | YTD Delta Actual PM% to BPM% | Forecast PM at Completion (Manual input from PTT) | Average Sale Rate | CSat score for last quarter (Manual input from PTT) | Comments and Actions | Judged income adjustment at completion | Profit to take now | Provision required now | Fully Traded | Last Months Comments and Actions
1729 | 2024-03-14 00:33 | P23411 | Agile & Scrum Delivery Service | Peter Williams | BDZ | MBDA UK LIMITED | DET | Level 2 | REIM | 2023-08-14 | 0 |  |  | 36.3% | 170.5% | 170.5% | 0 | 13.08% | 2487000 | 902903.79 | 1584096.21 | 0 | 894178.59 | 894178.59 | 0 | 1539600 | 19368.95 | 16140.79 | 0 | 1539600 | 0 | 0 | 0 | 0 | 0 | 29% | 42.08% | 0% | -29% |  | 74.57 | [5 empty] | 652837
1729 | 2024-03-14 00:33 | P23435 | Andy Baker Portfolio | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 25.7225 | 53.1% | 82.91% | 75.72% | 0 | -7.23% | 3377457.4 | 1793431.51 | 1584025.89 | 61581.42 | 2352.57 | 2352.57 | 0 | 1486941.37 | 70.95 | 306490.14 | 154740 | 1357991.37 | 0 | 154740.27 | 0 | 0 | 0 | 25% | 17.77% | 20.69% | -4.31% |  | 79.95 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23711 | DO NOT USE - RAISED IN ERROR | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23717 | GKN Ted Tomblin 2024 | Matthew Tweed | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 10047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23506 | ASTER Mid-Life Refurbishment Project Manager | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 9.8752 | 81.36% | 95.49% | 85.06% | 0 | 1.01% | 224900 | 182986.41 | 41913.59 | 4244.32 | 2806.41 | 2806.41 | 0 | 174736.41 | 50.04 | 8250 | 22897 | 155655.5767 | 0 | 22896.62 | 0 | 0 | 0 | 25% | 26.01% | 26.28% | 1.28% |  | 110 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23366 | Business Analyst Support | Peter Williams | BDZ | MBDA UK LIMITED | DET | Level NC | REIM |  |  |  | 33.8166 | 37.87% | 255.4% | 194.4% | 0 | 10.12% | 583200 | 220853.83 | 362346.17 | 10715.05 | 220853.47 | 416921.86 | 0 | 564160 | 41.2 | -90171.17 | 161856 | 429280 | 81792 | 80064 | 0 | 0 | 0 | 43% | 53.12% | 23.07% | -19.93% |  | 0.01 | [5 empty] | 253135
1729 | 2024-03-14 00:33 | P23437 | Embedded Software Engineer | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 2.2104 | 96.79% | 98% | 87.7% | 0 | -6.31% | 150150 | 145334.86 | 4815.14 | 2178.38 | 737.86 | 737.86 | 0 | 142430.36 | 52.1 | 2904.5 | 17961 | 127462.86 | 0 | 17960.7 | 0 | 0 | 0 | 22% | 15.69% | 16.24% | -5.76% |  | 78.5 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23641 | Drawing Triage | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM | 2024-01-25 | 0 |  | -43022 |  | 0% | 0% | 0 | -1043168% | 0 | 10755.5 | -10755.5 | 0.25 | 0 | 0 | 0 | 0 | 0.04 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | -1043168% | 100% | 100% |  | 49 | [5 empty] | -10755
1729 | 2024-03-14 00:33 | P23730 | FLE Project | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -9.8462 |  | 0% | 0% | 0 | -16.79% | 0 | 1120 | -1120 | 113.75 | 0 | 0 | 24000 | 0 | 69 | 1120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | -16.79% | -16.79% | -16.79% |  | 35 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23831 | Contract DM/00113 for maintenance, repair and post | Harry James Kellett | BXW | MOD | EES | Level 2 | FIX |  |  |  | 28.9028 | 3.344% | 0% | 0% | 0 | 10.19% | 40800 | 1364.42 | 39435.58 | 1364.42 | 0 | 0 | 0 | 0 | 91 | 1364.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37% | 47.19% | 47.19% | 10.19% |  | 80.26 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23463 | A220 Wing MaMo Design Checking | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-03-07 | 0 |  |  |  | 0% | 0% | 0 | 7.85% | 0 | 1628 | -1628 | 0 | 0 | 0 | 15000 | 0 | 1953.6 | 1628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | 10.85% | 0% | -3% |  | 44 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P21028 | Rebate Collection (BACC) | David Catchpole | TOO | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | [5 empty] | 0% | 0% | 0 | 0% | 0 | 2680 | -2680 | 0 | 2680 | 2680 | 0 | 0 | 3216 | 2680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23578 | ESN Work Package | Hannah Mead | COZ | CHELTON LIMITED | DET | Level 3 | FIX | 2024-01-01 | 0 |  |  | 86.17% | 116.1% | 116.1% | 0 | 35.86% | 4410 | 3800 | 610 | 0 | 0 | 0 | 0 | 4410 | 0 | -610 | 0 | 4410 | 0 | 0 | 0 | 0 | 0 | 24% | 59.86% | 0% | -24% |  | 95 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23628 | Design Assurance | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -6.67% | 0 | 3909.24 | -3909.24 | 0 | 0 | 0 | 4454.8 | 0 | 4691.09 | 3909.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 0.33% | 0% | -7% |  | 15.05 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23002 | WoT MAJ Transit Flag Stress | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 30.89% | 323.8% | 323.8% | 0 | 53.84% | 4735 | 1462.5 | 3272.5 | 0 | 0 | 2242.5 | 0 | 4735 | 0.6 | 0.5 | 0 | 4735 | 0 | 0 | 0 | 0 | 0 | 10% | 63.84% | 0% | -10% |  | 45 | [5 empty] | 3273
1729 | 2024-03-14 00:33 | P23718 | Requalification of EJ200 GSS ESS EHM SW module | Vijayakumara Nanjundappa | ARZ | MTU AERO ENGINES AG | DET | Level 3 | FIX |  |  |  | 263.3391 | 8.892% | 273.7% | 45.62% | 0 | -3.02% | 74463 | 6621.57 | 67841.43 | 257.62 | 991.93 | 991.93 | 0 | 18125 | 70.17 | -11503.43 | 18125 | 3020.8333 | 0 | 18125 | 0 | 0 | 0 | 28% | 24.98% | 24.98% | -3.02% |  | 80 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23742 | Cyber Security Support | Hannah Mead | COZ | CHELTON LIMITED | DET | Level 3 | FIX |  |  |  | -21.6 |  | 0% | 0% | 0 | 31.67% | 0 | 8100 | -8100 | 375 | 0 | 0 | 27500 | 0 | 91 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 31.67% | 31.67% | 31.67% |  | 100 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23607 | SAFRAN - A330neo Turnover Frame | Gary Kempster | TOO | SAFRAN SEATS GB LIMITED | MPE | Level 3 | FIX |  |  |  |  | 95.68% | 104.5% | 0.001994% | 0 | -19.75% | 8736 | 8359 | 377 | 0 | 0 | 0 | 0 | 8736 | 10030.8 | -377 | 10483 | 0.16667 | 0 | 0 | 10483.2 | 0 | 0 | 23% | 3.25% | 0% | -23% |  | 52 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23274 | ME Support (Aim Altitude - Cambridge) | James Montgomery | AVI | AVIC CABIN SYSTEMS (UK) LIMITED | ME | Level 3 | FIX | 2023-08-18 | 0 |  |  | 51.88% | 56.3% | 56.3% | 0 | -0.17% | 17280 | 8964 | 8316 | 0 | 0 | 0 | 0 | 5046.3 | 4701.24 | 3917.7 | 0 | 5046.3 | 0 | 0 | 0 | 0 | 0 | 21% | 20.83% | 0% | -21% |  | 48 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23283 | Spirit Tooling Audit | Charidimos Valadakis | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-05-03 | 0 |  |  | 97.22% | 48.57% | 48.57% | 0 | -7.99% | 9910.08 | 9634.8 | 275.28 | 0 | 0 | 0 | 0 | 4679.76 | 5946.05 | 4955.04 | 0 | 4679.76 | 0 | 0 | 0 | 0 | 0 | 7% | -0.99% | 0% | -7% |  | 34.41 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23127 | Loft Hall Design Support | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 101% | 99.06% | 99.06% | 0 | -9.55% | 9680 | 9772 | -92 | 0 | 0 | 0 | 0 | 9680 | 110.4 | 92 | 0 | 9680 | 0 | 0 | 0 | 0 | 0 | 41% | 31.45% | 0% | -41% |  | 44 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23630 | 2Excel CFD Analysis Support | Dushan Fernando | BAX | STIRLING DYNAMICS LTD | MPE | Level NC | FIX |  |  |  |  | 61.2% | 100% | 100% | 0 | -1.87% | 16195.49 | 9911.34 | 6284.15 | 0 | 0 | 0 | 0 | 9911.63 | 0 | -0.29 | 0 | 9911.63 | 0 | 0 | 0 | 0 | 0 | 26% | 24.13% | 0% | -26% |  | 64.78 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23740 | Phase 2 - EJ200 ESS EHM Platform Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 3 | FIX |  |  |  | 91.9661 | 6.02% | 237.3% | -0.001573% | 0 | 0.21% | 175971 | 10593 | 165378 | 1798.25 | 0 | 0 | 0 | 25139 | 69 | -14546 | 30167 | -0.16667 | 0 | 0 | 30166.8 | 0 | 0 | 28% | 28.21% | 28.21% | 0.21% |  | 54.89 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23007 | EXP-006A - Brimstone 3 | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 51.6619 | 65.08% | 98.2% | 92.39% | 0 | -3.02% | 406450 | 264509.03 | 141940.97 | 2747.5 | 0 | 0 | 0 | 259759.75 | 60.93 | 4719.28 | 18463 | 244373.9167 | 0 | 18463.2 | 0 | 0 | 0 | 25% | 21.98% | 29.94% | 4.94% |  | 69.58 | [5 empty] | -30
1729 | 2024-03-14 00:33 | P23811 | Spirit T300 MRB Concessions | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -4 |  | 0% | 0% | 0 | -7.18% | 0 | 11959.96 | -11959.96 | 2989.99 | 0 | 0 | 34639 | 0 | 28 | 11959.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21% | 13.82% | 13.82% | -7.18% |  | 46.81 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23313 | Laser Trim Fixtures | Gary Kempster | TOO | ALKEN ENGINEERING LIMITED | MPE | Level 3 | FIX | 2023-11-20 | 0 |  |  | 89.87% | 111.3% | 111.3% | 0 | 0.53% | 13770 | 12375 | 1395 | 0 | 0 | 0 | 0 | 13770 | 0 | -1395 | 0 | 13770 | 0 | 0 | 0 | 0 | 0 | 17% | 17.53% | 0% | -17% |  | 45 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P22761 | Red Bull Chassis Spit | James Montgomery | TOO | MANUFAX ENGINEERING LTD | MPE | Level 3 | FIX | 2022-11-15 | 0 |  |  | 72.18% | 96.98% | 96.98% | 0 | 7.92% | 12961.2 | 9355.5 | 3605.7 | 0 | 0 | 0 | 0 | 9072.84 | 4666.39 | 3888.66 | 0 | 9072.84 | 0 | 0 | 0 | 0 | 0 | 23% | 30.92% | 0% | -23% |  | 42.19 | [5 empty] | 3606
1729 | 2024-03-14 00:33 | P23433 | Cavendish | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 32.81% | 100% | 100% | 0 | -0.34% | 42240 | 13859.2 | 28380.8 | 0 | 0 | 0 | 0 | 13859.2 | 0 | 0 | 0 | 13859.2 | 0 | 0 | 0 | 0 | 0 | 7% | 6.66% | 0% | -7% |  | 43.93 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23350 | Spirit 2023 - Stress Approve Man Serv (DH) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 14.15% | 72.64% | 72.64% | 0 | -0.29% | 97920 | 13860 | 84060 | 0 | 0 | 0 | 0 | 10068 | 4550.4 | 3792 | 0 | 10068 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23344 | Spirit A320 Spoilers Support 2023 | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 38.75% | 100% | 100% | 0 | 5.82% | 35786.4 | 13867.23 | 21919.17 | 0 | 0 | 0 | 0 | 13867.23 | 0 | 0 | 0 | 13867.23 | 0 | 0 | 0 | 0 | 0 | 7% | 12.82% | 0% | -7% |  | 34.41 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23337 | Spirit 2023 - Steve Grimley | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 25.28% | 100% | 100% | 0 | 0.01% | 56812.9 | 14362.47 | 42450.43 | 0 | 0 | 0 | 0 | 14362.47 | 0 | 0 | 0 | 14362.47 | 0 | 0 | 0 | 0 | 0 | 7% | 7.01% | 0% | -7% |  | 30.11 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23663 | Spirit Tooling Verification and Inspection | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 6.25 | 73.96% | 0% | 0% | 0 | -7.5% | 19820.16 | 14658.66 | 5161.5 | 825.84 | 0 | 0 | 7392 | 0 | 137.47 | 14658.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12% | 4.5% | 4.82% | -7.18% |  | 34.41 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23597 | MRB Onsite support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-02-16 | 1 |  |  |  | 0% | 0% | 0 | -10.04% | 0 | 15100.57 | -15100.57 | 0 | 9448.07 | 17381.62 | 24200 | 0 | 91 | 15100.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 7.96% | 8.95% | -9.05% |  | 42.5 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23821 | Supply of Safety Engineer | Dinna Elkhalifa | BXW | STIRLING DYNAMICS LTD | EES | Level NC | REIM |  |  |  | 2.951 | 50.41% | 0% | 0% | 0 | 20.48% | 34006.44 | 17143.32 | 16863.12 | 5714.44 | 0 | 0 | 0 | 0 | 87 | 17143.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 20.48% | 20.48% | 20.48% |  | 55.48 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23724 | GKN S McConnell 2024 | Matthew Tweed | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  | 17.2432 | 36.2% | 79.56% | -0.0009611% | 0 | 1.51% | 49820 | 18034.84 | 31785.16 | 1843.34 | 0 | 0 | 0 | 14348.16 | 69 | 3686.68 | 17218 | -0.17333 | 0 | 17217.79 | 0 | 0 | 0 | 19% | 20.51% | 20.51% | 1.51% |  | 49.82 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23635 | Engineering Services: FAI Support | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 80.3359 | 49.9% | 0% | 0% | 0 | -3.4% | 37230 | 18576 | 18654 | 232.2 | 0 | 0 | 0 | 0 | 227.5 | 18576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8% | 4.6% | 5.04% | -2.96% |  | 38.7 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23343 | Spirit 2023 - John Agnew | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-08-09 | 0 |  |  | 28.56% | 86.27% | 86.27% | 0 | -0.02% | 65120.37 | 18600.89 | 46519.48 | 0 | 0 | 0 | 0 | 16047.15 | 3064.49 | 2553.74 | 0 | 16047.15 | 0 | 0 | 0 | 0 | 0 | 7% | 6.98% | 0% | -7% |  | 34.51 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23355 | Spirit Tooling Support 2023 | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-23 | 0 |  |  | 22.93% | 89.02% | 89.02% | 0 | -0.82% | 91800 | 21053.34 | 70746.66 | 0 | 0 | 0 | 0 | 18742.5 | 2773.01 | 2310.84 | 0 | 18742.5 | 0 | 0 | 0 | 0 | 0 | 20% | 19.18% | 0% | -20% |  | 44.46 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23651 | PMO Spirit | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -35.5355 |  | 0% | 0% | 0 | 23.97% | 0 | 24786 | -24786 | 697.5 | 0 | 0 | 42680 | 0 | 204.08 | 24786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 23.97% | 23.23% | 23.23% |  | 36 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23351 | Spirit 2023 - Design Man Serv (KL) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 26.47% | 93.15% | 93.15% | 0 | 0.09% | 93840 | 24840 | 69000 | 0 | 0 | 0 | 0 | 23138 | 2042.4 | 1702 | 0 | 23138 | 0 | 0 | 0 | 0 | 0 | 26% | 26.09% | 0% | -26% |  | 46 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23356 | Spirit 2023 - Design Man Serv (AH) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX | 2023-08-09 | 1 |  |  |  | 76.66% | 0.001332% | 23018.4 | 0.48% | 0 | 25023.08 | -25023.08 | 0 | 0 | 0 | 25300 | 19182 | 30027.7 | 5841.08 | 23018 | 0.33333 | 0 | 0 | 0 | 23018.4 | 23018.4 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P22884 | Spirit Shorts Config Eng | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 66.3% | 100.1% | 100.1% | 0 | 0.56% | 38976 | 25841.9 | 13134.1 | 0 | 0 | 0 | 0 | 25863.2 | 0 | -0.3 | 0 | 25863.2 | 0 | 0 | 0 | 0 | 0 | 7% | 7.56% | 0% | -7% |  | 20.3 | [5 empty] | 21
1729 | 2024-03-14 00:33 | P23354 | Spirit 2023 - Design Man Serv (PC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 27.97% | 99.36% | 99.36% | 0 | 0.48% | 93840 | 26248.98 | 67591.02 | 0 | 0 | 0 | 0 | 26082 | 200.38 | 166.98 | 0 | 26082 | 0 | 0 | 0 | 0 | 0 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23598 | MRB Onsite support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 33.732 | 20.27% | 0% | 0% | 0 | -13.63% | 133056 | 26968.92 | 106087.08 | 3145 | 8736.42 | 14079.58 | 0 | 0 | 91 | 26968.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 14.37% | 14.85% | -13.15% |  | 42.5 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P22756 | A350 FLE Design Checker | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2022-03-23 | 1 |  |  | 68.39% | 119.7% | 119.7% | 0 | 16.46% | 34898.4 | 23867.15 | 11031.25 | 0 | 23867.15 | 24342.3 | 0 | 28571.1 | 0.06 | 0.05 | 0 | 28571.1 | 0 | 0 | 0 | 0 | 0 | 0% | 16.46% | 0% | 0% |  | 0 | [5 empty] | 4704
1729 | 2024-03-14 00:33 | P23505 | EXP-022 Meteor TBUS T&E support | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 14.6232 | 76.04% | 95.69% | 87.13% | 0 | -0.91% | 246744.4 | 187632.41 | 59111.99 | 4042.35 | 0 | 0 | 0 | 179547.72 | 49.33 | 8084.69 | 19269 | 163490.22 | 0 | 19268.53 | 0 | 0 | 0 | 20% | 19.09% | 15.67% | -4.33% |  | 89.83 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23338 | Spirit 2023 - Blair Hainey | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 5.7529 | 87.04% | 60.09% | 60.09% | 0 | 4.65% | 34494.36 | 30024.9 | 4469.46 | 776.9 | 0 | 0 | 0 | 18042.36 | 147.65 | 11982.54 | 0 | 18042.36 | 0 | 0 | 0 | 0 | 0 | 7% | 11.65% | 19.31% | 12.31% |  | 18.28 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23458 | Spirit Belfast Tooling Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-08-11 | 0 |  |  | 101.3% | 94.65% | 94.65% | 0 | 8.64% | 30384 | 30784.9 | -400.9 | 0 | 0 | 0 | 0 | 29139.1 | 1974.96 | 1645.8 | 0 | 29139.1 | 0 | 0 | 0 | 0 | 0 | 7% | 15.64% | 0% | -7% |  | 42.2 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23365 | GKN 777x Lip Skin Fixture | Steven Lawton | TOO | GKN AEROSPACE SERVICES LTD | MPE | Level 3 | FIX | 2023-10-12 | 0 |  |  | 41.91% | 113.2% | 113.2% | 0 | -9.26% | 79161.46 | 33175.67 | 45985.79 | 0 | 5109.88 | 5109.88 | 0 | 37544.22 | 0 | -4368.55 | 0 | 37544.22 | 0 | 0 | 0 | 0 | 0 | 22% | 12.74% | 0% | -22% |  | 56 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P22768 | MRB Onsite Support - Spirit Belfast | James Montgomery | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2023-07-27 | 0 |  |  |  | 0% | 0% | 0 | -17.07% | 0 | 34614 | -34614 | 0 | 0 | 0 | 36800 | 0 | 41536.8 | 34614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | -7.07% | 0% | -10% |  | 36 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23347 | WoT Fixed Leading Edge - Industrial 2023 | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 112.8% | 42.03% | 42.03% | 0 | -0.41% | 31034.12 | 35002.1 | -3967.98 | 0 | 0 | 0 | 10500 | 14710.56 | 24349.85 | 20291.54 | 0 | 14710.56 | 0 | 0 | 0 | 0 | 0 | 7% | 6.59% | 0% | -7% |  | 32.26 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23642 | MRB Belfast Support | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -17.7323 |  | 0% | 0% | 0 | -42.59% | 0 | 38458.94 | -38458.94 | 2168.86 | 2947.65 | 2947.65 | 42350 | 0 | 150.25 | 38458.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22% | -20.59% | -23.06% | -45.06% |  | 38.52 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23051 | Spirit Shorts A350 PAX Door | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 3A | REIM |  |  |  |  | 205.9% | 105.4% | 105.4% | 0 | -0.63% | 18216 | 37513 | -19297 | 0 | 0 | 0 | 0 | 39537 | 0 | 0 | 0 | 39537 | 0 | 0 | 0 | 0 | 0 | 30% | 29.37% | 0% | -30% |  | 46 | [5 empty] | 2024
1729 | 2024-03-14 00:33 | P22752 | Tooling WoT - 2021 (Spirit) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | REIM | 2023-05-03 | 0 |  |  | 101.1% | 74.02% | 74.02% | 0 | -8.5% | 41525.1 | 41982.28 | -457.18 | 0 | 0 | 0 | 0 | 31076.1 | 13087.42 | 10906.18 | 0 | 31076.1 | 0 | 0 | 0 | 0 | 0 | 0% | -8.5% | 0% | 0% |  | 39.09 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23700 | IPDT Leads | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 78.6815 | 24.95% | 59.03% | -0.0008996% | 0 | -1.55% | 169263.9 | 42239.73 | 127024.17 | 1614.41 | 0 | 0 | 0 | 24932.12 | 91 | 17307.61 | 29919 | -0.38 | 29918.54 | 0 | 0 | 0 | 0 | 26% | 24.45% | 21.19% | -4.81% |  | 50.83 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23729 | Honda Tooling | Paul Watson | STX | SHORT BROTHERS PLC | MPE | Level NC | FIX |  |  |  | 7.1711 | 56.5% | 75.96% | 0% | 0 | 4.74% | 75600 | 42714 | 32886 | 4585.88 | 0 | 0 | 0 | 32445 | 63 | 10269 | 38934 | 0 | 38934 | 0 | 0 | 0 | 0 | 10% | 14.74% | 14.74% | 4.74% |  | 42 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23339 | Spirit 2023 - Stewart Russell | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 64.51% | 100% | 100% | 0 | 0.62% | 72766.8 | 46941.72 | 25825.08 | 0 | 0 | 0 | 0 | 46941.74 | 0 | -0.02 | 0 | 46941.74 | 0 | 0 | 0 | 0 | 0 | 7% | 7.62% | 0% | -7% |  | 35.67 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23744 | Model Factory | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 42.5282 | 18.15% | 93.95% | 0.0003502% | 0 | 6.38% | 262300 | 47596.5 | 214703.5 | 5048.5 | 0 | 0 | 0 | 44716 | 69 | 2880.5 | 53659 | 0.16667 | 0 | 26229.6 | 27429.6 | 0 | 0 | 28% | 34.38% | 34.38% | 6.38% |  | 50.63 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23753 | Tempest Composites Maturation | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | -6.7106 |  | 0% | 0% | 0 | -20.28% | 0 | 47857.64 | -47857.64 | 7131.7 | 0 | 0 | 54398.4 | 0 | 70 | 47857.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37% | 16.72% | 16.72% | -20.28% |  | 64.76 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P22760 | SA Leading Edge Transport Media ('A' Frames) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-11-15 | 1 |  |  | 85.99% | 110.7% | 116.3% | -3082.8 | 3.97% | 53480.8 | 45985.5 | 7495.3 | 0 | 42804 | 42804 | 0 | 50911.8 | 0 | -0.3 | -3083 | 53480.9667 | 0 | 0 | 0 | -3082.8 | -3082.8 | 6% | 9.97% | 0% | -6% |  | 42 | [5 empty] | 4926
1729 | 2024-03-14 00:33 | P23543 | EXP-024 FCAS AP Transformation & Change Enablers | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -26% | 385921 | 0 | 385921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26% | 0% | 0% | -26% |  | 0 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23349 | Spirit 2023 - Stress Approve Man Serv (SB) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 58.24% | 80.05% | 80.05% | 0 | -0.29% | 97920 | 57024 | 40896 | 0 | 0 | 0 | 0 | 45648 | 13651.2 | 11376 | 0 | 45648 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23322 | GKN T Tomblin 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  | 0.97974 | 98.2% | 96.48% | 84.66% | 0 | -0.33% | 58952 | 57888 | 1064 | 1086 | 0 | 0 | 0 | 55848 | 88.61 | 2040 | 8208 | 49008 | 0 | 8208 | 0 | 0 | 0 | 17% | 16.67% | 16.67% | -0.33% |  | 48 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23341 | Spirit 2023 - Tom McFarlane | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 39.5919 | 56.45% | 79.79% | 70.13% | 0 | -0.01% | 108666.4 | 61344.92 | 47321.48 | 1195.23 | 0 | 0 | 0 | 48944.66 | 134.48 | 12400.26 | 7110 | 43019.66 | 0 | 0 | 0 | 7110.19 | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23193 | Spirit Shorts Stephen Greer | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -1.0717 | 101.1% | 97.72% | 87.97% | 0 | 8.52% | 61472 | 62129.9 | -657.9 | 613.91 | 0 | 0 | 10878 | 60712.78 | 84.03 | 1417.12 | 7269 | 54655.28 | 7268.72 | 0 | 0 | 0 | 0 | 23% | 31.52% | 34.03% | 11.03% |  | 35.05 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23106 | ME Support to NPD - Bobby Haggart | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  |  | 95.79% | 97.03% | 97.03% | 0 | 0.3% | 65675 | 62912.11 | 2762.89 | 0 | 0 | 0 | 0 | 61042.75 | 2243.24 | 1869.36 | 0 | 61042.75 | 0 | 0 | 0 | 0 | 0 | 15% | 15.3% | 0% | -15% |  | 35.65 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23561 | SAAB | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2024-01-01 | 0 |  |  | 82.46% | 121.1% | 121.1% | 0 | 3.5% | 67485 | 55649.23 | 11835.77 | 0 | 0 | 0 | 0 | 67399.4 | 0 | -4408.17 | 0 | 67399.4 | 0 | 0 | 0 | 0 | 0 | 16% | 19.5% | 0% | -16% |  | 36.82 | [5 empty] | 7342
1729 | 2024-03-14 00:33 | P22967 | Spirit 2022 - Channapa Laxmeshwar | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2023-01-26 | 2 |  |  | 69.69% | 121.3% | 121.3% | 0 | 9.53% | 75159.1 | 52376.15 | 22782.95 | 0 | 52376.15 | 54898.1 | 0 | 63508.8 | 0.42 | 0.35 | 0 | 63508.8 | 0 | 0 | 0 | 0 | 0 | 8% | 17.53% | 0% | -8% |  | 0 | [5 empty] | 11133
1729 | 2024-03-14 00:33 | P23754 | Tempest Composites WP4 | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -7.9035 |  | 0% | 0% | 0 | 7.83% | 0 | 65377.47 | -65377.47 | 8271.99 | 149.25 | 149.25 | 97140 | 0 | 84 | 65377.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 35.83% | 35.83% | 7.83% |  | 63.28 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23784 | Tempest Tooling Offload 2024 | Christopher McCarthy | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  | -8.898 |  | 0% | 0% | 0 | -11.16% | 0 | 67710.84 | -67710.84 | 7609.66 | 0 | 0 | 74725 | 0 | 69 | 67710.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 18.84% | 18.84% | -11.16% |  | 54.86 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23080 | Spirit Shorts DManagement Cairan Cullen | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 787.1952 | 49.33% | 97.96% | 93.68% | 3787.8 | -0.95% | 149600 | 73793.1 | 75806.9 | 96.3 | 0 | 0 | 0 | 72284.4 | 281.39 | 1508.7 | 3788 | 69127.7333 | 0 | 0 | 0 | 3787.8 | 3787.8 | 24% | 23.05% | 13.22% | -10.78% |  | 44.44 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23602 | EXP-025 Portfolio Software Engineering Support | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 21.6828 | 48.02% | 90.33% | 56.2% | 112950.72 | -0.66% | 1327080 | 637302.72 | 689777.28 | 31812.13 | 1836.85 | 2251.8 | 0 | 575685.84 | 79.65 | 61616.88 | 261025 | 358165.0067 | 0 | 148074.11 | 0 | 112950.72 | 112950.72 | 24% | 23.34% | 23.26% | -0.74% |  | 82.94 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23438 | A220 Spirit Shorts DTC - Stephen Corry | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 11.8021 | 82.41% | 81.53% | 51.1% | 0 | -7.3% | 95928.4 | 79057.9 | 16870.5 | 1429.45 | 0 | 0 | 0 | 64459.8 | 240.15 | 14598.1 | 28872 | 40399.8 | 28872.36 | 0 | 0 | 0 | 0 | 23% | 15.7% | 17.18% | -5.82% |  | 49.78 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P22505 | Spirit MRB Engineering Support 2021 | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 1 |  |  | 91.17% | 100% | 95.78% | 4020.48 | 21.2% | 87110.4 | 79414.95 | 7695.45 | 0 | 0 | 0 | 0 | 79414.95 | 4020.48 | 0 | 4020 | 76064.95 | 0 | 0 | 0 | 4020.48 | 4020.48 | 0% | 21.2% | 0% | 0% |  | 41.88 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23560 | NJEWCS TAF202302 SM | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level 2 | FIX |  |  |  | 0.86802 | 97.96% | 50.1% | 50.1% | 0 | 11.46% | 81500 | 79836.44 | 1663.56 | 1916.51 | 0 | 0 | 0 | 40000 | 157.63 | 39836.44 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 28% | 39.46% | 37.81% | 9.81% |  | 73.01 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23340 | Spirit 2023 - John Cole | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -4 | 107.4% | 77.95% | 68.82% | 0 | -0.01% | 75064.86 | 80634.06 | -5569.2 | 1392.3 | 0 | 0 | 8831 | 62852.4 | 137.59 | 17781.66 | 8831 | 55493.2333 | 0 | 0 | 0 | 8831.16 | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 39.78 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P22885 | ME Support (Baxi) | James Montgomery | HUV | BAXI HEATING UK LIMITED | ME | Level 3 | FIX | 2023-01-12 | 0 |  |  | 68.78% | 108.7% | 108.7% | 0 | 13.05% | 106632.96 | 73340.24 | 33292.72 | 0 | 0 | 0 | 0 | 79748.12 | 1531.35 | 1276.12 | 0 | 79748.12 | 0 | 0 | 0 | 0 | 0 | 15% | 28.05% | 0% | -15% |  | 44.37 | [5 empty] | 7684
1729 | 2024-03-14 00:33 | P23345 | Spirit 2023- Jonathan Escosio | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | -3.9407 | 108.8% | 77.98% | 62.01% | 7150.18 | -6.68% | 75970.62 | 82653.78 | -6683.16 | 1695.95 | 0 | 0 | 8938 | 64456.26 | 169 | 18197.52 | 15846 | 51251.26 | 0 | 0 | 0 | 15846.34 | 7150.18 | 7% | 0.32% | -1.22% | -8.22% |  | 40.26 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23171 | Spirt Shorts Weights Eng | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 69.18% | 122.7% | 96.15% | 0 | 2.68% | 103113.14 | 71329.32 | 31783.82 | 0 | 71329.32 | 85975.13 | 0 | 87531.56 | 105.02 | -3932.24 | 22740 | 68581.56 | 0 | 16774.18 | 5965.46 | 0 | 0 | 12% | 14.68% | 0% | -12% |  | 0 | [5 empty] | 12270
1729 | 2024-03-14 00:33 | P23648 | EXP-032 Delivery of Datalink Eng support - FCAS AP | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 27.7814 | 40.89% | 89.59% | 67.79% | 0 | 5.06% | 371000 | 151700.45 | 219299.55 | 7893.75 | 1032.95 | 1032.95 | 0 | 135912.95 | 49.24 | 15787.5 | 39685 | 102842.1167 | 0 | 39684.54 | 0 | 0 | 0 | 22% | 27.06% | 27.04% | 5.04% |  | 103.55 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23465 | A220 ToW Design Offload (Wing) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 17.9065 | 63.42% | 80.93% | 66.62% | 0 | -4.49% | 132000 | 83716.8 | 48283.2 | 2696.4 | 0 | 0 | 0 | 67752.4 | 82.3 | 15964.4 | 14381 | 55768.2333 | 14380.8 | 0 | 0 | 0 | 0 | 20% | 15.51% | 14.37% | -5.63% |  | 42.8 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23336 | Spirit 2023 - Neil Rampling | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 33.227 | 62.69% | 78.44% | 57.02% | 13070.83 | -0.01% | 133901.52 | 83945.68 | 49955.84 | 1503.47 | 0 | 0 | 0 | 65850.88 | 195.87 | 18094.8 | 21586 | 47862.5467 | 0 | 0 | 0 | 21586.03 | 13070.83 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23335 | GKN S McConnell 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2023-12-31 | 2 |  |  | 96.61% | 100% | 83.53% | 0 | 0.74% | 87420 | 84459 | 2961 | 0 | 0 | 0 | 0 | 84459 | 364 | 0 | 16694 | 70547.3333 | 0 | 0 | 0 | 16694.4 | 0 | 15% | 15.74% | 0% | -15% |  | 47 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23551 | Ian Berry 2023 H2 | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  | -3.1217 | 111.9% | 79.21% | 79.21% | 0 | 12.89% | 75810 | 84856.52 | -9046.52 | 2897.98 | 0 | 0 | 24259.2 | 67217.49 | 51.98 | 17639.03 | 0 | 67217.49 | 0 | 0 | 0 | 0 | 0 | 22% | 34.89% | 36.83% | 14.83% |  | 77.27 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P22965 | Spirit 2022 - Design Man Serv (AH) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 1 |  |  | 106.7% | 96.66% | 92.02% | 4759.75 | 3.14% | 80079.56 | 85441.32 | -5361.76 | 0 | 0 | 0 | 0 | 82588.96 | 8182.59 | 2852.36 | 4760 | 78622.2933 | 0 | 0 | 0 | 4759.75 | 4759.75 | 14% | 17.14% | 0% | -14% |  | 42.44 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23523 | Applique Armour Support | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 1 |  |  | 72.43% | 138.1% | 98.47% | 0 | 3.42% | 118200 | 85606.5 | 32593.5 | 0 | 0 | 0 | 0 | 118200 | 1567.8 | -32593.5 | 40680 | 84300 | 40680 | 0 | 0 | 0 | 0 | 25% | 28.42% | 0% | -25% |  | 64.29 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P22964 | Spirit 2022 - MRB Man Serv (JC) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 100.6% | 97.95% | 97.95% | 0 | 1.91% | 85435.2 | 85960.26 | -525.06 | 0 | 0 | 0 | 0 | 84199.74 | 2112.62 | 1760.52 | 0 | 84199.74 | 0 | 0 | 0 | 0 | 0 | 16% | 17.91% | 0% | -16% |  | 42.69 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23342 | Spirit 2023 - Channapa Laxmeshwar | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -0.73336 | 104.8% | 78.4% | 74.35% | 0 | -3.69% | 79348.35 | 83134.33 | -3785.98 | 5162.52 | 83134.33 | 94827 | 0 | 65177.5 | 29005 | 20806.83 | 4037 | 61813.3333 | 0 | 0 | 0 | 4036.8 | 0 | 7% | 3.31% | 0% | -7% |  | 0 | [5 empty] | 2850
1729 | 2024-03-14 00:33 | P23079 | Spirit Shorts Nomenclature | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 3.0271 | 97.8% | 84.64% | 79% | 10554.48 | 1.93% | 88455 | 86511.6 | 1943.4 | 642 | 0 | 0 | 0 | 73222.2 | 222.01 | 13289.4 | 5855 | 68343.0333 | -4699.44 | 0 | 0 | 10554.48 | 10554.48 | 20% | 21.93% | 25.23% | 5.23% |  | 30.74 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P22963 | Spirit 2022 - Design Man Serv (PC) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 1 |  |  | 108.6% | 104% | 94.46% | 9938.48 | 3.18% | 80079.56 | 86926.74 | -6847.18 | 0 | 0 | 0 | 0 | 90389.95 | 5782.63 | -3463.21 | 9938 | 82108.2833 | 0 | 0 | 0 | 9938.48 | 9938.48 | 13% | 16.18% | 0% | -13% |  | 42.39 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23375 | GKN Jaap Peters NL 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2024-03-01 | 3 |  |  | 93.37% | 105.3% | 76.88% | 0 | -15.93% | 97123.22 | 90686.41 | 6436.81 | 0 | 90686.41 | 90686.41 | 0 | 95456.72 | 92.36 | -920.31 | 30879 | 69724.22 | 0 | 8793.29 | 0 | 22086.17 | 0 | 20% | 4.07% | 0% | -20% |  | 0 | [5 empty] | 3850
1729 | 2024-03-14 00:33 | P23583 | Castalla - Test Rig Design | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -16.606 | 140% | 64.79% | 64.79% | 0 | -6.46% | 67520 | 94554.5 | -27034.5 | 1628 | 0 | 0 | 36106 | 61257.6 | 129.65 | 33296.9 | 0 | 61257.6 | 0 | 0 | 0 | 0 | 0 | 21% | 14.54% | 17.17% | -3.83% |  | 42.72 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23545 | Ultra CSS continuation 2023 H2 | Natalie Sinclair | ULT | ULTRA SONAR SYSTEMS LIMITED | EES | Level NC | REIM |  |  |  | -15.5834 | 129% | 76.97% | 44.84% | 0 | 2.23% | 76000 | 98022.4 | -22022.4 | 1413.2 | 0 | 0 | 24259.2 | 75451.2 | 190.25 | 22571.2 | 37794 | 43956.2 | 0 | 37794.24 | 0 | 0 | 0 | 23% | 25.23% | 25% | 2% |  | 80 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23741 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  | 44.7412 | 15.61% | 88.75% | 0% | 0 | 0.48% | 640812 | 100021.9 | 540790.1 | 12087.08 | 0 | 0 | 0 | 88770 | 69 | 11251.9 | 106524 | 0 | 0 | 52662 | 53862 | 0 | 0 | 28% | 28.48% | 28.48% | 0.48% |  | 38.63 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23353 | Spirit 2023 - MRB Man Serv (JC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  | -3.7409 | 113.8% | 65.68% | 65.68% | 0 | 10.29% | 91800 | 104467.5 | -12667.5 | 3386.25 | 0 | 0 | 13320 | 68615.25 | 170.19 | 35852.25 | 0 | 68615.25 | 0 | 0 | 0 | 0 | 0 | 7% | 17.29% | 14.44% | 7.44% |  | 45 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23588 | BAE Typhoon MRB MC Shop Concessions | Andrew Houghton | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 26.9344 | 60.71% | 86.85% | 48.5% | 0 | -3.91% | 175060.5 | 106270.8 | 68789.7 | 2553.97 | 0 | 0 | 0 | 92295.97 | 155.08 | 13974.83 | 48910 | 51537.6367 | 0 | 48910.43 | 0 | 0 | 0 | 31% | 27.09% | 29.23% | -1.77% |  | 55.52 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23352 | Spirit 2023 - Stress Approve Man Serv (CC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  | -3.85 | 109.4% | 65.24% | 65.24% | 0 | 7.29% | 97920 | 107160 | -9240 | 2400 | 0 | 0 | 29856 | 69912 | 193.47 | 37248 | 0 | 69912 | 0 | 0 | 0 | 0 | 0 | 7% | 14.29% | 4.69% | -2.31% |  | 48 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23664 | Tempest Composites WP3 | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 3.814 | 90.46% | 14.91% | 14.91% | 0 | -5.11% | 122455.49 | 110775.12 | 11680.37 | 3062.49 | 0 | 0 | 0 | 16518.7 | 172.67 | 94256.42 | 0 | 16518.7 | 0 | 0 | 0 | 0 | 0 | 37% | 31.89% | 33.95% | -3.05% |  | 60.72 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P22918 | Spirit Shorts Graduates | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 11.111 | 85.79% | 95.71% | 63.08% | 0 | 9.72% | 130000 | 111523.54 | 18476.46 | 1662.9 | 0 | 0 | 9900 | 106734.95 | 206.18 | 4788.59 | 43660 | 70351.6167 | 0 | 43659.95 | 0 | 0 | 0 | 7% | 16.72% | 19.09% | 12.09% |  | 23.28 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23760 | EXP-033 Systems Engineering Support | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 39.2309 | 20.47% | 81.81% | -0.0008584% | 0 | -0.02% | 142300 | 29123.5 | 113176.5 | 2884.88 | 0 | 0 | 0 | 23824.75 | 69 | 5298.75 | 28590 | -0.25 | 0 | 28589.7 | 0 | 0 | 0 | 29% | 28.98% | 28.98% | -0.02% |  | 78.5 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P22883 | Spirit Shorts Evtol PMO C. Hatton | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 41.5601 | 63.58% | 92.22% | 81.79% | 14784 | -11.87% | 185800 | 118140.15 | 67659.85 | 1628 | 0 | 0 | 0 | 108946.73 | 169.82 | 9193.42 | 14784 | 96626.73 | 0 | 0 | 0 | 14784 | 14784 | 26% | 14.13% | 24.2% | -1.8% |  | 36.64 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23739 | Lifing Services DACs | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  | 44.0371 | 18.09% | 93% | -0.0002807% | 0 | 2.98% | 656508 | 118729.7 | 537778.3 | 12211.93 | 0 | 0 | 0 | 110418 | 69 | 8311.7 | 132502 | -0.33333 | 0 | 65650.8 | 66850.8 | 0 | 0 | 28% | 30.98% | 30.98% | 2.98% |  | 37.79 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23270 | Shorts Project X | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 13.7482 | 83.49% | 85.2% | 74% | 0 | 0.69% | 142248 | 118769.84 | 23478.16 | 1707.72 | 0 | 0 | 0 | 101191.5 | 140.52 | 17578.34 | 15963 | 87889 | 15962.69 | 0 | 0 | 0 | 0 | 13% | 13.69% | 10.99% | -2.01% |  | 45.36 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P22736 | WoT Fixed Leading Edge - Industrial | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 106.7% | 93.42% | 91.32% | 3019.54 | 0.01% | 112196.27 | 119668.47 | -7472.2 | 0 | 0 | 0 | 0 | 111796.68 | 12465.69 | 7871.79 | 3020 | 109280.0133 | 0 | 0 | 0 | 3019.54 | 3019.54 | 7% | 7.01% | 0% | -7% |  | 32.26 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23816 | Typhoon FTI Works - 2024 Fixed Price Element | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -3 |  | 0% | 0% | 0 | -3.09% | 0 | 122887.55 | -122887.55 | 40962.52 | 0 | 0 | 146328 | 0 | 35 | 122887.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29% | 25.91% | 25.91% | -3.09% |  | 53.33 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P22861 | WoT FLE Lifting & Handling Tools | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2023-06-14 | 1 |  |  | 65.17% | 101.6% | 101.6% | 0 | 12.01% | 173987.21 | 113381.75 | 60605.46 | 0 | 50078 | 58423.58 | 0 | 115203.5 | 12813.9 | 10678.25 | 0 | 115203.5 | 0 | 0 | 0 | 0 | 0 | 1% | 13.01% | 0% | -1% |  | 45 | [5 empty] | 12500
1729 | 2024-03-14 00:33 | P23743 | EHM Cloud Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 44.1741 | 12.81% | 131.2% | 0.0002562% | 0 | -0.59% | 1016000 | 130104.25 | 885895.75 | 20054.63 | 0 | 0 | 0 | 170752 | 69 | -40647.75 | 204902 | 0.33333 | 0 | 102412.8 | 102489.6 | 0 | 0 | 28% | 27.41% | 27.41% | -0.59% |  | 52.76 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23810 | Strategic Enablement | Owain Jones | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -4 |  | 0% | 0% | 0 | -20.58% | 0 | 133060.2 | -133060.2 | 33265.05 | 0 | 0 | 134000 | 0 | 70 | 133060.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | -2.58% | -2.58% | -20.58% |  | 42 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23533 | External Stowage Design and Detail Support | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 1 |  |  | 102.4% | 97.65% | 73.24% | 0 | 3.33% | 140000 | 143368.75 | -3368.75 | 0 | 0 | 0 | 12936 | 140000 | 41999.7 | -0.25 | 42000 | 105000 | 42000 | 0 | 0 | 0 | 0 | 27% | 30.33% | 0% | -27% |  | 60.04 | [5 empty] | -3369
1729 | 2024-03-14 00:33 | P23823 | EXP-034 Spear 3 Test Equip Requirement Authority | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 19.21 | 13.51% | 31.71% | -0.0007188% | 0 | 0.32% | 85825 | 11592.75 | 74232.25 | 3864.25 | 0 | 0 | 0 | 3675.75 | 28 | 7917 | 4411 | -0.083333 | 4410.9 | 0 | 0 | 0 | 0 | 14% | 14.32% | 14.32% | 0.32% |  | 94.25 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23019 | EXP034-B Actuator Development | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | -89.9992 | 103.1% | 89.91% | 89.91% | 0 | -14.64% | 215541.2 | 222215.54 | -6674.34 | 74.16 | 12297.9 | 12297.9 | 0 | 199796.76 | 395.05 | 5441.78 | 0 | 199796.76 | 0 | 0 | 0 | 0 | 0 | 34% | 19.36% | 35.7% | 1.7% |  | 58.45 | [5 empty] | -16977
1729 | 2024-03-14 00:33 | P23421 | A220 DTC | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 15.19 | 67.86% | 81.64% | 72.7% | 0 | -29.61% | 217089.12 | 147310.02 | 69779.1 | 4593.75 | 0 | 0 | 0 | 120261.6 | 80.08 | 27048.42 | 15801 | 107094.1 | 15800.9 | 0 | 0 | 0 | 0 | 29% | -0.61% | 4.23% | -24.77% |  | 45.41 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P22954 | Technical Support Step 1 | Owain Jones | HUV | HUARUI SPIRIT AEROSPACE MANUFACT | ME | Level 2 | REIM |  |  |  |  | 94.81% | 58.01% | 58.01% | 0 | 0.31% | 155501.18 | 147431.58 | 8069.6 | 0 | 23043 | 23043 | 0 | 85525.49 | 61906.09 | 61906.09 | 0 | 85525.49 | 0 | 0 | 0 | 0 | 0 | 30% | 30.31% | 0% | -30% |  | 60.79 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23520 | FCAS AP Portfolio Systems | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 27.071 | 54.19% | 94.14% | 82.9% | 0 | -6.4% | 810821 | 439423.3 | 371397.7 | 13719.41 | 319.5 | 319.5 | 0 | 413678.31 | 52 | 25744.99 | 59261 | 364294.1433 | 0 | 59261.4 | 0 | 0 | 0 | 22% | 15.6% | 17.82% | -4.18% |  | 79.99 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P22982 | Spirit 2022 - Hugh Sloan | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 105.4558 | 60.31% | 89.64% | 85.05% | 0 | -0.37% | 247473 | 149256.7 | 98216.3 | 931.35 | 0 | 0 | 0 | 133795.08 | 173.13 | 15461.62 | 8217 | 126947.58 | 0 | 0 | 0 | 8217.17 | 0 | 7% | 6.63% | 1.35% | -5.65% |  | 35.42 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23550 | Tempest Composites | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -0.40847 | 100.2% | 99.78% | 84.34% | 0 | 5.13% | 149494.92 | 149819.5 | -324.58 | 794.62 | 0 | 0 | 2396.12 | 149494.92 | 97.18 | 324.58 | 27760 | 126361.5867 | 0 | 27760.26 | 0 | 0 | 0 | 26% | 31.13% | 34.43% | 8.43% |  | 61.6 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23552 | FCAS AP Product Technology Development | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -25% | 597871 | 0 | 597871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0% | -25% |  | 0 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23822 | FCASW Requirements Management | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 3 | REIM | [7 empty] | 0 | -16% | 0 | 0 | 0 | 0 | 0 | 0 | 35930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16% | 0% | 0% | -16% |  | 0 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P22440 | Spirit Managed Service - F&DT and Static Approval | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 3 |  |  | 88.56% | 92.56% | 92.56% | 0 | 11.51% | 173500 | 153656.25 | 19843.75 | 0 | 52115 | 55720 | 0 | 142225.12 | 13717.36 | 11431.13 | 0 | 142225.12 | 0 | 0 | 0 | 0 | 0 | 0% | 11.51% | 0% | 0% |  | 44.73 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23677 | ME Managed Service - Phase 1 | Paul Watson | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  | 22.6283 | 28.23% | 0% | 0% | 0 | -19.73% | 554400 | 156510 | 397890 | 17583.75 | 0 | 0 | 0 | 0 | 113.44 | 156510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33% | 13.27% | 16.86% | -16.14% |  | 45 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23464 | A220 Project X Design Offload | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 56.4954 | 48.89% | 96.3% | 67.76% | 27862.8 | -9.09% | 332340 | 162475.3 | 169864.7 | 3006.7 | 0 | 0 | 0 | 156461.9 | 140.77 | 6013.4 | 55649 | 110087.7333 | 27785.76 | 0 | 0 | 27862.8 | 27862.8 | 26% | 16.91% | 15.3% | -10.7% |  | 42.88 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23600 | MBDA EXP-EE-023 Bristone Certification | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 59.65% | 100% | 100% | 0 | 0.4% | 126600 | 75517 | 51083 | 0 | 0 | 0 | 0 | 75517 | 0 | 0 | 0 | 75517 | 0 | 0 | 0 | 0 | 0 | 41% | 41.4% | 0% | -41% |  | 78.5 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23650 | MBDA Recruitment Management costs | Brian Maddrell | BDW | MBDA UK LIMITED | EES | Level NC | REIM | 2024-02-01 | 0 |  |  |  | 0% | 0% | 0 | 28.46% | 0 | 240971.5 | -240971.5 | 0 | 0 | 0 | 266000 | 0 | 156.66 | 240971.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | 31.46% | 28.48% | 25.48% |  | 82.3 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23637 | MBSE Proposal | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 | 0 | 0 | 0 | 49980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23524 | Bombardier Regional Jets (BRJ) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 130.8% | 56.89% | 44.32% | 28851.48 | -4.69% | 146287.84 | 191311.68 | -45023.84 | 0 | 0 | 0 | 46750 | 108838.22 | 226.25 | 82473.46 | 28851 | 84795.72 | 0 | 0 | 0 | 28851.48 | 28851.48 | 18% | 13.31% | 15.43% | -2.57% |  | 43.92 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23382 | Performance Modelling | Dushan Fernando | BDX | MBDA UK LIMITED | MPE | Level NC | REIM | 2023-07-09 | 0 |  |  | 40.95% | 79.09% | 79.09% | 0 | -16.36% | 170009.66 | 69625.98 | 100383.68 | 0 | 14559.9 | 14559.9 | 0 | 55066.08 | 0 | -0.1 | 0 | 55066.08 | 0 | 0 | 0 | 0 | 0 | 20% | 3.64% | 0% | -20% |  | 77.05 | [5 empty] | -14560
1729 | 2024-03-14 00:33 | P23373 | Raytheon Michael Bellini | Natalie Sinclair | RAS | RAYTHEON UNITED KINGDOM LIMITED | EES | Level NC | REIM |  |  |  | 4.405 | 91.53% | 97.72% | 87.22% | 0 | -8.57% | 214367.4 | 196208.15 | 18159.25 | 4122.45 | 0 | 0 | 0 | 191739.73 | 46.92 | 4468.42 | 24735 | 171127.23 | 24734.7 | 0 | 0 | 0 | 0 | 45% | 36.43% | 36.07% | -8.93% |  | 91.61 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23008 | Spirit Shorts Project Rachel | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 85.87% | 91.32% | 91.32% | 0 | -7.7% | 228880 | 196531.2 | 32348.8 | 0 | 0 | 0 | 0 | 179472.8 | 288.94 | 17058.4 | 0 | 179472.8 | 0 | 0 | 0 | 0 | 0 | 13% | 5.3% | 0.31% | -12.69% |  | 46.04 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23629 | F35 FTI | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level NC | REIM |  |  |  | -20.9677 |  | 83.3% | 83.3% | 0 | -0.76% | 0 | 197994.39 | -197994.39 | 9442.82 | 0 | 0 | 0 | 164920.77 | 29.1 | 33073.62 | 0 | 164920.77 | 0 | 0 | 0 | 0 | 0 | 31% | 30.24% | 28.85% | -2.15% |  | 61.88 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23242 | Physical Architecture & System Engineering Support | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 30.703 | 63.51% | 96.61% | 86.13% | 0 | 8.92% | 305459 | 193987.71 | 111471.29 | 3630.63 | 775.55 | 775.55 | 0 | 187412.05 | 83.1 | 6575.66 | 24398 | 167080.3833 | 0 | 13941.6 | 10456.2 | 0 | 0 | 15% | 23.92% | 7.84% | -7.16% |  | 78.18 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23472 | Tempest Wing Design | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 163.694 | 45.03% | 118.2% | 105.7% | 0 | -19.95% | 483869.78 | 217867.11 | 266002.67 | 1625 | 201987.5 | 356900 | 0 | 257531.55 | 0 | -39664.45 | 32753 | 230237.3833 | 0 | 32753.16 | 0 | 0 | 0 | 23% | 3.05% | 12.51% | -10.49% |  | 46.74 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P22798 | CO2MAP MGSE | Harry James Kellett | DTW | THALES ALENIA SPACE UK (60DAYS) | EES | Level 2 | REIM | 2023-11-08 | 0 |  | -5.7263 | 85.75% | 105% | 105% | 0 | -3.47% | 252086 | 216157.82 | 35928.18 | -6274.25 | 0 | 0 | 0 | 227052.6 | 0.26 | 0.22 | 0 | 227052.6 | 0 | 0 | 0 | 0 | 0 | 29% | 25.53% | 100% | 71% |  | 50.31 | [5 empty] | 10895
1729 | 2024-03-14 00:33 | P23316 | Model Factory IL and AW | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX | 2024-01-12 | 0 |  | 129.9988 | 88.13% | 104.1% | 104.1% | 20248.8 | 2.41% | 250000 | 220327.78 | 29672.22 | 228.25 | 0 | 0 | 0 | 229409 | 0 | -0.22 | 0 | 229409 | 0 | 0 | 0 | 0 | 20248.8 | 30% | 32.41% | 42.82% | 12.82% |  | 45.31 | [5 empty] | 9081
1729 | 2024-03-14 00:33 | P23586 | Project Management Support | Peter Bowen | BDX | MBDA UK LIMITED | MPE | Level NC | REIM |  |  |  | -1.3774 | 104.6% | 80.21% | 77.07% | 0 | -26.03% | 80000 | 83663.86 | -3663.86 | 2660 | 1140.6 | 1140.6 | 16000 | 67103.86 | 52.92 | 16560 | 3149 | 64479.6933 | 0 | 3148.63 | 0 | 0 | 0 | 49% | 22.97% | 22.4% | -26.6% |  | 80 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23317 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX | 2024-01-12 | 0 |  | 35.1852 | 95.89% | 104.3% | 104.3% | 17760 | 4.3% | 251800 | 241446.75 | 10353.25 | 294.25 | 0 | 0 | 0 | 251800 | 0 | -0.25 | 0 | 251800 | 0 | 0 | 0 | 0 | 17760 | 25% | 29.3% | 49.01% | 24.01% |  | 36.29 | [5 empty] | 10353
1729 | 2024-03-14 00:33 | P23603 | Typhoon IMDLR | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 9.8031 | 83.01% | 0% | 0% | 0 | 2.28% | 305067.09 | 253226.49 | 51840.6 | 5288.21 | 0 | 0 | 4271.91 | 0 | 305.89 | 253226.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29% | 31.28% | 32.69% | 3.69% |  | 57.33 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23685 | DAC LUC Support and Recompliance | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 25.3996 | 22.19% | 187.7% | -0.0001273% | 0 | -1.25% | 1180000 | 261844.84 | 918155.16 | 36148.34 | 0 | 0 | 0 | 491428 | 69 | -229583.16 | 589714 | -0.33333 | 0 | 288001.2 | 301712.4 | 0 | 0 | 28% | 26.75% | 26.75% | -1.25% |  | 59.78 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23667 | Safety Systems Engineer | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 62.113 | 36.48% | 94.39% | 72.58% | 0 | -9.15% | 398000 | 145200 | 252800 | 4070 | 0 | 0 | 0 | 137060 | 73.7 | 8140 | 38016 | 105380 | 0 | 19536 | 18480 | 0 | 0 | 47% | 37.85% | 29.32% | -17.68% |  | 110 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P21463 | Safety & Monitoring Systems at DM Beith & Gosport | Harry James Kellett | BXW | MOD | EES | Level 2 | FIX |  |  |  | 301.3434 | 77.52% | 129% | 129% | 0 | -26.93% | 349404.99 | 270871.88 | 78533.11 | 260.61 | 56750.54 | 69642.23 | 21721 | 349386.99 | 0 | -78515.11 | 0 | 349386.99 | 0 | 0 | 0 | 0 | 0 | 48% | 21.07% | 39.88% | -8.12% |  | 52.91 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23699 | A220 Stress Checkers | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -8.3849 |  | 0% | 0% | 0 | -2% | 0 | 274037.57 | -274037.57 | 32682.11 | 7000 | 7000 | 321520 | 0 | 98.33 | 274037.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22% | 20% | 20.03% | -1.97% |  | 61.88 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23308 | NATO JEWCS | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  | 29.8428 | 81.43% | 94.18% | 81.2% | 45213.08 | -3.58% | 356307 | 290132.28 | 66174.72 | 2217.44 | 613.89 | 613.89 | 0 | 273254.06 | 163.66 | 16878.22 | 45213 | 235576.56 | 0 | 0 | 45213.08 | 0 | 45213.08 | 24% | 20.42% | 11.82% | -12.18% |  | 75.81 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23045 | Shotgun Adaptors - 10 Sets | Harry James Kellett | BDW | MBDA UK LIMITED | EES | Level 2 | FIX | 2024-02-27 | 6 |  | 3347.6156 | 74.76% | 133.8% | 95.11% | 0 | -19.12% | 399276.11 | 298512.88 | 100763.23 | 30.1 | 214550.47 | 214550.47 | 0 | 399276.11 | 5744.55 | -100763.23 | 138421 | 283925.2767 | 0 | 138420.73 | 0 | 0 | 0 | 29% | 9.88% | 0% | -29% |  | 55.76 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23617 | Tempest Composites WP2 | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -15.5404 | 124% | 27.21% | 11.23% | 29536.68 | 2.76% | 244405.26 | 302968.31 | -58563.05 | 3768.45 | 0 | 0 | 57651.28 | 82447.45 | 265.02 | 220520.86 | 58103 | 34028.2833 | 0 | 28565.94 | 0 | 29536.68 | 29536.68 | 31% | 33.76% | 33.62% | 2.62% |  | 62.32 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P22515 | Shorts A220 100/300 ALI Phase III | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 43.349 | 79.97% | 97.63% | 92.85% | 0 | 1.21% | 400628.76 | 320376.71 | 80252.05 | 1851.3 | 3450.98 | 3450.98 | 0 | 312787.53 | 94.64 | 7589.18 | 18387 | 297465.03 | 18386.68 | 0 | 0 | 0 | 0 | 10% | 11.21% | 14.16% | 4.16% |  | 40.42 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P22953 | Spirit Shorts eVTOL | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-05-08 | 2 |  |  | 103.1% | 80.83% | 79.36% | 0 | -6.74% | 324272 | 334483.6 | -10211.6 | 0 | 66696.6 | 67387.9 | 0 | 270366 | 179.02 | 64117.6 | 5921 | 265431.8333 | 5920.8 | 0 | 0 | 0 | 0 | 17% | 10.26% | 0% | -17% |  | 46.19 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P22842 | ME Support (Aim Altitude) | James Montgomery | AVI | AIM ALTITUDE UK LIMITED | ME | Level 3 | FIX | 2023-06-14 | 4 |  |  | 99.31% | 100.5% | 86.63% | 57290.84 | 0.49% | 346293.67 | 343918.08 | 2375.59 | 0 | 2909.86 | 2909.86 | 0 | 345673.01 | 55184.93 | -1754.93 | 57291 | 297930.51 | 0 | 0 | 0 | 57290.84 | 57290.84 | 13% | 13.49% | 0% | -13% |  | 46.3 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P22391 | GE System Engineering support | Vinayakumar Sugur | GEE | EXPERIS LIMITED | EES | Level NC | REIM |  |  |  |  | 82.01% | 99.51% | 98.82% | 0 | 0.13% | 434434.25 | 356260.63 | 78173.62 | 0 | 0 | 0 | 0 | 354519.5 | 88.97 | 1741.13 | 2939 | 352070.3333 | 0 | 2939.04 | 0 | 0 | 0 | 6% | 6.13% | 6.09% | 0.09% |  | 57.33 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23023 | Spirit Shorts R Foster/M Gourley | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 7.0798 | 81.57% | 97.89% | 87.4% | 0 | -20.71% | 480221.04 | 391732.35 | 88488.69 | 12498.79 | 229061.5 | 267726 | 0 | 383474.07 | 93.95 | 22769.28 | 49334 | 342362.4033 | 0 | 21204.59 | 28129.27 | 0 | 0 | 27% | 6.29% | 3.05% | -23.95% |  | 29.57 | [5 empty] | 14511
1729 | 2024-03-14 00:33 | P23432 | Spirit Belfast MRB On-Site Support (Mon & Clear) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 65.77% | 125.6% | 103.8% | 77391.6 | -11.53% | 449545 | 295665.27 | 153879.73 | 0 | 295665.27 | 451827.33 | 0 | 371465.75 | 75.91 | 36199.52 | 77392 | 306972.4167 | 0 | 0 | 0 | 77391.6 | 77391.6 | 39% | 27.47% | 0% | -39% |  | 0 | [5 empty] | 112000
1729 | 2024-03-14 00:33 | P23386 | Software Development - BMS | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 98.78% | 100% | 95.49% | 0 | 4.31% | 149650 | 147823.35 | 1826.65 | 0 | 0 | 0 | 0 | 147823.35 | 28.32 | 0 | 8007 | 141150.85 | 0 | 8007 | 0 | 0 | 0 | 18% | 22.31% | 22.61% | 4.61% |  | 78.5 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23320 | Lifing Services DACs | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX | 2024-01-12 | 0 |  | 35.8098 | 95.56% | 104.6% | 104.6% | 34138.8 | 2.98% | 413300 | 394956.45 | 18343.55 | 512.25 | 0 | 0 | 0 | 413300 | 0 | -0.55 | 0 | 413300 | 0 | 0 | 0 | 0 | 34138.8 | 26% | 28.98% | 52.05% | 26.05% |  | 33.15 | [5 empty] | 18343
1729 | 2024-03-14 00:33 | P23531 | BAe Systems F35 MRB Support | Andrew Houghton | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | -35.2705 |  | 73.37% | 73.37% | 0 | 2.97% | 0 | 426974.23 | -426974.23 | 12105.72 | 287.44 | 287.44 | 0 | 313283.73 | 76.78 | 113690.5 | 0 | 313283.73 | 0 | 0 | 0 | 0 | 0 | 25% | 27.97% | 32.02% | 7.02% |  | 59.55 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23585 | Systems Design - Missile Systems, Meteor,Brimstone | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 | 0 | 0 | 0 | 49500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23554 | Dornier Seawings 328 2023 H2 Support | Steven Lawton | DAX | EXPLEO GERMANY GMBH (EC) | MPE | Level 2 | REIM |  |  |  | 2.3179 | 93.8% | 90% | 85.89% | 0 | 8.01% | 474542.24 | 445135.09 | 29407.15 | 12686.92 | 4046.44 | 4046.44 | 0 | 400640 | 54.3 | 44495.09 | 21955 | 382344.1667 | 21955.08 | 0 | 0 | 0 | 0 | 21% | 29.01% | 31.5% | 10.5% |  | 67.71 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P22906 | Spirit Shorts - MRB JD Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 10.8637 | 91.18% | 88.04% | 69.17% | 13497.6 | -7.7% | 481714 | 439205.68 | 42508.32 | 3912.88 | 0 | 0 | 0 | 386687.62 | 285.63 | 60518.06 | 99451 | 303811.7867 | 0 | 0 | 85953.72 | 13497.6 | 13497.6 | 13% | 5.3% | 3.09% | -9.91% |  | 36.88 | [5 empty] | 8000
1729 | 2024-03-14 00:33 | P23372 | BAE Carbon Tooling Off-load | Gary Kempster | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  |  | 165.3% | 56.3% | 56.3% | 0 | -4.13% | 276718 | 457433.31 | -180715.31 | 0 | 0 | 0 | 197460.8 | 257521.57 | 691.79 | 199911.74 | 0 | 257521.57 | 0 | 0 | 0 | 0 | 0 | 27% | 22.87% | 20.94% | -6.06% |  | 53.57 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23140 | Spirit Shorts A220 MLG Stress Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  | 40.8388 | 69.71% | 83.64% | 74.55% | 48343.2 | -8.39% | 636032.4 | 443402.2 | 192630.2 | 4716.84 | 20870.3 | 87811.88 | 0 | 370857.4 | 200.57 | 97544.8 | 48343 | 330571.5667 | 0 | 0 | 0 | 48343.2 | 48343.2 | 25% | 16.61% | 13.45% | -11.55% |  | 47.37 | [5 empty] | 25000
1729 | 2024-03-14 00:33 | P23518 | Systems Engineering support to FCAS | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 14.4745 | 78.23% | 93.32% | 85.65% | 0 | -2.85% | 193736.8 | 151553.5 | 42183.3 | 2914.31 | 3927.4 | 3927.4 | 0 | 141422.18 | 54.93 | 10131.32 | 13942 | 129803.8467 | 0 | 13941.6 | 0 | 0 | 0 | 30% | 27.15% | 3.5% | -26.5% |  | 67.54 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23473 | Tempest Vertical Tail | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 21.1374 | 67.27% | 90.76% | 80.75% | 0 | -2.7% | 723866.48 | 486922.09 | 236944.39 | 11209.74 | 91875 | 100425 | 0 | 441918.18 | 61.94 | 45003.91 | 58490 | 393176.5133 | 0 | 58489.72 | 0 | 0 | 0 | 24% | 21.3% | 23.88% | -0.12% |  | 62.4 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P22652 | L3 - Saftey Engineering | Sean Simmons | LHW | L3HARRIS MAPPS LIMITED | EES | Level NC | FIX |  |  |  |  | 95.63% | 86.69% | 86.69% | 0 | 5.66% | 523390 | 500497.5 | 22892.5 | 0 | 0 | 0 | 0 | 433882.5 | 79938 | 66615 | 0 | 433882.5 | 0 | 0 | 0 | 0 | 0 | 21% | 26.66% | 25.88% | 4.88% |  | 83.05 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23281 | Systems Portfolio | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM | 2024-02-28 | 1 |  |  | 44.43% | 97.31% | 97.19% | 0 | -17.1% | 1177697.24 | 523236.96 | 654460.28 | 0 | 2133.28 | 2133.28 | 0 | 509179.87 | 17523.23 | 13968.09 | 762 | 508544.87 | 0 | 761.53 | 0 | 0 | 0 | 25% | 7.9% | 0% | -25% |  | 70.48 | [5 empty] | -89
1729 | 2024-03-14 00:33 | P23001 | Spirit Shorts A220 Design | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -19.0426 | 113% | 74.61% | 69.95% | 0 | -4.11% | 463100 | 523411.6 | -60311.6 | 3167.2 | 0 | 0 | 65953.2 | 390511.7 | 366.42 | 132899.9 | 29237 | 366147.5333 | 29236.68 | 0 | 0 | 0 | 0 | 25% | 20.89% | 11.8% | -13.2% |  | 43.6 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23323 | CNC-CMM Programming Support | Andrew Houghton | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | 5.9794 | 88.23% | 85.97% | 66.61% | 0 | -3.1% | 617809.74 | 545071.98 | 72737.76 | 12164.72 | 15941.56 | 15941.56 | 0 | 468617.85 | 152.55 | 76454.13 | 126649 | 363077.0167 | 49693.78 | 76955.66 | 0 | 0 | 0 | 32% | 28.9% | 37.28% | 5.28% |  | 57.09 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P21138 | D&A Vibration Reduc Damping Struc FOGV Components | Steven Lawton | ATC | AECC SICHUAN GAS TURBINE | MPE | Level 1 | FIX | 2022-09-07 | 0 |  | 8042.8691 | 96.12% | 104% | 104% | 0 | -3.44% | 569346 | 547228.11 | 22117.89 | 2.75 | 75181.75 | 75181.75 | 0 | 569346 | 0 | 0.11 | 0 | 569346 | 0 | 0 | 0 | 0 | 0 | 36% | 32.56% | 0.08% | -35.92% |  | 73.95 | [5 empty] | 22118
1729 | 2024-03-14 00:33 | P23426 | BAE Tempest WP 3 Harness Maturation | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 14.4997 | 71.17% | 83.14% | 74.32% | 0 | -5.97% | 884012.04 | 629139.4 | 254872.64 | 17577.79 | 213.34 | 213.34 | 0 | 523063.01 | 76.41 | 106076.39 | 66565 | 467592.1767 | 0 | 66565.09 | 0 | 0 | 0 | 33% | 27.03% | 28.22% | -4.78% |  | 51.24 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23219 | Tornado Air 800 Engineering Support | Richard Brook | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 3 | REIM |  |  |  | -1.5565 | 102.9% | 91.39% | 91.39% | 0 | 1.83% | 615046 | 632848.56 | -17802.56 | 11437.55 | 459.21 | 459.21 | 0 | 578373.17 | 108.35 | 54475.39 | 0 | 578373.17 | 0 | 0 | 0 | 0 | 0 | 31% | 32.83% | 37.65% | 6.65% |  | 81.54 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23694 | Systems Portfolio EXP-011a | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 10.2937 | 63.7% | 87.83% | 69.31% | 0 | 2.6% | 648492.8 | 413059 | 235433.8 | 22871.63 | 157.75 | 157.75 | 0 | 362778.8 | 44.13 | 50280.2 | 91787 | 286289.6333 | 0 | 91786.96 | 0 | 0 | 0 | 21% | 23.6% | 18.93% | -2.07% |  | 89.42 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23605 | Typhoon Work Package 2 Continuation | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM |  |  |  | -1003.5327 | 119.7% | 41.27% | -4.544e-05% | 0 | 5.21% | 545536.01 | 652813.66 | -107277.65 | 106.9 | 4054 | 4054 | 81999.09 | 269393.87 | 272.49 | 383419.79 | 323273 | -0.29667 | 89358.36 | 233914.28 | 0 | 0 | 0 | 23% | 28.21% | 29.01% | 6.01% |  | 55.82 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P22790 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 2 | REIM |  |  |  |  | 194.5% | 90.44% | 90.44% | 0 | 1.37% | 352240 | 685262.25 | -333022.25 | 0 | 1611.52 | 1611.52 | 515246 | 619743.88 | 41098.04 | 34248.37 | 0 | 619743.88 | 0 | 0 | 0 | 0 | 0 | 13% | 14.37% | 0% | -13% |  | 45.06 | [5 empty] | -31270
1729 | 2024-03-14 00:33 | P23451 | BAE Tempest - DFM-ASO Planning | Andrew Houghton | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | 8.733 | 79.24% | 54.27% | 51.27% | 27224.9 | -3.27% | 953905.42 | 755847.93 | 198057.49 | 22679.12 | 0 | 0 | 0 | 410201.83 | 128.47 | 345646.1 | 27225 | 387514.33 | 0 | 0 | 27224.9 | 0 | 27224.9 | 28% | 24.73% | 26.94% | -1.06% |  | 53.6 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23321 | EHM Cloud Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX | 2024-01-29 | 0 |  | 99.5882 | 89.76% | 111.4% | 111.4% | 69002.4 | 2.92% | 839969 | 753974.58 | 85994.42 | 863.5 | 0 | 0 | 0 | 839969 | 0 | -0.42 | 0 | 839969 | 0 | 0 | 0 | 0 | 69002.4 | 28% | 30.92% | 57.47% | 29.47% |  | 49.95 | [5 empty] | 85994
1729 | 2024-03-14 00:33 | P23105 | Raytheon Supply Engineering Support | Natalie Sinclair | RAY | RAYTHEON UNITED KINGDOM LIMITED | MPE | Level 3A | REIM | 2023-07-13 | 2 |  | -469.7339 | 76.96% | 94.49% | 90.07% | 49156.8 | -2.02% | 1205008 | 927395.25 | 277612.75 | -591 | 0 | 0 | 0 | 876291.5 | 107644.5 | 48739.75 | 49157 | 835327.3333 | 0 | 0 | 49156.8 | 0 | 49156.8 | 26% | 23.98% | 100% | 74% |  | 48.97 | [5 empty] | -2364
1729 | 2024-03-14 00:33 | P22350 | EMP 2020-2021 | Natalie Sinclair | ARY | GUIDANT GROUP (trading name) | PCPR | Level NC | REIM |  |  |  | 7.9473 | 94.84% | 99.03% | 94.23% | 0 | -2.07% | 1017579.76 | 965025.39 | 52554.37 | 6612.83 | 400 | 400 | 0 | 955626.67 | 66.02 | 9398.72 | 55595 | 909297.5033 | 15720.92 | 31809.66 | 8064.8 | 0 | 0 | 32% | 29.93% | 26.88% | -5.12% |  | 44.09 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23117 | BAE Typhoon Eng Support | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | 2024-03-12 | 9 |  |  | 107.6% | 88.52% | 88.52% | 0 | -1.44% | 950771.99 | 1022826.17 | -72054.18 | 0 | 19090.01 | 21165.02 | 69773.84 | 905367.99 | 108434.61 | 90362.18 | 0 | 905367.99 | 0 | 0 | 0 | 0 | 0 | 30% | 28.56% | 0% | -30% |  | 52.3 | [5 empty] | -27096
1729 | 2024-03-14 00:33 | P23292 | BAE Tempest WP 4 AV Trays | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 14.5907 | 78.18% | 88% | 80.6% | 0 | 2.01% | 1498284.22 | 1171331.41 | 326952.81 | 22408.24 | 0 | 0 | 0 | 1030717.75 | 75.86 | 140613.66 | 104015 | 944038.5833 | 0 | 104014.85 | 0 | 0 | 0 | 32% | 34.01% | 33.41% | 1.41% |  | 53.2 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P22671 | Spirit Shorts Pylon and Fairing Package | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX | 2023-05-03 | 4 |  | -5480.8022 | 105% | 95.26% | 95.26% | 0 | -7.21% | 1198494.77 | 1258071.09 | -59576.32 | 10.87 | 106494.89 | 174907.39 | 0 | 1198494.77 | 2544.39 | 2120.32 | 0 | 1198494.77 | 0 | 0 | 0 | 0 | 0 | 20% | 12.79% | 0% | -20% |  | 45.4 | [5 empty] | -57456
1729 | 2024-03-14 00:33 | P23519 | Mechanical and Electrical Design Eng Support | Dushan Fernando | BAX | SAFRAN SEATS GB LIMITED | MPE | Level 2 | REIM |  |  |  | 14.3576 | 66.54% | 92.58% | 68.35% | 0 | -1.53% | 1807261.3 | 1202513.55 | 604747.75 | 42120.48 | 727 | 727 | 0 | 1113289.55 | 88.25 | 89224 | 349575 | 821977.05 | 0 | 349574.52 | 0 | 0 | 0 | 33% | 31.47% | 31.6% | -1.4% |  | 56.63 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23152 | Project Aragon - Design and Stress Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 6.5511 | 93.41% | 58.55% | 58.55% | 0 | -9.53% | 1333452.21 | 1245582.89 | 87869.32 | 13412.83 | 0 | 0 | 0 | 729295.96 | 315.36 | 516286.93 | 0 | 729295.96 | 0 | 0 | 0 | 0 | 0 | 39% | 29.47% | 29.23% | -9.77% |  | 51.91 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23282 | Tooling Support (MBDA) | Dushan Fernando | BDV | MBDA UK LIMITED | ME | Level NC | REIM |  |  |  | -6.7354 | 111.8% | 88.59% | 88.59% | 0 | -8.83% | 104834.4 | 117167.35 | -12332.95 | 1831.07 | 0 | 0 | 19964 | 103803.97 | 59.17 | 13363.38 | 0 | 103803.97 | 0 | 0 | 0 | 0 | 0 | 30% | 21.17% | 30.37% | 0.37% |  | 49.71 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23315 | DAC LUC BAU and Service Workbench | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX | 2024-02-16 | 0 |  | 36.2551 | 85.17% | 117.4% | 117.4% | 195596.4 | 3.27% | 1573630 | 1340192.3 | 233437.7 | 6438.75 | 180.3 | 180.3 | 0 | 1573630 | 0 | -13235.7 | 0 | 1573630 | 0 | 0 | 0 | 0 | 195596.4 | 28% | 31.27% | 43.82% | 15.82% |  | 52.35 | [5 empty] | 220202
1729 | 2024-03-14 00:33 | P23508 | Verification and Validation | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 16.1036 | 80% | 97.98% | 89.77% | 0 | 10.86% | 212950 | 170364.63 | 42585.37 | 2644.47 | 0 | 0 | 0 | 166930.28 | 34 | 3434.35 | 16791 | 152937.78 | 0 | 16791.16 | 0 | 0 | 0 | 24% | 34.86% | 33.97% | 9.97% |  | 78.5 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23006 | Spirit Shorts A350 Freighter Toulouse | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -31.2085 | 150.7% | 80.94% | 79.15% | 0 | 19.19% | 1035745.92 | 1560462.56 | -524716.64 | 16813.28 | 1086670.26 | 1708220.2 | 0 | 1262988.03 | 302.58 | 608748.53 | 33464 | 1235101.3633 | 33464.4 | 0 | 0 | 0 | 0 | 5% | 24.19% | 35.94% | 30.94% |  | 47.88 | [5 empty] | 311274
1729 | 2024-03-14 00:33 | P22278 | TAI Supply Engineers to Ankara | Natalie Sinclair | TAI | TUSAS-TURK HAVACILIK VE UZAY | MPE | Level 3A | REIM |  |  |  | 465.799 | 19.32% | 469.8% | 469.8% | 0 | -15.62% | 2105282 | 406745.91 | 1698536.09 | 3646.5 | 49400.29 | 49400.29 | 0 | 1910696.33 | 0 | -10544.42 | 0 | 1910696.33 | 0 | 0 | 0 | 0 | 0 | 95% | 79.38% | 65.48% | -29.52% |  | 34.25 | [5 empty] | 1493406
1729 | 2024-03-14 00:33 | P23175 | BAe Aero Typhoon Package 2 | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM | 2024-03-12 | 2 |  |  | 103.8% | 96.32% | 96.32% | 0 | -1.63% | 1984265.09 | 2060011.83 | -75746.74 | 0 | 57677.87 | 86030.82 | 15444.64 | 1984257.03 | 84731.75 | 70609.8 | 0 | 1984257.03 | 0 | 0 | 0 | 0 | 0 | 29% | 27.37% | 0% | -29% |  | 51.76 | [5 empty] | -5145
1729 | 2024-03-14 00:33 | P23257 | BAE Tempest WP 5 Centre Fuselage | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 1.4226 | 98.75% | 95.63% | 92.08% | 0 | -5.74% | 2106860.71 | 2080449.92 | 26410.79 | 18565.16 | 78100 | 78100 | 0 | 1989561.03 | 64.62 | 90888.89 | 88762 | 1915592.6967 | 0 | 88762 | 0 | 0 | 0 | 33% | 27.26% | 28.56% | -4.44% |  | 61.06 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P19020 | Spirit Concessions - 2018 | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2024-01-23 | 3 |  |  | 90.82% | 111.8% | 107% | 99792.83 | 2.09% | 1914846.83 | 1739018.14 | 175828.69 | 0 | 44317.61 | 44317.61 | 15178.88 | 1944710.76 | 5424.14 | 196987.38 | 99793 | 1861549.9267 | 0 | 0 | 0 | 99792.83 | 99792.83 | 25% | 27.09% | 9.32% | -15.68% |  | 40.87 | [5 empty] | 402680
1729 | 2024-03-14 00:33 | P23207 | A350 Approvers - Design and Stress Support | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  | 7.8164 | 82.63% | 89.39% | 49.42% | 169776.21 | -4.58% | 2728308 | 2254518.55 | 473789.45 | 60614.44 | 26624.64 | 27084.59 | 0 | 2015419.25 | 149.24 | 239099.3 | 1081494 | 1114174.25 | 0 | 570705.26 | 341012.63 | 169776.21 | 169776.21 | 23% | 18.42% | 18.57% | -4.43% |  | 54.7 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23179 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX |  |  |  | -114.9717 | 129.6% | 89.81% | 82.08% | 35500.91 | -9.34% | 1955410.8 | 2534892.18 | -579481.38 | 5040.21 | 156991.12 | 248243.92 | 492000 | 2276494.65 | 453.93 | 258397.53 | 235154 | 2080532.9833 | 49890.05 | 140266.99 | 9496.08 | 35500.91 | 35500.91 | 22% | 12.66% | 16.76% | -5.24% |  | 44.4 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P23487 | Tornado Air 800 Engineering Support | Richard Brook | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 2 | FIX |  |  |  | 4.0573 | 93.3% | 84.13% | 79.38% | 30074.38 | -4.3% | 2928777.63 | 2732475.86 | 196301.77 | 48382.06 | 0 | 0 | 0 | 2298724.51 | 79.2 | 433751.35 | 155495 | 2169145.3433 | 0 | 125420.63 | 30074.38 | 0 | 30074.38 | 40% | 35.7% | 38.16% | -1.84% |  | 78.71 | [5 empty] | 0
1729 | 2024-03-14 00:33 | P19731 | Hapri HPC Rear Bearing Housing PDR & CDR | Steven Lawton | ATC | AECC Hunan Aviation Powerplant | MPE | Level 1 | FIX |  |  |  | 1.8027 | 99.84% | 100.2% | 87.64% | 447000 | -15.38% | 2980000 | 2975321.17 | 4678.83 | 2595.41 | 363828.33 | 518253.56 | 0 | 2980000 | 862 | -229678.83 | 447000 | 2607500 | 0 | 0 | 0 | 447000 | 447000 | 38% | 22.62% | 14.11% | -23.89% |  | 64.86 | [5 empty] | -225000
Extend Table

## AP3-3
WIP No | Date Created | Project ID | Project Description | Project Manager | Department Id | Client | CBU | Complexity | Type | Stop Booking Hrs | Closing Project: Action(s) to close | RAG | Approx. PO Burndown (weeks) | Turnover vs Contract Value | Invoice To Date vs Turnover | Cash in vs Turnover | Open Amount Overdue | Actual PM% to Baseline PM% delta | Contract Value | Total Project Turnover | Contract Value - Total Turnover | Run Rate (based on total turnover) | Total BOI Spend to Date | Total Committed PO (supplier/best shore) | Current AA in PT3 | Invoiced To Date | DSO | Unbilled (WIP) | Total Open Amount | Cash in (Invoiced - (Open amount -VAT)) | Debt <=30 Days | Debt 31 - 60 Days | Debt 61 - 90 Days | Debt >= 90 Days | Open Amount Overdue2 | Baseline Project Margin | Project To Date (PTD) PM | Year to Date (YTD) PM | YTD Delta Actual PM% to BPM% | Forecast PM at Completion (Manual input from PTT) | Average Sale Rate | CSat score for last quarter (Manual input from PTT) | Comments and Actions | Judged income adjustment at completion | Profit to take now | Provision required now | Fully Traded | Last Months Comments and Actions
1730 | 2024-03-21 00:35 | P23411 | Agile & Scrum Delivery Service | Peter Williams | BDZ | MBDA UK LIMITED | DET | Level 2 | REIM | 2023-08-14 | 0 |  |  | 36.3% | 170.5% | 170.5% | 0 | 13.08% | 2487000 | 902903.79 | 1584096.21 | 0 | 894178.59 | 894178.59 | 0 | 1539600 | 19368.95 | 16140.79 | 0 | 1539600 | 0 | 0 | 0 | 0 | 0 | 29% | 42.08% | 0% | -29% |  | 74.57 | [5 empty] | 652837
1730 | 2024-03-21 00:35 | P23435 | Andy Baker Portfolio | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 27.7854 | 54.57% | 80.67% | 73.68% | 0 | -7.18% | 3377457.4 | 1843195.25 | 1534262.15 | 55218.22 | 2352.57 | 2352.57 | 0 | 1486941.37 | 78.06 | 356253.88 | 154740 | 1357991.37 | 0 | 154740.27 | 0 | 0 | 0 | 25% | 17.82% | 20.6% | -4.4% |  | 80.08 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23717 | GKN Ted Tomblin 2024 | Matthew Tweed | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 10047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23543 | EXP-024 FCAS AP Transformation & Change Enablers | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -26% | 385921 | 0 | 385921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26% | 0% | 0% | -26% |  | 0 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23677 | ME Managed Service - Phase 1 | Paul Watson | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  | 20.6379 | 31.73% | 0% | 0% | 0 | -16.59% | 554400 | 175893.75 | 378506.25 | 18340.31 | 0 | 0 | 0 | 0 | 114.57 | 175893.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33% | 16.41% | 20.44% | -12.56% |  | 45 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23473 | Tempest Vertical Tail | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 20.2597 | 68.69% | 97.44% | 79.08% | 0 | -2.61% | 723866.48 | 497208.56 | 226657.92 | 11187.63 | 91875 | 100425 | 0 | 484472.71 | 75.22 | 12735.85 | 109555 | 393176.8767 | 51065.44 | 58489.72 | 0 | 0 | 0 | 24% | 21.39% | 24.04% | 0.04% |  | 62.39 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23437 | Embedded Software Engineer | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 0.87709 | 98.73% | 96.08% | 85.98% | 0 | -6.29% | 150150 | 148239.36 | 1910.64 | 2178.38 | 737.86 | 737.86 | 0 | 142430.36 | 61.44 | 5809 | 17961 | 127462.86 | 0 | 17960.7 | 0 | 0 | 0 | 22% | 15.71% | 16.24% | -5.76% |  | 78.5 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23730 | FLE Project | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -16.79% | 0 | 1120 | -1120 | 0 | 0 | 0 | 24000 | 0 | 76 | 1120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | -16.79% | -16.79% | -16.79% |  | 35 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23463 | A220 Wing MaMo Design Checking | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-03-07 | 0 |  |  |  | 0% | 0% | 0 | 7.85% | 0 | 1628 | -1628 | 0 | 0 | 0 | 15000 | 0 | 1953.6 | 1628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | 10.85% | 0% | -3% |  | 44 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P21028 | Rebate Collection (BACC) | David Catchpole | TOO | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | [5 empty] | 0% | 0% | 0 | 0% | 0 | 2680 | -2680 | 0 | 2680 | 2680 | 0 | 0 | 3216 | 2680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23578 | ESN Work Package | Hannah Mead | COZ | CHELTON LIMITED | DET | Level 3 | FIX | 2024-01-01 | 0 |  |  | 86.17% | 116.1% | 116.1% | 0 | 35.86% | 4410 | 3800 | 610 | 0 | 0 | 0 | 0 | 4410 | 0 | -610 | 0 | 4410 | 0 | 0 | 0 | 0 | 0 | 24% | 59.86% | 0% | -24% |  | 95 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23628 | Design Assurance | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -6.67% | 0 | 3909.24 | -3909.24 | 0 | 0 | 0 | 4454.8 | 0 | 4691.09 | 3909.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 0.33% | 0% | -7% |  | 15.05 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23002 | WoT MAJ Transit Flag Stress | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 30.89% | 323.8% | 323.8% | 0 | 53.84% | 4735 | 1462.5 | 3272.5 | 0 | 0 | 2242.5 | 0 | 4735 | 0.6 | 0.5 | 0 | 4735 | 0 | 0 | 0 | 0 | 0 | 10% | 63.84% | 0% | -10% |  | 45 | [5 empty] | 3273
1730 | 2024-03-21 00:35 | P23718 | Requalification of EJ200 GSS ESS EHM SW module | Vijayakumara Nanjundappa | ARZ | MTU AERO ENGINES AG | DET | Level 3 | FIX |  |  |  | 183.3454 | 9.483% | 256.7% | 42.78% | 0 | -2.61% | 74463 | 7061.57 | 67401.43 | 367.62 | 991.93 | 991.93 | 0 | 18125 | 76 | -11063.43 | 18125 | 3020.8333 | 0 | 18125 | 0 | 0 | 0 | 28% | 25.39% | 25.39% | -2.61% |  | 80 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23607 | SAFRAN - A330neo Turnover Frame | Gary Kempster | TOO | SAFRAN SEATS GB LIMITED | MPE | Level 3 | FIX |  |  |  | 4 | 95.68% | 104.5% | 0.001994% | 0 | -15.57% | 8736 | 8359 | 377 | 94.25 | 0 | 0 | 0 | 8736 | 10483.2 | 0 | 10483 | 0.16667 | 0 | 0 | 10483.2 | 0 | 0 | 23% | 7.43% | 100% | 77% |  | 52 | [5 empty] | 377
1730 | 2024-03-21 00:35 | P23274 | ME Support (Aim Altitude - Cambridge) | James Montgomery | AVI | AVIC CABIN SYSTEMS (UK) LIMITED | ME | Level 3 | FIX | 2023-08-18 | 0 |  |  | 51.88% | 56.3% | 56.3% | 0 | -0.17% | 17280 | 8964 | 8316 | 0 | 0 | 0 | 0 | 5046.3 | 4701.24 | 3917.7 | 0 | 5046.3 | 0 | 0 | 0 | 0 | 0 | 21% | 20.83% | 0% | -21% |  | 48 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23283 | Spirit Tooling Audit | Charidimos Valadakis | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-05-03 | 0 |  |  | 97.22% | 48.57% | 48.57% | 0 | -7.99% | 9910.08 | 9634.8 | 275.28 | 0 | 0 | 0 | 0 | 4679.76 | 5946.05 | 4955.04 | 0 | 4679.76 | 0 | 0 | 0 | 0 | 0 | 7% | -0.99% | 0% | -7% |  | 34.41 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23127 | Loft Hall Design Support | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 101% | 99.06% | 99.06% | 0 | -9.55% | 9680 | 9772 | -92 | 0 | 0 | 0 | 0 | 9680 | 110.4 | 92 | 0 | 9680 | 0 | 0 | 0 | 0 | 0 | 41% | 31.45% | 0% | -41% |  | 44 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23630 | 2Excel CFD Analysis Support | Dushan Fernando | BAX | STIRLING DYNAMICS LTD | MPE | Level NC | FIX |  |  |  |  | 61.2% | 100% | 100% | 0 | -1.87% | 16195.49 | 9911.34 | 6284.15 | 0 | 0 | 0 | 0 | 9911.63 | 0 | -0.29 | 0 | 9911.63 | 0 | 0 | 0 | 0 | 0 | 26% | 24.13% | 0% | -26% |  | 64.78 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23313 | Laser Trim Fixtures | Gary Kempster | TOO | ALKEN ENGINEERING LIMITED | MPE | Level 3 | FIX | 2023-11-20 | 0 |  |  | 89.87% | 111.3% | 111.3% | 0 | 0.53% | 13770 | 12375 | 1395 | 0 | 0 | 0 | 0 | 13770 | 0 | -1395 | 0 | 13770 | 0 | 0 | 0 | 0 | 0 | 17% | 17.53% | 0% | -17% |  | 45 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P22761 | Red Bull Chassis Spit | James Montgomery | TOO | MANUFAX ENGINEERING LTD | MPE | Level 3 | FIX | 2022-11-15 | 0 |  |  | 72.18% | 96.98% | 96.98% | 0 | 7.92% | 12961.2 | 9355.5 | 3605.7 | 0 | 0 | 0 | 0 | 9072.84 | 4666.39 | 3888.66 | 0 | 9072.84 | 0 | 0 | 0 | 0 | 0 | 23% | 30.92% | 0% | -23% |  | 42.19 | [5 empty] | 3606
1730 | 2024-03-21 00:35 | P23433 | Cavendish | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 32.81% | 100% | 100% | 0 | -0.34% | 42240 | 13859.2 | 28380.8 | 0 | 0 | 0 | 0 | 13859.2 | 0 | 0 | 0 | 13859.2 | 0 | 0 | 0 | 0 | 0 | 7% | 6.66% | 0% | -7% |  | 43.93 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23350 | Spirit 2023 - Stress Approve Man Serv (DH) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 14.15% | 72.64% | 72.64% | 0 | -0.29% | 97920 | 13860 | 84060 | 0 | 0 | 0 | 0 | 10068 | 4550.4 | 3792 | 0 | 10068 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P21463 | Safety & Monitoring Systems at DM Beith & Gosport | Harry James Kellett | BXW | MOD | EES | Level 2 | FIX |  |  |  | 268.9286 | 77.6% | 128.9% | 128.9% | 0 | -26.95% | 349404.99 | 271130.63 | 78274.36 | 291.06 | 57009.29 | 69911.88 | 21721 | 349386.99 | 0 | -78256.36 | 0 | 349386.99 | 0 | 0 | 0 | 0 | 0 | 48% | 21.05% | 39.26% | -8.74% |  | 52.91 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23742 | Cyber Security Support | Hannah Mead | COZ | CHELTON LIMITED | DET | Level 3 | FIX |  |  |  | -9.4 |  | 0% | 0% | 0 | 31.67% | 0 | 14100 | -14100 | 1500 | 0 | 0 | 27500 | 0 | 91 | 14100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 31.67% | 31.67% | 31.67% |  | 100 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23740 | Phase 2 - EJ200 ESS EHM Platform Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 3 | FIX |  |  |  | 60.644 | 6.934% | 206% | -0.001366% | 0 | 9.99% | 175971 | 12202 | 163769 | 2700.5 | 0 | 0 | 0 | 25139 | 88.46 | -10937 | 30167 | -0.16667 | 0 | 0 | 30166.8 | 0 | 0 | 28% | 37.99% | 37.99% | 9.99% |  | 52.37 | [5 empty] | 2000
1730 | 2024-03-21 00:35 | P23337 | Spirit 2023 - Steve Grimley | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 25.28% | 100% | 100% | 0 | 0.01% | 56812.9 | 14362.47 | 42450.43 | 0 | 0 | 0 | 0 | 14362.47 | 0 | 0 | 0 | 14362.47 | 0 | 0 | 0 | 0 | 0 | 7% | 7.01% | 0% | -7% |  | 30.11 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23831 | Contract DM/00113 for maintenance, repair and post | Harry James Kellett | BXW | MOD | EES | Level 2 | FIX |  |  |  | 3.4957 | 36.39% | 0% | 0% | 0 | 16.59% | 40800 | 14848.1 | 25951.9 | 7424.05 | 0 | 0 | 0 | 0 | 91 | 14848.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37% | 53.59% | 53.59% | 16.59% |  | 80.26 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23597 | MRB Onsite support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-02-16 | 1 |  |  |  | 0% | 0% | 0 | -10.04% | 0 | 15100.57 | -15100.57 | 0 | 9448.07 | 17381.62 | 24200 | 0 | 102.4 | 15100.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 7.96% | 8.95% | -9.05% |  | 42.5 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23811 | Spirit T300 MRB Concessions | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -4 |  | 0% | 0% | 0 | -7.14% | 0 | 15199.21 | -15199.21 | 3799.8 | 0 | 0 | 34639 | 0 | 35 | 15199.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21% | 13.86% | 13.86% | -7.14% |  | 46.81 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23823 | EXP-034 Spear 3 Test Equip Requirement Authority | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 18.3462 | 17.9% | 23.93% | -0.0005424% | 0 | 0.32% | 85825 | 15362.75 | 70462.25 | 3840.69 | 0 | 0 | 0 | 3675.75 | 35 | 11687 | 4411 | -0.083333 | 4410.9 | 0 | 0 | 0 | 0 | 14% | 14.32% | 14.32% | 0.32% |  | 94.25 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23663 | Spirit Tooling Verification and Inspection | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 5.25 | 78.12% | 0% | 0% | 0 | -7.49% | 19820.16 | 15484.5 | 4335.66 | 825.84 | 0 | 0 | 7392 | 0 | 145.21 | 15484.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12% | 4.51% | 4.82% | -7.18% |  | 34.41 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23821 | Supply of Safety Engineer | Dinna Elkhalifa | BXW | STIRLING DYNAMICS LTD | EES | Level NC | REIM |  |  |  | 3.9346 | 50.41% | 0% | 0% | 0 | 20.48% | 34006.44 | 17143.32 | 16863.12 | 4285.83 | 0 | 0 | 0 | 0 | 91 | 17143.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 20.48% | 20.48% | 20.48% |  | 55.48 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23635 | Engineering Services: FAI Support | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 49.9% | 0% | 0% | 0 | -3.4% | 37230 | 18576 | 18654 | 0 | 0 | 0 | 0 | 0 | 248.18 | 18576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8% | 4.6% | 5.04% | -2.96% |  | 38.7 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23343 | Spirit 2023 - John Agnew | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-08-09 | 0 |  |  | 28.56% | 86.27% | 86.27% | 0 | -0.02% | 65120.37 | 18600.89 | 46519.48 | 0 | 0 | 0 | 0 | 16047.15 | 3064.49 | 2553.74 | 0 | 16047.15 | 0 | 0 | 0 | 0 | 0 | 7% | 6.98% | 0% | -7% |  | 34.51 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23724 | GKN S McConnell 2024 | Matthew Tweed | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  | 16.2432 | 39.9% | 72.18% | -0.000872% | 0 | 1.51% | 49820 | 19878.18 | 29941.82 | 1843.34 | 0 | 0 | 0 | 14348.16 | 76 | 5530.02 | 17218 | -0.17333 | 0 | 17217.79 | 0 | 0 | 0 | 19% | 20.51% | 20.51% | 1.51% |  | 49.82 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23355 | Spirit Tooling Support 2023 | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-23 | 0 |  |  | 22.93% | 89.02% | 89.02% | 0 | -0.82% | 91800 | 21053.34 | 70746.66 | 0 | 0 | 0 | 0 | 18742.5 | 2773.01 | 2310.84 | 0 | 18742.5 | 0 | 0 | 0 | 0 | 0 | 20% | 19.18% | 0% | -20% |  | 44.46 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23351 | Spirit 2023 - Design Man Serv (KL) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 26.47% | 93.15% | 93.15% | 0 | 0.09% | 93840 | 24840 | 69000 | 0 | 0 | 0 | 0 | 23138 | 2042.4 | 1702 | 0 | 23138 | 0 | 0 | 0 | 0 | 0 | 26% | 26.09% | 0% | -26% |  | 46 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23356 | Spirit 2023 - Design Man Serv (AH) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX | 2023-08-09 | 1 |  |  |  | 76.66% | 0.001332% | 23018.4 | 0.48% | 0 | 25023.08 | -25023.08 | 0 | 0 | 0 | 25300 | 19182 | 30027.7 | 5841.08 | 23018 | 0.33333 | 0 | 0 | 0 | 23018.4 | 23018.4 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P22884 | Spirit Shorts Config Eng | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 66.3% | 100.1% | 100.1% | 0 | 0.56% | 38976 | 25841.9 | 13134.1 | 0 | 0 | 0 | 0 | 25863.2 | 0 | -0.3 | 0 | 25863.2 | 0 | 0 | 0 | 0 | 0 | 7% | 7.56% | 0% | -7% |  | 20.3 | [5 empty] | 21
1730 | 2024-03-21 00:35 | P23354 | Spirit 2023 - Design Man Serv (PC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 27.97% | 99.36% | 99.36% | 0 | 0.48% | 93840 | 26248.98 | 67591.02 | 0 | 0 | 0 | 0 | 26082 | 200.38 | 166.98 | 0 | 26082 | 0 | 0 | 0 | 0 | 0 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23651 | PMO Spirit | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -20.132 |  | 0% | 0% | 0 | 23.87% | 0 | 27450 | -27450 | 1363.5 | 0 | 0 | 42680 | 0 | 201.71 | 27450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 23.87% | 23.18% | 23.18% |  | 36 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P22756 | A350 FLE Design Checker | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2022-03-23 | 1 |  |  | 68.39% | 119.7% | 119.7% | 0 | 16.46% | 34898.4 | 23867.15 | 11031.25 | 0 | 23867.15 | 24342.3 | 0 | 28571.1 | 0.06 | 0.05 | 0 | 28571.1 | 0 | 0 | 0 | 0 | 0 | 0% | 16.46% | 0% | 0% |  | 0 | [5 empty] | 4704
1730 | 2024-03-21 00:35 | P23598 | MRB Onsite support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 26.1856 | 22.63% | 0% | 0% | 0 | -12.91% | 133056 | 30113.92 | 102942.08 | 3931.25 | 8736.42 | 14079.58 | 0 | 0 | 93.74 | 30113.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 15.09% | 15.54% | -12.46% |  | 42.5 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23338 | Spirit 2023 - Blair Hainey | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 5.6081 | 89% | 58.77% | 58.77% | 0 | 4.82% | 34494.36 | 30701.26 | 3793.1 | 676.36 | 0 | 0 | 0 | 18042.36 | 154.83 | 12658.9 | 0 | 18042.36 | 0 | 0 | 0 | 0 | 0 | 7% | 11.82% | 19.31% | 12.31% |  | 18.28 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23506 | ASTER Mid-Life Refurbishment Project Manager | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 7.7032 | 82.9% | 93.72% | 83.48% | 0 | 1.02% | 224900 | 186451.41 | 38448.59 | 4991.25 | 2806.41 | 2806.41 | 0 | 174736.41 | 58.39 | 11715 | 22897 | 155655.5767 | 0 | 22896.62 | 0 | 0 | 0 | 25% | 26.02% | 26.31% | 1.31% |  | 110 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23760 | EXP-033 Systems Engineering Support | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 30.4442 | 22.53% | 74.3% | -0.0007796% | 0 | -0.02% | 142300 | 32067.25 | 110232.75 | 3620.81 | 0 | 0 | 0 | 23824.75 | 76 | 8242.5 | 28590 | -0.25 | 0 | 28589.7 | 0 | 0 | 0 | 29% | 28.98% | 28.98% | -0.02% |  | 78.5 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23365 | GKN 777x Lip Skin Fixture | Steven Lawton | TOO | GKN AEROSPACE SERVICES LTD | MPE | Level 3 | FIX | 2023-10-12 | 0 |  |  | 41.91% | 113.2% | 113.2% | 0 | -9.26% | 79161.46 | 33175.67 | 45985.79 | 0 | 5109.88 | 5109.88 | 0 | 37544.22 | 0 | -4368.55 | 0 | 37544.22 | 0 | 0 | 0 | 0 | 0 | 22% | 12.74% | 0% | -22% |  | 56 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P22768 | MRB Onsite Support - Spirit Belfast | James Montgomery | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2023-07-27 | 0 |  |  |  | 0% | 0% | 0 | -17.07% | 0 | 34614 | -34614 | 0 | 0 | 0 | 36800 | 0 | 41536.8 | 34614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | -7.07% | 0% | -10% |  | 36 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23347 | WoT Fixed Leading Edge - Industrial 2023 | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 112.8% | 42.03% | 42.03% | 0 | -0.41% | 31034.12 | 35002.1 | -3967.98 | 0 | 0 | 0 | 10500 | 14710.56 | 24349.85 | 20291.54 | 0 | 14710.56 | 0 | 0 | 0 | 0 | 0 | 7% | 6.59% | 0% | -7% |  | 32.26 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23051 | Spirit Shorts A350 PAX Door | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 3A | REIM |  |  |  |  | 205.9% | 105.4% | 105.4% | 0 | -0.63% | 18216 | 37513 | -19297 | 0 | 0 | 0 | 0 | 39537 | 0 | 0 | 0 | 39537 | 0 | 0 | 0 | 0 | 0 | 30% | 29.37% | 0% | -30% |  | 46 | [5 empty] | 2024
1730 | 2024-03-21 00:35 | P23642 | MRB Belfast Support | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -18.5848 |  | 0% | 0% | 0 | -42.84% | 0 | 40307.9 | -40307.9 | 2168.86 | 2947.65 | 2947.65 | 42350 | 0 | 175.46 | 40307.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22% | -20.84% | -23.31% | -45.31% |  | 38.52 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P22752 | Tooling WoT - 2021 (Spirit) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | REIM | 2023-05-03 | 0 |  |  | 101.1% | 74.02% | 74.02% | 0 | -8.5% | 41525.1 | 41982.28 | -457.18 | 0 | 0 | 0 | 0 | 31076.1 | 13087.42 | 10906.18 | 0 | 31076.1 | 0 | 0 | 0 | 0 | 0 | 0% | -8.5% | 0% | 0% |  | 39.09 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23700 | IPDT Leads | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 79.9639 | 27.18% | 54.2% | -0.0008261% | 0 | -1.53% | 169263.9 | 46001.15 | 123262.75 | 1541.48 | 0 | 0 | 0 | 24932.12 | 99.13 | 21069.03 | 29919 | -0.38 | 29918.54 | 0 | 0 | 0 | 0 | 26% | 24.47% | 21.55% | -4.45% |  | 50.83 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23822 | FCASW Requirements Management | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | -4 |  | 0% | 0% | 0 | -7.46% | 0 | 46911.32 | -46911.32 | 11727.83 | 0 | 0 | 49946.3 | 0 | 42 | 46911.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 12.54% | 12.54% | -7.46% |  | 76.09 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23339 | Spirit 2023 - Stewart Russell | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 64.51% | 100% | 100% | 0 | 0.62% | 72766.8 | 46941.72 | 25825.08 | 0 | 0 | 0 | 0 | 46941.74 | 0 | -0.02 | 0 | 46941.74 | 0 | 0 | 0 | 0 | 0 | 7% | 7.62% | 0% | -7% |  | 35.67 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P22760 | SA Leading Edge Transport Media ('A' Frames) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-11-15 | 1 |  |  | 85.99% | 110.7% | 116.3% | -3082.8 | 3.97% | 53480.8 | 45985.5 | 7495.3 | 0 | 42804 | 42804 | 0 | 50911.8 | 0 | -0.3 | -3083 | 53480.9667 | 0 | 0 | 0 | -3082.8 | -3082.8 | 6% | 9.97% | 0% | -6% |  | 42 | [5 empty] | 4926
1730 | 2024-03-21 00:35 | P23729 | Honda Tooling | Paul Watson | STX | SHORT BROTHERS PLC | MPE | Level NC | FIX |  |  |  | 4.5288 | 67.39% | 63.69% | 0% | 0 | 4.44% | 75600 | 50946 | 24654 | 5443.81 | 0 | 0 | 0 | 32445 | 70 | 18501 | 38934 | 0 | 38934 | 0 | 0 | 0 | 0 | 10% | 14.44% | 14.44% | 4.44% |  | 42 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23744 | Model Factory | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 41.8021 | 19.54% | 87.27% | 0.0003253% | 0 | 8.83% | 262300 | 51241 | 211059 | 5049 | 0 | 0 | 0 | 44716 | 78.97 | 8525 | 53659 | 0.16667 | 0 | 26229.6 | 27429.6 | 0 | 0 | 28% | 36.83% | 36.83% | 8.83% |  | 50.53 | [5 empty] | 2000
1730 | 2024-03-21 00:35 | P23753 | Tempest Composites Maturation | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | -7.5849 |  | 0% | 0% | 0 | -19.99% | 0 | 53847.94 | -53847.94 | 7099.32 | 0 | 0 | 54398.4 | 0 | 77 | 53847.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37% | 17.01% | 17.01% | -19.99% |  | 64.76 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23552 | FCAS AP Product Technology Development | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -25% | 597871 | 0 | 597871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0% | -25% |  | 0 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23349 | Spirit 2023 - Stress Approve Man Serv (SB) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 58.24% | 80.05% | 80.05% | 0 | -0.29% | 97920 | 57024 | 40896 | 0 | 0 | 0 | 0 | 45648 | 13651.2 | 11376 | 0 | 45648 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23322 | GKN T Tomblin 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  | 0.15361 | 99.66% | 95.06% | 83.42% | 0 | -0.33% | 58952 | 58752 | 200 | 1302 | 0 | 0 | 0 | 55848 | 91 | 2904 | 8208 | 49008 | 0 | 8208 | 0 | 0 | 0 | 17% | 16.67% | 16.67% | -0.33% |  | 48 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23341 | Spirit 2023 - Tom McFarlane | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 38.6321 | 57.35% | 78.54% | 69.03% | 0 | -0.01% | 108666.4 | 62320.62 | 46345.78 | 1199.67 | 0 | 0 | 0 | 48944.66 | 141.74 | 13375.96 | 7110 | 43019.66 | 0 | 0 | 0 | 7110.19 | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23106 | ME Support to NPD - Bobby Haggart | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  |  | 95.79% | 97.03% | 97.03% | 0 | 0.3% | 65675 | 62912.11 | 2762.89 | 0 | 0 | 0 | 0 | 61042.75 | 2243.24 | 1869.36 | 0 | 61042.75 | 0 | 0 | 0 | 0 | 0 | 15% | 15.3% | 0% | -15% |  | 35.65 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23193 | Spirit Shorts Stephen Greer | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -2.3407 | 102.4% | 96.48% | 86.85% | 0 | 8.55% | 61472 | 62930.26 | -1458.26 | 623.01 | 0 | 0 | 10878 | 60712.78 | 93.03 | 2217.48 | 7269 | 54655.28 | 7268.72 | 0 | 0 | 0 | 0 | 23% | 31.55% | 34.03% | 11.03% |  | 35.06 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P22967 | Spirit 2022 - Channapa Laxmeshwar | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2023-01-26 | 2 |  |  | 69.69% | 121.3% | 121.3% | 0 | 9.53% | 75159.1 | 52376.15 | 22782.95 | 0 | 52376.15 | 54898.1 | 0 | 63508.8 | 0.42 | 0.35 | 0 | 63508.8 | 0 | 0 | 0 | 0 | 0 | 8% | 17.53% | 0% | -8% |  | 0 | [5 empty] | 11133
1730 | 2024-03-21 00:35 | P23561 | SAAB | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2024-01-01 | 1 |  | 10.7403 | 82.46% | 121.1% | 121.1% | 0 | 8.77% | 67485 | 55649.23 | 11835.77 | 1102 | 0 | 0 | 0 | 67399.4 | 0 | -0.17 | 0 | 67399.4 | 0 | 0 | 0 | 0 | 0 | 16% | 24.77% | 100% | 84% |  | 36.82 | [5 empty] | 11750
1730 | 2024-03-21 00:35 | P23784 | Tempest Tooling Offload 2024 | Christopher McCarthy | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  | -9.7064 |  | 0% | 0% | 0 | -11.3% | 0 | 73684.82 | -73684.82 | 7591.35 | 0 | 0 | 74725 | 0 | 76 | 73684.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 18.7% | 18.7% | -11.3% |  | 55 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23080 | Spirit Shorts DManagement Cairan Cullen | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 152.5002 | 50.37% | 98.47% | 91.74% | 3787.8 | -1.15% | 149600 | 75355.3 | 74244.7 | 486.85 | 0 | 0 | 0 | 74199.7 | 184.54 | 1155.6 | 6086 | 69128.0333 | 2298.36 | 0 | 0 | 3787.8 | 3787.8 | 24% | 22.85% | 13.22% | -10.78% |  | 44.41 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23600 | MBDA EXP-EE-023 Bristone Certification | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 59.65% | 100% | 100% | 0 | 0.4% | 126600 | 75517 | 51083 | 0 | 0 | 0 | 0 | 75517 | 0 | 0 | 0 | 75517 | 0 | 0 | 0 | 0 | 0 | 41% | 41.4% | 0% | -41% |  | 78.5 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23605 | Typhoon Work Package 2 Continuation | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM |  |  |  | -396.4704 | 119.8% | 41.22% | -4.54e-05% | 0 | 5.21% | 545536.01 | 653475.07 | -107939.06 | 272.25 | 4054 | 4054 | 81999.09 | 269393.87 | 326.66 | 384081.2 | 323273 | -0.29667 | 89358.36 | 233914.28 | 0 | 0 | 0 | 23% | 28.21% | 29.02% | 6.02% |  | 55.82 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23560 | NJEWCS TAF202302 SM | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level 2 | FIX |  |  |  | 1.3502 | 97.96% | 50.1% | 50.1% | 0 | 12.15% | 81500 | 79836.44 | 1663.56 | 1232.05 | 0 | 0 | 0 | 40000 | 157.63 | 39836.44 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 28% | 40.15% | 40.2% | 12.2% |  | 73.01 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23438 | A220 Spirit Shorts DTC - Stephen Corry | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -11.2219 | 83.57% | 80.4% | 50.39% | 0 | -7.27% | 95928.4 | 80171.1 | 15757.3 | -1404.15 | 0 | 0 | 0 | 64459.8 | 263.45 | 15711.3 | 28872 | 40399.8 | 28872.36 | 0 | 0 | 0 | 0 | 23% | 15.73% | 17.27% | -5.73% |  | 49.8 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23754 | Tempest Composites WP4 | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -7.8682 |  | 0% | 0% | 0 | 7.41% | 0 | 80516.03 | -80516.03 | 10233.12 | 149.25 | 149.25 | 97140 | 0 | 91 | 80516.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 35.41% | 35.41% | 7.41% |  | 63.14 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P22885 | ME Support (Baxi) | James Montgomery | HUV | BAXI HEATING UK LIMITED | ME | Level 3 | FIX | 2023-01-12 | 0 |  |  | 68.78% | 108.7% | 108.7% | 0 | 13.05% | 106632.96 | 73340.24 | 33292.72 | 0 | 0 | 0 | 0 | 79748.12 | 1531.35 | 1276.12 | 0 | 79748.12 | 0 | 0 | 0 | 0 | 0 | 15% | 28.05% | 0% | -15% |  | 44.37 | [5 empty] | 7684
1730 | 2024-03-21 00:35 | P23340 | Spirit 2023 - John Cole | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 48.8571 | 54.69% | 76.55% | 67.59% | 0 | -0.01% | 150129.72 | 82105.92 | 68023.8 | 1392.3 | 0 | 0 | 0 | 62852.4 | 145.64 | 19253.52 | 8831 | 55493.2333 | 0 | 0 | 0 | 8831.16 | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 39.78 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23171 | Spirt Shorts Weights Eng | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 69.18% | 122.7% | 96.15% | 0 | 2.68% | 103113.14 | 71329.32 | 31783.82 | 0 | 71329.32 | 85975.13 | 0 | 87531.56 | 105.02 | -3932.24 | 22740 | 68581.56 | 0 | 16774.18 | 5965.46 | 0 | 0 | 12% | 14.68% | 0% | -12% |  | 0 | [5 empty] | 12270
1730 | 2024-03-21 00:35 | P23345 | Spirit 2023- Jonathan Escosio | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | -5.4865 | 110.8% | 76.6% | 60.91% | 7150.18 | -6.7% | 75970.62 | 84143.4 | -8172.78 | 1489.62 | 0 | 0 | 8938 | 64456.26 | 177.02 | 19687.14 | 15846 | 51251.26 | 0 | 0 | 0 | 15846.34 | 7150.18 | 7% | 0.3% | -1.22% | -8.22% |  | 40.26 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23648 | EXP-032 Delivery of Datalink Eng support - FCAS AP | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 26.6521 | 43.04% | 85.12% | 64.41% | 0 | 5.14% | 371000 | 159665.45 | 211334.55 | 7929.38 | 1032.95 | 1032.95 | 0 | 135912.95 | 57.47 | 23752.5 | 39685 | 102842.1167 | 0 | 39684.54 | 0 | 0 | 0 | 22% | 27.14% | 27.16% | 5.16% |  | 103.48 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23465 | A220 ToW Design Offload (Wing) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 17.5279 | 64.62% | 79.43% | 65.38% | 0 | -4.57% | 132000 | 85300.4 | 46699.6 | 2664.3 | 0 | 0 | 0 | 67752.4 | 90.09 | 17548 | 14381 | 55768.2333 | 14380.8 | 0 | 0 | 0 | 0 | 20% | 15.43% | 14.2% | -5.8% |  | 42.8 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23336 | Spirit 2023 - Neil Rampling | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 32.3432 | 63.79% | 77.09% | 56.03% | 13070.83 | -0.01% | 133901.52 | 85418.1 | 48483.42 | 1499.03 | 0 | 0 | 0 | 65850.88 | 202.15 | 19567.22 | 21586 | 47862.5467 | 0 | 0 | 0 | 21586.03 | 13070.83 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P22965 | Spirit 2022 - Design Man Serv (AH) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 1 |  |  | 106.7% | 96.66% | 92.02% | 4759.75 | 3.14% | 80079.56 | 85441.32 | -5361.76 | 0 | 0 | 0 | 0 | 82588.96 | 8182.59 | 2852.36 | 4760 | 78622.2933 | 0 | 0 | 0 | 4759.75 | 4759.75 | 14% | 17.14% | 0% | -14% |  | 42.44 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23523 | Applique Armour Support | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 1 |  |  | 72.43% | 138.1% | 98.47% | 0 | 3.42% | 118200 | 85606.5 | 32593.5 | 0 | 0 | 0 | 0 | 118200 | 1567.8 | -32593.5 | 40680 | 84300 | 40680 | 0 | 0 | 0 | 0 | 25% | 28.42% | 0% | -25% |  | 64.29 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P22964 | Spirit 2022 - MRB Man Serv (JC) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 100.6% | 97.95% | 97.95% | 0 | 1.91% | 85435.2 | 85960.26 | -525.06 | 0 | 0 | 0 | 0 | 84199.74 | 2112.62 | 1760.52 | 0 | 84199.74 | 0 | 0 | 0 | 0 | 0 | 16% | 17.91% | 0% | -16% |  | 42.69 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23342 | Spirit 2023 - Channapa Laxmeshwar | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -0.73336 | 104.8% | 78.4% | 74.35% | 0 | -3.69% | 79348.35 | 83134.33 | -3785.98 | 5162.52 | 83134.33 | 94827 | 0 | 65177.5 | 106.52 | 20806.83 | 4037 | 61813.3333 | 0 | 0 | 0 | 4036.8 | 0 | 7% | 3.31% | 0% | -7% |  | 0 | [5 empty] | 2850
1730 | 2024-03-21 00:35 | P23586 | Project Management Support | Peter Bowen | BDX | MBDA UK LIMITED | MPE | Level NC | REIM |  |  |  | -2.4902 | 108.3% | 77.47% | 74.44% | 0 | -26.05% | 80000 | 86623.86 | -6623.86 | 2660 | 1140.6 | 1140.6 | 16000 | 67103.86 | 63.69 | 19520 | 3149 | 64479.6933 | 0 | 3148.63 | 0 | 0 | 0 | 49% | 22.95% | 22.4% | -26.6% |  | 80 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P22963 | Spirit 2022 - Design Man Serv (PC) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 1 |  |  | 108.6% | 104% | 94.46% | 9938.48 | 3.18% | 80079.56 | 86926.74 | -6847.18 | 0 | 0 | 0 | 0 | 90389.95 | 5782.63 | -3463.21 | 9938 | 82108.2833 | 0 | 0 | 0 | 9938.48 | 9938.48 | 13% | 16.18% | 0% | -13% |  | 42.39 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23079 | Spirit Shorts Nomenclature | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 2.0271 | 98.53% | 84.02% | 78.42% | 0 | 1.96% | 88455 | 87153.6 | 1301.4 | 642 | 0 | 0 | 0 | 73222.2 | 229.85 | 13931.4 | 5855 | 68343.0333 | 5855.04 | 0 | 0 | 0 | 0 | 20% | 21.96% | 25.23% | 5.23% |  | 30.75 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23551 | Ian Berry 2023 H2 | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  | -4.1615 | 115.9% | 76.5% | 76.5% | 0 | 13.73% | 75810 | 87870.02 | -12060.02 | 2897.98 | 0 | 0 | 24259.2 | 67217.49 | 60.16 | 20652.53 | 0 | 67217.49 | 0 | 0 | 0 | 0 | 0 | 22% | 35.73% | 39.01% | 17.01% |  | 77.37 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23375 | GKN Jaap Peters NL 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2024-03-01 | 3 |  |  | 93.37% | 105.3% | 76.88% | 0 | -15.93% | 97123.22 | 90686.41 | 6436.81 | 0 | 90686.41 | 90686.41 | 0 | 95456.72 | 154.92 | -920.31 | 30879 | 69724.22 | 0 | 8793.29 | 0 | 22086.17 | 0 | 20% | 4.07% | 0% | -20% |  | 0 | [5 empty] | 3850
1730 | 2024-03-21 00:35 | P23583 | Castalla - Test Rig Design | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -17.606 | 142.5% | 63.69% | 63.69% | 0 | -6.45% | 67520 | 96182.5 | -28662.5 | 1628 | 0 | 0 | 36106 | 61257.6 | 134.64 | 34924.9 | 0 | 61257.6 | 0 | 0 | 0 | 0 | 0 | 21% | 14.55% | 17% | -4% |  | 42.74 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23545 | Ultra CSS continuation 2023 H2 | Natalie Sinclair | ULT | ULTRA SONAR SYSTEMS LIMITED | EES | Level NC | REIM |  |  |  | -17.1674 | 133% | 74.66% | 43.5% | 37794.24 | 2.22% | 76000 | 101057.6 | -25057.6 | 1459.6 | 0 | 0 | 24259.2 | 75451.2 | 201.23 | 25606.4 | 37794 | 43956.2 | 0 | 37794.24 | 0 | 0 | 37794.24 | 23% | 25.22% | 25% | 2% |  | 80 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23353 | Spirit 2023 - MRB Man Serv (JC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  | 23.3688 | 56.9% | 65.68% | 65.68% | 0 | 10.29% | 183600 | 104467.5 | 79132.5 | 3386.25 | 0 | 0 | 0 | 68615.25 | 188.31 | 35852.25 | 0 | 68615.25 | 0 | 0 | 0 | 0 | 0 | 7% | 17.29% | 14.44% | 7.44% |  | 45 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23352 | Spirit 2023 - Stress Approve Man Serv (CC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  |  | 109.4% | 65.24% | 65.24% | 0 | 7.29% | 97920 | 107160 | -9240 | 0 | 0 | 0 | 29856 | 69912 | 220.68 | 37248 | 0 | 69912 | 0 | 0 | 0 | 0 | 0 | 7% | 14.29% | 4.69% | -2.31% |  | 48 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23588 | BAE Typhoon MRB MC Shop Concessions | Andrew Houghton | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 26.3925 | 62.13% | 84.86% | 47.38% | 0 | -3.86% | 175060.5 | 108766.59 | 66293.91 | 2511.85 | 0 | 0 | 0 | 92295.97 | 168.76 | 16470.62 | 48910 | 51537.6367 | 0 | 48910.43 | 0 | 0 | 0 | 31% | 27.14% | 29.23% | -1.77% |  | 55.53 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P22918 | Spirit Shorts Graduates | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 11.4456 | 86.47% | 94.95% | 62.58% | 0 | 9.74% | 130000 | 112415.24 | 17584.76 | 1536.38 | 0 | 0 | 9900 | 106734.95 | 221.52 | 5680.29 | 43660 | 70351.6167 | 0 | 43659.95 | 0 | 0 | 0 | 7% | 16.74% | 19.09% | 12.09% |  | 23.28 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23741 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  | 42.0481 | 17.39% | 79.65% | 0% | 0 | 1.79% | 640812 | 111449.6 | 529362.4 | 12589.45 | 0 | 0 | 0 | 88770 | 77.36 | 24679.6 | 106524 | 0 | 0 | 52662 | 53862 | 0 | 0 | 28% | 29.79% | 29.79% | 1.79% |  | 38.72 | [5 empty] | 2000
1730 | 2024-03-21 00:35 | P23664 | Tempest Composites WP3 | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 2.4942 | 93.53% | 14.42% | 14.42% | 0 | -5.06% | 122455.49 | 114537.18 | 7918.31 | 3174.74 | 0 | 0 | 0 | 16518.7 | 198.52 | 98018.48 | 0 | 16518.7 | 0 | 0 | 0 | 0 | 0 | 37% | 31.94% | 33.92% | -3.08% |  | 60.72 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23458 | Spirit Belfast Tooling Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-08-11 | 0 |  |  | 101.3% | 94.65% | 94.65% | 0 | 8.64% | 30384 | 30784.9 | -400.9 | 0 | 0 | 0 | 0 | 29139.1 | 1974.96 | 1645.8 | 0 | 29139.1 | 0 | 0 | 0 | 0 | 0 | 7% | 15.64% | 0% | -7% |  | 42.2 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P22736 | WoT Fixed Leading Edge - Industrial | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 106.7% | 93.42% | 91.32% | 3019.54 | 0.01% | 112196.27 | 119668.47 | -7472.2 | 0 | 0 | 0 | 0 | 111796.68 | 12465.69 | 7871.79 | 3020 | 109280.0133 | 0 | 0 | 0 | 3019.54 | 3019.54 | 7% | 7.01% | 0% | -7% |  | 32.26 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P22883 | Spirit Shorts Evtol PMO C. Hatton | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 40.5601 | 64.46% | 90.96% | 90.96% | 0 | -11.73% | 185800 | 119768.15 | 66031.85 | 1628 | 0 | 0 | 0 | 108946.73 | 86.25 | 10821.42 | 0 | 108946.73 | 0 | 0 | 0 | 0 | 0 | 26% | 14.27% | 24.2% | -1.8% |  | 36.73 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23270 | Shorts Project X | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 12.9449 | 84.66% | 84.02% | 72.98% | 0 | 0.65% | 142248 | 120432.62 | 21815.38 | 1685.25 | 0 | 0 | 0 | 101191.5 | 148.08 | 19241.12 | 15963 | 87889 | 15962.69 | 0 | 0 | 0 | 0 | 13% | 13.65% | 10.99% | -2.01% |  | 45.35 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P22861 | WoT FLE Lifting & Handling Tools | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2023-06-14 | 1 |  |  | 65.17% | 101.6% | 101.6% | 0 | 12.01% | 173987.21 | 113381.75 | 60605.46 | 0 | 50078 | 58423.58 | 0 | 115203.5 | 12813.9 | 10678.25 | 0 | 115203.5 | 0 | 0 | 0 | 0 | 0 | 1% | 13.01% | 0% | -1% |  | 45 | [5 empty] | 12500
1730 | 2024-03-21 00:35 | P23739 | Lifing Services DACs | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  | 44.3555 | 19.81% | 84.89% | -0.0002563% | 0 | 3.01% | 656508 | 130066.5 | 526441.5 | 11868.68 | 0 | 0 | 0 | 110418 | 76 | 19648.5 | 132502 | -0.33333 | 0 | 65650.8 | 66850.8 | 0 | 0 | 28% | 31.01% | 31.01% | 3.01% |  | 37.83 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23810 | Strategic Enablement | Owain Jones | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -6.3391 |  | 0% | 0% | 0 | -20.58% | 0 | 133060.2 | -133060.2 | 20990.55 | 0 | 0 | 134000 | 0 | 77 | 133060.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | -2.58% | -2.58% | -20.58% |  | 42 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23533 | External Stowage Design and Detail Support | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 1 |  |  | 102.4% | 97.65% | 73.24% | 0 | 3.33% | 140000 | 143368.75 | -3368.75 | 0 | 0 | 0 | 12936 | 140000 | 41999.7 | -0.25 | 42000 | 105000 | 42000 | 0 | 0 | 0 | 0 | 27% | 30.33% | 0% | -27% |  | 60.04 | [5 empty] | -3369
1730 | 2024-03-21 00:35 | P23650 | MBDA Recruitment Management costs | Brian Maddrell | BDW | MBDA UK LIMITED | EES | Level NC | REIM | 2024-02-01 | 1 |  | 9.6389 |  | 0% | 0% | 0 | -20.15% | 0 | 240971.5 | -240971.5 | -25000 | 0 | 0 | 266000 | 0 | 100.9 | 140971.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | -17.15% | -440.7% | -443.6% |  | 82.3 | [5 empty] | -100000
1730 | 2024-03-21 00:35 | P22954 | Technical Support Step 1 | Owain Jones | HUV | HUARUI SPIRIT AEROSPACE MANUFACT | ME | Level 2 | REIM |  |  |  |  | 94.81% | 58.01% | 58.01% | 0 | 0.31% | 155501.18 | 147431.58 | 8069.6 | 0 | 23043 | 23043 | 0 | 85525.49 | 61906.09 | 61906.09 | 0 | 85525.49 | 0 | 0 | 0 | 0 | 0 | 30% | 30.31% | 0% | -30% |  | 60.79 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23344 | Spirit A320 Spoilers Support 2023 | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 38.75% | 100% | 100% | 0 | 5.82% | 35786.4 | 13867.23 | 21919.17 | 0 | 0 | 0 | 0 | 13867.23 | 0 | 0 | 0 | 13867.23 | 0 | 0 | 0 | 0 | 0 | 7% | 12.82% | 0% | -7% |  | 34.41 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23019 | EXP034-B Actuator Development | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 5.2929 | 103.1% | 89.91% | 89.91% | 0 | -16.68% | 215541.2 | 222215.54 | -6674.34 | -1261 | 12297.9 | 12297.9 | 0 | 199796.76 | 91.24 | 397.78 | 0 | 199796.76 | 0 | 0 | 0 | 0 | 0 | 34% | 17.32% | 79.64% | 45.64% |  | 58.45 | [5 empty] | -22021
1730 | 2024-03-21 00:35 | P23667 | Safety Systems Engineer | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 61.113 | 37.51% | 91.82% | 80.91% | 0 | -9.39% | 398000 | 149270 | 248730 | 4070 | 0 | 0 | 0 | 137060 | 59.07 | 12210 | 19536 | 120780 | 0 | 19536 | 0 | 0 | 0 | 47% | 37.61% | 29.32% | -17.68% |  | 110 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23550 | Tempest Composites | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -8.1906 | 100.3% | 99.66% | 84.24% | 0 | 5.13% | 149494.92 | 150002.74 | -507.82 | 62 | 0 | 0 | 2396.12 | 149494.92 | 104.22 | 507.82 | 27760 | 126361.5867 | 0 | 27760.26 | 0 | 0 | 0 | 26% | 31.13% | 34.47% | 8.47% |  | 61.58 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23520 | FCAS AP Portfolio Systems | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 30.0628 | 55.8% | 91.43% | 80.51% | 0 | -7.14% | 810821 | 452467.3 | 358353.7 | 11920.16 | 423 | 423 | 0 | 413678.31 | 57.52 | 34505.99 | 59261 | 364294.1433 | 0 | 59261.4 | 0 | 0 | 0 | 22% | 14.86% | 14.89% | -7.11% |  | 80.16 | [5 empty] | -4283
1730 | 2024-03-21 00:35 | P23518 | Systems Engineering support to FCAS | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 19.2777 | 78.23% | 93.32% | 85.65% | 0 | -2.85% | 193736.8 | 151553.5 | 42183.3 | 2188.19 | 3927.4 | 3927.4 | 0 | 141422.18 | 62.56 | 10131.32 | 13942 | 129803.8467 | 0 | 13941.6 | 0 | 0 | 0 | 30% | 27.15% | 3.5% | -26.5% |  | 67.54 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P22440 | Spirit Managed Service - F&DT and Static Approval | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 3 |  |  | 88.56% | 92.56% | 92.56% | 0 | 11.51% | 173500 | 153656.25 | 19843.75 | 0 | 52115 | 55720 | 0 | 142225.12 | 13717.36 | 11431.13 | 0 | 142225.12 | 0 | 0 | 0 | 0 | 0 | 0% | 11.51% | 0% | 0% |  | 44.73 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23641 | Drawing Triage | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM | 2024-01-25 | 0 |  |  |  | 0% | 0% | 0 | -1043168% | 0 | 10755.5 | -10755.5 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | -1043168% | 100% | 100% |  | 49 | [5 empty] | -10755
1730 | 2024-03-21 00:35 | P23637 | MBSE Proposal | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 | 0 | 0 | 0 | 49980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23816 | Typhoon FTI Works - 2024 Fixed Price Element | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 6.0488 | 39.81% | 0% | 0% | 0 | -3.95% | 404176.65 | 160886.12 | 243290.53 | 40221.53 | 0 | 0 | 0 | 0 | 42 | 160886.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 26.05% | 26.05% | -3.95% |  | 53.91 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23464 | A220 Project X Design Offload | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 54.0007 | 49.84% | 94.46% | 66.46% | 27862.8 | -9.14% | 332340 | 165642.5 | 166697.5 | 3086.95 | 0 | 0 | 0 | 156461.9 | 145.2 | 9180.6 | 55649 | 110087.7333 | 27785.76 | 0 | 0 | 27862.8 | 27862.8 | 26% | 16.86% | 15.23% | -10.77% |  | 42.88 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23743 | EHM Cloud Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 35.7635 | 14.62% | 115% | 0.0002244% | 0 | 7.46% | 1016000 | 148511.75 | 867488.25 | 24256.25 | 0 | 0 | 0 | 170752 | 85.21 | -4240.25 | 204902 | 0.33333 | 0 | 102412.8 | 102489.6 | 0 | 0 | 28% | 35.46% | 35.46% | 7.46% |  | 53.06 | [5 empty] | 18000
1730 | 2024-03-21 00:35 | P22505 | Spirit MRB Engineering Support 2021 | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 1 |  |  | 91.17% | 100% | 95.78% | 4020.48 | 21.2% | 87110.4 | 79414.95 | 7695.45 | 0 | 0 | 0 | 0 | 79414.95 | 4020.48 | 0 | 4020 | 76064.95 | 0 | 0 | 0 | 4020.48 | 4020.48 | 0% | 21.2% | 0% | 0% |  | 41.88 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23472 | Tempest Wing Design | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 33.7781 | 45.03% | 118.2% | 105.7% | 0 | -9.97% | 483869.78 | 217867.11 | 266002.67 | 7875 | 201987.5 | 356900 | 0 | 257531.55 | 26.3 | -14664.45 | 32753 | 230237.3833 | 0 | 32753.16 | 0 | 0 | 0 | 23% | 13.03% | 44.54% | 21.54% |  | 46.74 | [5 empty] | 25000
1730 | 2024-03-21 00:35 | P23711 | DO NOT USE - RAISED IN ERROR | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23524 | Bombardier Regional Jets (BRJ) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 130.8% | 56.89% | 44.32% | 28851.48 | -4.69% | 146287.84 | 191311.68 | -45023.84 | 0 | 0 | 0 | 46750 | 108838.22 | 285.14 | 82473.46 | 28851 | 84795.72 | 0 | 0 | 0 | 28851.48 | 28851.48 | 18% | 13.31% | 15.43% | -2.57% |  | 43.92 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23382 | Performance Modelling | Dushan Fernando | BDX | MBDA UK LIMITED | MPE | Level NC | REIM | 2023-07-09 | 0 |  |  | 40.95% | 79.09% | 79.09% | 0 | -16.36% | 170009.66 | 69625.98 | 100383.68 | 0 | 14559.9 | 14559.9 | 0 | 55066.08 | 0 | -0.1 | 0 | 55066.08 | 0 | 0 | 0 | 0 | 0 | 20% | 3.64% | 0% | -20% |  | 77.05 | [5 empty] | -14560
1730 | 2024-03-21 00:35 | P23373 | Raytheon Michael Bellini | Natalie Sinclair | RAS | RAYTHEON UNITED KINGDOM LIMITED | EES | Level NC | REIM |  |  |  | 4.405 | 91.53% | 97.72% | 87.22% | 0 | -7.9% | 214367.4 | 196208.15 | 18159.25 | 4122.45 | 0 | 0 | 0 | 191739.73 | 51.26 | 4468.42 | 24735 | 171127.23 | 24734.7 | 0 | 0 | 0 | 0 | 45% | 37.1% | 38.79% | -6.21% |  | 91.61 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23008 | Spirit Shorts Project Rachel | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 85.87% | 91.32% | 91.32% | 0 | -7.7% | 228880 | 196531.2 | 32348.8 | 0 | 0 | 0 | 0 | 179472.8 | 454.93 | 17058.4 | 0 | 179472.8 | 0 | 0 | 0 | 0 | 0 | 13% | 5.3% | 0.31% | -12.69% |  | 46.04 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23242 | Physical Architecture & System Engineering Support | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 37.9686 | 64.51% | 95.11% | 89.21% | 0 | 8.54% | 305459 | 197049.21 | 108409.79 | 2855.25 | 775.55 | 775.55 | 0 | 187412.05 | 64.21 | 9283.16 | 13942 | 175793.7167 | 0 | 13941.6 | 0 | 0 | 0 | 15% | 23.54% | 6.73% | -8.27% |  | 78.19 | [5 empty] | -354
1730 | 2024-03-21 00:35 | P23505 | EXP-022 Meteor TBUS T&E support | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 13.6969 | 77.65% | 93.71% | 85.33% | 0 | -0.98% | 246744.4 | 191607.39 | 55137.01 | 4025.51 | 0 | 0 | 0 | 179547.72 | 55.9 | 12059.67 | 19269 | 163490.22 | 0 | 19268.53 | 0 | 0 | 0 | 20% | 19.02% | 15.67% | -4.33% |  | 89.83 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23629 | F35 FTI | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level NC | REIM |  |  |  | -21.7164 |  | 79.38% | 79.38% | 0 | -0.79% | 0 | 207762.17 | -207762.17 | 9567.06 | 0 | 0 | 0 | 164920.77 | 36.82 | 42841.4 | 0 | 164920.77 | 0 | 0 | 0 | 0 | 0 | 31% | 30.21% | 28.93% | -2.07% |  | 61.84 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P22798 | CO2MAP MGSE | Harry James Kellett | DTW | THALES ALENIA SPACE UK (60DAYS) | EES | Level 2 | REIM | 2023-11-08 | 0 |  |  | 85.75% | 105% | 105% | 0 | -3.47% | 252086 | 216157.82 | 35928.18 | 0 | 0 | 0 | 0 | 227052.6 | 0.26 | 0.22 | 0 | 227052.6 | 0 | 0 | 0 | 0 | 0 | 29% | 25.53% | 100% | 71% |  | 50.31 | [5 empty] | 10895
1730 | 2024-03-21 00:35 | P23316 | Model Factory IL and AW | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX | 2024-01-12 | 0 |  |  | 88.13% | 104.1% | 104.1% | 0 | 2.41% | 250000 | 220327.78 | 29672.22 | 0 | 0 | 0 | 0 | 229409 | 0 | -0.22 | 0 | 229409 | 0 | 0 | 0 | 0 | 0 | 30% | 32.41% | 42.82% | 12.82% |  | 45.31 | [5 empty] | 9081
1730 | 2024-03-21 00:35 | P23335 | GKN S McConnell 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2023-12-31 | 2 |  |  | 96.61% | 100% | 83.53% | 0 | 0.74% | 87420 | 84459 | 2961 | 0 | 0 | 0 | 0 | 84459 | 728 | 0 | 16694 | 70547.3333 | 0 | 0 | 0 | 16694.4 | 0 | 15% | 15.74% | 0% | -15% |  | 47 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23317 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX | 2024-01-12 | 0 |  |  | 95.89% | 104.3% | 104.3% | 0 | 4.3% | 251800 | 241446.75 | 10353.25 | 0 | 0 | 0 | 0 | 251800 | 0 | -0.25 | 0 | 251800 | 0 | 0 | 0 | 0 | 0 | 25% | 29.3% | 49.01% | 24.01% |  | 36.29 | [5 empty] | 10353
1730 | 2024-03-21 00:35 | P23603 | Typhoon IMDLR | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 7.1489 | 84.66% | 46.39% | 0.0001316% | 0 | 2.36% | 305067.09 | 258262.21 | 46804.88 | 6547.14 | 0 | 0 | 4271.91 | 119807.84 | 315.36 | 138454.37 | 143769 | 0.34 | 143769.41 | 0 | 0 | 0 | 0 | 29% | 31.36% | 32.89% | 3.89% |  | 57.24 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23007 | EXP-006A - Brimstone 3 | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 53.1884 | 65.72% | 97.25% | 91.49% | 0 | -2.95% | 406450 | 267099.53 | 139350.47 | 2619.94 | 0 | 0 | 0 | 259759.75 | 69.51 | 7309.78 | 18463 | 244373.9167 | 0 | 18463.2 | 0 | 0 | 0 | 25% | 22.05% | 29.94% | 4.94% |  | 69.66 | [5 empty] | -30
1730 | 2024-03-21 00:35 | P23386 | Software Development - BMS | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 98.78% | 100% | 95.49% | 0 | 4.31% | 149650 | 147823.35 | 1826.65 | 0 | 0 | 0 | 0 | 147823.35 | 33.48 | 0 | 8007 | 141150.85 | 0 | 8007 | 0 | 0 | 0 | 18% | 22.31% | 22.61% | 4.61% |  | 78.5 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23308 | NATO JEWCS | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  | 32.1093 | 81.85% | 93.69% | 80.77% | 45213.08 | -3.62% | 356307 | 291648.48 | 64658.52 | 2013.7 | 613.89 | 613.89 | 0 | 273254.06 | 173.08 | 18394.42 | 45213 | 235576.56 | 0 | 0 | 45213.08 | 0 | 45213.08 | 24% | 20.38% | 11.83% | -12.17% |  | 75.81 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23699 | A220 Stress Checkers | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -7.6863 |  | 0% | 0% | 0 | -2.2% | 0 | 298811.94 | -298811.94 | 38875.7 | 12000 | 12000 | 321520 | 0 | 102.41 | 298811.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22% | 19.8% | 19.8% | -2.2% |  | 61.88 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23617 | Tempest Composites WP2 | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -13.0806 | 129.9% | 25.96% | 10.72% | 29536.68 | 11.75% | 244405.26 | 317545.17 | -73139.91 | 5591.48 | 0 | 0 | 77669.2 | 82447.45 | 278.41 | 235097.72 | 58103 | 34028.2833 | 0 | 28565.94 | 0 | 29536.68 | 29536.68 | 22% | 33.75% | 33.61% | 11.61% |  | 62.14 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P22515 | Shorts A220 100/300 ALI Phase III | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 44.499 | 80.28% | 97.25% | 92.48% | 0 | 1.23% | 400628.76 | 321639.95 | 78988.81 | 1775.07 | 3450.98 | 3450.98 | 0 | 312787.53 | 100.45 | 8852.42 | 18387 | 297465.03 | 18386.68 | 0 | 0 | 0 | 0 | 10% | 11.23% | 14.29% | 4.29% |  | 40.43 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P22953 | Spirit Shorts eVTOL | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-05-08 | 3 |  | 4.0846 | 103.1% | 80.83% | 79.36% | 0 | -9.51% | 324272 | 334483.6 | -10211.6 | -2500 | 66696.6 | 67387.9 | 0 | 270366 | 70861.92 | 54117.6 | 5921 | 265431.8333 | 5920.8 | 0 | 0 | 0 | 0 | 17% | 7.49% | 100% | 83% |  | 46.19 | [5 empty] | -10000
1730 | 2024-03-21 00:35 | P23685 | DAC LUC Support and Recompliance | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 18.8181 | 25.47% | 163.5% | -0.0001109% | 0 | 5.96% | 1180000 | 300592.84 | 879407.16 | 46731.96 | 0 | 0 | 0 | 491428 | 84.28 | -158071.16 | 589714 | -0.33333 | 0 | 288001.2 | 301712.4 | 0 | 0 | 28% | 33.96% | 33.96% | 5.96% |  | 59.23 | [5 empty] | 32764
1730 | 2024-03-21 00:35 | P22842 | ME Support (Aim Altitude) | James Montgomery | AVI | AIM ALTITUDE UK LIMITED | ME | Level 3 | FIX | 2023-06-14 | 4 |  |  | 99.31% | 100.5% | 86.63% | 57290.84 | 0.49% | 346293.67 | 343918.08 | 2375.59 | 0 | 2909.86 | 2909.86 | 0 | 345673.01 | 55184.93 | -1754.93 | 57291 | 297930.51 | 0 | 0 | 0 | 57290.84 | 57290.84 | 13% | 13.49% | 0% | -13% |  | 46.3 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P22391 | GE System Engineering support | Vinayakumar Sugur | GEE | EXPERIS LIMITED | EES | Level NC | REIM |  |  |  |  | 82.01% | 99.51% | 99.51% | 0 | 0.13% | 434434.25 | 356260.63 | 78173.62 | 0 | 0 | 0 | 0 | 354519.5 | 86.26 | 1741.13 | 0 | 354519.5 | 0 | 0 | 0 | 0 | 0 | 6% | 6.13% | 6.09% | 0.09% |  | 57.33 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23045 | Shotgun Adaptors - 10 Sets | Harry James Kellett | BDW | MBDA UK LIMITED | EES | Level 2 | FIX | 2024-02-27 | 7 |  | 4.3283 | 74.76% | 133.8% | 95.11% | 0 | 2.29% | 399276.11 | 298512.88 | 100763.23 | 23280.1 | 214550.47 | 214550.47 | 0 | 399276.11 | 47356.35 | -7763.23 | 138421 | 283925.2767 | 0 | 138420.73 | 0 | 0 | 0 | 29% | 31.29% | 99.78% | 70.78% |  | 55.76 | [5 empty] | 93000
1730 | 2024-03-21 00:35 | P23432 | Spirit Belfast MRB On-Site Support (Mon & Clear) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 65.77% | 128.6% | 103.8% | 0 | -11.53% | 449545 | 295665.27 | 153879.73 | 0 | 295665.27 | 451827.33 | 0 | 380234.75 | 120831.02 | 27430.52 | 87914 | 306973.0833 | 87914.4 | 0 | 0 | 0 | 0 | 39% | 27.47% | 0% | -39% |  | 0 | [5 empty] | 112000
1730 | 2024-03-21 00:35 | P23023 | Spirit Shorts R Foster/M Gourley | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 6.9031 | 82.07% | 101.3% | 86.87% | 0 | -20.7% | 480221.04 | 394093.55 | 86127.49 | 12476.72 | 229061.5 | 267726 | 0 | 399408 | 89.47 | 9196.55 | 68455 | 342362.1667 | 19120.72 | 21204.59 | 28129.27 | 0 | 0 | 27% | 6.3% | 3.24% | -23.76% |  | 29.59 | [5 empty] | 14511
1730 | 2024-03-21 00:35 | P22982 | Spirit 2022 - Hugh Sloan | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 101.5265 | 60.7% | 89.07% | 84.51% | 0 | -0.4% | 247473 | 150214.66 | 97258.34 | 957.96 | 0 | 0 | 0 | 133795.08 | 184.47 | 16419.58 | 8217 | 126947.58 | 0 | 0 | 0 | 8217.17 | 0 | 7% | 6.6% | 1.35% | -5.65% |  | 35.42 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23694 | Systems Portfolio EXP-011a | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 9.3461 | 67.36% | 83.05% | 65.54% | 0 | 2.5% | 648492.8 | 436840.25 | 211652.55 | 22645.97 | 157.75 | 157.75 | 0 | 362778.8 | 52.26 | 74061.45 | 91787 | 286289.6333 | 0 | 91786.96 | 0 | 0 | 0 | 21% | 23.5% | 19.23% | -1.77% |  | 89.29 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23531 | BAe Systems F35 MRB Support | Andrew Houghton | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | -31.4188 |  | 71.39% | 71.39% | 0 | 3.08% | 0 | 438843.77 | -438843.77 | 13967.54 | 287.44 | 287.44 | 0 | 313283.73 | 83.68 | 125560.04 | 0 | 313283.73 | 0 | 0 | 0 | 0 | 0 | 25% | 28.08% | 32.03% | 7.03% |  | 59.64 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23585 | Systems Design - Missile Systems, Meteor,Brimstone | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 | 0 | 0 | 0 | 49500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P22906 | Spirit Shorts - MRB JD Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 9.0427 | 92.03% | 87.22% | 68.53% | 99451.32 | -7.72% | 481714 | 443326.68 | 38387.32 | 4245.13 | 0 | 0 | 0 | 386687.62 | 289.34 | 64639.06 | 99451 | 303811.7867 | 0 | 0 | 85953.72 | 13497.6 | 99451.32 | 13% | 5.28% | 3.08% | -9.92% |  | 36.89 | [5 empty] | 8000
1730 | 2024-03-21 00:35 | P23554 | Dornier Seawings 328 2023 H2 Support | Steven Lawton | DAX | EXPLEO GERMANY GMBH (EC) | MPE | Level 2 | REIM |  |  |  | 1.418 | 96.38% | 87.6% | 83.6% | 0 | 8.1% | 474542.24 | 457347.04 | 17195.2 | 12126.08 | 4046.44 | 4046.44 | 0 | 400640 | 62.05 | 56707.04 | 21955 | 382344.1667 | 21955.08 | 0 | 0 | 0 | 0 | 21% | 29.1% | 31.61% | 10.61% |  | 67.79 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23372 | BAE Carbon Tooling Off-load | Gary Kempster | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  |  | 165.3% | 56.3% | 56.3% | 0 | -4.13% | 276718 | 457433.31 | -180715.31 | 0 | 0 | 0 | 197460.8 | 257521.57 | 1097.29 | 199911.74 | 0 | 257521.57 | 0 | 0 | 0 | 0 | 0 | 27% | 22.87% | 20.94% | -6.06% |  | 53.57 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23140 | Spirit Shorts A220 MLG Stress Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  | 36.5544 | 70.61% | 82.58% | 73.61% | 48343.2 | -8.5% | 636032.4 | 449088.32 | 186944.08 | 5114.14 | 20870.3 | 87811.88 | 0 | 370857.4 | 216.71 | 103230.92 | 48343 | 330571.5667 | 0 | 0 | 0 | 48343.2 | 48343.2 | 25% | 16.5% | 12.82% | -12.18% |  | 47.37 | [5 empty] | 25000
1730 | 2024-03-21 00:35 | P23421 | A220 DTC | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 11.9407 | 70.82% | 78.22% | 69.66% | 0 | -29.33% | 217089.12 | 153748.62 | 63340.5 | 5304.6 | 0 | 0 | 0 | 120261.6 | 87.22 | 33487.02 | 15801 | 107094.1 | 15800.9 | 0 | 0 | 0 | 0 | 29% | -0.33% | 4.49% | -24.51% |  | 45.77 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P22652 | L3 - Saftey Engineering | Sean Simmons | LHW | L3HARRIS MAPPS LIMITED | EES | Level NC | FIX |  |  |  |  | 95.63% | 86.69% | 86.69% | 0 | 5.66% | 523390 | 500497.5 | 22892.5 | 0 | 0 | 0 | 0 | 433882.5 | 79938 | 66615 | 0 | 433882.5 | 0 | 0 | 0 | 0 | 0 | 21% | 26.66% | 25.88% | 4.88% |  | 83.05 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23366 | Business Analyst Support | Peter Williams | BDZ | MBDA UK LIMITED | DET | Level NC | REIM |  |  |  | 25.0498 | 37.87% | 255.4% | 194.4% | 0 | 12.91% | 583200 | 220853.83 | 362346.17 | 14465.05 | 220853.47 | 416921.86 | 0 | 564160 | 81.57 | -60171.17 | 161856 | 429280 | 81792 | 80064 | 0 | 0 | 0 | 43% | 55.91% | 39.76% | -3.24% |  | 0.01 | [5 empty] | 283135
1730 | 2024-03-21 00:35 | P23281 | Systems Portfolio | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM | 2024-02-28 | 2 |  | -3239.9024 | 44.43% | 97.31% | 97.19% | 0 | -17.25% | 1177697.24 | 523236.96 | 654460.28 | -202 | 2133.28 | 2133.28 | 0 | 509179.87 | 16553.63 | 13160.09 | 762 | 508544.87 | 0 | 761.53 | 0 | 0 | 0 | 25% | 7.75% | 100% | 75% |  | 70.48 | [5 empty] | -897
1730 | 2024-03-21 00:35 | P23001 | Spirit Shorts A220 Design | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -20.0426 | 113.7% | 74.16% | 69.53% | 0 | -4.17% | 463100 | 526578.8 | -63478.8 | 3167.2 | 0 | 0 | 65953.2 | 390511.7 | 373.8 | 136067.1 | 29237 | 366147.5333 | 29236.68 | 0 | 0 | 0 | 0 | 25% | 20.83% | 11.75% | -13.25% |  | 43.6 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23323 | CNC-CMM Programming Support | Andrew Houghton | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | 5.8216 | 89.59% | 92.59% | 65.6% | 0 | -2.95% | 617809.74 | 553478.07 | 64331.67 | 11050.59 | 15941.56 | 15941.56 | 0 | 512445.08 | 157.17 | 41032.99 | 179242 | 363076.7467 | 102286.46 | 76955.66 | 0 | 0 | 0 | 32% | 29.05% | 37.37% | 5.37% |  | 57.14 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P21138 | D&A Vibration Reduc Damping Struc FOGV Components | Steven Lawton | ATC | AECC SICHUAN GAS TURBINE | MPE | Level 1 | FIX | 2022-09-07 | 0 |  |  | 96.12% | 104% | 104% | 0 | -3.44% | 569346 | 547228.11 | 22117.89 | 0 | 75181.75 | 75181.75 | 0 | 569346 | 0 | 0.11 | 0 | 569346 | 0 | 0 | 0 | 0 | 0 | 36% | 32.56% | 0.08% | -35.92% |  | 73.95 | [5 empty] | 22118
1730 | 2024-03-21 00:35 | P23219 | Tornado Air 800 Engineering Support | Richard Brook | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 3 | REIM |  |  |  | -27.204 | 96.34% | 97.61% | 97.61% | 0 | 0.5% | 615046 | 592509.68 | 22536.32 | -828.42 | 459.21 | 459.21 | 0 | 578373.17 | 91 | 5411.51 | 0 | 578373.17 | 0 | 0 | 0 | 0 | 0 | 31% | 31.5% | 200.4% | 169.4% |  | 81.74 | [5 empty] | -8725
1730 | 2024-03-21 00:35 | P23426 | BAE Tempest WP 3 Harness Maturation | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 13.0929 | 73.49% | 91.09% | 71.97% | 0 | -5.96% | 884012.04 | 649685.14 | 234326.9 | 17897.3 | 213.34 | 213.34 | 0 | 591770.47 | 84.31 | 57914.67 | 149014 | 467592.1367 | 82448.95 | 66565.09 | 0 | 0 | 0 | 33% | 27.04% | 28.14% | -4.86% |  | 51.25 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23320 | Lifing Services DACs | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX | 2024-01-12 | 0 |  |  | 95.56% | 104.6% | 104.6% | 0 | 2.98% | 413300 | 394956.45 | 18343.55 | 0 | 0 | 0 | 0 | 413300 | 0 | -0.55 | 0 | 413300 | 0 | 0 | 0 | 0 | 0 | 26% | 28.98% | 52.05% | 26.05% |  | 33.15 | [5 empty] | 18343
1730 | 2024-03-21 00:35 | P22790 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 2 | REIM | 2024-03-18 | 0 |  |  | 194.5% | 90.44% | 90.44% | 0 | 1.37% | 352240 | 685262.25 | -333022.25 | 0 | 1611.52 | 1611.52 | 515246 | 619743.88 | 41098.04 | 34248.37 | 0 | 619743.88 | 0 | 0 | 0 | 0 | 0 | 13% | 14.37% | 0% | -13% |  | 45.06 | [5 empty] | -31270
1730 | 2024-03-21 00:35 | P23602 | EXP-025 Portfolio Software Engineering Support | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 20.9608 | 50.48% | 85.93% | 67.51% | 0 | -0.66% | 1327080 | 669934.2 | 657145.8 | 31351.14 | 1836.85 | 2492.6 | 0 | 575685.84 | 60.41 | 94248.36 | 148074 | 452290.84 | 0 | 148074.11 | 0 | 0 | 0 | 24% | 23.34% | 23.26% | -0.74% |  | 83.07 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23451 | BAE Tempest - DFM-ASO Planning | Andrew Houghton | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | 8.5254 | 81.35% | 71.3% | 49.93% | 27224.9 | -3.24% | 953905.42 | 776045.58 | 177859.84 | 20862.31 | 0 | 0 | 0 | 553327.81 | 136.84 | 222717.77 | 198976 | 387514.4767 | 171751.17 | 0 | 27224.9 | 0 | 27224.9 | 28% | 24.76% | 26.83% | -1.17% |  | 53.61 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23321 | EHM Cloud Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX | 2024-01-29 | 0 |  |  | 89.76% | 111.4% | 111.4% | 0 | 2.92% | 839969 | 753974.58 | 85994.42 | 0 | 0 | 0 | 0 | 839969 | 0 | -0.42 | 0 | 839969 | 0 | 0 | 0 | 0 | 0 | 28% | 30.92% | 57.47% | 29.47% |  | 49.95 | [5 empty] | 85994
1730 | 2024-03-21 00:35 | P23105 | Raytheon Supply Engineering Support | Natalie Sinclair | RAY | RAYTHEON UNITED KINGDOM LIMITED | MPE | Level 3A | REIM | 2023-07-13 | 2 |  |  | 76.96% | 94.49% | 90.07% | 49156.8 | -2.02% | 1205008 | 927395.25 | 277612.75 | 0 | 0 | 0 | 0 | 876291.5 | 107644.5 | 48739.75 | 49157 | 835327.3333 | 0 | 0 | 49156.8 | 0 | 49156.8 | 26% | 23.98% | 100% | 74% |  | 48.97 | [5 empty] | -2364
1730 | 2024-03-21 00:35 | P22350 | EMP 2020-2021 | Natalie Sinclair | ARY | GUIDANT GROUP (trading name) | PCPR | Level NC | REIM |  |  |  | 5.5268 | 95.5% | 98.34% | 93.57% | 0 | -2.09% | 1017579.76 | 971746.07 | 45833.69 | 8293 | 400 | 400 | 0 | 955626.67 | 73.68 | 16119.4 | 55595 | 909297.5033 | 15720.92 | 31809.66 | 8064.8 | 0 | 0 | 32% | 29.91% | 26.86% | -5.14% |  | 44.09 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23117 | BAE Typhoon Eng Support | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | 2024-03-12 | 9 |  |  | 107.6% | 88.52% | 88.52% | 0 | -1.44% | 950771.99 | 1022826.17 | -72054.18 | 0 | 19090.01 | 21165.02 | 69773.84 | 905367.99 | 108434.61 | 90362.18 | 0 | 905367.99 | 0 | 0 | 0 | 0 | 0 | 30% | 28.56% | 0% | -30% |  | 52.3 | [5 empty] | -27096
1730 | 2024-03-21 00:35 | P23292 | BAE Tempest WP 4 AV Trays | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 13.4812 | 79.68% | 94.48% | 79.07% | 0 | 1.98% | 1498284.22 | 1193858.14 | 304426.08 | 22581.6 | 0 | 0 | 0 | 1127946.23 | 83.87 | 65911.91 | 220689 | 944038.73 | 116674.18 | 104014.85 | 0 | 0 | 0 | 32% | 33.98% | 33.3% | 1.3% |  | 53.27 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P22671 | Spirit Shorts Pylon and Fairing Package | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX | 2023-05-03 | 0 |  |  | 105% | 95.26% | 95.26% | 0 | -7.21% | 1198494.77 | 1258071.09 | -59576.32 | 0 | 106494.89 | 106494.89 | 0 | 1198494.77 | 2544.39 | 2120.32 | 0 | 1198494.77 | 0 | 0 | 0 | 0 | 0 | 20% | 12.79% | 0% | -20% |  | 45.4 | [5 empty] | -57456
1730 | 2024-03-21 00:35 | P23519 | Mechanical and Electrical Design Eng Support | Dushan Fernando | BAX | SAFRAN SEATS GB LIMITED | MPE | Level 2 | REIM |  |  |  | 16.6757 | 68.46% | 89.98% | 66.43% | 0 | -1.53% | 1807261.3 | 1237330.55 | 569930.75 | 34177.35 | 727 | 727 | 0 | 1113289.55 | 95.96 | 124041 | 349575 | 821977.05 | 0 | 349574.52 | 0 | 0 | 0 | 33% | 31.47% | 31.59% | -1.41% |  | 56.63 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23152 | Project Aragon - Design and Stress Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 5.6098 | 94.42% | 57.92% | 57.92% | 0 | -9.53% | 1333452.21 | 1259093.05 | 74359.16 | 13255.17 | 0 | 0 | 0 | 729295.96 | 324.61 | 529797.09 | 0 | 729295.96 | 0 | 0 | 0 | 0 | 0 | 39% | 29.47% | 29.3% | -9.7% |  | 51.92 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23282 | Tooling Support (MBDA) | Dushan Fernando | BDV | MBDA UK LIMITED | ME | Level NC | REIM |  |  |  | 41.9604 | 60.87% | 87.16% | 87.16% | 0 | -8.68% | 195672.4 | 119101.36 | 76571.04 | 1824.84 | 0 | 0 | 0 | 103803.97 | 66.81 | 15297.39 | 0 | 103803.97 | 0 | 0 | 0 | 0 | 0 | 30% | 21.32% | 30.37% | 0.37% |  | 49.71 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23315 | DAC LUC BAU and Service Workbench | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX | 2024-02-16 | 1 |  | 70.5463 | 85.17% | 117.4% | 117.4% | 0 | 3.85% | 1573630 | 1340192.3 | 233437.7 | 3309 | 180.3 | 180.3 | 0 | 1573630 | 0 | 0.3 | 0 | 1573630 | 0 | 0 | 0 | 0 | 0 | 28% | 31.85% | 47.32% | 19.32% |  | 52.35 | [5 empty] | 233438
1730 | 2024-03-21 00:35 | P23508 | Verification and Validation | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 23.3179 | 80.77% | 97.06% | 88.92% | 0 | 10.81% | 212950 | 171993.5 | 40956.5 | 1756.44 | 0 | 0 | 0 | 166930.28 | 40.22 | 5063.22 | 16791 | 152937.78 | 0 | 16791.16 | 0 | 0 | 0 | 24% | 34.81% | 33.75% | 9.75% |  | 78.5 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23006 | Spirit Shorts A350 Freighter Toulouse | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -31.2973 | 152.3% | 80.06% | 78.29% | 0 | 19.29% | 1035745.92 | 1577615.3 | -541869.38 | 17313.62 | 1086670.26 | 1708220.2 | 0 | 1262988.03 | 312.45 | 625901.27 | 33464 | 1235101.3633 | 33464.4 | 0 | 0 | 0 | 0 | 5% | 24.29% | 35.91% | 30.91% |  | 47.92 | [5 empty] | 311274
1730 | 2024-03-21 00:35 | P22278 | TAI Supply Engineers to Ankara | Natalie Sinclair | TAI | TUSAS-TURK HAVACILIK VE UZAY | MPE | Level 3A | REIM |  |  |  | 427.5798 | 19.43% | 467.2% | 467.2% | 0 | -15.57% | 2105282 | 408965.91 | 1696316.09 | 3967.25 | 49400.29 | 49400.29 | 0 | 1910696.33 | 24.58 | 3329.58 | 0 | 1910696.33 | 0 | 0 | 0 | 0 | 0 | 95% | 79.43% | 72.9% | -22.1% |  | 34.22 | [5 empty] | 1505060
1730 | 2024-03-21 00:35 | P23175 | BAe Aero Typhoon Package 2 | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM | 2024-03-12 | 2 |  |  | 103.8% | 96.32% | 96.32% | 0 | -1.63% | 1984265.09 | 2060011.83 | -75746.74 | 0 | 57677.87 | 86030.82 | 15444.64 | 1984257.03 | 84731.75 | 70609.8 | 0 | 1984257.03 | 0 | 0 | 0 | 0 | 0 | 29% | 27.37% | 0% | -29% |  | 51.76 | [5 empty] | -5145
1730 | 2024-03-21 00:35 | P23257 | BAE Tempest WP 5 Centre Fuselage | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 0.48979 | 99.56% | 99.23% | 91.32% | 0 | -5.72% | 2106860.71 | 2097631.85 | 9228.86 | 18842.48 | 78100 | 78100 | 0 | 2081529.48 | 73.17 | 16102.37 | 199124 | 1915592.8133 | 110362.14 | 88762 | 0 | 0 | 0 | 33% | 27.28% | 28.59% | -4.41% |  | 61.06 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P19020 | Spirit Concessions - 2018 | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2024-01-23 | 3 |  |  | 90.82% | 111.8% | 107% | 99792.83 | 2.09% | 1914846.83 | 1739018.14 | 175828.69 | 0 | 44317.61 | 44317.61 | 15178.88 | 1944710.76 | 6536.79 | 196987.38 | 99793 | 1861549.9267 | 0 | 0 | 0 | 99792.83 | 99792.83 | 25% | 27.09% | 9.32% | -15.68% |  | 40.87 | [5 empty] | 402680
1730 | 2024-03-21 00:35 | P23207 | A350 Approvers - Design and Stress Support | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  | 6.7045 | 84.85% | 90.66% | 54.24% | 0 | -4.57% | 2728308 | 2315092.09 | 413215.91 | 61632.44 | 28022.36 | 28482.31 | 0 | 2098862.69 | 137.8 | 216229.4 | 1011850 | 1255654.3567 | 100132.13 | 570705.26 | 341012.63 | 0 | 0 | 23% | 18.43% | 18.58% | -4.42% |  | 54.7 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P23179 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX |  |  |  | -270.4814 | 126.9% | 89.8% | 82.07% | 0 | -9.34% | 1996985.84 | 2535122.18 | -538136.34 | 1989.55 | 156991.12 | 248243.92 | 100000 | 2276494.65 | 516.84 | 258627.53 | 235154 | 2080532.9833 | 85390.96 | 140266.99 | 9496.08 | 0 | 0 | 22% | 12.66% | 16.8% | -5.2% |  | 44.4 | [5 empty] | 0
1730 | 2024-03-21 00:35 | P19731 | Hapri HPC Rear Bearing Housing PDR & CDR | Steven Lawton | ATC | AECC Hunan Aviation Powerplant | MPE | Level 1 | FIX |  |  |  | 1.9985 | 99.84% | 100.2% | 87.64% | 447000 | -15.38% | 2980000 | 2975321.17 | 4678.83 | 2341.16 | 363828.33 | 497928.33 | 0 | 2980000 | 1041.81 | -229678.83 | 447000 | 2607500 | 0 | 0 | 0 | 447000 | 447000 | 38% | 22.62% | 14.11% | -23.89% |  | 64.86 | [5 empty] | -225000
1730 | 2024-03-21 00:35 | P23487 | Tornado Air 800 Engineering Support | Richard Brook | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 2 | FIX |  |  |  | 1.3475 | 96.98% | 80.93% | 76.37% | 30074.38 | -3.55% | 2928777.63 | 2840347.12 | 88430.51 | 65624.88 | 0 | 0 | 0 | 2298724.51 | 91.67 | 568622.61 | 155495 | 2169145.3433 | 0 | 125420.63 | 30074.38 | 0 | 30074.38 | 40% | 36.45% | 40.85% | 0.85% |  | 78.71 | [5 empty] | 27000
Extend Table

## AP3-4
WIP No | Date Created | Project ID | Project Description | Project Manager | Department Id | Client | CBU | Complexity | Type | Stop Booking Hrs | Closing Project: Action(s) to close | RAG | Approx. PO Burndown (weeks) | Turnover vs Contract Value | Invoice To Date vs Turnover | Cash in vs Turnover | Open Amount Overdue | Actual PM% to Baseline PM% delta | Contract Value | Total Project Turnover | Contract Value - Total Turnover | Run Rate (based on total turnover) | Total BOI Spend to Date | Total Committed PO (supplier/best shore) | Current AA in PT3 | Invoiced To Date | DSO | Unbilled (WIP) | Total Open Amount | Cash in (Invoiced - (Open amount -VAT)) | Debt <=30 Days | Debt 31 - 60 Days | Debt 61 - 90 Days | Debt >= 90 Days | Open Amount Overdue2 | Baseline Project Margin | Project To Date (PTD) PM | Year to Date (YTD) PM | YTD Delta Actual PM% to BPM% | Forecast PM at Completion (Manual input from PTT) | Average Sale Rate | CSat score for last quarter (Manual input from PTT) | Comments and Actions | Judged income adjustment at completion | Profit to take now | Provision required now | Fully Traded | Last Months Comments and Actions
1731 | 2024-03-28 00:37 | P23292 | BAE Tempest WP 4 AV Trays | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 11.8702 | 81.31% | 92.59% | 77.49% | 0 | 1.91% | 1498284.22 | 1218274.4 | 280009.82 | 23589.36 | 0 | 0 | 0 | 1127946.23 | 91 | 90328.17 | 220689 | 944038.73 | 116674.18 | 104014.85 | 0 | 0 | 0 | 32% | 33.91% | 33.06% | 1.06% |  | 53.32 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23519 | Mechanical and Electrical Design Eng Support | Dushan Fernando | BAX | SAFRAN SEATS GB LIMITED | MPE | Level 2 | REIM |  |  |  | 15.8555 | 70.3% | 87.62% | 64.69% | 0 | -1.53% | 1807261.3 | 1270593.05 | 536668.25 | 33847.35 | 727 | 1227 | 0 | 1113289.55 | 101.52 | 157303.5 | 349575 | 821977.05 | 0 | 349574.52 | 0 | 0 | 0 | 33% | 31.47% | 31.59% | -1.41% |  | 56.63 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23637 | MBSE Proposal | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 | 0 | 0 | 0 | 49980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23711 | DO NOT USE - RAISED IN ERROR | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23508 | Verification and Validation | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 32.356 | 80.77% | 100% | 88.92% | 0 | 10.81% | 212950 | 171993.5 | 40956.5 | 1265.81 | 0 | 0 | 0 | 171993.53 | 45.76 | -0.03 | 22867 | 152937.6967 | 6075.9 | 16791.16 | 0 | 0 | 0 | 24% | 34.81% | 33.75% | 9.75% |  | 78.5 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23520 | FCAS AP Portfolio Systems | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 28.9674 | 57.41% | 100% | 78.25% | 0 | -7.04% | 810821 | 465525.55 | 345295.45 | 11920.16 | 423 | 423 | 0 | 465538.44 | 64.62 | -4295.89 | 121494 | 364293.44 | 62232.16 | 59261.4 | 0 | 0 | 0 | 22% | 14.96% | 15.21% | -6.79% |  | 80.32 | [5 empty] | -4283
1731 | 2024-03-28 00:37 | P23650 | MBDA Recruitment Management costs | Brian Maddrell | BDW | MBDA UK LIMITED | EES | Level NC | REIM | 2024-02-01 | 1 |  | 9.6389 |  | 0% | 0% | 0 | -20.15% | 0 | 240971.5 | -240971.5 | -25000 | 0 | 0 | 266000 | 0 | 115.05 | 140971.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | -17.15% | -440.7% | -443.6% |  | 82.3 | [5 empty] | -100000
1731 | 2024-03-28 00:37 | P23543 | EXP-024 FCAS AP Transformation & Change Enablers | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -26% | 385921 | 0 | 385921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26% | 0% | 0% | -26% |  | 0 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23641 | Drawing Triage | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM | 2024-01-25 | 0 |  |  |  | 0% | 0% | 0 | -1043168% | 0 | 10755.5 | -10755.5 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | -1043168% | 100% | 100% |  | 49 | [5 empty] | -10755
1731 | 2024-03-28 00:37 | P23730 | FLE Project | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -16.79% | 0 | 1120 | -1120 | 0 | 0 | 0 | 24000 | 0 | 83 | 1120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | -16.79% | -16.79% | -16.79% |  | 35 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23463 | A220 Wing MaMo Design Checking | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-03-07 | 0 |  |  |  | 0% | 0% | 0 | 7.85% | 0 | 1628 | -1628 | 0 | 0 | 0 | 15000 | 0 | 1953.6 | 1628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | 10.85% | 0% | -3% |  | 44 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P21028 | Rebate Collection (BACC) | David Catchpole | TOO | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | [5 empty] | 0% | 0% | 0 | 0% | 0 | 2680 | -2680 | 0 | 2680 | 2680 | 0 | 0 | 3216 | 2680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23578 | ESN Work Package | Hannah Mead | COZ | CHELTON LIMITED | DET | Level 3 | FIX | 2024-01-01 | 0 |  |  | 86.17% | 116.1% | 116.1% | 0 | 35.86% | 4410 | 3800 | 610 | 0 | 0 | 0 | 0 | 4410 | 0 | -610 | 0 | 4410 | 0 | 0 | 0 | 0 | 0 | 24% | 59.86% | 0% | -24% |  | 95 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23628 | Design Assurance | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -6.67% | 0 | 3909.24 | -3909.24 | 0 | 0 | 0 | 4454.8 | 0 | 4691.09 | 3909.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 0.33% | 0% | -7% |  | 15.05 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23002 | WoT MAJ Transit Flag Stress | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 30.89% | 323.8% | 323.8% | 0 | 53.84% | 4735 | 1462.5 | 3272.5 | 0 | 0 | 2242.5 | 0 | 4735 | 0.6 | 0.5 | 0 | 4735 | 0 | 0 | 0 | 0 | 0 | 10% | 63.84% | 0% | -10% |  | 45 | [5 empty] | 3273
1731 | 2024-03-28 00:37 | P23718 | Requalification of EJ200 GSS ESS EHM SW module | Vijayakumara Nanjundappa | ARZ | MTU AERO ENGINES AG | DET | Level 3 | FIX |  |  |  | 193.2036 | 9.806% | 248.2% | 248.2% | 0 | -2.41% | 74463 | 7301.57 | 67161.43 | 347.62 | 991.93 | 991.93 | 0 | 18125 | 0 | -10823.43 | 0 | 18125 | 0 | 0 | 0 | 0 | 0 | 28% | 25.59% | 25.59% | -2.41% |  | 80 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23607 | SAFRAN - A330neo Turnover Frame | Gary Kempster | TOO | SAFRAN SEATS GB LIMITED | MPE | Level 3 | FIX |  |  |  | 4 | 95.68% | 104.5% | 104.5% | 0 | -15.57% | 8736 | 8359 | 377 | 94.25 | 0 | 0 | 0 | 8736 | 0 | 0 | 0 | 8736 | 0 | 0 | 0 | 0 | 0 | 23% | 7.43% | 100% | 77% |  | 52 | [5 empty] | 377
1731 | 2024-03-28 00:37 | P23274 | ME Support (Aim Altitude - Cambridge) | James Montgomery | AVI | AVIC CABIN SYSTEMS (UK) LIMITED | ME | Level 3 | FIX | 2023-08-18 | 0 |  |  | 51.88% | 56.3% | 56.3% | 0 | -0.17% | 17280 | 8964 | 8316 | 0 | 0 | 0 | 0 | 5046.3 | 4701.24 | 3917.7 | 0 | 5046.3 | 0 | 0 | 0 | 0 | 0 | 21% | 20.83% | 0% | -21% |  | 48 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23283 | Spirit Tooling Audit | Charidimos Valadakis | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-05-03 | 0 |  |  | 97.22% | 48.57% | 48.57% | 0 | -7.99% | 9910.08 | 9634.8 | 275.28 | 0 | 0 | 0 | 0 | 4679.76 | 5946.05 | 4955.04 | 0 | 4679.76 | 0 | 0 | 0 | 0 | 0 | 7% | -0.99% | 0% | -7% |  | 34.41 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23127 | Loft Hall Design Support | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 101% | 99.06% | 99.06% | 0 | -9.55% | 9680 | 9772 | -92 | 0 | 0 | 0 | 0 | 9680 | 110.4 | 92 | 0 | 9680 | 0 | 0 | 0 | 0 | 0 | 41% | 31.45% | 0% | -41% |  | 44 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23630 | 2Excel CFD Analysis Support | Dushan Fernando | BAX | STIRLING DYNAMICS LTD | MPE | Level NC | FIX |  |  |  |  | 61.2% | 100% | 100% | 0 | -1.87% | 16195.49 | 9911.34 | 6284.15 | 0 | 0 | 0 | 0 | 9911.63 | 0 | -0.29 | 0 | 9911.63 | 0 | 0 | 0 | 0 | 0 | 26% | 24.13% | 0% | -26% |  | 64.78 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23313 | Laser Trim Fixtures | Gary Kempster | TOO | ALKEN ENGINEERING LIMITED | MPE | Level 3 | FIX | 2023-11-20 | 0 |  |  | 89.87% | 111.3% | 111.3% | 0 | 0.53% | 13770 | 12375 | 1395 | 0 | 0 | 0 | 0 | 13770 | 0 | -1395 | 0 | 13770 | 0 | 0 | 0 | 0 | 0 | 17% | 17.53% | 0% | -17% |  | 45 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P22761 | Red Bull Chassis Spit | James Montgomery | TOO | MANUFAX ENGINEERING LTD | MPE | Level 3 | FIX | 2022-11-15 | 0 |  |  | 72.18% | 96.98% | 96.98% | 0 | 7.92% | 12961.2 | 9355.5 | 3605.7 | 0 | 0 | 0 | 0 | 9072.84 | 4666.39 | 3888.66 | 0 | 9072.84 | 0 | 0 | 0 | 0 | 0 | 23% | 30.92% | 0% | -23% |  | 42.19 | [5 empty] | 3606
1731 | 2024-03-28 00:37 | P23317 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX | 2024-01-12 | 0 |  |  | 95.89% | 104.3% | 104.3% | 0 | 4.3% | 251800 | 241446.75 | 10353.25 | 0 | 0 | 0 | 0 | 251800 | 0 | -0.25 | 0 | 251800 | 0 | 0 | 0 | 0 | 0 | 25% | 29.3% | 49.01% | 24.01% |  | 36.29 | [5 empty] | 10353
1731 | 2024-03-28 00:37 | P23350 | Spirit 2023 - Stress Approve Man Serv (DH) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 14.15% | 72.64% | 72.64% | 0 | -0.29% | 97920 | 13860 | 84060 | 0 | 0 | 0 | 0 | 10068 | 4550.4 | 3792 | 0 | 10068 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23344 | Spirit A320 Spoilers Support 2023 | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 38.75% | 100% | 100% | 0 | 5.82% | 35786.4 | 13867.23 | 21919.17 | 0 | 0 | 0 | 0 | 13867.23 | 0 | 0 | 0 | 13867.23 | 0 | 0 | 0 | 0 | 0 | 7% | 12.82% | 0% | -7% |  | 34.41 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23337 | Spirit 2023 - Steve Grimley | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 25.28% | 100% | 100% | 0 | 0.01% | 56812.9 | 14362.47 | 42450.43 | 0 | 0 | 0 | 0 | 14362.47 | 0 | 0 | 0 | 14362.47 | 0 | 0 | 0 | 0 | 0 | 7% | 7.01% | 0% | -7% |  | 30.11 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23831 | Contract DM/00113 for maintenance, repair and post | Harry James Kellett | BXW | MOD | EES | Level 2 | FIX |  |  |  | 5.2435 | 36.39% | 0% | 0% | 0 | 16.59% | 40800 | 14848.1 | 25951.9 | 4949.37 | 0 | 0 | 0 | 0 | 91 | 14848.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37% | 53.59% | 53.59% | 16.59% |  | 80.26 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23839 | Stirling Dynamics - ST002-GFEM | Carrie (Caroline)Rosemary Frosin | BAX | STIRLING DYNAMICS LTD | MPE | Level NC | FIX |  |  |  | -1 |  | 0% | 0% | 0 | -4.87% | 0 | 15030.29 | -15030.29 | 15030.29 | 0 | 0 | 19985.76 | 0 | 63 | 15030.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 2.13% | 2.13% | -4.87% |  | 44.01 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23597 | MRB Onsite support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-02-16 | 1 |  |  |  | 0% | 0% | 0 | -10.04% | 0 | 15100.57 | -15100.57 | 0 | 9448.07 | 17381.62 | 24200 | 0 | 102.4 | 15100.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 7.96% | 8.95% | -9.05% |  | 42.5 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23742 | Cyber Security Support | Hannah Mead | COZ | CHELTON LIMITED | DET | Level 3 | FIX |  |  |  | -8.32 |  | 0% | 0% | 0 | 31.67% | 0 | 15600 | -15600 | 1875 | 0 | 0 | 27500 | 0 | 91 | 15600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 31.67% | 31.67% | 31.67% |  | 100 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23663 | Spirit Tooling Verification and Inspection | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 4.25 | 82.29% | 40.51% | 0.000327% | 0 | -7.47% | 19820.16 | 16310.34 | 3509.82 | 825.84 | 0 | 0 | 7392 | 6606.72 | 152.96 | 9703.62 | 7928 | 0.053333 | 7928.06 | 0 | 0 | 0 | 0 | 12% | 4.53% | 4.82% | -7.18% |  | 34.41 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23740 | Phase 2 - EJ200 ESS EHM Platform Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 3 | FIX |  |  |  | 56.9644 | 8.502% | 168% | -0.001114% | 0 | 8.61% | 175971 | 14961 | 161010 | 2826.5 | 0 | 0 | 0 | 25139 | 94.1 | -8178 | 30167 | -0.16667 | 0 | 0 | 30166.8 | 0 | 0 | 28% | 36.61% | 36.61% | 8.61% |  | 48.18 | [5 empty] | 2000
1731 | 2024-03-28 00:37 | P23823 | EXP-034 Spear 3 Test Equip Requirement Authority | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 15.0206 | 21.03% | 20.37% | -0.0004617% | 0 | 0.32% | 85825 | 18048.88 | 67776.12 | 4512.22 | 0 | 0 | 0 | 3675.75 | 42 | 14373.13 | 4411 | -0.083333 | 4410.9 | 0 | 0 | 0 | 0 | 14% | 14.32% | 14.32% | 0.32% |  | 94.25 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23811 | Spirit T300 MRB Concessions | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -4 |  | 0% | 0% | 0 | -7.14% | 0 | 18219.39 | -18219.39 | 4554.85 | 0 | 0 | 34639 | 0 | 42 | 18219.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21% | 13.86% | 13.86% | -7.14% |  | 46.81 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23635 | Engineering Services: FAI Support | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 49.9% | 68.33% | 0.001436% | 0 | -3.4% | 37230 | 18576 | 18654 | 0 | 0 | 0 | 0 | 12693.6 | 287.37 | 5882.4 | 15232 | 0.26667 | 15232.32 | 0 | 0 | 0 | 0 | 8% | 4.6% | 5.04% | -2.96% |  | 38.7 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23343 | Spirit 2023 - John Agnew | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-08-09 | 0 |  |  | 28.56% | 86.27% | 86.27% | 0 | -0.02% | 65120.37 | 18600.89 | 46519.48 | 0 | 0 | 0 | 0 | 16047.15 | 3064.49 | 2553.74 | 0 | 16047.15 | 0 | 0 | 0 | 0 | 0 | 7% | 6.98% | 0% | -7% |  | 34.51 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23355 | Spirit Tooling Support 2023 | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-23 | 0 |  |  | 22.93% | 89.02% | 89.02% | 0 | -0.82% | 91800 | 21053.34 | 70746.66 | 0 | 0 | 0 | 0 | 18742.5 | 2773.01 | 2310.84 | 0 | 18742.5 | 0 | 0 | 0 | 0 | 0 | 20% | 19.18% | 0% | -20% |  | 44.46 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23724 | GKN S McConnell 2024 | Matthew Tweed | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  | 15.2432 | 43.6% | 66.06% | -0.000798% | 0 | 1.51% | 49820 | 21721.52 | 28098.48 | 1843.34 | 0 | 0 | 0 | 14348.16 | 83 | 7373.36 | 17218 | -0.17333 | 0 | 17217.79 | 0 | 0 | 0 | 19% | 20.51% | 20.51% | 1.51% |  | 49.82 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23351 | Spirit 2023 - Design Man Serv (KL) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 26.47% | 93.15% | 93.15% | 0 | 0.09% | 93840 | 24840 | 69000 | 0 | 0 | 0 | 0 | 23138 | 2042.4 | 1702 | 0 | 23138 | 0 | 0 | 0 | 0 | 0 | 26% | 26.09% | 0% | -26% |  | 46 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23356 | Spirit 2023 - Design Man Serv (AH) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX | 2023-08-09 | 1 |  |  |  | 76.66% | 0.001332% | 23018.4 | 0.48% | 0 | 25023.08 | -25023.08 | 0 | 0 | 0 | 25300 | 19182 | 30027.7 | 5841.08 | 23018 | 0.33333 | 0 | 0 | 0 | 23018.4 | 23018.4 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P22884 | Spirit Shorts Config Eng | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 66.3% | 100.1% | 100.1% | 0 | 0.56% | 38976 | 25841.9 | 13134.1 | 0 | 0 | 0 | 0 | 25863.2 | 0 | -0.3 | 0 | 25863.2 | 0 | 0 | 0 | 0 | 0 | 7% | 7.56% | 0% | -7% |  | 20.3 | [5 empty] | 21
1731 | 2024-03-28 00:37 | P23354 | Spirit 2023 - Design Man Serv (PC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 27.97% | 99.36% | 99.36% | 0 | 0.48% | 93840 | 26248.98 | 67591.02 | 0 | 0 | 0 | 0 | 26082 | 200.38 | 166.98 | 0 | 26082 | 0 | 0 | 0 | 0 | 0 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23821 | Supply of Safety Engineer | Dinna Elkhalifa | BXW | STIRLING DYNAMICS LTD | EES | Level NC | REIM |  |  |  | 1.6311 | 82.14% | 0% | 0% | 0 | 45.35% | 34006.44 | 27932.58 | 6073.86 | 3723.7 | 0 | 0 | 0 | 0 | 91 | 27932.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 45.35% | 45.35% | 45.35% |  | 80.73 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23651 | PMO Spirit | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -22.548 |  | 82.26% | -0.0005845% | 0 | 23.84% | 0 | 28512 | -28512 | 1264.5 | 0 | 0 | 42680 | 23454 | 205.04 | 5058 | 28145 | -0.16667 | 28144.8 | 0 | 0 | 0 | 0 | 0% | 23.84% | 23.17% | 23.17% |  | 36 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23743 | EHM Cloud Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 34.4388 | 16.66% | 100.9% | 0.0001969% | 0 | 6.81% | 1016000 | 169287.25 | 846712.75 | 24586 | 0 | 0 | 0 | 170752 | 91.83 | 16535.25 | 204902 | 0.33333 | 0 | 102412.8 | 102489.6 | 0 | 0 | 28% | 34.81% | 34.81% | 6.81% |  | 53.42 | [5 empty] | 18000
1731 | 2024-03-28 00:37 | P23458 | Spirit Belfast Tooling Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-08-11 | 0 |  |  | 101.3% | 94.65% | 94.65% | 0 | 8.64% | 30384 | 30784.9 | -400.9 | 0 | 0 | 0 | 0 | 29139.1 | 1974.96 | 1645.8 | 0 | 29139.1 | 0 | 0 | 0 | 0 | 0 | 7% | 15.64% | 0% | -7% |  | 42.2 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23338 | Spirit 2023 - Blair Hainey | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 4.6081 | 90.96% | 57.5% | 57.5% | 0 | 4.98% | 34494.36 | 31377.62 | 3116.74 | 676.36 | 0 | 0 | 0 | 18042.36 | 160.35 | 13335.26 | 0 | 18042.36 | 0 | 0 | 0 | 0 | 0 | 7% | 11.98% | 19.31% | 12.31% |  | 18.28 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23598 | MRB Onsite support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 24.1139 | 24.52% | 0% | 0% | 0 | -12.44% | 133056 | 32621.42 | 100434.58 | 4165 | 8736.42 | 14079.58 | 0 | 0 | 93.52 | 32621.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 15.56% | 15.99% | -12.01% |  | 42.5 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23365 | GKN 777x Lip Skin Fixture | Steven Lawton | TOO | GKN AEROSPACE SERVICES LTD | MPE | Level 3 | FIX | 2023-10-12 | 0 |  |  | 41.91% | 113.2% | 113.2% | 0 | -9.26% | 79161.46 | 33175.67 | 45985.79 | 0 | 5109.88 | 5109.88 | 0 | 37544.22 | 0 | -4368.55 | 0 | 37544.22 | 0 | 0 | 0 | 0 | 0 | 22% | 12.74% | 0% | -22% |  | 56 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23760 | EXP-033 Systems Engineering Support | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 40.3894 | 24.25% | 100% | -0.0002415% | 0 | -0.02% | 142300 | 34500.75 | 107799.25 | 2669 | 0 | 0 | 0 | 34500.75 | 83 | 0 | 41401 | -0.083333 | 12811.2 | 28589.7 | 0 | 0 | 0 | 29% | 28.98% | 28.98% | -0.02% |  | 78.5 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P22768 | MRB Onsite Support - Spirit Belfast | James Montgomery | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2023-07-27 | 0 |  |  |  | 0% | 0% | 0 | -17.07% | 0 | 34614 | -34614 | 0 | 0 | 0 | 36800 | 0 | 41536.8 | 34614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | -7.07% | 0% | -10% |  | 36 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23347 | WoT Fixed Leading Edge - Industrial 2023 | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 112.8% | 42.03% | 42.03% | 0 | -0.41% | 31034.12 | 35002.1 | -3967.98 | 0 | 0 | 0 | 10500 | 14710.56 | 24349.85 | 20291.54 | 0 | 14710.56 | 0 | 0 | 0 | 0 | 0 | 7% | 6.59% | 0% | -7% |  | 32.26 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23051 | Spirit Shorts A350 PAX Door | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 3A | REIM |  |  |  |  | 205.9% | 105.4% | 105.4% | 0 | -0.63% | 18216 | 37513 | -19297 | 0 | 0 | 0 | 0 | 39537 | 0 | 0 | 0 | 39537 | 0 | 0 | 0 | 0 | 0 | 30% | 29.37% | 0% | -30% |  | 46 | [5 empty] | 2024
1731 | 2024-03-28 00:37 | P23642 | MRB Belfast Support | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -22.5901 |  | 0% | 0% | 0 | -43.03% | 0 | 41829.44 | -41829.44 | 1851.67 | 2947.65 | 2947.65 | 42350 | 0 | 169.73 | 41829.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22% | -21.03% | -23.48% | -45.48% |  | 38.52 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P22752 | Tooling WoT - 2021 (Spirit) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | REIM | 2023-05-03 | 0 |  |  | 101.1% | 74.02% | 74.02% | 0 | -8.5% | 41525.1 | 41982.28 | -457.18 | 0 | 0 | 0 | 0 | 31076.1 | 13087.42 | 10906.18 | 0 | 31076.1 | 0 | 0 | 0 | 0 | 0 | 0% | -8.5% | 0% | 0% |  | 39.09 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23339 | Spirit 2023 - Stewart Russell | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 64.51% | 100% | 100% | 0 | 0.62% | 72766.8 | 46941.72 | 25825.08 | 0 | 0 | 0 | 0 | 46941.74 | 0 | -0.02 | 0 | 46941.74 | 0 | 0 | 0 | 0 | 0 | 7% | 7.62% | 0% | -7% |  | 35.67 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23822 | FCASW Requirements Management | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | -4 |  | 0% | 0% | 0 | -6.99% | 0 | 50679.32 | -50679.32 | 12669.83 | 0 | 0 | 49946.3 | 0 | 49 | 50679.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 13.01% | 13.01% | -6.99% |  | 76.27 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P22760 | SA Leading Edge Transport Media ('A' Frames) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-11-15 | 1 |  |  | 85.99% | 110.7% | 116.3% | -3082.8 | 3.97% | 53480.8 | 45985.5 | 7495.3 | 0 | 42804 | 42804 | 0 | 50911.8 | 0 | -0.3 | -3083 | 53480.9667 | 0 | 0 | 0 | -3082.8 | -3082.8 | 6% | 9.97% | 0% | -6% |  | 42 | [5 empty] | 4926
1731 | 2024-03-28 00:37 | P23700 | IPDT Leads | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 48.974 | 31.13% | 47.31% | -0.0007211% | 0 | -1.58% | 169263.9 | 52697.46 | 116566.44 | 2380.17 | 0 | 0 | 0 | 24932.12 | 106.18 | 27765.34 | 29919 | -0.38 | 29918.54 | 0 | 0 | 0 | 0 | 26% | 24.42% | 21.94% | -4.06% |  | 50.54 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23717 | GKN Ted Tomblin 2024 | Matthew Tweed | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 10047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23729 | Honda Tooling | Paul Watson | STX | SHORT BROTHERS PLC | MPE | Level NC | FIX |  |  |  | 9.7615 | 49.43% | 57.78% | 0% | 0 | 4.09% | 113610 | 56154 | 57456 | 5885.99 | 0 | 0 | 0 | 32445 | 77 | 23709 | 38934 | 0 | 38934 | 0 | 0 | 0 | 0 | 10% | 14.09% | 14.09% | 4.09% |  | 42 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23744 | Model Factory | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 45.5906 | 20.92% | 81.47% | 0.0003037% | 27429.6 | 8.66% | 262300 | 54885.5 | 207414.5 | 4549.5 | 0 | 0 | 0 | 44716 | 86.02 | 12169.5 | 53659 | 0.16667 | 0 | 26229.6 | 27429.6 | 0 | 27429.6 | 28% | 36.66% | 36.66% | 8.66% |  | 50.45 | [5 empty] | 2000
1731 | 2024-03-28 00:37 | P23349 | Spirit 2023 - Stress Approve Man Serv (SB) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 58.24% | 80.05% | 80.05% | 0 | -0.29% | 97920 | 57024 | 40896 | 0 | 0 | 0 | 0 | 45648 | 13651.2 | 11376 | 0 | 45648 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23322 | GKN T Tomblin 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  | 0.27548 | 99.66% | 100% | 83.41% | 0 | -0.33% | 58952 | 58752 | 200 | 726 | 0 | 0 | 0 | 58752 | 91 | 0 | 11693 | 49007.8333 | 3484.8 | 8208 | 0 | 0 | 0 | 17% | 16.67% | 16.67% | -0.33% |  | 48 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23106 | ME Support to NPD - Bobby Haggart | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  |  | 95.79% | 97.03% | 97.03% | 0 | 0.3% | 65675 | 62912.11 | 2762.89 | 0 | 0 | 0 | 0 | 61042.75 | 2243.24 | 1869.36 | 0 | 61042.75 | 0 | 0 | 0 | 0 | 0 | 15% | 15.3% | 0% | -15% |  | 35.65 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23341 | Spirit 2023 - Tom McFarlane | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 37.6649 | 58.26% | 80.37% | 67.95% | 0 | -0.01% | 108666.4 | 63314.06 | 45352.34 | 1204.1 | 0 | 0 | 0 | 50887.19 | 148.61 | 12426.87 | 9441 | 43019.69 | 2331.04 | 0 | 0 | 7110.19 | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23753 | Tempest Composites Maturation | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 7.9895 | 49.56% | 49.05% | -0.0003156% | 0 | -13.45% | 127848.45 | 63367.66 | 64480.79 | 8070.72 | 0 | 0 | 0 | 31084.8 | 84 | 32282.86 | 37302 | -0.2 | 37301.76 | 0 | 0 | 0 | 0 | 32% | 18.55% | 18.55% | -13.45% |  | 64.76 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P22967 | Spirit 2022 - Channapa Laxmeshwar | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2023-01-26 | 2 |  |  | 69.69% | 121.3% | 121.3% | 0 | 9.53% | 75159.1 | 52376.15 | 22782.95 | 0 | 52376.15 | 54898.1 | 0 | 63508.8 | 0.42 | 0.35 | 0 | 63508.8 | 0 | 0 | 0 | 0 | 0 | 8% | 17.53% | 0% | -8% |  | 0 | [5 empty] | 11133
1731 | 2024-03-28 00:37 | P23193 | Spirit Shorts Stephen Greer | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -3.6468 | 103.6% | 95.32% | 85.81% | 0 | 8.58% | 61472 | 63694.24 | -2222.24 | 609.37 | 0 | 0 | 10878 | 60712.78 | 96.83 | 2981.46 | 7269 | 54655.28 | 7268.72 | 0 | 0 | 0 | 0 | 23% | 31.58% | 34.03% | 11.03% |  | 35.08 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23561 | SAAB | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2024-01-01 | 1 |  | 10.7403 | 82.46% | 121.1% | 121.1% | 0 | 8.77% | 67485 | 55649.23 | 11835.77 | 1102 | 0 | 0 | 0 | 67399.4 | 0 | -0.17 | 0 | 67399.4 | 0 | 0 | 0 | 0 | 0 | 16% | 24.77% | 100% | 84% |  | 36.82 | [5 empty] | 11750
1731 | 2024-03-28 00:37 | P21138 | D&A Vibration Reduc Damping Struc FOGV Components | Steven Lawton | ATC | AECC SICHUAN GAS TURBINE | MPE | Level 1 | FIX | 2022-09-07 | 0 |  |  | 96.12% | 104% | 104% | 0 | -3.44% | 569346 | 547228.11 | 22117.89 | 0 | 75181.75 | 75181.75 | 0 | 569346 | 0 | 0.11 | 0 | 569346 | 0 | 0 | 0 | 0 | 0 | 36% | 32.56% | 0.08% | -35.92% |  | 73.95 | [5 empty] | 22118
1731 | 2024-03-28 00:37 | P23080 | Spirit Shorts DManagement Cairan Cullen | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 129.0983 | 50.6% | 98.02% | 91.32% | 3787.8 | -1.19% | 149600 | 75697.7 | 73902.3 | 572.45 | 0 | 0 | 0 | 74199.7 | 175.15 | 1498 | 6086 | 69128.0333 | 2298.36 | 0 | 0 | 3787.8 | 3787.8 | 24% | 22.81% | 13.22% | -10.78% |  | 44.4 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P22505 | Spirit MRB Engineering Support 2021 | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 1 |  |  | 91.17% | 100% | 95.78% | 4020.48 | 21.2% | 87110.4 | 79414.95 | 7695.45 | 0 | 0 | 0 | 0 | 79414.95 | 4020.48 | 0 | 4020 | 76064.95 | 0 | 0 | 0 | 4020.48 | 4020.48 | 0% | 21.2% | 0% | 0% |  | 41.88 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23560 | NJEWCS TAF202302 SM | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level 2 | FIX |  |  |  | 3.038 | 97.96% | 50.1% | 50.1% | 0 | 12.15% | 81500 | 79836.44 | 1663.56 | 547.58 | 0 | 0 | 0 | 40000 | 157.63 | 39836.44 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 28% | 40.15% | 40.2% | 12.2% |  | 73.01 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P22885 | ME Support (Baxi) | James Montgomery | HUV | BAXI HEATING UK LIMITED | ME | Level 3 | FIX | 2023-01-12 | 0 |  |  | 68.78% | 108.7% | 108.7% | 0 | 13.05% | 106632.96 | 73340.24 | 33292.72 | 0 | 0 | 0 | 0 | 79748.12 | 1531.35 | 1276.12 | 0 | 79748.12 | 0 | 0 | 0 | 0 | 0 | 15% | 28.05% | 0% | -15% |  | 44.37 | [5 empty] | 7684
1731 | 2024-03-28 00:37 | P23438 | A220 Spirit Shorts DTC - Stephen Corry | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 10.3851 | 85.55% | 78.54% | 49.23% | 0 | -7.21% | 95928.4 | 82068.6 | 13859.8 | 1334.58 | 0 | 0 | 0 | 64459.8 | 325.11 | 17608.8 | 28872 | 40399.8 | 28872.36 | 0 | 0 | 0 | 0 | 23% | 15.79% | 17.39% | -5.61% |  | 49.81 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23784 | Tempest Tooling Offload 2024 | Christopher McCarthy | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  | -10.6132 |  | 0% | 0% | 0 | -11.36% | 0 | 83029.43 | -83029.43 | 7823.23 | 0 | 0 | 107936.4 | 0 | 83 | 83029.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 18.64% | 18.64% | -11.36% |  | 54.91 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23340 | Spirit 2023 - John Cole | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 45.2162 | 55.67% | 80.01% | 66.4% | 0 | -0.01% | 150129.72 | 83577.78 | 66551.94 | 1471.86 | 0 | 0 | 0 | 66870.18 | 152.97 | 16707.6 | 13653 | 55492.68 | 4821.34 | 0 | 0 | 8831.16 | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 39.78 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P22440 | Spirit Managed Service - F&DT and Static Approval | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 3 |  |  | 88.56% | 92.56% | 92.56% | 0 | 11.51% | 173500 | 153656.25 | 19843.75 | 0 | 52115 | 55720 | 0 | 142225.12 | 13717.36 | 11431.13 | 0 | 142225.12 | 0 | 0 | 0 | 0 | 0 | 0% | 11.51% | 0% | 0% |  | 44.73 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23335 | GKN S McConnell 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2023-12-31 | 1 |  |  | 96.61% | 100% | 91.76% | 0 | 0.74% | 87420 | 84459 | 2961 | 0 | 0 | 0 | 0 | 84459 | 8347.2 | 0 | 8347 | 77503.1667 | 0 | 0 | 0 | 8347.2 | 0 | 15% | 15.74% | 0% | -15% |  | 47 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23345 | Spirit 2023- Jonathan Escosio | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | -6.8863 | 111.6% | 80.66% | 60.43% | 7150.18 | -6.71% | 75970.62 | 84807.69 | -8837.07 | 1283.29 | 0 | 0 | 8938 | 68401.74 | 186.13 | 16405.95 | 20581 | 51250.9067 | 4734.58 | 0 | 0 | 15846.34 | 7150.18 | 7% | 0.29% | -1.22% | -8.22% |  | 40.26 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P22965 | Spirit 2022 - Design Man Serv (AH) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 1 |  |  | 106.7% | 96.66% | 92.02% | 4759.75 | 3.14% | 80079.56 | 85441.32 | -5361.76 | 0 | 0 | 0 | 0 | 82588.96 | 8182.59 | 2852.36 | 4760 | 78622.2933 | 0 | 0 | 0 | 4759.75 | 4759.75 | 14% | 17.14% | 0% | -14% |  | 42.44 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23523 | Applique Armour Support | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-18 | 1 |  |  | 72.43% | 138.1% | 98.47% | 0 | 3.42% | 118200 | 85606.5 | 32593.5 | 0 | 0 | 0 | 0 | 118200 | 1567.8 | -32593.5 | 40680 | 84300 | 40680 | 0 | 0 | 0 | 0 | 25% | 28.42% | 0% | -25% |  | 64.29 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P22964 | Spirit 2022 - MRB Man Serv (JC) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 100.6% | 97.95% | 97.95% | 0 | 1.91% | 85435.2 | 85960.26 | -525.06 | 0 | 0 | 0 | 0 | 84199.74 | 2112.62 | 1760.52 | 0 | 84199.74 | 0 | 0 | 0 | 0 | 0 | 16% | 17.91% | 0% | -16% |  | 42.69 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23342 | Spirit 2023 - Channapa Laxmeshwar | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 14.6367 | 52.39% | 78.4% | 74.35% | 0 | -3.69% | 158696.7 | 83134.33 | 75562.37 | 5162.52 | 83134.33 | 94827 | 0 | 65177.5 | 106.52 | 20806.83 | 4037 | 61813.3333 | 0 | 0 | 0 | 4036.8 | 0 | 7% | 3.31% | 0% | -7% |  | 0 | [5 empty] | 2850
1731 | 2024-03-28 00:37 | P23465 | A220 ToW Design Offload (Wing) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 25.2646 | 65.59% | 93.03% | 64.41% | 0 | -4.63% | 132000 | 86584.4 | 45415.6 | 1797.6 | 0 | 0 | 0 | 80549.6 | 94.27 | 6034.8 | 29737 | 55768.7667 | 29737.44 | 0 | 0 | 0 | 0 | 20% | 15.37% | 14.07% | -5.93% |  | 42.8 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23336 | Spirit 2023 - Neil Rampling | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 31.4539 | 64.89% | 80.24% | 55.08% | 13070.83 | -0.01% | 133901.52 | 86890.52 | 47011 | 1494.6 | 0 | 0 | 0 | 69718.2 | 206.82 | 17172.32 | 26227 | 47862.3667 | 4640.79 | 0 | 0 | 21586.03 | 13070.83 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P22963 | Spirit 2022 - Design Man Serv (PC) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 1 |  |  | 108.6% | 104% | 94.46% | 9938.48 | 3.18% | 80079.56 | 86926.74 | -6847.18 | 0 | 0 | 0 | 0 | 90389.95 | 5782.63 | -3463.21 | 9938 | 82108.2833 | 0 | 0 | 0 | 9938.48 | 9938.48 | 13% | 16.18% | 0% | -13% |  | 42.39 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23079 | Spirit Shorts Nomenclature | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 1.0271 | 99.25% | 89.05% | 77.84% | 0 | 1.98% | 88455 | 87795.6 | 659.4 | 642 | 0 | 0 | 0 | 78185.2 | 237.7 | 9610.4 | 11811 | 68342.7 | 11810.64 | 0 | 0 | 0 | 0 | 20% | 21.98% | 25.23% | 5.23% |  | 30.76 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23754 | Tempest Composites WP4 | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -8.0692 |  | 0% | 0% | 0 | 6.98% | 0 | 88484.04 | -88484.04 | 10965.64 | 884.24 | 884.24 | 97140 | 0 | 91 | 88484.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 34.98% | 34.98% | 6.98% |  | 63 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23586 | Project Management Support | Peter Bowen | BDX | MBDA UK LIMITED | MPE | Level NC | REIM |  |  |  | -3.4106 | 112% | 74.91% | 71.98% | 0 | -26.07% | 80000 | 89583.86 | -9583.86 | 2810 | 1140.6 | 1140.6 | 16000 | 67103.86 | 72.2 | 22480 | 3149 | 64479.6933 | 0 | 3148.63 | 0 | 0 | 0 | 49% | 22.93% | 22.4% | -26.6% |  | 80 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23551 | Ian Berry 2023 H2 | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  | -5.2014 | 119.9% | 73.96% | 73.96% | 0 | 13.84% | 75810 | 90883.52 | -15073.52 | 2897.98 | 0 | 0 | 24259.2 | 67217.49 | 62.87 | 23666.03 | 0 | 67217.49 | 0 | 0 | 0 | 0 | 0 | 22% | 35.84% | 39.01% | 17.01% |  | 77.46 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23375 | GKN Jaap Peters NL 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2024-03-01 | 2 |  |  | 93.37% | 105.3% | 85.02% | 0 | -15.93% | 97123.22 | 90686.41 | 6436.81 | 0 | 90686.41 | 90686.41 | 0 | 95456.72 | 108.86 | -920.31 | 22027 | 77100.8867 | 0 | 8793.29 | 0 | 13234.06 | 0 | 20% | 4.07% | 0% | -20% |  | 0 | [5 empty] | 3850
1731 | 2024-03-28 00:37 | P23583 | Castalla - Test Rig Design | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -19.3856 | 144.4% | 69.23% | 62.84% | 0 | -6.45% | 67520 | 97480.5 | -29960.5 | 1545.5 | 0 | 0 | 36106 | 67482.1 | 141.22 | 29998.4 | 7469 | 61257.9333 | 7469.4 | 0 | 0 | 0 | 0 | 21% | 14.55% | 16.88% | -4.12% |  | 42.75 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23545 | Ultra CSS continuation 2023 H2 | Natalie Sinclair | ULT | ULTRA SONAR SYSTEMS LIMITED | EES | Level NC | REIM |  |  |  | -17.1674 | 133% | 74.66% | 43.5% | 37794.24 | 2.22% | 76000 | 101057.6 | -25057.6 | 1459.6 | 0 | 0 | 24259.2 | 75451.2 | 225.96 | 25606.4 | 37794 | 43956.2 | 0 | 37794.24 | 0 | 0 | 37794.24 | 23% | 25.22% | 25% | 2% |  | 80 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23353 | Spirit 2023 - MRB Man Serv (JC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  | 25.4318 | 58.86% | 63.49% | 63.49% | 0 | 10.08% | 183600 | 108067.5 | 75532.5 | 2970 | 0 | 0 | 0 | 68615.25 | 189.5 | 39452.25 | 0 | 68615.25 | 0 | 0 | 0 | 0 | 0 | 7% | 17.08% | 13.81% | 6.81% |  | 45 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23588 | BAE Typhoon MRB MC Shop Concessions | Andrew Houghton | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 26.5067 | 63.38% | 83.18% | 46.45% | 0 | -3.81% | 175060.5 | 110956.99 | 64103.51 | 2418.39 | 0 | 0 | 0 | 92295.97 | 177.86 | 18661.02 | 48910 | 51537.6367 | 0 | 48910.43 | 0 | 0 | 0 | 31% | 27.19% | 29.26% | -1.74% |  | 55.51 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23352 | Spirit 2023 - Stress Approve Man Serv (CC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  | -13.625 | 113.4% | 62.98% | 62.98% | 0 | 6.96% | 97920 | 111000 | -13080 | 960 | 0 | 0 | 29856 | 69912 | 221.3 | 41088 | 0 | 69912 | 0 | 0 | 0 | 0 | 0 | 7% | 13.96% | 4.69% | -2.31% |  | 48 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P22756 | A350 FLE Design Checker | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2022-03-23 | 1 |  |  | 68.39% | 119.7% | 119.7% | 0 | 16.46% | 34898.4 | 23867.15 | 11031.25 | 0 | 23867.15 | 24342.3 | 0 | 28571.1 | 0.06 | 0.05 | 0 | 28571.1 | 0 | 0 | 0 | 0 | 0 | 0% | 16.46% | 0% | 0% |  | 0 | [5 empty] | 4704
1731 | 2024-03-28 00:37 | P23664 | Tempest Composites WP3 | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 2.9163 | 93.69% | 14.4% | 14.4% | 0 | -5.05% | 122455.49 | 114731.46 | 7724.03 | 2648.56 | 0 | 0 | 0 | 16518.7 | 228.77 | 98212.76 | 0 | 16518.7 | 0 | 0 | 0 | 0 | 0 | 37% | 31.95% | 33.92% | -3.08% |  | 60.73 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P22736 | WoT Fixed Leading Edge - Industrial | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 106.7% | 93.42% | 91.32% | 3019.54 | 0.01% | 112196.27 | 119668.47 | -7472.2 | 0 | 0 | 0 | 0 | 111796.68 | 12465.69 | 7871.79 | 3020 | 109280.0133 | 0 | 0 | 0 | 3019.54 | 3019.54 | 7% | 7.01% | 0% | -7% |  | 32.26 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23282 | Tooling Support (MBDA) | Dushan Fernando | BDV | MBDA UK LIMITED | ME | Level NC | REIM |  |  |  | 40.831 | 61.86% | 99.98% | 85.76% | 0 | -8.54% | 195672.4 | 121035.37 | 74637.03 | 1827.95 | 0 | 0 | 0 | 121010.44 | 75.3 | 24.93 | 20648 | 103803.7733 | 20647.76 | 0 | 0 | 0 | 0 | 30% | 21.46% | 30.37% | 0.37% |  | 49.71 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P22883 | Spirit Shorts Evtol PMO C. Hatton | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 41.8854 | 65.16% | 89.99% | 89.99% | 0 | -11.62% | 185800 | 121066.15 | 64733.85 | 1545.5 | 0 | 0 | 0 | 108946.73 | 89.2 | 12119.42 | 0 | 108946.73 | 0 | 0 | 0 | 0 | 0 | 26% | 14.38% | 24.2% | -1.8% |  | 36.79 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23270 | Shorts Project X | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 12.0384 | 85.83% | 88.12% | 71.98% | 0 | 0.61% | 142248 | 122095.4 | 20152.6 | 1674.02 | 0 | 0 | 0 | 107585.5 | 155.65 | 14509.9 | 23635 | 87889.6667 | 23635.49 | 0 | 0 | 0 | 0 | 13% | 13.61% | 10.99% | -2.01% |  | 45.35 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P22861 | WoT FLE Lifting & Handling Tools | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2023-06-14 | 1 |  |  | 65.17% | 101.6% | 101.6% | 0 | 12.01% | 173987.21 | 113381.75 | 60605.46 | 0 | 50078 | 58423.58 | 0 | 115203.5 | 12813.9 | 10678.25 | 0 | 115203.5 | 0 | 0 | 0 | 0 | 0 | 1% | 13.01% | 0% | -1% |  | 45 | [5 empty] | 12500
1731 | 2024-03-28 00:37 | P23741 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  | 39.6843 | 19.4% | 71.4% | 0% | 0 | 1.64% | 640812 | 124322.3 | 516489.7 | 13014.95 | 0 | 0 | 0 | 88770 | 84.34 | 37552.3 | 106524 | 0 | 0 | 52662 | 53862 | 0 | 0 | 28% | 29.64% | 29.64% | 1.64% |  | 38.8 | [5 empty] | 2000
1731 | 2024-03-28 00:37 | P23810 | Strategic Enablement | Owain Jones | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -18.6167 |  | 0% | 0% | 0 | -20.58% | 0 | 133060.2 | -133060.2 | 7147.35 | 0 | 0 | 134000 | 0 | 84 | 133060.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | -2.58% | -2.58% | -20.58% |  | 42 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23533 | External Stowage Design and Detail Support | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 1 |  |  | 102.4% | 97.65% | 73.24% | 0 | 3.33% | 140000 | 143368.75 | -3368.75 | 0 | 0 | 0 | 12936 | 140000 | 41999.7 | -0.25 | 42000 | 105000 | 42000 | 0 | 0 | 0 | 0 | 27% | 30.33% | 0% | -27% |  | 60.04 | [5 empty] | -3369
1731 | 2024-03-28 00:37 | P23433 | Cavendish | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 32.81% | 100% | 100% | 0 | -0.34% | 42240 | 13859.2 | 28380.8 | 0 | 0 | 0 | 0 | 13859.2 | 0 | 0 | 0 | 13859.2 | 0 | 0 | 0 | 0 | 0 | 7% | 6.66% | 0% | -7% |  | 43.93 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23008 | Spirit Shorts Project Rachel | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 85.87% | 91.32% | 91.32% | 0 | -7.7% | 228880 | 196531.2 | 32348.8 | 0 | 0 | 0 | 0 | 179472.8 | 1034.6 | 17058.4 | 0 | 179472.8 | 0 | 0 | 0 | 0 | 0 | 13% | 5.3% | 0.31% | -12.69% |  | 46.04 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P22954 | Technical Support Step 1 | Owain Jones | HUV | HUARUI SPIRIT AEROSPACE MANUFACT | ME | Level 2 | REIM |  |  |  |  | 94.81% | 58.01% | 58.01% | 0 | 0.31% | 155501.18 | 147431.58 | 8069.6 | 0 | 23043 | 23043 | 0 | 85525.49 | 61906.09 | 61906.09 | 0 | 85525.49 | 0 | 0 | 0 | 0 | 0 | 30% | 30.31% | 0% | -30% |  | 60.79 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23386 | Software Development - BMS | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 98.78% | 100% | 95.49% | 0 | 4.31% | 149650 | 147823.35 | 1826.65 | 0 | 0 | 0 | 0 | 147823.35 | 36.13 | 0 | 8007 | 141150.85 | 0 | 8007 | 0 | 0 | 0 | 18% | 22.31% | 22.61% | 4.61% |  | 78.5 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23320 | Lifing Services DACs | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX | 2024-01-12 | 0 |  |  | 95.56% | 104.6% | 104.6% | 0 | 2.98% | 413300 | 394956.45 | 18343.55 | 0 | 0 | 0 | 0 | 413300 | 0 | -0.55 | 0 | 413300 | 0 | 0 | 0 | 0 | 0 | 26% | 28.98% | 52.05% | 26.05% |  | 33.15 | [5 empty] | 18343
1731 | 2024-03-28 00:37 | P23550 | Tempest Composites | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -8.1906 | 100.3% | 99.66% | 84.24% | 0 | 5.13% | 149494.92 | 150002.74 | -507.82 | 62 | 0 | 0 | 2396.12 | 149494.92 | 112.7 | 507.82 | 27760 | 126361.5867 | 0 | 27760.26 | 0 | 0 | 0 | 26% | 31.13% | 34.47% | 8.47% |  | 61.58 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P22982 | Spirit 2022 - Hugh Sloan | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 100.5265 | 61.09% | 90.88% | 83.98% | 0 | -0.44% | 247473 | 151172.62 | 96300.38 | 957.96 | 0 | 0 | 0 | 137378.56 | 193.26 | 13794.06 | 12517 | 126947.7267 | 4300.18 | 0 | 0 | 8217.17 | 0 | 7% | 6.56% | 1.35% | -5.65% |  | 35.42 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23552 | FCAS AP Product Technology Development | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -25% | 597871 | 0 | 597871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0% | -25% |  | 0 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23842 | Tranche 1 Evolution Package Step 2 | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX | [7 empty] | 0 | -31% | 0 | 0 | 0 | 0 | 0 | 0 | 67488.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31% | 0% | 0% | -31% |  | 0 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23518 | Systems Engineering support to FCAS | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 19.4208 | 79.44% | 97.22% | 84.34% | 0 | -3.21% | 193736.8 | 153908.5 | 39828.3 | 2050.81 | 3927.4 | 3927.4 | 0 | 149625.43 | 70.56 | 4283.07 | 23786 | 129803.7633 | 9843.9 | 13941.6 | 0 | 0 | 0 | 30% | 26.79% | 3.5% | -26.5% |  | 67.69 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23421 | A220 DTC | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 10.7271 | 72.26% | 76.66% | 68.27% | 0 | -28.99% | 217089.12 | 156871.95 | 60217.17 | 5613.56 | 0 | 0 | 0 | 120261.6 | 93.71 | 36610.35 | 15801 | 107094.1 | 15800.9 | 0 | 0 | 0 | 0 | 29% | 0.01% | 5.27% | -23.73% |  | 45.75 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23648 | EXP-032 Delivery of Datalink Eng support - FCAS AP | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 25.6476 | 45.18% | 81.08% | 61.35% | 0 | 5.21% | 371000 | 167630.45 | 203369.55 | 7929.38 | 1032.95 | 1032.95 | 0 | 135912.95 | 62.44 | 31717.5 | 39685 | 102842.1167 | 0 | 39684.54 | 0 | 0 | 0 | 22% | 27.21% | 27.27% | 5.27% |  | 103.41 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23600 | MBDA EXP-EE-023 Bristone Certification | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 59.65% | 100% | 100% | 0 | 0.4% | 126600 | 75517 | 51083 | 0 | 0 | 0 | 0 | 75517 | 0 | 0 | 0 | 75517 | 0 | 0 | 0 | 0 | 0 | 41% | 41.4% | 0% | -41% |  | 78.5 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23629 | F35 FTI | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level NC | REIM |  |  |  | -21.5695 |  | 94.04% | 75.75% | 0 | -0.83% | 0 | 217723 | -217723 | 10094.02 | 0 | 0 | 0 | 204738.05 | 44.28 | 12984.95 | 47781 | 164920.55 | 47780.74 | 0 | 0 | 0 | 0 | 31% | 30.17% | 28.97% | -2.03% |  | 61.81 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23843 | EXP-035 FT15 Exemplar information set | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 3 | REIM | [7 empty] | 0 | -21% | 0 | 0 | 0 | 0 | 0 | 0 | 21180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21% | 0% | 0% | -21% |  | 0 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23506 | ASTER Mid-Life Refurbishment Project Manager | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 8.7562 | 84.69% | 91.74% | 81.72% | 0 | 1.03% | 224900 | 190466.41 | 34433.59 | 3932.5 | 2806.41 | 2806.41 | 0 | 174736.41 | 65.03 | 15730 | 22897 | 155655.5767 | 0 | 22896.62 | 0 | 0 | 0 | 25% | 26.03% | 26.33% | 1.33% |  | 110 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23382 | Performance Modelling | Dushan Fernando | BDX | MBDA UK LIMITED | MPE | Level NC | REIM | 2023-07-09 | 0 |  |  | 40.95% | 79.09% | 79.09% | 0 | -16.36% | 170009.66 | 69625.98 | 100383.68 | 0 | 14559.9 | 14559.9 | 0 | 55066.08 | 0 | -0.1 | 0 | 55066.08 | 0 | 0 | 0 | 0 | 0 | 20% | 3.64% | 0% | -20% |  | 77.05 | [5 empty] | -14560
1731 | 2024-03-28 00:37 | P23524 | Bombardier Regional Jets (BRJ) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 130.8% | 56.89% | 44.32% | 28851.48 | -4.69% | 146287.84 | 191311.68 | -45023.84 | 0 | 0 | 0 | 46750 | 108838.22 | 343.27 | 82473.46 | 28851 | 84795.72 | 0 | 0 | 0 | 28851.48 | 28851.48 | 18% | 13.31% | 15.43% | -2.57% |  | 43.92 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23505 | EXP-022 Meteor TBUS T&E support | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 12.7628 | 79.27% | 100% | 83.59% | 0 | -1.05% | 246744.4 | 195582.37 | 51162.03 | 4008.67 | 0 | 0 | 0 | 195582.38 | 62.13 | -0.01 | 38510 | 163490.7133 | 19241.59 | 19268.53 | 0 | 0 | 0 | 20% | 18.95% | 15.67% | -4.33% |  | 89.83 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23373 | Raytheon Michael Bellini | Natalie Sinclair | RAS | RAYTHEON UNITED KINGDOM LIMITED | EES | Level NC | REIM |  |  |  | 5.8733 | 91.53% | 97.72% | 87.22% | 0 | -7.9% | 214367.4 | 196208.15 | 18159.25 | 3091.84 | 0 | 0 | 0 | 191739.73 | 56.49 | 4468.42 | 24735 | 171127.23 | 24734.7 | 0 | 0 | 0 | 0 | 45% | 37.1% | 38.79% | -6.21% |  | 91.61 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23816 | Typhoon FTI Works - 2024 Fixed Price Element | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 6.5 | 47.26% | 0% | 0% | 0 | -3.66% | 404176.65 | 191009.71 | 213166.94 | 32794.72 | 0 | 0 | 0 | 0 | 56 | 191009.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 26.34% | 26.34% | -3.66% |  | 53.67 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23677 | ME Managed Service - Phase 1 | Paul Watson | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  | 17.4972 | 35.85% | 57.35% | 0% | 0 | -15.81% | 554400 | 198753.75 | 355646.25 | 20325.94 | 0 | 0 | 0 | 113985 | 114.78 | 84768.75 | 136782 | 0 | 136782 | 0 | 0 | 0 | 0 | 33% | 17.19% | 20.85% | -12.15% |  | 45 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23242 | Physical Architecture & System Engineering Support | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 36.9513 | 65.46% | 99.62% | 87.92% | 0 | 8.31% | 305459 | 199953.71 | 105505.29 | 2855.25 | 775.55 | 775.55 | 0 | 199187.05 | 66.6 | 412.66 | 28072 | 175793.7167 | 14130 | 13941.6 | 0 | 0 | 0 | 15% | 23.31% | 6.84% | -8.16% |  | 78.19 | [5 empty] | -354
1731 | 2024-03-28 00:37 | P23019 | EXP034-B Actuator Development | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 5.2929 | 103.1% | 89.91% | 89.91% | 0 | -16.68% | 215541.2 | 222215.54 | -6674.34 | -1261 | 12297.9 | 12297.9 | 0 | 199796.76 | 91.24 | 397.78 | 0 | 199796.76 | 0 | 0 | 0 | 0 | 0 | 34% | 17.32% | 79.64% | 45.64% |  | 58.45 | [5 empty] | -22021
1731 | 2024-03-28 00:37 | P23171 | Spirt Shorts Weights Eng | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 69.18% | 122.7% | 96.15% | 5965.46 | 2.68% | 103113.14 | 71329.32 | 31783.82 | 0 | 71329.32 | 85975.13 | 0 | 87531.56 | 105.02 | -3932.24 | 22740 | 68581.56 | 0 | 16774.18 | 5965.46 | 0 | 5965.46 | 12% | 14.68% | 0% | -12% |  | 0 | [5 empty] | 12270
1731 | 2024-03-28 00:37 | P22798 | CO2MAP MGSE | Harry James Kellett | DTW | THALES ALENIA SPACE UK (60DAYS) | EES | Level 2 | REIM | 2023-11-08 | 0 |  |  | 85.75% | 105% | 105% | 0 | -3.47% | 252086 | 216157.82 | 35928.18 | 0 | 0 | 0 | 0 | 227052.6 | 0.26 | 0.22 | 0 | 227052.6 | 0 | 0 | 0 | 0 | 0 | 29% | 25.53% | 100% | 71% |  | 50.31 | [5 empty] | 10895
1731 | 2024-03-28 00:37 | P23316 | Model Factory IL and AW | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX | 2024-01-12 | 0 |  |  | 88.13% | 104.1% | 104.1% | 0 | 2.41% | 250000 | 220327.78 | 29672.22 | 0 | 0 | 0 | 0 | 229409 | 0 | -0.22 | 0 | 229409 | 0 | 0 | 0 | 0 | 0 | 30% | 32.41% | 42.82% | 12.82% |  | 45.31 | [5 empty] | 9081
1731 | 2024-03-28 00:37 | P23472 | Tempest Wing Design | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 42.5604 | 45.03% | 127.4% | 105.7% | 0 | -9.97% | 483869.78 | 217867.11 | 266002.67 | 6250 | 201987.5 | 356900 | 0 | 277493.82 | 26.55 | -34626.72 | 56708 | 230237.1533 | 23954.72 | 32753.16 | 0 | 0 | 0 | 23% | 13.03% | 44.54% | 21.54% |  | 46.74 | [5 empty] | 25000
1731 | 2024-03-28 00:37 | P23739 | Lifing Services DACs | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  | 45.7038 | 21.38% | 78.67% | -0.0002375% | 0 | 3.01% | 656508 | 140353.9 | 516154.1 | 11293.45 | 0 | 0 | 0 | 110418 | 83 | 29935.9 | 132502 | -0.33333 | 0 | 65650.8 | 66850.8 | 0 | 0 | 28% | 31.01% | 31.01% | 3.01% |  | 37.81 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23603 | Typhoon IMDLR | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 8.849 | 86.18% | 45.57% | 0.0001293% | 0 | 5.42% | 305067.09 | 262907.03 | 42160.06 | 4764.39 | 0 | 0 | 61083.75 | 119807.84 | 323.01 | 143099.19 | 143769 | 0.34 | 143769.41 | 0 | 0 | 0 | 0 | 26% | 31.42% | 33.04% | 7.04% |  | 57.16 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23007 | EXP-006A - Brimstone 3 | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 57.2677 | 66.27% | 96.44% | 90.73% | 0 | -2.88% | 406450 | 269336.78 | 137113.22 | 2394.25 | 0 | 0 | 0 | 259759.75 | 75.07 | 9547.03 | 18463 | 244373.9167 | 0 | 18463.2 | 0 | 0 | 0 | 25% | 22.12% | 29.94% | 4.94% |  | 69.72 | [5 empty] | -30
1731 | 2024-03-28 00:37 | P21463 | Safety & Monitoring Systems at DM Beith & Gosport | Harry James Kellett | BXW | MOD | EES | Level 2 | FIX |  |  |  | 504.3776 | 77.6% | 128.9% | 128.9% | 0 | -26.95% | 349404.99 | 271130.63 | 78274.36 | 155.19 | 57009.29 | 77031.85 | 21721 | 349386.99 | 0 | -78256.36 | 0 | 349386.99 | 0 | 0 | 0 | 0 | 0 | 48% | 21.05% | 39.26% | -8.74% |  | 52.91 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23308 | NATO JEWCS | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  | 42.9134 | 81.85% | 93.69% | 80.77% | 45213.08 | -3.62% | 356307 | 291648.48 | 64658.52 | 1506.72 | 613.89 | 613.89 | 0 | 273254.06 | 191.27 | 18394.42 | 45213 | 235576.56 | 0 | 0 | 45213.08 | 0 | 45213.08 | 24% | 20.38% | 11.83% | -12.17% |  | 75.81 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23699 | A220 Stress Checkers | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -14.8849 |  | 0% | 0% | 0 | -2.23% | 0 | 318152.54 | -318152.54 | 21374.15 | 12000 | 12000 | 321520 | 0 | 105.7 | 318152.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22% | 19.77% | 19.77% | -2.23% |  | 61.88 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23617 | Tempest Composites WP2 | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -16.0778 | 131.7% | 25.62% | 10.57% | 29536.68 | 11.72% | 244405.26 | 321867.9 | -77462.64 | 4817.99 | 0 | 0 | 77669.2 | 82447.45 | 297.38 | 239420.45 | 58103 | 34028.2833 | 0 | 28565.94 | 0 | 29536.68 | 29536.68 | 22% | 33.72% | 33.5% | 11.5% |  | 62.17 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P22515 | Shorts A220 100/300 ALI Phase III | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 47.6868 | 80.69% | 96.76% | 92.02% | 0 | 0.85% | 400628.76 | 323251.67 | 77377.09 | 1622.61 | 3450.98 | 3450.98 | 0 | 312787.53 | 107.58 | 10464.14 | 18387 | 297465.03 | 18386.68 | 0 | 0 | 0 | 0 | 10% | 10.85% | 8.45% | -1.55% |  | 40.44 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P22953 | Spirit Shorts eVTOL | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-05-08 | 3 |  | 4.0846 | 103.1% | 80.83% | 79.36% | 0 | -9.51% | 324272 | 334483.6 | -10211.6 | -2500 | 66696.6 | 67387.9 | 0 | 270366 | 70861.92 | 54117.6 | 5921 | 265431.8333 | 5920.8 | 0 | 0 | 0 | 0 | 17% | 7.49% | 100% | 83% |  | 46.19 | [5 empty] | -10000
1731 | 2024-03-28 00:37 | P22842 | ME Support (Aim Altitude) | James Montgomery | AVI | AIM ALTITUDE UK LIMITED | ME | Level 3 | FIX | 2023-06-14 | 4 |  |  | 99.31% | 100.5% | 86.63% | 57290.84 | 0.49% | 346293.67 | 343918.08 | 2375.59 | 0 | 2909.86 | 2909.86 | 0 | 345673.01 | 55184.93 | -1754.93 | 57291 | 297930.51 | 0 | 0 | 0 | 57290.84 | 57290.84 | 13% | 13.49% | 0% | -13% |  | 46.3 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P22391 | GE System Engineering support | Vinayakumar Sugur | GEE | EXPERIS LIMITED | EES | Level NC | REIM |  |  |  |  | 82.01% | 99.51% | 99.51% | 0 | 0.13% | 434434.25 | 356260.63 | 78173.62 | 0 | 0 | 0 | 0 | 354519.5 | 2089.36 | 1741.13 | 0 | 354519.5 | 0 | 0 | 0 | 0 | 0 | 6% | 6.13% | 6.09% | 0.09% |  | 57.33 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23685 | DAC LUC Support and Recompliance | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 39.2641 | 15.52% | 145.3% | -9.852e-05% | 0 | 3.23% | 2180000 | 338330.59 | 1841669.41 | 46904.69 | 0 | 0 | 0 | 491428 | 91.04 | -120333.41 | 589714 | -0.33333 | 0 | 288001.2 | 301712.4 | 0 | 0 | 30% | 33.23% | 33.23% | 3.23% |  | 58.82 | [5 empty] | 32764
1731 | 2024-03-28 00:37 | P23437 | Embedded Software Engineer | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 1.3156 | 98.73% | 100% | 85.98% | 0 | -6.29% | 150150 | 148239.36 | 1910.64 | 1452.25 | 737.86 | 737.86 | 0 | 148239.36 | 66.53 | 0 | 24932 | 127462.6933 | 6970.8 | 17960.7 | 0 | 0 | 0 | 22% | 15.71% | 16.24% | -5.76% |  | 78.5 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23432 | Spirit Belfast MRB On-Site Support (Mon & Clear) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 65.77% | 128.6% | 103.8% | 0 | -11.53% | 449545 | 295665.27 | 153879.73 | 0 | 295665.27 | 451827.33 | 0 | 380234.75 | 120831.02 | 27430.52 | 87914 | 306973.0833 | 87914.4 | 0 | 0 | 0 | 0 | 39% | 27.47% | 0% | -39% |  | 0 | [5 empty] | 112000
1731 | 2024-03-28 00:37 | P23023 | Spirit Shorts R Foster/M Gourley | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 23.7333 | 82.45% | 100.9% | 86.47% | 28129.27 | -20.69% | 480221.04 | 395949.88 | 84271.16 | 3550.75 | 229061.5 | 267726 | 0 | 399408 | 91.04 | 11052.88 | 68455 | 342362.1667 | 19120.72 | 21204.59 | 28129.27 | 0 | 28129.27 | 27% | 6.31% | 3.38% | -23.62% |  | 29.6 | [5 empty] | 14511
1731 | 2024-03-28 00:37 | P23585 | Systems Design - Missile Systems, Meteor,Brimstone | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 | 0 | 0 | 0 | 49500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23554 | Dornier Seawings 328 2023 H2 Support | Steven Lawton | DAX | EXPLEO GERMANY GMBH (EC) | MPE | Level 2 | REIM |  |  |  | 8.6376 | 88.13% | 89.4% | 85.32% | 21955.08 | 6.6% | 508481.81 | 448123.07 | 60358.74 | 6987.89 | 4046.44 | 4046.44 | 0 | 400640 | 64.11 | 47483.07 | 21955 | 382344.1667 | 21955.08 | 0 | 0 | 0 | 21955.08 | 21% | 27.6% | 25.02% | 4.02% |  | 66.56 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23531 | BAe Systems F35 MRB Support | Andrew Houghton | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | -37.8688 |  | 96.18% | 69.58% | 0 | 3.19% | 0 | 450249.06 | -450249.06 | 11889.71 | 287.44 | 287.44 | 0 | 433032.73 | 86.77 | 17216.33 | 143699 | 313283.5633 | 143698.75 | 0 | 0 | 0 | 0 | 25% | 28.19% | 32.05% | 7.05% |  | 59.72 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P22906 | Spirit Shorts - MRB JD Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 8.8538 | 92.84% | 86.46% | 67.93% | 99451.32 | -7.74% | 481714 | 447239.68 | 34474.32 | 3893.75 | 0 | 0 | 0 | 386687.62 | 298.85 | 68552.06 | 99451 | 303811.7867 | 0 | 0 | 85953.72 | 13497.6 | 99451.32 | 13% | 5.26% | 3.11% | -9.89% |  | 36.9 | [5 empty] | 8000
1731 | 2024-03-28 00:37 | P23372 | BAE Carbon Tooling Off-load | Gary Kempster | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  |  | 100.5% | 95.27% | 56.3% | 0 | -1.13% | 454982.37 | 457433.31 | -2450.94 | 0 | 0 | 0 | 19196.43 | 435785.94 | 3010.28 | 21647.37 | 213917 | 257521.7733 | 213917.24 | 0 | 0 | 0 | 0 | 24% | 22.87% | 20.94% | -3.06% |  | 53.57 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23667 | Safety Systems Engineer | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 60.113 | 38.53% | 89.38% | 78.77% | 0 | -9.61% | 398000 | 153340 | 244660 | 4070 | 0 | 0 | 0 | 137060 | 61.78 | 16280 | 19536 | 120780 | 0 | 19536 | 0 | 0 | 0 | 47% | 37.39% | 29.32% | -17.68% |  | 110 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23694 | Systems Portfolio EXP-011a | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 7.6462 | 71.18% | 78.59% | 62.02% | 0 | 2.38% | 648492.8 | 461598.88 | 186893.92 | 24442.63 | 157.75 | 157.75 | 0 | 362778.8 | 60.26 | 98820.08 | 91787 | 286289.6333 | 0 | 91786.96 | 0 | 0 | 0 | 21% | 23.38% | 19.42% | -1.58% |  | 89.16 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23140 | Spirit Shorts A220 MLG Stress Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  | 34.4477 | 71.42% | 81.65% | 72.78% | 0 | -8.68% | 636032.4 | 454227.52 | 181804.88 | 5277.71 | 20870.3 | 87811.88 | 0 | 370857.4 | 227.77 | 108370.12 | 48343 | 330571.5667 | 48343.2 | 0 | 0 | 0 | 0 | 25% | 16.32% | 11.66% | -13.34% |  | 47.35 | [5 empty] | 25000
1731 | 2024-03-28 00:37 | P22652 | L3 - Saftey Engineering | Sean Simmons | LHW | L3HARRIS MAPPS LIMITED | EES | Level NC | FIX |  |  |  |  | 95.63% | 86.69% | 86.69% | 0 | 5.66% | 523390 | 500497.5 | 22892.5 | 0 | 0 | 0 | 0 | 433882.5 | 79938 | 66615 | 0 | 433882.5 | 0 | 0 | 0 | 0 | 0 | 21% | 26.66% | 25.88% | 4.88% |  | 83.05 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23366 | Business Analyst Support | Peter Williams | BDZ | MBDA UK LIMITED | DET | Level 3 | REIM |  |  |  | 74.7558 | 16.96% | 255.4% | 194.4% | 0 | 12.91% | 1302200 | 220853.83 | 1081346.17 | 14465.05 | 220853.47 | 416921.86 | 0 | 564160 | 81.57 | -60171.17 | 161856 | 429280 | 81792 | 80064 | 0 | 0 | 0 | 43% | 55.91% | 39.76% | -3.24% |  | 0.01 | [5 empty] | 283135
1731 | 2024-03-28 00:37 | P23473 | Tempest Vertical Tail | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 20.6719 | 70.16% | 97.11% | 77.42% | 0 | -2.51% | 723866.48 | 507858.71 | 216007.77 | 10449.32 | 91875 | 100425 | 0 | 493182.93 | 78.16 | 14675.78 | 120007 | 393177.0967 | 61517.7 | 58489.72 | 0 | 0 | 0 | 24% | 21.49% | 24.21% | 0.21% |  | 62.38 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23281 | Systems Portfolio | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM | 2024-02-28 | 2 |  | -3239.9024 | 44.43% | 97.31% | 97.19% | 0 | -17.25% | 1177697.24 | 523236.96 | 654460.28 | -202 | 2133.28 | 2133.28 | 0 | 509179.87 | 16553.63 | 13160.09 | 762 | 508544.87 | 0 | 761.53 | 0 | 0 | 0 | 25% | 7.75% | 100% | 75% |  | 70.48 | [5 empty] | -897
1731 | 2024-03-28 00:37 | P23001 | Spirit Shorts A220 Design | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -21.0426 | 114.4% | 73.72% | 69.12% | 0 | -4.22% | 463100 | 529746 | -66646 | 3167.2 | 0 | 0 | 65953.2 | 390511.7 | 381.17 | 139234.3 | 29237 | 366147.5333 | 29236.68 | 0 | 0 | 0 | 0 | 25% | 20.78% | 11.7% | -13.3% |  | 43.59 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23323 | CNC-CMM Programming Support | Andrew Houghton | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | 5.3055 | 91.18% | 90.96% | 64.45% | 0 | -2.79% | 617809.74 | 563347.11 | 54462.63 | 10265.28 | 15941.56 | 15941.56 | 0 | 512445.08 | 157.45 | 50902.03 | 179242 | 363076.7467 | 102286.46 | 76955.66 | 0 | 0 | 0 | 32% | 29.21% | 37.43% | 5.43% |  | 57.18 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23045 | Shotgun Adaptors - 10 Sets | Harry James Kellett | BDW | MBDA UK LIMITED | EES | Level 2 | FIX | 2024-02-27 | 7 |  | 4.3339 | 74.76% | 133.8% | 95.11% | 0 | 2.29% | 399276.11 | 298512.88 | 100763.23 | 23250 | 214550.47 | 214550.47 | 0 | 399276.11 | 47356.35 | -7763.23 | 138421 | 283925.2767 | 0 | 138420.73 | 0 | 0 | 0 | 29% | 31.29% | 99.78% | 70.78% |  | 55.76 | [5 empty] | 93000
1731 | 2024-03-28 00:37 | P23219 | Tornado Air 800 Engineering Support | Richard Brook | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 3 | REIM |  |  |  | -27.204 | 96.34% | 97.61% | 97.61% | 0 | 0.5% | 615046 | 592509.68 | 22536.32 | -828.42 | 459.21 | 459.21 | 0 | 578373.17 | 91 | 5411.51 | 0 | 578373.17 | 0 | 0 | 0 | 0 | 0 | 31% | 31.5% | 200.4% | 169.4% |  | 81.74 | [5 empty] | -8725
1731 | 2024-03-28 00:37 | P23605 | Typhoon Work Package 2 Continuation | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM |  |  |  | -607.5364 | 119.8% | 81.03% | -4.845e-05% | 0 | 5.21% | 545536.01 | 653604.59 | -108068.58 | 177.88 | 4054 | 4054 | 81999.09 | 529626.35 | 367.71 | 123978.24 | 635552 | -0.31667 | 317677.15 | 317874.46 | 0 | 0 | 0 | 23% | 28.21% | 29.02% | 6.02% |  | 55.82 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P22790 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 2 | REIM | 2024-03-18 | 0 |  |  | 194.5% | 90.44% | 90.44% | 0 | 1.37% | 352240 | 685262.25 | -333022.25 | 0 | 1611.52 | 1611.52 | 515246 | 619743.88 | 41098.04 | 34248.37 | 0 | 619743.88 | 0 | 0 | 0 | 0 | 0 | 13% | 14.37% | 0% | -13% |  | 45.06 | [5 empty] | -31270
1731 | 2024-03-28 00:37 | P23426 | BAE Tempest WP 3 Harness Maturation | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 11.9054 | 75.67% | 88.47% | 69.9% | 0 | -5.93% | 884012.04 | 668930.48 | 215081.56 | 18065.84 | 213.34 | 213.34 | 0 | 591770.47 | 90.92 | 77160.01 | 149014 | 467592.1367 | 82448.95 | 66565.09 | 0 | 0 | 0 | 33% | 27.07% | 28.12% | -4.88% |  | 51.38 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23602 | EXP-025 Portfolio Software Engineering Support | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 19.6003 | 52.97% | 81.89% | 64.34% | 0 | -0.69% | 1327080 | 703009.93 | 624070.07 | 31839.78 | 2113.5 | 2577.61 | 0 | 575685.84 | 66.97 | 127324.09 | 148074 | 452290.84 | 0 | 148074.11 | 0 | 0 | 0 | 24% | 23.31% | 23.2% | -0.8% |  | 83.16 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23451 | BAE Tempest - DFM-ASO Planning | Andrew Houghton | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | 7.711 | 83.41% | 72.61% | 48.71% | 27224.9 | -3.21% | 953905.42 | 795604.98 | 158300.44 | 20529.1 | 0 | 0 | 0 | 577706.94 | 145.16 | 217898.04 | 228231 | 387514.44 | 201006.13 | 0 | 27224.9 | 0 | 27224.9 | 28% | 24.79% | 26.77% | -1.23% |  | 53.61 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23321 | EHM Cloud Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX | 2024-01-29 | 0 |  |  | 89.76% | 111.4% | 111.4% | 0 | 2.92% | 839969 | 753974.58 | 85994.42 | 0 | 0 | 0 | 0 | 839969 | 0 | -0.42 | 0 | 839969 | 0 | 0 | 0 | 0 | 0 | 28% | 30.92% | 57.47% | 29.47% |  | 49.95 | [5 empty] | 85994
1731 | 2024-03-28 00:37 | P23105 | Raytheon Supply Engineering Support | Natalie Sinclair | RAY | RAYTHEON UNITED KINGDOM LIMITED | MPE | Level 3A | REIM | 2023-07-13 | 2 |  |  | 76.96% | 94.49% | 90.07% | 49156.8 | -2.02% | 1205008 | 927395.25 | 277612.75 | 0 | 0 | 0 | 0 | 876291.5 | 107644.5 | 48739.75 | 49157 | 835327.3333 | 0 | 0 | 49156.8 | 0 | 49156.8 | 26% | 23.98% | 100% | 74% |  | 48.97 | [5 empty] | -2364
1731 | 2024-03-28 00:37 | P22350 | EMP 2020-2021 | Natalie Sinclair | ARY | GUIDANT GROUP (trading name) | PCPR | Level NC | REIM |  |  |  | 5.8945 | 96.16% | 98.18% | 93.62% | 0 | -2.12% | 1017579.76 | 978466.75 | 39113.01 | 6635.54 | 400 | 400 | 0 | 960667.18 | 72.13 | 17799.57 | 53579 | 916018.0133 | 21769.52 | 31809.66 | 0 | 0 | 0 | 32% | 29.88% | 26.83% | -5.17% |  | 44.1 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23117 | BAE Typhoon Eng Support | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | 2024-03-12 | 11 |  |  | 107.6% | 92.94% | 88.52% | 0 | -1.44% | 950771.99 | 1022826.17 | -72054.18 | 0 | 19090.01 | 21165.02 | 69773.84 | 950609.41 | 108434.62 | 45120.76 | 54290 | 905367.7433 | 54289.71 | 0 | 0 | 0 | 0 | 30% | 28.56% | 0% | -30% |  | 52.3 | [5 empty] | -27096
1731 | 2024-03-28 00:37 | P22671 | Spirit Shorts Pylon and Fairing Package | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX | 2023-05-03 | 0 |  |  | 105% | 95.26% | 95.26% | 0 | -7.21% | 1198494.77 | 1258071.09 | -59576.32 | 0 | 106494.89 | 106494.89 | 0 | 1198494.77 | 2544.39 | 2120.32 | 0 | 1198494.77 | 0 | 0 | 0 | 0 | 0 | 20% | 12.79% | 0% | -20% |  | 45.4 | [5 empty] | -57456
1731 | 2024-03-28 00:37 | P22918 | Spirit Shorts Graduates | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 10.8423 | 87.61% | 93.71% | 61.77% | 0 | 9.77% | 130000 | 113897.39 | 16102.61 | 1485.16 | 0 | 0 | 9900 | 106734.95 | 221.75 | 7162.44 | 43660 | 70351.6167 | 0 | 43659.95 | 0 | 0 | 0 | 7% | 16.77% | 19.09% | 12.09% |  | 23.29 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23152 | Project Aragon - Design and Stress Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 4.9809 | 95.26% | 57.42% | 57.42% | 0 | -9.53% | 1333452.21 | 1270207.33 | 63244.88 | 12697.36 | 0 | 0 | 0 | 729295.96 | 325.03 | 540911.37 | 0 | 729295.96 | 0 | 0 | 0 | 0 | 0 | 39% | 29.47% | 29.32% | -9.68% |  | 51.93 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23464 | A220 Project X Design Offload | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 52.9747 | 50.79% | 92.69% | 65.21% | 27862.8 | -9.18% | 332340 | 168809.7 | 163530.3 | 3086.95 | 0 | 0 | 0 | 156461.9 | 150.51 | 12347.8 | 55649 | 110087.7333 | 27785.76 | 0 | 0 | 27862.8 | 27862.8 | 26% | 16.82% | 15.18% | -10.82% |  | 42.88 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23411 | Agile & Scrum Delivery Service | Peter Williams | BDZ | MBDA UK LIMITED | DET | Level 2 | REIM | 2023-08-14 | 0 |  |  | 36.3% | 170.5% | 170.5% | 0 | 13.08% | 2487000 | 902903.79 | 1584096.21 | 0 | 894178.59 | 894178.59 | 0 | 1539600 | 19368.95 | 16140.79 | 0 | 1539600 | 0 | 0 | 0 | 0 | 0 | 29% | 42.08% | 0% | -29% |  | 74.57 | [5 empty] | 652837
1731 | 2024-03-28 00:37 | P23315 | DAC LUC BAU and Service Workbench | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX | 2024-02-16 | 1 |  | 70.5463 | 85.17% | 117.4% | 117.4% | 0 | 3.85% | 1573630 | 1340192.3 | 233437.7 | 3309 | 180.3 | 180.3 | 0 | 1573630 | 0 | 0.3 | 0 | 1573630 | 0 | 0 | 0 | 0 | 0 | 28% | 31.85% | 47.32% | 19.32% |  | 52.35 | [5 empty] | 233438
1731 | 2024-03-28 00:37 | P23435 | Andy Baker Portfolio | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 27.8049 | 56.11% | 100% | 71.66% | 0 | -7.24% | 3377457.4 | 1894944.99 | 1482512.41 | 53318.47 | 2352.57 | 2352.57 | 0 | 1894945.09 | 83.8 | -0.1 | 644345 | 1357990.9233 | 489604.46 | 154740.27 | 0 | 0 | 0 | 25% | 17.76% | 20.21% | -4.79% |  | 80.15 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23006 | Spirit Shorts A350 Freighter Toulouse | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -33.6891 | 153.6% | 99.25% | 77.65% | 0 | 19.37% | 1035745.92 | 1590650.3 | -554904.38 | 16471.35 | 1086670.26 | 1708220.2 | 0 | 1578683.21 | 318.2 | 323241.09 | 412299 | 1235100.71 | 412298.62 | 0 | 0 | 0 | 0 | 5% | 24.37% | 35.86% | 30.86% |  | 47.97 | [5 empty] | 311274
1731 | 2024-03-28 00:37 | P22278 | TAI Supply Engineers to Ankara | Natalie Sinclair | TAI | TUSAS-TURK HAVACILIK VE UZAY | MPE | Level 3A | REIM |  |  |  | 421.3262 | 19.48% | 465.9% | 465.9% | 0 | -15.61% | 2105282 | 410075.91 | 1695206.09 | 4023.5 | 49400.29 | 49400.29 | 0 | 1910696.33 | 31.07 | 4439.58 | 0 | 1910696.33 | 0 | 0 | 0 | 0 | 0 | 95% | 79.39% | 71.28% | -23.72% |  | 34.21 | [5 empty] | 1505060
1731 | 2024-03-28 00:37 | P23175 | BAe Aero Typhoon Package 2 | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM | 2024-03-12 | 2 |  |  | 103.8% | 96.32% | 96.32% | 0 | -1.63% | 1984265.09 | 2060011.83 | -75746.74 | 0 | 57677.87 | 86030.82 | 15444.64 | 1984257.03 | 84731.75 | 70609.8 | 0 | 1984257.03 | 0 | 0 | 0 | 0 | 0 | 29% | 27.37% | 0% | -29% |  | 51.76 | [5 empty] | -5145
1731 | 2024-03-28 00:37 | P23257 | BAE Tempest WP 5 Centre Fuselage | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | -0.32621 | 100.3% | 98.53% | 90.67% | 0 | -5.71% | 2106860.71 | 2112661.54 | -5800.83 | 17782.51 | 78100 | 78100 | 0 | 2081529.48 | 81.47 | 31132.06 | 199124 | 1915592.8133 | 110362.14 | 88762 | 0 | 0 | 0 | 33% | 27.29% | 28.63% | -4.37% |  | 61.06 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P19020 | Spirit Concessions - 2018 | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2024-01-23 | 3 |  |  | 90.82% | 111.8% | 107% | 99792.83 | 2.09% | 1914846.83 | 1739018.14 | 175828.69 | 0 | 44317.61 | 44317.61 | 15178.88 | 1944710.76 | 7454.23 | 196987.38 | 99793 | 1861549.9267 | 0 | 0 | 0 | 99792.83 | 99792.83 | 25% | 27.09% | 9.32% | -15.68% |  | 40.87 | [5 empty] | 402680
1731 | 2024-03-28 00:37 | P23207 | A350 Approvers - Design and Stress Support | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  | 5.8268 | 87.08% | 91.49% | 52.85% | 341012.63 | -4.56% | 2728308 | 2375674.88 | 352633.12 | 60519.21 | 28782.95 | 29418.7 | 0 | 2173467.84 | 143.5 | 202207.04 | 1101376 | 1255654.5067 | 189658.31 | 570705.26 | 341012.63 | 0 | 341012.63 | 23% | 18.44% | 18.62% | -4.38% |  | 54.71 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P23179 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX |  |  |  | -189.6784 | 127.3% | 94.88% | 81.83% | 9496.08 | -9.33% | 1996985.84 | 2542500.98 | -545515.14 | 2876 | 156991.12 | 248243.92 | 100000 | 2412235.69 | 517.04 | 130265.29 | 398043 | 2080533.19 | 248280.21 | 140266.99 | 9496.08 | 0 | 9496.08 | 22% | 12.67% | 16.79% | -5.21% |  | 44.4 | [5 empty] | 0
1731 | 2024-03-28 00:37 | P19731 | Hapri HPC Rear Bearing Housing PDR & CDR | Steven Lawton | ATC | AECC Hunan Aviation Powerplant | MPE | Level 1 | FIX |  |  |  | 5.5425 | 99.86% | 100.1% | 87.62% | 447000 | -15.39% | 2980000 | 2975827.47 | 4172.53 | 752.83 | 363828.33 | 497928.33 | 0 | 2980000 | 1017.11 | -229172.53 | 447000 | 2607500 | 0 | 0 | 0 | 447000 | 447000 | 38% | 22.61% | 13.77% | -24.23% |  | 64.86 | [5 empty] | -225000
1731 | 2024-03-28 00:37 | P23487 | Tornado Air 800 Engineering Support | Richard Brook | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 2 | FIX |  |  |  | 2.1726 | 95.25% | 90.07% | 74.69% | 30074.38 | -3.5% | 3049066.2 | 2904338.35 | 144727.85 | 66613.68 | 0 | 0 | 0 | 2616021.67 | 97.9 | 315316.68 | 536252 | 2169145.0033 | 380756.59 | 125420.63 | 30074.38 | 0 | 30074.38 | 40% | 36.5% | 40.67% | 0.67% |  | 78.71 | [5 empty] | 27000
Extend Table

## AP3-5
WIP No | Date Created | Project ID | Project Description | Project Manager | Department Id | Client | CBU | Complexity | Type | Stop Booking Hrs | Closing Project: Action(s) to close | RAG | Approx. PO Burndown (weeks) | Turnover vs Contract Value | Invoice To Date vs Turnover | Cash in vs Turnover | Open Amount Overdue | Actual PM% to Baseline PM% delta | Contract Value | Total Project Turnover | Contract Value - Total Turnover | Run Rate (based on total turnover) | Total BOI Spend to Date | Total Committed PO (supplier/best shore) | Current AA in PT3 | Invoiced To Date | DSO | Unbilled (WIP) | Total Open Amount | Cash in (Invoiced - (Open amount -VAT)) | Debt <=30 Days | Debt 31 - 60 Days | Debt 61 - 90 Days | Debt >= 90 Days | Open Amount Overdue2 | Baseline Project Margin | Project To Date (PTD) PM | Year to Date (YTD) PM | YTD Delta Actual PM% to BPM% | Forecast PM at Completion (Manual input from PTT) | Average Sale Rate | CSat score for last quarter (Manual input from PTT) | Comments and Actions | Judged income adjustment at completion | Profit to take now | Provision required now | Fully Traded | Last Months Comments and Actions
1732 | 2024-04-03 23:37 | P23175 | BAe Aero Typhoon Package 2 | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM | 2024-03-12 | 2 |  |  | 103.8% | 96.32% | 96.32% | 0 | -1.63% | 1984265.09 | 2060011.83 | -75746.74 | 0 | 57677.87 | 86030.82 | 15444.64 | 1984257.03 | 84731.75 | 70609.8 | 0 | 1984257.03 | 0 | 0 | 0 | 0 | 0 | 29% | 27.37% | 0% | -29% |  | 51.76 | [5 empty] | -5145
1732 | 2024-04-03 23:37 | P19020 | Spirit Concessions - 2018 | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2024-01-23 | 3 |  |  | 90.82% | 111.8% | 107% | 99792.83 | 2.09% | 1914846.83 | 1739018.14 | 175828.69 | 0 | 44317.61 | 44317.61 | 15178.88 | 1944710.76 | 7454.23 | 196987.38 | 99793 | 1861549.9267 | 0 | 0 | 0 | 99792.83 | 99792.83 | 25% | 27.09% | 9.32% | -15.68% |  | 40.87 | [5 empty] | 402680
1732 | 2024-04-03 23:37 | P23711 | DO NOT USE - RAISED IN ERROR | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23717 | GKN Ted Tomblin 2024 | Matthew Tweed | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 10047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23506 | ASTER Mid-Life Refurbishment Project Manager | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 8.0009 | 86.35% | 89.97% | 80.15% | 0 | 1.04% | 224900 | 194206.41 | 30693.59 | 3836.25 | 2806.41 | 2806.41 | 0 | 174736.41 | 66.88 | 19470 | 22897 | 155655.5767 | 0 | 22896.62 | 0 | 0 | 0 | 25% | 26.04% | 26.35% | 1.35% |  | 110 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23001 | Spirit Shorts A220 Design | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -22.0426 | 115.1% | 74.76% | 68.71% | 0 | -4.28% | 463100 | 532913.2 | -69813.2 | 3167.2 | 0 | 0 | 65953.2 | 398429.7 | 359.41 | 134483.5 | 38738 | 366148.0333 | 38738.28 | 0 | 0 | 0 | 0 | 25% | 20.72% | 11.64% | -13.36% |  | 43.59 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23437 | Embedded Software Engineer | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 2.6313 | 98.73% | 100% | 85.98% | 0 | -6.29% | 150150 | 148239.36 | 1910.64 | 726.13 | 737.86 | 737.86 | 0 | 148239.36 | 66.53 | 0 | 24932 | 127462.6933 | 6970.8 | 17960.7 | 0 | 0 | 0 | 22% | 15.71% | 16.24% | -5.76% |  | 78.5 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23842 | Tranche 1 Evolution Package Step 2 | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -2 |  | 0% | 0% | 0 | 3.68% | 0 | 229.56 | -229.56 | 114.78 | 0 | 0 | 67488.9 | 0 | 14 | 229.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31% | 34.68% | 34.68% | 3.68% |  | 57.39 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23730 | FLE Project | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -18.03% | 0 | 1120 | -1120 | 0 | 0 | 0 | 24000 | 0 | 90 | 1120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | -18.03% | -18.03% | -18.03% |  | 35 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23463 | A220 Wing MaMo Design Checking | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-03-07 | 0 |  |  |  | 0% | 0% | 0 | 7.85% | 0 | 1628 | -1628 | 0 | 0 | 0 | 15000 | 0 | 1953.6 | 1628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | 10.85% | 0% | -3% |  | 44 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P21028 | Rebate Collection (BACC) | David Catchpole | TOO | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | [5 empty] | 0% | 0% | 0 | 0% | 0 | 2680 | -2680 | 0 | 2680 | 2680 | 0 | 0 | 3216 | 2680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23578 | ESN Work Package | Hannah Mead | COZ | CHELTON LIMITED | DET | Level 3 | FIX | 2024-01-01 | 0 |  |  | 86.17% | 116.1% | 116.1% | 0 | 35.86% | 4410 | 3800 | 610 | 0 | 0 | 0 | 0 | 4410 | 0 | -610 | 0 | 4410 | 0 | 0 | 0 | 0 | 0 | 24% | 59.86% | 0% | -24% |  | 95 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23628 | Design Assurance | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -6.67% | 0 | 3909.24 | -3909.24 | 0 | 0 | 0 | 4454.8 | 0 | 4691.09 | 3909.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 0.33% | 0% | -7% |  | 15.05 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23002 | WoT MAJ Transit Flag Stress | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2024-04-03 | 0 |  |  | 30.89% | 323.8% | 323.8% | 0 | 53.84% | 4735 | 1462.5 | 3272.5 | 0 | 0 | 0 | 0 | 4735 | 0.6 | 0.5 | 0 | 4735 | 0 | 0 | 0 | 0 | 0 | 10% | 63.84% | 0% | -10% |  | 45 | [5 empty] | 3273
1732 | 2024-04-03 23:37 | P23718 | Requalification of EJ200 GSS ESS EHM SW module | Vijayakumara Nanjundappa | ARZ | MTU AERO ENGINES AG | DET | Level 3 | FIX |  |  |  | 210.9484 | 10.02% | 242.9% | 242.9% | 0 | -2.28% | 74463 | 7461.57 | 67001.43 | 317.62 | 991.93 | 991.93 | 0 | 18125 | 0 | -10663.43 | 0 | 18125 | 0 | 0 | 0 | 0 | 0 | 28% | 25.72% | 25.72% | -2.28% |  | 80 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23607 | SAFRAN - A330neo Turnover Frame | Gary Kempster | TOO | SAFRAN SEATS GB LIMITED | MPE | Level 3 | FIX |  |  |  | 3.999 | 95.69% | 104.5% | 104.5% | 0 | -19.52% | 8736 | 8359.05 | 376.95 | 94.26 | 0 | 0 | 0 | 8736 | 0.06 | 0.05 | 0 | 8736 | 0 | 0 | 0 | 0 | 0 | 23% | 3.48% | 8.5% | -14.5% |  | 50.46 | [5 empty] | 377
1732 | 2024-04-03 23:37 | P23274 | ME Support (Aim Altitude - Cambridge) | Trevor Knox | AVI | AVIC CABIN SYSTEMS (UK) LIMITED | ME | Level 3 | FIX | 2023-08-18 | 0 |  |  | 51.88% | 56.3% | 56.3% | 0 | -0.17% | 17280 | 8964 | 8316 | 0 | 0 | 0 | 0 | 5046.3 | 4701.24 | 3917.7 | 0 | 5046.3 | 0 | 0 | 0 | 0 | 0 | 21% | 20.83% | 0% | -21% |  | 48 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23283 | Spirit Tooling Audit | Charidimos Valadakis | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-05-03 | 0 |  |  | 97.22% | 48.57% | 48.57% | 0 | -7.99% | 9910.08 | 9634.8 | 275.28 | 0 | 0 | 0 | 0 | 4679.76 | 5946.05 | 4955.04 | 0 | 4679.76 | 0 | 0 | 0 | 0 | 0 | 7% | -0.99% | 0% | -7% |  | 34.41 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23127 | Loft Hall Design Support | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 101% | 99.06% | 99.06% | 0 | -9.55% | 9680 | 9772 | -92 | 0 | 0 | 0 | 0 | 9680 | 110.4 | 92 | 0 | 9680 | 0 | 0 | 0 | 0 | 0 | 41% | 31.45% | 0% | -41% |  | 44 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23630 | 2Excel CFD Analysis Support | Dushan Fernando | BAX | STIRLING DYNAMICS LTD | MPE | Level NC | FIX |  |  |  |  | 61.2% | 100% | 100% | 0 | -1.87% | 16195.49 | 9911.34 | 6284.15 | 0 | 0 | 0 | 0 | 9911.63 | 0 | -0.29 | 0 | 9911.63 | 0 | 0 | 0 | 0 | 0 | 26% | 24.13% | 0% | -26% |  | 64.78 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23313 | Laser Trim Fixtures | Gary Kempster | TOO | ALKEN ENGINEERING LIMITED | MPE | Level 3 | FIX | 2023-11-20 | 0 |  |  | 89.87% | 111.3% | 111.3% | 0 | 0.53% | 13770 | 12375 | 1395 | 0 | 0 | 0 | 0 | 13770 | 0 | -1395 | 0 | 13770 | 0 | 0 | 0 | 0 | 0 | 17% | 17.53% | 0% | -17% |  | 45 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P22761 | Red Bull Chassis Spit | Trevor Knox | TOO | MANUFAX ENGINEERING LTD | MPE | Level 3 | FIX | 2022-11-15 | 0 |  |  | 72.18% | 96.98% | 96.98% | 0 | 7.92% | 12961.2 | 9355.5 | 3605.7 | 0 | 0 | 0 | 0 | 9072.84 | 4666.39 | 3888.66 | 0 | 9072.84 | 0 | 0 | 0 | 0 | 0 | 23% | 30.92% | 0% | -23% |  | 42.19 | [5 empty] | 3606
1732 | 2024-04-03 23:37 | P23433 | Cavendish | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 32.81% | 100% | 100% | 0 | -0.34% | 42240 | 13859.2 | 28380.8 | 0 | 0 | 0 | 0 | 13859.2 | 0 | 0 | 0 | 13859.2 | 0 | 0 | 0 | 0 | 0 | 7% | 6.66% | 0% | -7% |  | 43.93 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23617 | Tempest Composites WP2 | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -16.0778 | 131.7% | 25.62% | 17.97% | 29536.68 | 11.7% | 244405.26 | 321867.9 | -77462.64 | 4817.99 | 0 | 0 | 77669.2 | 82447.45 | 272.78 | 239420.45 | 29537 | 57833.2833 | 0 | 0 | 0 | 29536.68 | 29536.68 | 22% | 33.7% | 33.41% | 11.41% |  | 62.17 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23344 | Spirit A320 Spoilers Support 2023 | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 38.75% | 100% | 100% | 0 | 5.82% | 35786.4 | 13867.23 | 21919.17 | 0 | 0 | 0 | 0 | 13867.23 | 0 | 0 | 0 | 13867.23 | 0 | 0 | 0 | 0 | 0 | 7% | 12.82% | 0% | -7% |  | 34.41 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23337 | Spirit 2023 - Steve Grimley | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 25.28% | 100% | 100% | 0 | 0.01% | 56812.9 | 14362.47 | 42450.43 | 0 | 0 | 0 | 0 | 14362.47 | 0 | 0 | 0 | 14362.47 | 0 | 0 | 0 | 0 | 0 | 7% | 7.01% | 0% | -7% |  | 30.11 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23597 | MRB Onsite support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-02-16 | 1 |  |  |  | 0% | 0% | 0 | -10.04% | 0 | 15100.57 | -15100.57 | 0 | 9448.07 | 17381.62 | 24200 | 0 | 102.4 | 15100.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 7.96% | 8.95% | -9.05% |  | 42.5 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23831 | Contract DM/00113 for maintenance, repair and post | Harry James Kellett | BXW | MOD | EES | Level 2 | FIX |  |  |  | 5.8469 | 40.62% | 0% | 0% | 0 | 15.43% | 40800 | 16573.69 | 24226.31 | 4143.42 | 0 | 0 | 0 | 0 | 91 | 16573.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37% | 52.43% | 52.43% | 15.43% |  | 80.26 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23742 | Cyber Security Support | Hannah Mead | COZ | CHELTON LIMITED | DET | Level 3 | FIX |  |  |  | -7.6 |  | 0% | 0% | 0 | 31.04% | 0 | 17100 | -17100 | 2250 | 0 | 0 | 27500 | 0 | 91 | 17100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 31.04% | 31.04% | 31.04% |  | 100 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23663 | Spirit Tooling Verification and Inspection | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 3.25 | 86.46% | 38.55% | 0.0003112% | 0 | -7.46% | 19820.16 | 17136.18 | 2683.98 | 825.84 | 0 | 0 | 7392 | 6606.72 | 148.1 | 10529.46 | 7928 | 0.053333 | 7928.06 | 0 | 0 | 0 | 0 | 12% | 4.54% | 4.82% | -7.18% |  | 34.41 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23635 | Engineering Services: FAI Support | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 49.9% | 68.33% | 0.001436% | 0 | -3.4% | 37230 | 18576 | 18654 | 0 | 0 | 0 | 0 | 12693.6 | 287.37 | 5882.4 | 15232 | 0.26667 | 15232.32 | 0 | 0 | 0 | 0 | 8% | 4.6% | 5.04% | -2.96% |  | 38.7 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23343 | Spirit 2023 - John Agnew | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-08-09 | 0 |  |  | 28.56% | 86.27% | 86.27% | 0 | -0.02% | 65120.37 | 18600.89 | 46519.48 | 0 | 0 | 0 | 0 | 16047.15 | 3064.49 | 2553.74 | 0 | 16047.15 | 0 | 0 | 0 | 0 | 0 | 7% | 6.98% | 0% | -7% |  | 34.51 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23839 | Stirling Dynamics - ST002-GFEM | Carrie (Caroline)Rosemary Frosin | BAX | STIRLING DYNAMICS LTD | MPE | Level NC | FIX |  |  |  | -2 |  | 0% | 0% | 0 | -5.68% | 0 | 18628.7 | -18628.7 | 9314.35 | 0 | 0 | 19985.76 | 0 | 70 | 18628.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 1.32% | 1.32% | -5.68% |  | 43.32 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23740 | Phase 2 - EJ200 ESS EHM Platform Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 3 | FIX |  |  |  | 56.0219 | 10.01% | 285.5% | -0.001893% | 0 | 7.65% | 175971 | 17611 | 158360 | 2826.75 | 0 | 0 | 0 | 50278 | 100.22 | -30667 | 60334 | -0.33333 | 30166.8 | 0 | 30166.8 | 0 | 0 | 28% | 35.65% | 35.65% | 7.65% |  | 46.53 | [5 empty] | 2000
1732 | 2024-04-03 23:37 | P23823 | EXP-034 Spear 3 Test Equip Requirement Authority | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 21.625 | 23.12% | 90.97% | -0.001445% | 0 | 0.32% | 85825 | 19839.63 | 65985.37 | 3051.35 | 0 | 0 | 0 | 18048.88 | 49 | 1790.75 | 21659 | -0.28667 | 21658.66 | 0 | 0 | 0 | 0 | 14% | 14.32% | 14.32% | 0.32% |  | 94.25 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23355 | Spirit Tooling Support 2023 | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-23 | 0 |  |  | 22.93% | 89.02% | 89.02% | 0 | -0.82% | 91800 | 21053.34 | 70746.66 | 0 | 0 | 0 | 0 | 18742.5 | 2773.01 | 2310.84 | 0 | 18742.5 | 0 | 0 | 0 | 0 | 0 | 20% | 19.18% | 0% | -20% |  | 44.46 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23811 | Spirit T300 MRB Concessions | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -6.8753 |  | 0% | 0% | 0 | -7.16% | 0 | 21098.67 | -21098.67 | 3068.75 | 0 | 0 | 34639 | 0 | 49 | 21098.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21% | 13.84% | 13.84% | -7.16% |  | 46.81 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23724 | GKN S McConnell 2024 | Matthew Tweed | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  | 14.8811 | 46.8% | 61.54% | -0.0007434% | 0 | 0.61% | 49820 | 23315.79 | 26504.21 | 1781.07 | 0 | 0 | 0 | 14348.16 | 90 | 8967.63 | 17218 | -0.17333 | 0 | 17217.79 | 0 | 0 | 0 | 19% | 19.61% | 19.61% | 0.61% |  | 49.5 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23351 | Spirit 2023 - Design Man Serv (KL) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 26.47% | 93.15% | 93.15% | 0 | 0.09% | 93840 | 24840 | 69000 | 0 | 0 | 0 | 0 | 23138 | 2042.4 | 1702 | 0 | 23138 | 0 | 0 | 0 | 0 | 0 | 26% | 26.09% | 0% | -26% |  | 46 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23356 | Spirit 2023 - Design Man Serv (AH) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX | 2023-08-09 | 1 |  |  |  | 76.66% | 0.001332% | 23018.4 | 0.48% | 0 | 25023.08 | -25023.08 | 0 | 0 | 0 | 25300 | 19182 | 30027.7 | 5841.08 | 23018 | 0.33333 | 0 | 0 | 0 | 23018.4 | 23018.4 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P22884 | Spirit Shorts Config Eng | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 66.3% | 100.1% | 100.1% | 0 | 0.56% | 38976 | 25841.9 | 13134.1 | 0 | 0 | 0 | 0 | 25863.2 | 0 | -0.3 | 0 | 25863.2 | 0 | 0 | 0 | 0 | 0 | 7% | 7.56% | 0% | -7% |  | 20.3 | [5 empty] | 21
1732 | 2024-04-03 23:37 | P23354 | Spirit 2023 - Design Man Serv (PC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 27.97% | 99.36% | 99.36% | 0 | 0.48% | 93840 | 26248.98 | 67591.02 | 0 | 0 | 0 | 0 | 26082 | 200.38 | 166.98 | 0 | 26082 | 0 | 0 | 0 | 0 | 0 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23651 | PMO Spirit | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -30.6087 |  | 82.26% | -0.0005845% | 0 | 23.84% | 0 | 28512 | -28512 | 931.5 | 0 | 0 | 42680 | 23454 | 205.04 | 5058 | 28145 | -0.16667 | 28144.8 | 0 | 0 | 0 | 0 | 0% | 23.84% | 23.17% | 23.17% |  | 36 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P22756 | A350 FLE Design Checker | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2022-03-23 | 1 |  |  | 68.39% | 119.7% | 119.7% | 0 | 16.46% | 34898.4 | 23867.15 | 11031.25 | 0 | 23867.15 | 24342.3 | 0 | 28571.1 | 0.06 | 0.05 | 0 | 28571.1 | 0 | 0 | 0 | 0 | 0 | 0% | 16.46% | 0% | 0% |  | 0 | [5 empty] | 4704
1732 | 2024-04-03 23:37 | P23458 | Spirit Belfast Tooling Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-08-11 | 0 |  |  | 101.3% | 94.65% | 94.65% | 0 | 8.64% | 30384 | 30784.9 | -400.9 | 0 | 0 | 0 | 0 | 29139.1 | 1974.96 | 1645.8 | 0 | 29139.1 | 0 | 0 | 0 | 0 | 0 | 7% | 15.64% | 0% | -7% |  | 42.2 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23008 | Spirit Shorts Project Rachel | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 85.87% | 91.32% | 91.32% | 0 | -7.7% | 228880 | 196531.2 | 32348.8 | 0 | 0 | 0 | 0 | 179472.8 | 1034.6 | 17058.4 | 0 | 179472.8 | 0 | 0 | 0 | 0 | 0 | 13% | 5.3% | 0.31% | -12.69% |  | 46.04 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23365 | GKN 777x Lip Skin Fixture | Steven Lawton | TOO | GKN AEROSPACE SERVICES LTD | MPE | Level 3 | FIX | 2023-10-12 | 0 |  |  | 41.91% | 113.2% | 113.2% | 0 | -9.26% | 79161.46 | 33175.67 | 45985.79 | 0 | 5109.88 | 5109.88 | 0 | 37544.22 | 0 | -4368.55 | 0 | 37544.22 | 0 | 0 | 0 | 0 | 0 | 22% | 12.74% | 0% | -22% |  | 56 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23821 | Supply of Safety Engineer | Dinna Elkhalifa | BXW | STIRLING DYNAMICS LTD | EES | Level NC | REIM |  |  |  | 0.019137 | 99.71% | 55.95% | -0.0003441% | 0 | 45.1% | 34006.44 | 33906.6 | 99.84 | 5217.2 | 0 | 0 | 0 | 18971.55 | 91 | 14935.05 | 22766 | -0.11667 | 22765.86 | 0 | 0 | 0 | 0 | 0% | 45.1% | 45.1% | 45.1% |  | 80.73 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P22768 | MRB Onsite Support - Spirit Belfast | Trevor Knox | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2023-07-27 | 0 |  |  |  | 0% | 0% | 0 | -17.07% | 0 | 34614 | -34614 | 0 | 0 | 0 | 36800 | 0 | 41536.8 | 34614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | -7.07% | 0% | -10% |  | 36 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23347 | WoT Fixed Leading Edge - Industrial 2023 | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 112.8% | 42.03% | 42.03% | 0 | -0.41% | 31034.12 | 35002.1 | -3967.98 | 0 | 0 | 0 | 10500 | 14710.56 | 24349.85 | 20291.54 | 0 | 14710.56 | 0 | 0 | 0 | 0 | 0 | 7% | 6.59% | 0% | -7% |  | 32.26 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23598 | MRB Onsite support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 21.7091 | 26.5% | 0% | 0% | 0 | -12.01% | 133056 | 35256.42 | 97799.58 | 4505 | 8736.42 | 14079.58 | 0 | 0 | 93.33 | 35256.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 15.99% | 16.4% | -11.6% |  | 42.5 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23760 | EXP-033 Systems Engineering Support | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 39.507 | 25.9% | 93.61% | -0.0002261% | 0 | -0.02% | 142300 | 36855.75 | 105444.25 | 2669 | 0 | 0 | 0 | 34500.75 | 90 | 2355 | 41401 | -0.083333 | 12811.2 | 28589.7 | 0 | 0 | 0 | 29% | 28.98% | 28.98% | -0.02% |  | 78.5 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23051 | Spirit Shorts A350 PAX Door | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 3A | REIM |  |  |  |  | 205.9% | 105.4% | 105.4% | 0 | -0.63% | 18216 | 37513 | -19297 | 0 | 0 | 0 | 0 | 39537 | 0 | 0 | 0 | 39537 | 0 | 0 | 0 | 0 | 0 | 30% | 29.37% | 0% | -30% |  | 46 | [5 empty] | 2024
1732 | 2024-04-03 23:37 | P22752 | Tooling WoT - 2021 (Spirit) | Trevor Knox | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | REIM | 2023-05-03 | 0 |  |  | 101.1% | 74.02% | 74.02% | 0 | -8.5% | 41525.1 | 41982.28 | -457.18 | 0 | 0 | 0 | 0 | 31076.1 | 13087.42 | 10906.18 | 0 | 31076.1 | 0 | 0 | 0 | 0 | 0 | 0% | -8.5% | 0% | 0% |  | 39.09 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23642 | MRB Belfast Support | Carl Warren | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -19.6943 |  | 0% | 0% | 0 | -43.59% | 0 | 43596.41 | -43596.41 | 2213.66 | 3135.3 | 3135.3 | 42350 | 0 | 163.98 | 43596.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22% | -21.59% | -24.28% | -46.28% |  | 38.52 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23339 | Spirit 2023 - Stewart Russell | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 64.51% | 100% | 100% | 0 | 0.62% | 72766.8 | 46941.72 | 25825.08 | 0 | 0 | 0 | 0 | 46941.74 | 0 | -0.02 | 0 | 46941.74 | 0 | 0 | 0 | 0 | 0 | 7% | 7.62% | 0% | -7% |  | 35.67 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23822 | FCASW Requirements Management | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | -4 |  | 0% | 0% | 0 | -6.99% | 0 | 50679.32 | -50679.32 | 12669.83 | 0 | 0 | 49946.3 | 0 | 56 | 50679.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 13.01% | 13.01% | -6.99% |  | 76.27 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P22760 | SA Leading Edge Transport Media ('A' Frames) | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-11-15 | 1 |  |  | 85.99% | 110.7% | 116.3% | -3082.8 | 3.97% | 53480.8 | 45985.5 | 7495.3 | 0 | 42804 | 42804 | 0 | 50911.8 | 0 | -0.3 | -3083 | 53480.9667 | 0 | 0 | 0 | -3082.8 | -3082.8 | 6% | 9.97% | 0% | -6% |  | 42 | [5 empty] | 4926
1732 | 2024-04-03 23:37 | P23700 | IPDT Leads | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 61.708 | 31.13% | 47.31% | -0.0007211% | 0 | -1.58% | 169263.9 | 52697.46 | 116566.44 | 1889 | 0 | 0 | 0 | 24932.12 | 106.18 | 27765.34 | 29919 | -0.38 | 29918.54 | 0 | 0 | 0 | 0 | 26% | 24.42% | 21.94% | -4.06% |  | 50.54 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23349 | Spirit 2023 - Stress Approve Man Serv (SB) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 58.24% | 80.05% | 80.05% | 0 | -0.29% | 97920 | 57024 | 40896 | 0 | 0 | 0 | 0 | 45648 | 13651.2 | 11376 | 0 | 45648 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23543 | EXP-024 FCAS AP Transformation & Change Enablers | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -26% | 385921 | 0 | 385921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26% | 0% | 0% | -26% |  | 0 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23729 | Honda Tooling | Paul Watson | STX | SHORT BROTHERS PLC | MPE | Level NC | FIX |  |  |  | 8.6118 | 53.56% | 53.32% | 0% | 0 | 3.78% | 113610 | 60847.5 | 52762.5 | 6126.75 | 0 | 0 | 0 | 32445 | 84 | 28402.5 | 38934 | 0 | 38934 | 0 | 0 | 0 | 0 | 10% | 13.78% | 13.78% | 3.78% |  | 42 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23744 | Model Factory | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 46.3408 | 22.67% | 112% | -0.0002803% | 27429.6 | 8.49% | 262300 | 59460.5 | 202839.5 | 4377.13 | 0 | 0 | 0 | 66574 | 93.03 | -5113.5 | 79889 | -0.16667 | 26229.6 | 26229.6 | 27429.6 | 0 | 27429.6 | 28% | 36.49% | 36.49% | 8.49% |  | 50.48 | [5 empty] | 2000
1732 | 2024-04-03 23:37 | P23106 | ME Support to NPD - Bobby Haggart | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  |  | 95.79% | 97.03% | 97.03% | 0 | 0.3% | 65675 | 62912.11 | 2762.89 | 0 | 0 | 0 | 0 | 61042.75 | 2243.24 | 1869.36 | 0 | 61042.75 | 0 | 0 | 0 | 0 | 0 | 15% | 15.3% | 0% | -15% |  | 35.65 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P22967 | Spirit 2022 - Channapa Laxmeshwar | James Montgomery | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2023-01-26 | 2 |  |  | 69.69% | 121.3% | 121.3% | 0 | 9.53% | 75159.1 | 52376.15 | 22782.95 | 0 | 52376.15 | 54898.1 | 0 | 63508.8 | 0.42 | 0.35 | 0 | 63508.8 | 0 | 0 | 0 | 0 | 0 | 8% | 17.53% | 0% | -8% |  | 0 | [5 empty] | 11133
1732 | 2024-04-03 23:37 | P23193 | Spirit Shorts Stephen Greer | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -4.0055 | 103.6% | 95.32% | 85.81% | 0 | 8.58% | 61472 | 63694.24 | -2222.24 | 554.8 | 0 | 0 | 10878 | 60712.78 | 96.83 | 2981.46 | 7269 | 54655.28 | 7268.72 | 0 | 0 | 0 | 0 | 23% | 31.58% | 34.03% | 11.03% |  | 35.08 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23341 | Spirit 2023 - Tom McFarlane | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 45.5 | 59.15% | 93.93% | 66.93% | 7110.19 | -0.01% | 108666.4 | 64272.02 | 44394.38 | 975.7 | 0 | 0 | 0 | 60369.22 | 144.49 | 3902.8 | 20820 | 43019.22 | 13709.48 | 0 | 0 | 7110.19 | 7110.19 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23561 | SAAB | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2024-01-01 | 1 |  | 10.7403 | 82.46% | 121.1% | 121.1% | 0 | 8.77% | 67485 | 55649.23 | 11835.77 | 1102 | 0 | 0 | 0 | 67399.4 | 0 | -0.17 | 0 | 67399.4 | 0 | 0 | 0 | 0 | 0 | 16% | 24.77% | 100% | 84% |  | 36.82 | [5 empty] | 11750
1732 | 2024-04-03 23:37 | P23600 | MBDA EXP-EE-023 Bristone Certification | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 59.65% | 100% | 100% | 0 | 0.4% | 126600 | 75517 | 51083 | 0 | 0 | 0 | 0 | 75517 | 0 | 0 | 0 | 75517 | 0 | 0 | 0 | 0 | 0 | 41% | 41.4% | 0% | -41% |  | 78.5 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23080 | Spirit Shorts DManagement Cairan Cullen | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 136.2922 | 50.77% | 97.69% | 91.01% | 3787.8 | -1.23% | 149600 | 75954.5 | 73645.5 | 540.35 | 0 | 0 | 0 | 74199.7 | 169.27 | 1754.8 | 6086 | 69128.0333 | 2298.36 | 0 | 0 | 3787.8 | 3787.8 | 24% | 22.77% | 13.03% | -10.97% |  | 44.39 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23753 | Tempest Composites Maturation | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 5.3719 | 60.39% | 40.26% | -0.000259% | 0 | -12.82% | 127848.45 | 77209.99 | 50638.46 | 9426.6 | 0 | 0 | 0 | 31084.8 | 91 | 46125.19 | 37302 | -0.2 | 37301.76 | 0 | 0 | 0 | 0 | 32% | 19.18% | 19.18% | -12.82% |  | 64.69 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23105 | Raytheon Supply Engineering Support | Natalie Sinclair | RAY | RAYTHEON UNITED KINGDOM LIMITED | MPE | Level 3A | REIM | 2023-07-13 | 2 |  |  | 76.96% | 94.49% | 90.07% | 49156.8 | -2.02% | 1205008 | 927395.25 | 277612.75 | 0 | 0 | 0 | 0 | 876291.5 | 107644.5 | 48739.75 | 49157 | 835327.3333 | 0 | 0 | 49156.8 | 0 | 49156.8 | 26% | 23.98% | 100% | 74% |  | 48.97 | [5 empty] | -2364
1732 | 2024-04-03 23:37 | P23560 | NJEWCS TAF202302 SM | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level 2 | FIX |  |  |  |  | 97.96% | 50.1% | 50.1% | 0 | 11.94% | 81500 | 79836.44 | 1663.56 | 0 | 0 | 0 | 0 | 40000 | 157.63 | 39836.44 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 28% | 39.94% | 39.49% | 11.49% |  | 73.01 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P22885 | ME Support (Baxi) | Trevor Knox | HUV | BAXI HEATING UK LIMITED | ME | Level 3 | FIX | 2023-01-12 | 0 |  |  | 68.78% | 108.7% | 108.7% | 0 | 13.05% | 106632.96 | 73340.24 | 33292.72 | 0 | 0 | 0 | 0 | 79748.12 | 1531.35 | 1276.12 | 0 | 79748.12 | 0 | 0 | 0 | 0 | 0 | 15% | 28.05% | 0% | -15% |  | 44.37 | [5 empty] | 7684
1732 | 2024-04-03 23:37 | P23438 | A220 Spirit Shorts DTC - Stephen Corry | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 16.2316 | 85.55% | 78.54% | 49.23% | 0 | -7.3% | 95928.4 | 82068.6 | 13859.8 | 853.88 | 0 | 0 | 0 | 64459.8 | 325.11 | 17608.8 | 28872 | 40399.8 | 28872.36 | 0 | 0 | 0 | 0 | 23% | 15.7% | 16.75% | -6.25% |  | 49.81 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23171 | Spirt Shorts Weights Eng | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 69.18% | 133.5% | 96.15% | 5965.46 | 2.68% | 103113.14 | 71329.32 | 31783.82 | 0 | 71329.32 | 85975.13 | 0 | 95259.1 | 105.02 | -11659.78 | 32013 | 68581.6 | 9273.05 | 16774.18 | 5965.46 | 0 | 5965.46 | 12% | 14.68% | 0% | -12% |  | 0 | [5 empty] | 12270
1732 | 2024-04-03 23:37 | P23335 | GKN S McConnell 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2023-12-31 | 1 |  |  | 96.61% | 100% | 91.76% | 0 | 0.74% | 87420 | 84459 | 2961 | 0 | 0 | 0 | 0 | 84459 | 8347.2 | 0 | 8347 | 77503.1667 | 0 | 0 | 0 | 8347.2 | 0 | 15% | 15.74% | 0% | -15% |  | 47 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23340 | Spirit 2023 - John Cole | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 45.9019 | 56.52% | 93.3% | 65.4% | 8831.16 | -0.01% | 150129.72 | 84850.74 | 65278.98 | 1422.14 | 0 | 0 | 0 | 79162.2 | 148.58 | 5688.54 | 28403 | 55493.0333 | 19571.76 | 0 | 0 | 8831.16 | 8831.16 | 7% | 6.99% | 6.99% | -0.01% |  | 39.78 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P22965 | Spirit 2022 - Design Man Serv (AH) | Trevor Knox | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 1 |  |  | 106.7% | 96.66% | 92.02% | 4759.75 | 3.14% | 80079.56 | 85441.32 | -5361.76 | 0 | 0 | 0 | 0 | 82588.96 | 8182.59 | 2852.36 | 4760 | 78622.2933 | 0 | 0 | 0 | 4759.75 | 4759.75 | 14% | 17.14% | 0% | -14% |  | 42.44 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23421 | A220 DTC | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 10.9228 | 73.91% | 74.95% | 66.74% | 0 | -28.66% | 217089.12 | 160458.89 | 56630.23 | 5184.57 | 0 | 0 | 0 | 120261.6 | 93.52 | 40197.29 | 15801 | 107094.1 | 15800.9 | 0 | 0 | 0 | 0 | 29% | 0.34% | 5.93% | -23.07% |  | 45.9 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P22964 | Spirit 2022 - MRB Man Serv (JC) | Trevor Knox | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 100.6% | 97.95% | 97.95% | 0 | 1.91% | 85435.2 | 85960.26 | -525.06 | 0 | 0 | 0 | 0 | 84199.74 | 2112.62 | 1760.52 | 0 | 84199.74 | 0 | 0 | 0 | 0 | 0 | 16% | 17.91% | 0% | -16% |  | 42.69 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23342 | Spirit 2023 - Channapa Laxmeshwar | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 14.6367 | 52.39% | 88.11% | 74.35% | 4036.8 | -3.69% | 158696.7 | 83134.33 | 75562.37 | 5162.52 | 83134.33 | 94827 | 0 | 73251.1 | 106.52 | 12733.23 | 13725 | 61813.6 | 9688.32 | 0 | 0 | 4036.8 | 4036.8 | 7% | 3.31% | 0% | -7% |  | 0 | [5 empty] | 2850
1732 | 2024-04-03 23:37 | P23465 | A220 ToW Design Offload (Wing) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 40.812 | 65.59% | 93.03% | 64.41% | 0 | -4.63% | 132000 | 86584.4 | 45415.6 | 1112.8 | 0 | 0 | 0 | 80549.6 | 94.27 | 6034.8 | 29737 | 55768.7667 | 29737.44 | 0 | 0 | 0 | 0 | 20% | 15.37% | 14.07% | -5.93% |  | 42.8 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P22963 | Spirit 2022 - Design Man Serv (PC) | Trevor Knox | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 1 |  |  | 108.6% | 104% | 94.46% | 9938.48 | 3.18% | 80079.56 | 86926.74 | -6847.18 | 0 | 0 | 0 | 0 | 90389.95 | 5782.63 | -3463.21 | 9938 | 82108.2833 | 0 | 0 | 0 | 9938.48 | 9938.48 | 13% | 16.18% | 0% | -13% |  | 42.39 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23079 | Spirit Shorts Nomenclature | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 0.027103 | 99.98% | 88.41% | 77.28% | 0 | 2.01% | 88455 | 88437.6 | 17.4 | 642 | 0 | 0 | 0 | 78185.2 | 226.06 | 10252.4 | 11811 | 68342.7 | 11810.64 | 0 | 0 | 0 | 0 | 20% | 22.01% | 25.23% | 5.23% |  | 30.77 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23336 | Spirit 2023 - Neil Rampling | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 30.0058 | 66.11% | 93.17% | 54.07% | 21586.03 | -0.01% | 133901.52 | 88522.6 | 45378.92 | 1512.34 | 0 | 0 | 0 | 82473.26 | 196.77 | 6049.34 | 41533 | 47862.4267 | 19946.86 | 0 | 0 | 21586.03 | 21586.03 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23784 | Tempest Tooling Offload 2024 | Christopher McCarthy | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  | -12.1133 |  | 0% | 0% | 0 | -11.67% | 0 | 89060.44 | -89060.44 | 7352.29 | 0 | 0 | 107936.4 | 0 | 90 | 89060.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 18.33% | 18.33% | -11.67% |  | 54.83 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23586 | Project Management Support | Peter Bowen | BDX | MBDA UK LIMITED | MPE | Level NC | REIM |  |  |  | -4.2928 | 112.9% | 74.3% | 71.39% | 0 | -26.37% | 80000 | 90320.46 | -10320.46 | 2404.15 | 1277.2 | 1277.2 | 16000 | 67103.86 | 72.63 | 23216.6 | 3149 | 64479.6933 | 0 | 3148.63 | 0 | 0 | 0 | 49% | 22.63% | 21.56% | -27.44% |  | 80 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23345 | Spirit 2023- Jonathan Escosio | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | -6.2015 | 119.3% | 75.5% | 56.57% | 15846.34 | -0.34% | 75970.62 | 90600.57 | -14629.95 | 2359.1 | 0 | 0 | 8938 | 68401.74 | 204.31 | 22198.83 | 20581 | 51250.9067 | 4734.58 | 0 | 0 | 15846.34 | 15846.34 | 7% | 6.66% | 25.2% | 18.2% |  | 43.01 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23551 | Ian Berry 2023 H2 | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  | -7.0286 | 119.9% | 73.96% | 73.96% | 0 | 13.34% | 75810 | 90883.52 | -15073.52 | 2144.61 | 0 | 0 | 24259.2 | 67217.49 | 62.87 | 23666.03 | 0 | 67217.49 | 0 | 0 | 0 | 0 | 0 | 22% | 35.34% | 37.71% | 15.71% |  | 77.46 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23375 | GKN Jaap Peters NL 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2024-03-01 | 2 |  |  | 93.37% | 105.3% | 85.02% | 0 | -15.93% | 97123.22 | 90686.41 | 6436.81 | 0 | 90686.41 | 90686.41 | 0 | 95456.72 | 108.86 | -920.31 | 22027 | 77100.8867 | 0 | 8793.29 | 0 | 13234.06 | 0 | 20% | 4.07% | 0% | -20% |  | 0 | [5 empty] | 3850
1732 | 2024-04-03 23:37 | P23754 | Tempest Composites WP4 | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -8.6933 |  | 0% | 0% | 0 | 6.39% | 0 | 95894.61 | -95894.61 | 11030.86 | 1344.88 | 1344.88 | 97140 | 0 | 91.89 | 95894.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 34.39% | 34.39% | 6.39% |  | 63.14 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23583 | Castalla - Test Rig Design | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -17.5465 | 148.7% | 67.19% | 61% | 0 | -6.38% | 67520 | 100428.5 | -32908.5 | 1875.5 | 0 | 0 | 36106 | 67482.1 | 135.59 | 32946.4 | 7469 | 61257.9333 | 7469.4 | 0 | 0 | 0 | 0 | 21% | 14.62% | 16.88% | -4.12% |  | 42.79 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23545 | Ultra CSS continuation 2023 H2 | Natalie Sinclair | ULT | ULTRA SONAR SYSTEMS LIMITED | EES | Level NC | REIM |  |  |  | -33.0227 | 133% | 74.66% | 43.5% | 37794.24 | 2.22% | 76000 | 101057.6 | -25057.6 | 758.8 | 0 | 0 | 24259.2 | 75451.2 | 225.96 | 25606.4 | 37794 | 43956.2 | 0 | 37794.24 | 0 | 0 | 37794.24 | 23% | 25.22% | 25% | 2% |  | 80 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23353 | Spirit 2023 - MRB Man Serv (JC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  | 83.925 | 58.86% | 63.49% | 63.49% | 0 | 10.08% | 183600 | 108067.5 | 75532.5 | 900 | 0 | 0 | 0 | 68615.25 | 189.5 | 39452.25 | 0 | 68615.25 | 0 | 0 | 0 | 0 | 0 | 7% | 17.08% | 13.81% | 6.81% |  | 45 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23588 | BAE Typhoon MRB MC Shop Concessions | Andrew Houghton | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 22.537 | 64.28% | 99.63% | 71.35% | 14399.76 | -3.78% | 175060.5 | 112535.55 | 62524.95 | 2774.33 | 0 | 0 | 0 | 112121.71 | 91.74 | 413.84 | 38191 | 80295.8767 | 23790.89 | 14399.76 | 0 | 0 | 14399.76 | 31% | 27.22% | 29.25% | -1.75% |  | 55.53 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23352 | Spirit 2023 - Stress Approve Man Serv (CC) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  | -10.4167 | 115.3% | 61.91% | 61.91% | 0 | 6.8% | 97920 | 112920 | -15000 | 1440 | 0 | 0 | 29856 | 69912 | 208 | 43008 | 0 | 69912 | 0 | 0 | 0 | 0 | 0 | 7% | 13.8% | 4.69% | -2.31% |  | 48 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P22918 | Spirit Shorts Graduates | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 9.0265 | 88.73% | 92.54% | 60.99% | 0 | 9.47% | 130000 | 115343.39 | 14656.61 | 1623.74 | 0 | 0 | 9900 | 106734.95 | 211.96 | 8608.44 | 43660 | 70351.6167 | 0 | 43659.95 | 0 | 0 | 0 | 7% | 16.47% | 17.17% | 10.17% |  | 23.3 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23664 | Tempest Composites WP3 | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 2.3532 | 94.46% | 14.28% | 14.28% | 0 | -5.11% | 122455.49 | 115670.48 | 6785.01 | 2883.32 | 0 | 0 | 0 | 16518.7 | 225.54 | 99151.78 | 0 | 16518.7 | 0 | 0 | 0 | 0 | 0 | 37% | 31.89% | 33.71% | -3.29% |  | 60.76 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23338 | Spirit 2023 - Blair Hainey | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 4.7969 | 91.87% | 56.94% | 56.94% | 0 | 5.05% | 34494.36 | 31688.38 | 2805.98 | 584.96 | 0 | 0 | 0 | 18042.36 | 157.61 | 13646.02 | 0 | 18042.36 | 0 | 0 | 0 | 0 | 0 | 7% | 12.05% | 19.31% | 12.31% |  | 18.28 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P22883 | Spirit Shorts Evtol PMO C. Hatton | Julliah Allen | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 56.8589 | 65.16% | 89.99% | 89.99% | 0 | -11.75% | 185800 | 121066.15 | 64733.85 | 1138.5 | 0 | 0 | 0 | 108946.73 | 89.2 | 12119.42 | 0 | 108946.73 | 0 | 0 | 0 | 0 | 0 | 26% | 14.25% | 22.96% | -3.04% |  | 36.79 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23282 | Tooling Support (MBDA) | Dushan Fernando | BDV | MBDA UK LIMITED | ME | Level NC | REIM |  |  |  | 38.9781 | 62.72% | 98.61% | 84.59% | 0 | -8.42% | 195672.4 | 122719.84 | 72952.56 | 1871.63 | 0 | 0 | 0 | 121010.44 | 76.47 | 1709.4 | 20648 | 103803.7733 | 20647.76 | 0 | 0 | 0 | 0 | 30% | 21.58% | 30.37% | 0.37% |  | 49.71 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23270 | Shorts Project X | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 11.1198 | 87% | 93.69% | 71.02% | 0 | 0.58% | 142248 | 123758.18 | 18489.82 | 1662.78 | 0 | 0 | 0 | 115944.34 | 150.69 | 7813.84 | 33666 | 87889.34 | 33666.1 | 0 | 0 | 0 | 0 | 13% | 13.58% | 10.99% | -2.01% |  | 45.34 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P22861 | WoT FLE Lifting & Handling Tools | Trevor Knox | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2023-06-14 | 1 |  |  | 65.17% | 101.6% | 101.6% | 0 | 12.01% | 173987.21 | 113381.75 | 60605.46 | 0 | 50078 | 58423.58 | 0 | 115203.5 | 12813.9 | 10678.25 | 0 | 115203.5 | 0 | 0 | 0 | 0 | 0 | 1% | 13.01% | 0% | -1% |  | 45 | [5 empty] | 12500
1732 | 2024-04-03 23:37 | P23810 | Strategic Enablement | Owain Jones | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -20.58% | 0 | 133060.2 | -133060.2 | 0 | 0 | 0 | 134000 | 0 | 91 | 133060.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | -2.58% | -2.58% | -20.58% |  | 42 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23741 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  | 41.0157 | 20.99% | 104.8% | -0.0001239% | 0 | 1.55% | 640812 | 134517.8 | 506294.2 | 12343.9 | 0 | 0 | 0 | 140959 | 91.34 | -4441.2 | 169151 | -0.16667 | 62626.8 | 52662 | 53862 | 0 | 0 | 28% | 29.55% | 29.55% | 1.55% |  | 38.81 | [5 empty] | 2000
1732 | 2024-04-03 23:37 | P23533 | External Stowage Design and Detail Support | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 1 |  |  | 102.4% | 97.65% | 73.24% | 0 | 3.33% | 140000 | 143368.75 | -3368.75 | 0 | 0 | 0 | 12936 | 140000 | 41999.7 | -0.25 | 42000 | 105000 | 42000 | 0 | 0 | 0 | 0 | 27% | 30.33% | 0% | -27% |  | 60.04 | [5 empty] | -3369
1732 | 2024-04-03 23:37 | P23650 | MBDA Recruitment Management costs | Andrew Slaney | BDW | MBDA UK LIMITED | EES | Level NC | REIM | 2024-02-01 | 1 |  | 9.6389 |  | 0% | 0% | 0 | -20.2% | 0 | 240971.5 | -240971.5 | -25000 | 0 | 0 | 266000 | 0 | 117.06 | 140971.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | -17.2% | -441% | -444% |  | 82.3 | [5 empty] | -100000
1732 | 2024-04-03 23:37 | P22954 | Technical Support Step 1 | Owain Jones | HUV | HUARUI SPIRIT AEROSPACE MANUFACT | ME | Level 2 | REIM |  |  |  |  | 94.81% | 58.01% | 58.01% | 0 | 0.31% | 155501.18 | 147431.58 | 8069.6 | 0 | 23043 | 23043 | 0 | 85525.49 | 61906.09 | 61906.09 | 0 | 85525.49 | 0 | 0 | 0 | 0 | 0 | 30% | 30.31% | 0% | -30% |  | 60.79 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23350 | Spirit 2023 - Stress Approve Man Serv (DH) | Julliah Allen | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 14.15% | 72.64% | 72.64% | 0 | -0.29% | 97920 | 13860 | 84060 | 0 | 0 | 0 | 0 | 10068 | 4550.4 | 3792 | 0 | 10068 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23677 | ME Managed Service - Phase 1 | Paul Watson | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  | 16.3675 | 39.41% | 52.17% | 0% | 0 | -16.7% | 554400 | 218487.6 | 335912.4 | 20523.15 | 0 | 0 | 0 | 113985 | 112.13 | 104502.6 | 136782 | 0 | 136782 | 0 | 0 | 0 | 0 | 33% | 16.3% | 19.34% | -13.66% |  | 43.78 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23739 | Lifing Services DACs | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  | 47.9766 | 22.74% | 110.6% | 0.0002233% | 0 | 2.99% | 656508 | 149299.9 | 507208.1 | 10572 | 0 | 0 | 0 | 165127 | 90 | -15827.1 | 198152 | 0.33333 | 65650.8 | 65650.8 | 66850.8 | 0 | 0 | 28% | 30.99% | 30.99% | 2.99% |  | 37.78 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23550 | Tempest Composites | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -8.1906 | 100.3% | 99.66% | 99.66% | 0 | 5.11% | 149494.92 | 150002.74 | -507.82 | 62 | 0 | 0 | 2396.12 | 149494.92 | 2.42 | 507.82 | 0 | 149494.92 | 0 | 0 | 0 | 0 | 0 | 26% | 31.11% | 34.26% | 8.26% |  | 61.58 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23694 | Systems Portfolio EXP-011a | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 6.9451 | 74.56% | 75.03% | 59.21% | 0 | 2.31% | 648492.8 | 483487.75 | 165005.05 | 23758.59 | 157.75 | 157.75 | 0 | 362778.8 | 62.61 | 120708.95 | 91787 | 286289.6333 | 0 | 91786.96 | 0 | 0 | 0 | 21% | 23.31% | 19.61% | -1.39% |  | 89.07 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P22440 | Spirit Managed Service - F&DT and Static Approval | Trevor Knox | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 3 |  |  | 88.56% | 92.56% | 92.56% | 0 | 11.51% | 173500 | 153656.25 | 19843.75 | 0 | 52115 | 55720 | 0 | 142225.12 | 13717.36 | 11431.13 | 0 | 142225.12 | 0 | 0 | 0 | 0 | 0 | 0% | 11.51% | 0% | 0% |  | 44.73 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23518 | Systems Engineering support to FCAS | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 18.7472 | 80.82% | 95.56% | 82.9% | 0 | -3.61% | 193736.8 | 156577.5 | 37159.3 | 1982.13 | 3927.4 | 3927.4 | 0 | 149625.43 | 72.18 | 6952.07 | 23786 | 129803.7633 | 9843.9 | 13941.6 | 0 | 0 | 0 | 30% | 26.39% | 3.5% | -26.5% |  | 67.85 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23552 | FCAS AP Product Technology Development | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -25% | 597871 | 0 | 597871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0% | -25% |  | 0 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23843 | EXP-035 FT15 Exemplar information set | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 3 | REIM | [7 empty] | 0 | -21% | 0 | 0 | 0 | 0 | 0 | 0 | 21180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21% | 0% | 0% | -21% |  | 0 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23464 | A220 Project X Design Offload | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 51.5712 | 51.68% | 100% | 64.09% | 27862.8 | -9.3% | 332340 | 171762.9 | 160577.1 | 3113.7 | 0 | 0 | 0 | 171762.9 | 145.94 | 0 | 74010 | 110087.9 | 46146.96 | 0 | 0 | 27862.8 | 27862.8 | 26% | 16.7% | 14.75% | -11.25% |  | 42.88 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23508 | Verification and Validation | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 50.5929 | 80.77% | 100% | 88.92% | 0 | 10.77% | 212950 | 171993.5 | 40956.5 | 809.53 | 0 | 0 | 0 | 171993.53 | 45.76 | -0.03 | 22867 | 152937.6967 | 6075.9 | 16791.16 | 0 | 0 | 0 | 24% | 34.77% | 33.6% | 9.6% |  | 78.5 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23648 | EXP-032 Delivery of Datalink Eng support - FCAS AP | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 25.3396 | 47.11% | 87.09% | 58.85% | 0 | 5.28% | 371000 | 174760.45 | 196239.55 | 7744.38 | 1032.95 | 1032.95 | 0 | 152192.95 | 64.44 | 22567.5 | 59221 | 102842.1167 | 19536 | 39684.54 | 0 | 0 | 0 | 22% | 27.28% | 27.37% | 5.37% |  | 103.35 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P22505 | Spirit MRB Engineering Support 2021 | Trevor Knox | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 1 |  |  | 91.17% | 100% | 95.78% | 4020.48 | 21.2% | 87110.4 | 79414.95 | 7695.45 | 0 | 0 | 0 | 0 | 79414.95 | 4020.48 | 0 | 4020 | 76064.95 | 0 | 0 | 0 | 4020.48 | 4020.48 | 0% | 21.2% | 0% | 0% |  | 41.88 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23603 | Typhoon IMDLR | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 9.6448 | 86.77% | 45.26% | 0.0001284% | 0 | 5.41% | 305067.09 | 264705.93 | 40361.16 | 4184.75 | 0 | 0 | 61083.75 | 119807.84 | 330.19 | 144898.09 | 143769 | 0.34 | 143769.41 | 0 | 0 | 0 | 0 | 26% | 31.41% | 32.96% | 6.96% |  | 57.12 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23637 | MBSE Proposal | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 | 0 | 0 | 0 | 49980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23505 | EXP-022 Meteor TBUS T&E support | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 13.3591 | 80.3% | 98.71% | 82.51% | 0 | -1.09% | 246744.4 | 198142.52 | 48601.88 | 3638.12 | 0 | 0 | 0 | 195582.38 | 63.62 | 2560.14 | 38510 | 163490.7133 | 19241.59 | 19268.53 | 0 | 0 | 0 | 20% | 18.91% | 15.67% | -4.33% |  | 89.83 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23322 | GKN T Tomblin 2023 | Steven Lawton | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  | 0.48309 | 99.66% | 100% | 83.41% | 0 | -0.33% | 58952 | 58752 | 200 | 414 | 0 | 0 | 0 | 58752 | 91 | 0 | 11693 | 49007.8333 | 3484.8 | 8208 | 0 | 0 | 0 | 17% | 16.67% | 16.67% | -0.33% |  | 48 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23242 | Physical Architecture & System Engineering Support | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 35.8521 | 66.37% | 98.25% | 86.71% | 0 | 8.1% | 305459 | 202740.46 | 102718.54 | 2865.06 | 775.55 | 775.55 | 0 | 199187.05 | 68.53 | 3199.41 | 28072 | 175793.7167 | 14130 | 13941.6 | 0 | 0 | 0 | 15% | 23.1% | 6.93% | -8.07% |  | 78.2 | [5 empty] | -354
1732 | 2024-04-03 23:37 | P23743 | EHM Cloud Migration | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 35.0142 | 18.32% | 137.6% | 0.0001791% | 0 | 6.39% | 1016000 | 186132.25 | 829867.75 | 23700.88 | 0 | 0 | 0 | 256032 | 98.7 | -51899.75 | 307238 | 0.33333 | 102336 | 102412.8 | 102489.6 | 0 | 0 | 28% | 34.39% | 34.39% | 6.39% |  | 53.66 | [5 empty] | 18000
1732 | 2024-04-03 23:37 | P23373 | Raytheon Michael Bellini | Natalie Sinclair | RAS | RAYTHEON UNITED KINGDOM LIMITED | EES | Level NC | REIM |  |  |  | 1.7568 | 96.83% | 92.37% | 82.44% | 0 | -7.85% | 214367.4 | 207567.79 | 6799.61 | 3870.52 | 0 | 0 | 0 | 191739.73 | 64.07 | 15828.06 | 24735 | 171127.23 | 24734.7 | 0 | 0 | 0 | 0 | 45% | 37.15% | 38.63% | -6.37% |  | 91.61 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23019 | EXP034-B Actuator Development | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 5.2929 | 103.1% | 89.91% | 89.91% | 0 | -16.68% | 215541.2 | 222215.54 | -6674.34 | -1261 | 12297.9 | 12297.9 | 0 | 199796.76 | 91.24 | 397.78 | 0 | 199796.76 | 0 | 0 | 0 | 0 | 0 | 34% | 17.32% | 79.64% | 45.64% |  | 58.45 | [5 empty] | -22021
1732 | 2024-04-03 23:37 | P23816 | Typhoon FTI Works - 2024 Fixed Price Element | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 5.4091 | 55.08% | 0% | 0% | 0 | -3.84% | 404176.65 | 222628.27 | 181548.38 | 33563.62 | 0 | 0 | 0 | 0 | 63 | 222628.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 26.16% | 26.16% | -3.84% |  | 53.52 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23629 | F35 FTI | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level NC | REIM |  |  |  | -21.9956 |  | 90.46% | 72.87% | 0 | -0.94% | 0 | 226317.51 | -226317.51 | 10289.24 | 0 | 0 | 0 | 204738.05 | 47.71 | 21579.46 | 47781 | 164920.55 | 47780.74 | 0 | 0 | 0 | 0 | 31% | 30.06% | 28.85% | -2.15% |  | 61.81 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23472 | Tempest Wing Design | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 23.3563 | 48.65% | 117.9% | 109.4% | 0 | -10.85% | 483869.78 | 235417.11 | 248452.67 | 10637.5 | 219537.5 | 356900 | 0 | 277493.82 | 4.32 | -17076.72 | 23955 | 257531.32 | 23954.72 | 0 | 0 | 0 | 0 | 23% | 12.15% | 35.43% | 12.43% |  | 46.74 | [5 empty] | 25000
1732 | 2024-04-03 23:37 | P23523 | Applique Armour Support | Dushan Fernando | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-18 | 1 |  |  | 72.43% | 138.1% | 98.47% | 0 | 3.42% | 118200 | 85606.5 | 32593.5 | 0 | 0 | 0 | 0 | 118200 | 1567.8 | -32593.5 | 40680 | 84300 | 40680 | 0 | 0 | 0 | 0 | 25% | 28.42% | 0% | -25% |  | 64.29 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23007 | EXP-006A - Brimstone 3 | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 57.7869 | 66.8% | 95.68% | 90.01% | 0 | -2.82% | 406450 | 271495.53 | 134954.47 | 2335.38 | 0 | 0 | 0 | 259759.75 | 76.14 | 11705.78 | 18463 | 244373.9167 | 0 | 18463.2 | 0 | 0 | 0 | 25% | 22.18% | 29.94% | 4.94% |  | 69.78 | [5 empty] | -30
1732 | 2024-04-03 23:37 | P21463 | Safety & Monitoring Systems at DM Beith & Gosport | Harry James Kellett | BXW | MOD | EES | Level 2 | FIX |  |  |  | 235.1703 | 77.8% | 128.5% | 128.5% | 0 | -26.89% | 349404.99 | 271829.37 | 77575.62 | 329.87 | 57357.03 | 77379.59 | 21721 | 349386.99 | 0 | -77557.62 | 0 | 349386.99 | 0 | 0 | 0 | 0 | 0 | 48% | 21.11% | 39.59% | -8.41% |  | 53 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23308 | NATO JEWCS | Natalie Sinclair | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  | 68.9213 | 81.85% | 93.69% | 93.69% | 0 | -3.62% | 356307 | 291648.48 | 64658.52 | 938.15 | 613.89 | 613.89 | 0 | 273254.06 | 62.75 | 18394.42 | 0 | 273254.06 | 0 | 0 | 0 | 0 | 0 | 24% | 20.38% | 11.83% | -12.17% |  | 75.81 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23386 | Software Development - BMS | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 98.78% | 100% | 95.49% | 0 | 4.31% | 149650 | 147823.35 | 1826.65 | 0 | 0 | 0 | 0 | 147823.35 | 36.13 | 0 | 8007 | 141150.85 | 0 | 8007 | 0 | 0 | 0 | 18% | 22.31% | 22.61% | 4.61% |  | 78.5 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P22953 | Spirit Shorts eVTOL | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-05-08 | 3 |  | 4.0846 | 103.1% | 80.83% | 79.36% | 0 | -9.51% | 324272 | 334483.6 | -10211.6 | -2500 | 66696.6 | 67387.9 | 0 | 270366 | 70861.92 | 54117.6 | 5921 | 265431.8333 | 5920.8 | 0 | 0 | 0 | 0 | 17% | 7.49% | 100% | 83% |  | 46.19 | [5 empty] | -10000
1732 | 2024-04-03 23:37 | P22515 | Shorts A220 100/300 ALI Phase III | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 54.0879 | 81.03% | 98.78% | 91.63% | 0 | 0.8% | 400628.76 | 324645.59 | 75983.17 | 1404.81 | 3450.98 | 3450.98 | 0 | 320671.89 | 106.58 | 3973.7 | 27848 | 297465.2233 | 27847.91 | 0 | 0 | 0 | 0 | 10% | 10.8% | 7.88% | -2.12% |  | 40.46 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23699 | A220 Stress Checkers | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -16.5734 |  | 0% | 0% | 0 | -2.12% | 0 | 336410.23 | -336410.23 | 20298.21 | 12000 | 12000 | 321520 | 0 | 106.08 | 336410.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22% | 19.88% | 19.89% | -2.11% |  | 61.88 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P22842 | ME Support (Aim Altitude) | Trevor Knox | AVI | AIM ALTITUDE UK LIMITED | ME | Level 3 | FIX | 2023-06-14 | 4 |  |  | 99.31% | 100.5% | 86.63% | 57290.84 | 0.49% | 346293.67 | 343918.08 | 2375.59 | 0 | 2909.86 | 2909.86 | 0 | 345673.01 | 55184.93 | -1754.93 | 57291 | 297930.51 | 0 | 0 | 0 | 57290.84 | 57290.84 | 13% | 13.49% | 0% | -13% |  | 46.3 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P22391 | GE System Engineering support | Vinayakumar Sugur | GEE | EXPERIS LIMITED | EES | Level NC | REIM |  |  |  |  | 82.01% | 100.7% | 99.51% | 0 | 0.13% | 434434.25 | 356260.63 | 78173.62 | 0 | 0 | 0 | 0 | 358805.6 | 2089.36 | -2544.97 | 5143 | 354519.7667 | 5143.32 | 0 | 0 | 0 | 0 | 6% | 6.13% | 6.09% | 0.09% |  | 57.33 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23045 | Shotgun Adaptors - 10 Sets | Harry James Kellett | BDW | MBDA UK LIMITED | EES | Level 2 | FIX | 2024-02-27 | 7 |  | 4.3339 | 74.76% | 133.8% | 95.11% | 0 | 2.29% | 399276.11 | 298512.88 | 100763.23 | 23250 | 214550.47 | 214550.47 | 0 | 399276.11 | 47356.35 | -7763.23 | 138421 | 283925.2767 | 0 | 138420.73 | 0 | 0 | 0 | 29% | 31.29% | 99.78% | 70.78% |  | 55.76 | [5 empty] | 93000
1732 | 2024-04-03 23:37 | P23685 | DAC LUC Support and Recompliance | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 41.0631 | 16.87% | 195.7% | 0% | 0 | 2.69% | 2180000 | 367846.09 | 1812153.91 | 44131 | 0 | 0 | 0 | 720000 | 98.02 | -319389.91 | 864000 | 0 | 274286.4 | 288001.2 | 301712.4 | 0 | 0 | 30% | 32.69% | 32.69% | 2.69% |  | 58.62 | [5 empty] | 32764
1732 | 2024-04-03 23:37 | P23432 | Spirit Belfast MRB On-Site Support (Mon & Clear) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 65.77% | 128.6% | 103.8% | 0 | -11.53% | 449545 | 295665.27 | 153879.73 | 0 | 295665.27 | 451827.33 | 0 | 380234.75 | 120831.02 | 27430.52 | 87914 | 306973.0833 | 87914.4 | 0 | 0 | 0 | 0 | 39% | 27.47% | 0% | -39% |  | 0 | [5 empty] | 112000
1732 | 2024-04-03 23:37 | P23023 | Spirit Shorts R Foster/M Gourley | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 24.0504 | 82.85% | 105.6% | 86.05% | 28129.27 | -20.7% | 480221.04 | 397851.64 | 82369.4 | 3424.86 | 229061.5 | 267726 | 0 | 420217.26 | 91.04 | -7854.62 | 93426 | 342362.26 | 44091.83 | 21204.59 | 28129.27 | 0 | 28129.27 | 27% | 6.3% | 3.42% | -23.58% |  | 29.61 | [5 empty] | 14511
1732 | 2024-04-03 23:37 | P23554 | Dornier Seawings 328 2023 H2 Support | Steven Lawton | DAX | EXPLEO GERMANY GMBH (EC) | MPE | Level 2 | REIM |  |  |  | 8.7415 | 89.58% | 94.02% | 84.95% | 21955.08 | 6.4% | 508481.81 | 455497.92 | 52983.89 | 6061.21 | 4046.44 | 4046.44 | 0 | 428252.8 | 65.98 | 27245.12 | 49568 | 386946.1333 | 49567.88 | 0 | 0 | 0 | 21955.08 | 21% | 27.4% | 24.33% | 3.33% |  | 66.46 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P22906 | Spirit Shorts - MRB JD Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 10.3087 | 93.13% | 86.19% | 67.72% | 99451.32 | -7.8% | 481714 | 448625.68 | 33088.32 | 3209.75 | 0 | 0 | 0 | 386687.62 | 292.78 | 69938.06 | 99451 | 303811.7867 | 0 | 0 | 85953.72 | 13497.6 | 99451.32 | 13% | 5.2% | 2.59% | -10.41% |  | 36.91 | [5 empty] | 8000
1732 | 2024-04-03 23:37 | P22982 | Spirit 2022 - Hugh Sloan | Julliah Allen | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 84.737 | 61.73% | 95.51% | 83.1% | 8217.17 | -0.49% | 247473 | 152769.22 | 94703.78 | 1117.62 | 0 | 0 | 0 | 145911.5 | 180.7 | 6857.72 | 22757 | 126947.3333 | 14539.71 | 0 | 0 | 8217.17 | 8217.17 | 7% | 6.51% | 1.35% | -5.65% |  | 35.42 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23531 | BAe Systems F35 MRB Support | Andrew Houghton | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | -41.1046 |  | 94.16% | 68.12% | 0 | 3.04% | 0 | 459910.22 | -459910.22 | 11188.78 | 287.44 | 287.44 | 0 | 433032.73 | 87.03 | 26877.49 | 143699 | 313283.5633 | 143698.75 | 0 | 0 | 0 | 0 | 25% | 28.04% | 31.36% | 6.36% |  | 59.79 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23520 | FCAS AP Portfolio Systems | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 28.2602 | 58.95% | 97.4% | 76.22% | 0 | -6.95% | 810821 | 477975.43 | 332845.57 | 11777.88 | 423 | 423 | 0 | 465538.44 | 66.83 | 8153.99 | 121494 | 364293.44 | 62232.16 | 59261.4 | 0 | 0 | 0 | 22% | 15.05% | 15.48% | -6.52% |  | 80.47 | [5 empty] | -4283
1732 | 2024-04-03 23:37 | P23585 | Systems Design - Missile Systems, Meteor,Brimstone | Peter Bowen | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 | 0 | 0 | 0 | 49500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23140 | Spirit Shorts A220 MLG Stress Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  | 27.8228 | 72.74% | 80.16% | 71.45% | 0 | -11.78% | 636032.4 | 462664.25 | 173368.15 | 6231.16 | 20870.3 | 87811.88 | 0 | 370857.4 | 210.75 | 116806.85 | 48343 | 330571.5667 | 48343.2 | 0 | 0 | 0 | 0 | 25% | 13.22% | -10.03% | -35.03% |  | 46.25 | [5 empty] | 25000
1732 | 2024-04-03 23:37 | P22652 | L3 - Saftey Engineering | Sean Simmons | LHW | L3HARRIS MAPPS LIMITED | EES | Level NC | FIX |  |  |  |  | 95.63% | 86.69% | 86.69% | 0 | 5.66% | 523390 | 500497.5 | 22892.5 | 0 | 0 | 0 | 0 | 433882.5 | 79938 | 66615 | 0 | 433882.5 | 0 | 0 | 0 | 0 | 0 | 21% | 26.66% | 25.88% | 4.88% |  | 83.05 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23281 | Systems Portfolio | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM | 2024-02-28 | 2 |  | -3239.9024 | 44.43% | 97.31% | 97.19% | 0 | -17.25% | 1177697.24 | 523236.96 | 654460.28 | -202 | 2133.28 | 2133.28 | 0 | 509179.87 | 16553.63 | 13160.09 | 762 | 508544.87 | 0 | 761.53 | 0 | 0 | 0 | 25% | 7.75% | 100% | 75% |  | 70.48 | [5 empty] | -897
1732 | 2024-04-03 23:37 | P23473 | Tempest Vertical Tail | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 17.3601 | 72.2% | 94.36% | 84.55% | 0 | -2.75% | 723866.48 | 522639.86 | 201226.62 | 11591.36 | 97575 | 100425 | 0 | 493182.93 | 49.53 | 29456.93 | 61518 | 441917.93 | 61517.7 | 0 | 0 | 0 | 0 | 24% | 21.25% | 23.08% | -0.92% |  | 62.38 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23667 | Safety Systems Engineer | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 61.3198 | 39.41% | 97.76% | 77% | 0 | -9.79% | 398000 | 156860 | 241140 | 3932.5 | 0 | 0 | 0 | 153340 | 63.78 | 3520 | 39072 | 120780 | 19536 | 19536 | 0 | 0 | 0 | 47% | 37.21% | 29.32% | -17.68% |  | 110 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23366 | Business Analyst Support | Peter Williams | BDZ | MBDA UK LIMITED | DET | Level 3 | REIM |  |  |  | 38.5398 | 20.74% | 208.9% | 158.9% | 0 | 7.07% | 1302200 | 270112.83 | 1032087.17 | 26779.8 | 247149.55 | 416921.86 | 0 | 564160 | 85.07 | -10912.17 | 161856 | 429280 | 81792 | 80064 | 0 | 0 | 0 | 43% | 50.07% | 26.78% | -16.22% |  | 37.26 | [5 empty] | 283135
1732 | 2024-04-03 23:37 | P23323 | CNC-CMM Programming Support | Andrew Houghton | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | 5.033 | 92.32% | 95.73% | 74.9% | 0 | -2.8% | 617809.74 | 570367.02 | 47442.72 | 9426.37 | 15941.56 | 15941.56 | 0 | 546032.59 | 106.11 | 24334.43 | 142591 | 427206.7567 | 142591.47 | 0 | 0 | 0 | 0 | 32% | 29.2% | 36.94% | 4.94% |  | 57.22 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23219 | Tornado Air 800 Engineering Support | Richard Brook | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 3 | REIM |  |  |  | -0.94623 | 98.97% | 95.02% | 95.02% | 0 | -0.44% | 615046 | 608692 | 6354 | -6715.06 | 459.21 | 459.21 | 0 | 578373.17 | 91 | 21593.83 | 0 | 578373.17 | 0 | 0 | 0 | 0 | 0 | 31% | 30.56% | -55.91% | -86.91% |  | 82.29 | [5 empty] | -8725
1732 | 2024-04-03 23:37 | P23605 | Typhoon Work Package 2 Continuation | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM |  |  |  | -381.8887 | 119.8% | 81.03% | 4.178% | 70906.73 | 5.19% | 545536.01 | 653621.97 | -108085.96 | 283.03 | 4054 | 4054 | 81999.09 | 529626.35 | 352.31 | 123995.62 | 602778 | 27311.35 | 317677.15 | 285100.7 | 0 | 0 | 70906.73 | 23% | 28.19% | 28.93% | 5.93% |  | 55.82 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P22790 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 2 | REIM | 2024-03-18 | 0 |  |  | 194.5% | 90.44% | 90.44% | 0 | 1.37% | 352240 | 685262.25 | -333022.25 | 0 | 1611.52 | 1611.52 | 515246 | 619743.88 | 41098.04 | 34248.37 | 0 | 619743.88 | 0 | 0 | 0 | 0 | 0 | 13% | 14.37% | 0% | -13% |  | 45.06 | [5 empty] | -31270
1732 | 2024-04-03 23:37 | P23426 | BAE Tempest WP 3 Harness Maturation | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 10.9187 | 77.81% | 86.03% | 76.05% | 0 | -6.05% | 884012.04 | 687828.98 | 196183.06 | 17967.68 | 213.34 | 213.34 | 0 | 591770.47 | 68.03 | 96058.51 | 82449 | 523062.97 | 82448.95 | 0 | 0 | 0 | 0 | 33% | 26.95% | 27.67% | -5.33% |  | 51.48 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23602 | EXP-025 Portfolio Software Engineering Support | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 19.0543 | 55.08% | 95.07% | 61.88% | 0 | -0.91% | 1327080 | 730907.28 | 596172.72 | 31288.15 | 2542.8 | 3006.91 | 0 | 694893.55 | 68.79 | 36013.73 | 291123 | 452291.05 | 143049.25 | 148074.11 | 0 | 0 | 0 | 24% | 23.09% | 22.78% | -1.22% |  | 83.19 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23451 | BAE Tempest - DFM-ASO Planning | Andrew Houghton | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | 6.7634 | 85.44% | 76.71% | 34.54% | 27224.9 | -3.19% | 953905.42 | 815027.62 | 138877.8 | 20533.64 | 0 | 0 | 0 | 625210.17 | 176.4 | 189817.45 | 412472 | 281483.5033 | 385247.48 | 0 | 27224.9 | 0 | 27224.9 | 28% | 24.81% | 26.7% | -1.3% |  | 53.66 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23372 | BAE Carbon Tooling Off-load | Gary Kempster | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  |  | 100.5% | 95.27% | 56.3% | 0 | -1.13% | 454982.37 | 457433.31 | -2450.94 | 0 | 0 | 0 | 19196.43 | 435785.94 | 3010.28 | 21647.37 | 213917 | 257521.7733 | 213917.24 | 0 | 0 | 0 | 0 | 24% | 22.87% | 20.74% | -3.26% |  | 53.57 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P22350 | EMP 2020-2021 | Natalie Sinclair | ARY | GUIDANT GROUP (trading name) | PCPR | Level NC | REIM |  |  |  | 5.3196 | 96.68% | 97.65% | 93.12% | 0 | -2.17% | 1017579.76 | 983745.67 | 33834.09 | 6360.24 | 400 | 400 | 0 | 960667.18 | 73.31 | 23078.49 | 53579 | 916018.0133 | 21769.52 | 31809.66 | 0 | 0 | 0 | 32% | 29.83% | 26.36% | -5.64% |  | 44.11 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23117 | BAE Typhoon Eng Support | Christopher McCarthy | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | 2024-03-12 | 11 |  |  | 107.6% | 92.94% | 88.52% | 0 | -1.44% | 950771.99 | 1022826.17 | -72054.18 | 0 | 19090.01 | 21165.02 | 69773.84 | 950609.41 | 108434.62 | 45120.76 | 54290 | 905367.7433 | 54289.71 | 0 | 0 | 0 | 0 | 30% | 28.56% | 0% | -30% |  | 52.3 | [5 empty] | -27096
1732 | 2024-04-03 23:37 | P22671 | Spirit Shorts Pylon and Fairing Package | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX | 2023-05-03 | 0 |  |  | 105% | 95.26% | 95.26% | 0 | -7.21% | 1198494.77 | 1258071.09 | -59576.32 | 0 | 106494.89 | 106494.89 | 0 | 1198494.77 | 2544.39 | 2120.32 | 0 | 1198494.77 | 0 | 0 | 0 | 0 | 0 | 20% | 12.79% | 0% | -20% |  | 45.4 | [5 empty] | -57456
1732 | 2024-04-03 23:37 | P23292 | BAE Tempest WP 4 AV Trays | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 11.3212 | 82.65% | 93.71% | 83.24% | 0 | 1.77% | 1498284.22 | 1238303.06 | 259981.16 | 22964.02 | 0 | 0 | 0 | 1160371.79 | 64.19 | 77931.27 | 155585 | 1030717.6233 | 155584.85 | 0 | 0 | 0 | 0 | 32% | 33.77% | 32.54% | 0.54% |  | 53.38 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23152 | Project Aragon - Design and Stress Support | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 4.2876 | 96.08% | 79.45% | 56.92% | 0 | -9.56% | 1333452.21 | 1281174.26 | 52277.95 | 12192.85 | 0 | 0 | 0 | 1017835.58 | 309.23 | 263338.68 | 346248 | 729295.58 | 346247.55 | 0 | 0 | 0 | 0 | 39% | 29.44% | 29.09% | -9.91% |  | 51.94 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23519 | Mechanical and Electrical Design Eng Support | Dushan Fernando | BAX | SAFRAN SEATS GB LIMITED | MPE | Level 2 | REIM |  |  |  | 15.4485 | 71.91% | 85.66% | 85.66% | 0 | -1.64% | 1807261.3 | 1299617.05 | 507644.25 | 32860.48 | 1004.45 | 1504.45 | 0 | 1113289.55 | 39.33 | 186327.5 | 0 | 1113289.55 | 0 | 0 | 0 | 0 | 0 | 33% | 31.36% | 31.23% | -1.77% |  | 56.64 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23411 | Agile & Scrum Delivery Service | Peter Williams | BDZ | MBDA UK LIMITED | DET | Level 2 | REIM | 2023-08-14 | 0 |  |  | 36.3% | 170.5% | 170.5% | 0 | 13.08% | 2487000 | 902903.79 | 1584096.21 | 0 | 894178.59 | 894178.59 | 0 | 1539600 | 19368.95 | 16140.79 | 0 | 1539600 | 0 | 0 | 0 | 0 | 0 | 29% | 42.08% | 0% | -29% |  | 74.57 | [5 empty] | 652837
1732 | 2024-04-03 23:37 | P23315 | DAC LUC BAU and Service Workbench | Vijayakumara Nanjundappa | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX | 2024-02-16 | 1 |  | 70.5463 | 85.17% | 117.4% | 117.4% | 0 | 3.84% | 1573630 | 1340192.3 | 233437.7 | 3309 | 180.3 | 180.3 | 0 | 1573630 | 0 | 0.3 | 0 | 1573630 | 0 | 0 | 0 | 0 | 0 | 28% | 31.84% | 47.26% | 19.26% |  | 52.35 | [5 empty] | 233438
1732 | 2024-04-03 23:37 | P23006 | Spirit Shorts A350 Freighter Toulouse | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -37.346 | 154.8% | 105.8% | 77.04% | 0 | 19.41% | 1035745.92 | 1603239.58 | -567493.66 | 15195.57 | 1086670.26 | 1708220.2 | 0 | 1695787.93 | 304.13 | 218725.65 | 552824 | 1235101.2633 | 552824.28 | 0 | 0 | 0 | 0 | 5% | 24.41% | 35.59% | 30.59% |  | 48 | [5 empty] | 311274
1732 | 2024-04-03 23:37 | P22278 | TAI Supply Engineers to Ankara | Natalie Sinclair | TAI | TUSAS-TURK HAVACILIK VE UZAY | MPE | Level 3A | REIM |  |  |  | 426.6699 | 19.52% | 464.9% | 464.9% | 0 | -15.64% | 2105282 | 410975.91 | 1694306.09 | 3971 | 49400.29 | 49400.29 | 0 | 1910696.33 | 34.95 | 5339.58 | 0 | 1910696.33 | 0 | 0 | 0 | 0 | 0 | 95% | 79.36% | 70.03% | -24.97% |  | 34.2 | [5 empty] | 1505060
1732 | 2024-04-03 23:37 | P23435 | Andy Baker Portfolio | Dushan Fernando | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 42.6909 | 48.07% | 97.97% | 70.21% | 0 | -7.22% | 4023207.4 | 1934140.32 | 2089067.08 | 48934.68 | 2352.57 | 2352.57 | 0 | 1894945.09 | 84.26 | 39195.23 | 644345 | 1357990.9233 | 489604.46 | 154740.27 | 0 | 0 | 0 | 25% | 17.78% | 20.1% | -4.9% |  | 80.26 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P22736 | WoT Fixed Leading Edge - Industrial | Trevor Knox | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 106.7% | 93.42% | 91.32% | 3019.54 | 0.01% | 112196.27 | 119668.47 | -7472.2 | 0 | 0 | 0 | 0 | 111796.68 | 12465.69 | 7871.79 | 3020 | 109280.0133 | 0 | 0 | 0 | 3019.54 | 3019.54 | 7% | 7.01% | 0% | -7% |  | 32.26 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23257 | BAE Tempest WP 5 Centre Fuselage | Lauren Victoria Savage | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | -1.1023 | 100.8% | 97.99% | 93.66% | 0 | -5.78% | 2106860.71 | 2124311.61 | -17450.9 | 15831.8 | 78100 | 78100 | 0 | 2081529.48 | 52.91 | 42782.13 | 110362 | 1989561.1467 | 110362.14 | 0 | 0 | 0 | 0 | 33% | 27.22% | 27.97% | -5.03% |  | 61.05 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23524 | Bombardier Regional Jets (BRJ) | Carl Warren | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 130.8% | 56.89% | 44.32% | 28851.48 | -4.74% | 146287.84 | 191311.68 | -45023.84 | 0 | 0 | 0 | 46750 | 108838.22 | 343.27 | 82473.46 | 28851 | 84795.72 | 0 | 0 | 0 | 28851.48 | 28851.48 | 18% | 13.26% | 15.05% | -2.95% |  | 43.92 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23207 | A350 Approvers - Design and Stress Support | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  | 4.8322 | 89.26% | 101% | 51.56% | 432699.41 | -4.99% | 2728308 | 2435271.25 | 293036.75 | 60642.8 | 34418.19 | 35115.68 | 0 | 2458482.23 | 140.63 | -23210.98 | 1443393 | 1255654.73 | 531675.57 | 570705.26 | 341012.63 | 0 | 432699.41 | 23% | 18.01% | 17.23% | -5.77% |  | 54.61 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P23179 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX |  |  |  | -200.7637 | 127.3% | 94.88% | 81.83% | 9496.08 | -9.33% | 1996985.84 | 2542500.98 | -545515.14 | 2717.2 | 156991.12 | 248243.92 | 100000 | 2412235.69 | 517.04 | 130265.29 | 398043 | 2080533.19 | 248280.21 | 140266.99 | 9496.08 | 0 | 9496.08 | 22% | 12.67% | 16.7% | -5.3% |  | 44.4 | [5 empty] | 0
1732 | 2024-04-03 23:37 | P19731 | Hapri HPC Rear Bearing Housing PDR & CDR | Steven Lawton | ATC | AECC Hunan Aviation Powerplant | MPE | Level 1 | FIX |  |  |  | 1.7742 | 99.95% | 100.1% | 87.55% | 447000 | -15.41% | 2980000 | 2978363.27 | 1636.73 | 922.53 | 366232.13 | 500332.13 | 0 | 2980000 | 910.48 | -226636.73 | 447000 | 2607500 | 0 | 0 | 0 | 447000 | 447000 | 38% | 22.59% | 11.87% | -26.13% |  | 64.86 | [5 empty] | -225000
1732 | 2024-04-03 23:37 | P23487 | Tornado Air 800 Engineering Support | Richard Brook | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 2 | FIX |  |  |  | 1.1689 | 97.04% | 88.41% | 76.6% | 38732.48 | -3.49% | 3049066.2 | 2958805.67 | 90260.53 | 77219.85 | 0 | 0 | 0 | 2616021.67 | 85.8 | 369784 | 419489 | 2266447.5033 | 380756.59 | 8658.1 | 30074.38 | 0 | 38732.48 | 40% | 36.51% | 40.43% | 0.43% |  | 78.71 | [5 empty] | 27000
Extend Table

## AP4-1
WIP No | Date Created | Project ID | Project Description | Project Manager | Agency (1=yes, 0=no) | Department Id | Client | CBU | Complexity | Type | Stop Booking Hrs | Closing Project: Action(s) to close | RAG | Approx. PO Burndown (weeks) | Turnover vs Contract Value | Invoice To Date vs Turnover | Cash in vs Turnover | Open Amount Overdue | Actual PM% to Baseline PM% delta | Contract Value | Total Project Turnover | Contract Value - Total Turnover | Run Rate (based on total turnover) | Total BOI Spend to Date | Total Committed PO (supplier/best shore) | Current AA in PT3 | Exposure (turnover - contract value) | Invoiced To Date | DSO | Unbilled (WIP) | WIP / Run rate | WIP / Run rate >1.3 | WIP + Remaining Committed PO for BOI | Total Open Amount | Cash in (Invoiced - (Open amount -VAT)) | Debt <=30 Days | Debt 31 - 60 Days | Debt 61 - 90 Days | Debt >= 90 Days | Open Amount Overdue2 | Baseline Project Margin | Project To Date (PTD) PM | Year to Date (YTD) PM | YTD Delta Actual PM% to BPM% | Forecast PM at Completion (Manual input from PTT) | Average Sale Rate | CSat score for last quarter (Manual input from PTT) | Comments and Actions | Judged income adjustment at completion | Profit to take now | Provision required now | Fully Traded | Last Months Comments and Actions
1733 | 2024-04-10 23:28 | P23637 | MBSE Proposal | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 | 0 | 0 | 0 | 49980 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23711 | DO NOT USE - RAISED IN ERROR | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23717 | GKN Ted Tomblin 2024 | Matthew Tweed | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 10047 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23543 | EXP-024 FCAS AP Transformation & Change Enablers | Peter Bowen | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -26% | 385921 | 0 | 385921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26% | 0% | 0% | -26% |  | 0 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23585 | Systems Design - Missile Systems, Meteor,Brimstone | Peter Bowen | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 | 0 | 0 | 0 | 49500 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23552 | FCAS AP Product Technology Development | Peter Bowen | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -25% | 597871 | 0 | 597871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0% | -25% |  | 0 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23730 | FLE Project | Carl Warren | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -18.03% | 0 | 1120 | -1120 | 0 | 0 | 0 | 24000 | 1120 | 0 | 91 | 1120 | 0% | NO | 1120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | -18.03% | -18.03% | -18.03% |  | 35 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23463 | A220 Wing MaMo Design Checking | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-03-07 | 0 |  |  |  | 0% | 0% | 0 | 7.85% | 0 | 1628 | -1628 | 0 | 0 | 0 | 15000 | 1628 | 0 | 1953.6 | 1628 | 0% | NO | 1628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | 10.85% | 0% | -3% |  | 44 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23843 | EXP-035 FT15 Exemplar information set | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 220.3739 | 1.343% | 0% | 0% | 0 | -13.58% | 175985.16 | 2363.56 | 173621.6 | 787.85 | 0 | 0 | 0 | 0 | 0 | 21 | 2363.56 | 300% | YES | 2363.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 6.42% | 6.42% | -13.58% |  | 63.88 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23842 | Tranche 1 Evolution Package Step 2 | Christopher McCarthy | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -3 |  | 0% | 0% | 0 | -6.41% | 0 | 2496.16 | -2496.16 | 832.05 | 0 | 0 | 67488.9 | 2496.16 | 0 | 21 | 2496.16 | 300% | YES | 2496.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31% | 24.59% | 24.59% | -6.41% |  | 64 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P21028 | Rebate Collection (BACC) | David Catchpole | 0 | TOO | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | [5 empty] | 0% | 0% | 0 | 0% | 0 | 2680 | -2680 | 0 | 2680 | 2680 | 0 | 2680 | 0 | 3216 | 2680 | 0% | NO | 2680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23578 | ESN Work Package | Hannah Mead | 0 | COZ | CHELTON LIMITED | DET | Level 3 | FIX | 2024-01-01 | 0 |  |  | 86.17% | 116.1% | 116.1% | 0 | 35.86% | 4410 | 3800 | 610 | 0 | 0 | 0 | 0 | 0 | 4410 | 0 | -610 | 0% | NO | -610 | 0 | 4410 | 0 | 0 | 0 | 0 | 0 | 24% | 59.86% | 0% | -24% |  | 95 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23628 | Design Assurance | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -6.67% | 0 | 3909.24 | -3909.24 | 0 | 0 | 0 | 4454.8 | 3909.24 | 0 | 4691.09 | 3909.24 | 0% | NO | 3909.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 0.33% | 0% | -7% |  | 15.05 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23002 | WoT MAJ Transit Flag Stress | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2024-04-03 | 0 |  |  | 30.89% | 323.8% | 323.8% | 0 | 53.84% | 4735 | 1462.5 | 3272.5 | 0 | 0 | 0 | 0 | 0 | 4735 | 0.6 | 0.5 | 0% | NO | 0.5 | 0 | 4735 | 0 | 0 | 0 | 0 | 0 | 10% | 63.84% | 0% | -10% |  | 45 | [5 empty] | 3273
1733 | 2024-04-10 23:28 | P23718 | Requalification of EJ200 GSS ESS EHM SW module | Vijayakumara Nanjundappa | 0 | ARZ | MTU AERO ENGINES AG | DET | Level 3 | FIX |  |  |  | 247.2646 | 10.34% | 235.3% | 235.3% | 0 | -2.1% | 74463 | 7701.57 | 66761.43 | 270 | 991.93 | 991.93 | 0 | 0 | 18125 | 0 | -10423.43 | -3861% | NO | -10423.43 | 0 | 18125 | 0 | 0 | 0 | 0 | 0 | 28% | 25.9% | 25.9% | -2.1% |  | 80 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23607 | SAFRAN - A330neo Turnover Frame | Gary Kempster | 0 | TOO | SAFRAN SEATS GB LIMITED | MPE | Level 3 | FIX |  |  |  | 3.999 | 95.69% | 104.5% | 104.5% | 0 | -19.52% | 8736 | 8359.05 | 376.95 | 94.26 | 0 | 0 | 0 | 0 | 8736 | 0.06 | 0.05 | 0.05304% | NO | 0.05 | 0 | 8736 | 0 | 0 | 0 | 0 | 0 | 23% | 3.48% | 8.5% | -14.5% |  | 50.46 | [5 empty] | 377
1733 | 2024-04-10 23:28 | P23274 | ME Support (Aim Altitude - Cambridge) | Trevor Knox | 0 | AVI | AVIC CABIN SYSTEMS (UK) LIMITED | ME | Level 3 | FIX | 2023-08-18 | 0 |  |  | 51.88% | 56.3% | 56.3% | 0 | -0.17% | 17280 | 8964 | 8316 | 0 | 0 | 0 | 0 | 0 | 5046.3 | 4701.24 | 3917.7 | 0% | NO | 3917.7 | 0 | 5046.3 | 0 | 0 | 0 | 0 | 0 | 21% | 20.83% | 0% | -21% |  | 48 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23283 | Spirit Tooling Audit | Charidimos Valadakis | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-05-03 | 0 |  |  | 97.22% | 48.57% | 48.57% | 0 | -7.99% | 9910.08 | 9634.8 | 275.28 | 0 | 0 | 0 | 0 | 0 | 4679.76 | 5946.05 | 4955.04 | 0% | NO | 4955.04 | 0 | 4679.76 | 0 | 0 | 0 | 0 | 0 | 7% | -0.99% | 0% | -7% |  | 34.41 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23127 | Loft Hall Design Support | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 101% | 99.06% | 99.06% | 0 | -9.55% | 9680 | 9772 | -92 | 0 | 0 | 0 | 0 | 92 | 9680 | 110.4 | 92 | 0% | NO | 92 | 0 | 9680 | 0 | 0 | 0 | 0 | 0 | 41% | 31.45% | 0% | -41% |  | 44 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23630 | 2Excel CFD Analysis Support | Dushan Fernando | 0 | BAX | STIRLING DYNAMICS LTD | MPE | Level NC | FIX |  |  |  |  | 61.2% | 100% | 100% | 0 | -1.87% | 16195.49 | 9911.34 | 6284.15 | 0 | 0 | 0 | 0 | 0 | 9911.63 | 0 | -0.29 | 0% | NO | -0.29 | 0 | 9911.63 | 0 | 0 | 0 | 0 | 0 | 26% | 24.13% | 0% | -26% |  | 64.78 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23313 | Laser Trim Fixtures | Gary Kempster | 0 | TOO | ALKEN ENGINEERING LIMITED | MPE | Level 3 | FIX | 2023-11-20 | 0 |  |  | 89.87% | 111.3% | 111.3% | 0 | 0.53% | 13770 | 12375 | 1395 | 0 | 0 | 0 | 0 | 0 | 13770 | 0 | -1395 | 0% | NO | -1395 | 0 | 13770 | 0 | 0 | 0 | 0 | 0 | 17% | 17.53% | 0% | -17% |  | 45 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P22761 | Red Bull Chassis Spit | Trevor Knox | 0 | TOO | MANUFAX ENGINEERING LTD | MPE | Level 3 | FIX | 2022-11-15 | 0 |  |  | 72.18% | 96.98% | 96.98% | 0 | 7.92% | 12961.2 | 9355.5 | 3605.7 | 0 | 0 | 0 | 0 | 0 | 9072.84 | 4666.39 | 3888.66 | 0% | NO | 3888.66 | 0 | 9072.84 | 0 | 0 | 0 | 0 | 0 | 23% | 30.92% | 0% | -23% |  | 42.19 | [5 empty] | 3606
1733 | 2024-04-10 23:28 | P23350 | Spirit 2023 - Stress Approve Man Serv (DH) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 14.15% | 72.64% | 72.64% | 0 | -0.29% | 97920 | 13860 | 84060 | 0 | 0 | 0 | 0 | 0 | 10068 | 4550.4 | 3792 | 0% | NO | 3792 | 0 | 10068 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23344 | Spirit A320 Spoilers Support 2023 | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 38.75% | 100% | 100% | 0 | 5.82% | 35786.4 | 13867.23 | 21919.17 | 0 | 0 | 0 | 0 | 0 | 13867.23 | 0 | 0 | 0% | NO | 0 | 0 | 13867.23 | 0 | 0 | 0 | 0 | 0 | 7% | 12.82% | 0% | -7% |  | 34.41 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23337 | Spirit 2023 - Steve Grimley | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 25.28% | 100% | 100% | 0 | 0.01% | 56812.9 | 14362.47 | 42450.43 | 0 | 0 | 0 | 0 | 0 | 14362.47 | 0 | 0 | 0% | NO | 0 | 0 | 14362.47 | 0 | 0 | 0 | 0 | 0 | 7% | 7.01% | 0% | -7% |  | 30.11 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23597 | MRB Onsite support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-02-16 | 1 |  |  |  | 0% | 0% | 0 | -10.04% | 0 | 15100.57 | -15100.57 | 0 | 9448.07 | 17381.62 | 24200 | 15100.57 | 0 | 102.4 | 15100.57 | 0% | NO | 23034.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 7.96% | 8.95% | -9.05% |  | 42.5 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23831 | Contract DM/00113 for maintenance, repair and post | Harry James Kellett | 0 | BXW | MOD | EES | Level 2 | FIX |  |  |  | 5.7297 | 43.08% | 0% | 0% | 0 | 15.07% | 40800 | 17576.94 | 23223.06 | 4053.13 | 0 | 0 | 0 | 0 | 0 | 91 | 17576.94 | 433.7% | YES | 17576.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37% | 52.07% | 52.07% | 15.07% |  | 80.26 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23663 | Spirit Tooling Verification and Inspection | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 2.25 | 90.62% | 36.78% | 0.0002969% | 0 | -7.44% | 19820.16 | 17962.02 | 1858.14 | 825.84 | 0 | 0 | 7392 | 0 | 6606.72 | 153.73 | 11355.3 | 1375% | YES | 11355.3 | 7928 | 0.053333 | 0 | 7928.06 | 0 | 0 | 0 | 12% | 4.56% | 4.82% | -7.18% |  | 34.41 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23635 | Engineering Services: FAI Support | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 49.9% | 68.33% | 0.001436% | 0 | -3.4% | 37230 | 18576 | 18654 | 0 | 0 | 0 | 0 | 0 | 12693.6 | 321.18 | 5882.4 | 0% | NO | 5882.4 | 15232 | 0.26667 | 0 | 15232.32 | 0 | 0 | 0 | 8% | 4.6% | 5.04% | -2.96% |  | 38.7 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23742 | Cyber Security Support | Hannah Mead | 0 | COZ | CHELTON LIMITED | DET | Level 3 | FIX |  |  |  | -7.0857 |  | 0% | 0% | 0 | 31.04% | 0 | 18600 | -18600 | 2625 | 0 | 0 | 27500 | 18600 | 0 | 91 | 18600 | 708.6% | YES | 18600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 31.04% | 31.04% | 31.04% |  | 100 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23343 | Spirit 2023 - John Agnew | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-08-09 | 0 |  |  | 28.56% | 86.27% | 86.27% | 0 | -0.02% | 65120.37 | 18600.89 | 46519.48 | 0 | 0 | 0 | 0 | 0 | 16047.15 | 3064.49 | 2553.74 | 0% | NO | 2553.74 | 0 | 16047.15 | 0 | 0 | 0 | 0 | 0 | 7% | 6.98% | 0% | -7% |  | 34.51 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23839 | Stirling Dynamics - ST002-GFEM | Carrie (Caroline)Rosemary Frosin | 0 | BAX | STIRLING DYNAMICS LTD | MPE | Level NC | FIX |  |  |  | -3 |  | 0% | 0% | 0 | -5.54% | 0 | 19392.68 | -19392.68 | 6464.23 | 0 | 0 | 19985.76 | 19392.68 | 0 | 77 | 19392.68 | 300% | YES | 19392.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 1.46% | 1.46% | -5.54% |  | 43.38 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23355 | Spirit Tooling Support 2023 | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-23 | 0 |  |  | 22.93% | 89.02% | 89.02% | 0 | -0.82% | 91800 | 21053.34 | 70746.66 | 0 | 0 | 0 | 0 | 0 | 18742.5 | 2773.01 | 2310.84 | 0% | NO | 2310.84 | 0 | 18742.5 | 0 | 0 | 0 | 0 | 0 | 20% | 19.18% | 0% | -20% |  | 44.46 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23740 | Phase 2 - EJ200 ESS EHM Platform Migration | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 3 | FIX |  |  |  | 53.9437 | 11.45% | 249.5% | -0.001654% | 0 | 6.97% | 175971 | 20147.5 | 155823.5 | 2888.63 | 0 | 0 | 0 | 0 | 50278 | 100.03 | -28130.5 | -973.8% | NO | -28130.5 | 60334 | -0.33333 | 0 | 30166.8 | 0 | 30166.8 | 0 | 28% | 34.97% | 34.97% | 6.97% |  | 45.33 | [5 empty] | 2000
1733 | 2024-04-10 23:28 | P23823 | EXP-034 Spear 3 Test Equip Requirement Authority | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 21.9295 | 26.85% | 78.32% | -0.001244% | 0 | 0.32% | 85825 | 23044.13 | 62780.87 | 2862.85 | 0 | 0 | 0 | 0 | 18048.88 | 56 | 4995.25 | 174.5% | YES | 4995.25 | 21659 | -0.28667 | 0 | 21658.66 | 0 | 0 | 0 | 14% | 14.32% | 14.32% | 0.32% |  | 94.25 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23811 | Spirit T300 MRB Concessions | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -8.0244 |  | 0% | 0% | 0 | -7.2% | 0 | 23847.35 | -23847.35 | 2971.85 | 0 | 0 | 34639 | 23847.35 | 0 | 56 | 23847.35 | 802.4% | YES | 23847.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21% | 13.8% | 13.8% | -7.2% |  | 46.81 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23433 | Cavendish | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 6.5654 | 58.25% | 56.33% | 56.33% | 0 | -0.4% | 42240 | 24604 | 17636 | 2686.2 | 0 | 0 | 0 | 0 | 13859.2 | 91 | 10744.8 | 400% | YES | 10744.8 | 0 | 13859.2 | 0 | 0 | 0 | 0 | 0 | 7% | 6.6% | 6.51% | -0.49% |  | 45.77 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23724 | GKN S McConnell 2024 | Matthew Tweed | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  | 14.9036 | 49.7% | 57.95% | -0.0007% | 0 | 0.63% | 49820 | 24760.57 | 25059.43 | 1681.43 | 0 | 0 | 0 | 0 | 14348.16 | 96.64 | 10412.41 | 619.3% | YES | 10412.41 | 17218 | -0.17333 | 0 | 8848.03 | 8369.76 | 0 | 0 | 19% | 19.63% | 19.63% | 0.63% |  | 49.52 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23351 | Spirit 2023 - Design Man Serv (KL) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 26.47% | 93.15% | 93.15% | 0 | 0.09% | 93840 | 24840 | 69000 | 0 | 0 | 0 | 0 | 0 | 23138 | 2042.4 | 1702 | 0% | NO | 1702 | 0 | 23138 | 0 | 0 | 0 | 0 | 0 | 26% | 26.09% | 0% | -26% |  | 46 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23356 | Spirit 2023 - Design Man Serv (AH) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX | 2023-08-09 | 1 |  |  |  | 76.66% | 0.001332% | 23018.4 | 0.48% | 0 | 25023.08 | -25023.08 | 0 | 0 | 0 | 25300 | 25023.08 | 19182 | 30027.7 | 5841.08 | 0% | NO | 5841.08 | 23018 | 0.33333 | 0 | 0 | 0 | 23018.4 | 23018.4 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P22884 | Spirit Shorts Config Eng | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 66.3% | 100.1% | 100.1% | 0 | 0.56% | 38976 | 25841.9 | 13134.1 | 0 | 0 | 0 | 0 | 0 | 25863.2 | 0 | -0.3 | 0% | NO | -0.3 | 0 | 25863.2 | 0 | 0 | 0 | 0 | 0 | 7% | 7.56% | 0% | -7% |  | 20.3 | [5 empty] | 21
1733 | 2024-04-10 23:28 | P23354 | Spirit 2023 - Design Man Serv (PC) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 27.97% | 99.36% | 99.36% | 0 | 0.48% | 93840 | 26248.98 | 67591.02 | 0 | 0 | 0 | 0 | 0 | 26082 | 200.38 | 166.98 | 0% | NO | 166.98 | 0 | 26082 | 0 | 0 | 0 | 0 | 0 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23651 | PMO Spirit | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -30.6087 |  | 82.26% | -0.0005845% | 0 | 23.84% | 0 | 28512 | -28512 | 931.5 | 0 | 0 | 42680 | 28512 | 23454 | 218.73 | 5058 | 543% | YES | 5058 | 28145 | -0.16667 | 0 | 28144.8 | 0 | 0 | 0 | 0% | 23.84% | 23.17% | 23.17% |  | 36 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P22756 | A350 FLE Design Checker | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2022-03-23 | 1 |  |  | 68.39% | 119.7% | 119.7% | 0 | 16.46% | 34898.4 | 23867.15 | 11031.25 | 0 | 23867.15 | 24342.3 | 0 | 0 | 28571.1 | 0.06 | 0.05 | 0% | NO | 475.2 | 0 | 28571.1 | 0 | 0 | 0 | 0 | 0 | 0% | 16.46% | 0% | 0% |  | 0 | [5 empty] | 4704
1733 | 2024-04-10 23:28 | P23458 | Spirit Belfast Tooling Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-08-11 | 0 |  |  | 101.3% | 94.65% | 94.65% | 0 | 8.64% | 30384 | 30784.9 | -400.9 | 0 | 0 | 0 | 0 | 400.9 | 29139.1 | 1974.96 | 1645.8 | 0% | NO | 1645.8 | 0 | 29139.1 | 0 | 0 | 0 | 0 | 0 | 7% | 15.64% | 0% | -7% |  | 42.2 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23338 | Spirit 2023 - Blair Hainey | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 3.6406 | 93.83% | 55.75% | 55.75% | 0 | 5.21% | 34494.36 | 32364.74 | 2129.62 | 584.96 | 0 | 0 | 0 | 0 | 18042.36 | 159.86 | 14322.38 | 2448% | YES | 14322.38 | 0 | 18042.36 | 0 | 0 | 0 | 0 | 0 | 7% | 12.21% | 19.31% | 12.31% |  | 18.28 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23365 | GKN 777x Lip Skin Fixture | Steven Lawton | 0 | TOO | GKN AEROSPACE SERVICES LTD | MPE | Level 3 | FIX | 2023-10-12 | 0 |  |  | 41.91% | 113.2% | 113.2% | 0 | -9.26% | 79161.46 | 33175.67 | 45985.79 | 0 | 5109.88 | 5109.88 | 0 | 0 | 37544.22 | 0 | -4368.55 | 0% | NO | -4368.55 | 0 | 37544.22 | 0 | 0 | 0 | 0 | 0 | 22% | 12.74% | 0% | -22% |  | 56 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23821 | Supply of Safety Engineer | Dinna Elkhalifa | 0 | BXW | STIRLING DYNAMICS LTD | EES | Level NC | REIM |  |  |  | 0.023823 | 99.71% | 55.95% | -0.0003441% | 0 | 45.1% | 34006.44 | 33906.6 | 99.84 | 4190.82 | 0 | 0 | 0 | 0 | 18971.55 | 94.37 | 14935.05 | 356.4% | YES | 14935.05 | 22766 | -0.11667 | 0 | 22765.86 | 0 | 0 | 0 | 0% | 45.1% | 45.1% | 45.1% |  | 80.73 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P22768 | MRB Onsite Support - Spirit Belfast | Trevor Knox | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2023-07-27 | 0 |  |  |  | 0% | 0% | 0 | -17.07% | 0 | 34614 | -34614 | 0 | 0 | 0 | 36800 | 34614 | 0 | 41536.8 | 34614 | 0% | NO | 34614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | -7.07% | 0% | -10% |  | 36 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23347 | WoT Fixed Leading Edge - Industrial 2023 | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 112.8% | 42.03% | 42.03% | 0 | -0.41% | 31034.12 | 35002.1 | -3967.98 | 0 | 0 | 0 | 10500 | 3967.98 | 14710.56 | 24349.85 | 20291.54 | 0% | NO | 20291.54 | 0 | 14710.56 | 0 | 0 | 0 | 0 | 0 | 7% | 6.59% | 0% | -7% |  | 32.26 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23598 | MRB Onsite support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 47.2033 | 26.5% | 0% | 0% | 0 | -12.01% | 133056 | 35256.42 | 97799.58 | 2071.88 | 8736.42 | 14079.58 | 0 | 0 | 0 | 93.33 | 35256.42 | 1702% | YES | 40599.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 15.99% | 16.4% | -11.6% |  | 42.5 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23760 | EXP-033 Systems Engineering Support | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 40.5324 | 27.61% | 87.81% | 60.64% | 0 | -0.02% | 142300 | 39289.25 | 103010.75 | 2541.44 | 0 | 0 | 0 | 0 | 34500.75 | 37.31 | 4788.5 | 188.4% | YES | 4788.5 | 12811 | 23824.9167 | 0 | 12811.2 | 0 | 0 | 0 | 29% | 28.98% | 28.98% | -0.02% |  | 78.5 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23051 | Spirit Shorts A350 PAX Door | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3A | REIM |  |  |  |  | 205.9% | 105.4% | 105.4% | 0 | -0.63% | 18216 | 37513 | -19297 | 0 | 0 | 0 | 0 | 19297 | 39537 | 0 | 0 | 0% | NO | 0 | 0 | 39537 | 0 | 0 | 0 | 0 | 0 | 30% | 29.37% | 0% | -30% |  | 46 | [5 empty] | 2024
1733 | 2024-04-10 23:28 | P22752 | Tooling WoT - 2021 (Spirit) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | REIM | 2023-05-03 | 0 |  |  | 101.1% | 74.02% | 74.02% | 0 | -8.5% | 41525.1 | 41982.28 | -457.18 | 0 | 0 | 0 | 0 | 457.18 | 31076.1 | 13087.42 | 10906.18 | 0% | NO | 10906.18 | 0 | 31076.1 | 0 | 0 | 0 | 0 | 0 | 0% | -8.5% | 0% | 0% |  | 39.09 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23642 | MRB Belfast Support | Carl Warren | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -28.5204 |  | 0% | 0% | 0 | -43.73% | 0 | 44732.75 | -44732.75 | 1568.45 | 3135.3 | 3135.3 | 42350 | 44732.75 | 0 | 169.87 | 44732.75 | 2852% | YES | 44732.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22% | -21.73% | -24.39% | -46.39% |  | 38.52 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23339 | Spirit 2023 - Stewart Russell | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 64.51% | 100% | 100% | 0 | 0.62% | 72766.8 | 46941.72 | 25825.08 | 0 | 0 | 0 | 0 | 0 | 46941.74 | 0 | -0.02 | 0% | NO | -0.02 | 0 | 46941.74 | 0 | 0 | 0 | 0 | 0 | 7% | 7.62% | 0% | -7% |  | 35.67 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P22760 | SA Leading Edge Transport Media ('A' Frames) | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-11-15 | 1 |  |  | 85.99% | 110.7% | 116.3% | -3082.8 | 3.97% | 53480.8 | 45985.5 | 7495.3 | 0 | 42804 | 42804 | 0 | 0 | 50911.8 | 0 | -0.3 | 0% | NO | -0.3 | -3083 | 53480.9667 | 0 | 0 | 0 | -3082.8 | -3082.8 | 6% | 9.97% | 0% | -6% |  | 42 | [5 empty] | 4926
1733 | 2024-04-10 23:28 | P23822 | FCASW Requirements Management | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | -4 |  | 0% | 0% | 0 | -6.74% | 0 | 52249.32 | -52249.32 | 13062.33 | 0 | 0 | 98262.3 | 52249.32 | 0 | 63 | 52249.32 | 400% | YES | 52249.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 13.26% | 13.26% | -6.74% |  | 76.33 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23700 | IPDT Leads | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 32.9047 | 33.09% | 44.52% | -0.0006785% | 0 | -2.01% | 169263.9 | 56007.52 | 113256.38 | 3441.95 | 0 | 0 | 0 | 0 | 24932.12 | 112.08 | 31075.4 | 902.8% | YES | 31075.4 | 29919 | -0.38 | 0 | 29918.54 | 0 | 0 | 0 | 26% | 23.99% | 21.6% | -4.4% |  | 50.43 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23349 | Spirit 2023 - Stress Approve Man Serv (SB) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 58.24% | 80.05% | 80.05% | 0 | -0.29% | 97920 | 57024 | 40896 | 0 | 0 | 0 | 0 | 0 | 45648 | 13651.2 | 11376 | 0% | NO | 11376 | 0 | 45648 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23322 | GKN T Tomblin 2023 | Steven Lawton | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  | 0.92593 | 99.66% | 100% | 83.41% | 0 | -0.33% | 58952 | 58752 | 200 | 216 | 0 | 0 | 0 | 0 | 58752 | 91 | 0 | 0% | NO | 0 | 11693 | 49007.8333 | 0 | 8121.6 | 3571.2 | 0 | 0 | 17% | 16.67% | 16.67% | -0.33% |  | 48 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23106 | ME Support to NPD - Bobby Haggart | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  |  | 95.79% | 97.03% | 97.03% | 0 | 0.3% | 65675 | 62912.11 | 2762.89 | 0 | 0 | 0 | 0 | 0 | 61042.75 | 2243.24 | 1869.36 | 0% | NO | 1869.36 | 0 | 61042.75 | 0 | 0 | 0 | 0 | 0 | 15% | 15.3% | 0% | -15% |  | 35.65 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P22967 | Spirit 2022 - Channapa Laxmeshwar | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2023-01-26 | 2 |  |  | 69.69% | 121.3% | 121.3% | 0 | 9.53% | 75159.1 | 52376.15 | 22782.95 | 0 | 52376.15 | 54898.1 | 0 | 0 | 63508.8 | 0.42 | 0.35 | 0% | NO | 2522.3 | 0 | 63508.8 | 0 | 0 | 0 | 0 | 0 | 8% | 17.53% | 0% | -8% |  | 0 | [5 empty] | 11133
1733 | 2024-04-10 23:28 | P23193 | Spirit Shorts Stephen Greer | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -5.2472 | 104.5% | 94.51% | 85.08% | 0 | 8.6% | 61472 | 64239.94 | -2767.94 | 527.51 | 0 | 0 | 10878 | 2767.94 | 60712.78 | 104.92 | 3527.16 | 668.6% | YES | 3527.16 | 7269 | 54655.28 | 0 | 7268.72 | 0 | 0 | 0 | 23% | 31.6% | 34.03% | 11.03% |  | 35.09 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23341 | Spirit 2023 - Tom McFarlane | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 44.7213 | 60.03% | 92.55% | 65.95% | 7110.19 | -0.01% | 108666.4 | 65229.98 | 43436.42 | 971.27 | 0 | 0 | 0 | 0 | 60369.22 | 147.68 | 4860.76 | 500.5% | YES | 4860.76 | 20820 | 43019.22 | 11378.44 | 2331.04 | 0 | 7110.19 | 7110.19 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23729 | Honda Tooling | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | FIX |  |  |  | 8.5677 | 57.46% | 49.7% | 0% | 0 | 3.55% | 113610 | 65278.5 | 48331.5 | 5641.13 | 0 | 0 | 0 | 0 | 32445 | 91 | 32833.5 | 582% | YES | 32833.5 | 38934 | 0 | 0 | 38934 | 0 | 0 | 0 | 10% | 13.55% | 13.55% | 3.55% |  | 42 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23744 | Model Factory | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 43.205 | 24.38% | 104.1% | -0.0002606% | 27429.6 | 8.35% | 262300 | 63959.25 | 198340.75 | 4590.69 | 0 | 0 | 0 | 0 | 66574 | 93.85 | -614.75 | -13.39% | NO | -614.75 | 79889 | -0.16667 | 0 | 26229.6 | 26229.6 | 27429.6 | 27429.6 | 28% | 36.35% | 36.35% | 8.35% |  | 50.5 | [5 empty] | 2000
1733 | 2024-04-10 23:28 | P23561 | SAAB | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2024-01-01 | 0 |  | 10.7403 | 82.46% | 121.1% | 121.1% | 0 | 8.77% | 67485 | 55649.23 | 11835.77 | 1102 | 0 | 0 | 0 | 0 | 67399.4 | 0 | -0.17 | -0.01543% | NO | -0.17 | 0 | 67399.4 | 0 | 0 | 0 | 0 | 0 | 16% | 24.77% | 100% | 84% |  | 36.82 | [5 empty] | 11750
1733 | 2024-04-10 23:28 | P23600 | MBDA EXP-EE-023 Bristone Certification | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 59.65% | 100% | 100% | 0 | 0.4% | 126600 | 75517 | 51083 | 0 | 0 | 0 | 0 | 0 | 75517 | 0 | 0 | 0% | NO | 0 | 0 | 75517 | 0 | 0 | 0 | 0 | 0 | 41% | 41.4% | 0% | -41% |  | 78.5 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23080 | Spirit Shorts DManagement Cairan Cullen | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 136.2922 | 50.77% | 97.69% | 91.01% | 3787.8 | -1.23% | 149600 | 75954.5 | 73645.5 | 540.35 | 0 | 0 | 0 | 0 | 74199.7 | 179.75 | 1754.8 | 324.8% | YES | 1754.8 | 6086 | 69128.0333 | 0 | 2298.36 | 0 | 3787.8 | 3787.8 | 24% | 22.77% | 13.03% | -10.97% |  | 44.39 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P22505 | Spirit MRB Engineering Support 2021 | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 1 |  |  | 91.17% | 100% | 95.78% | 4020.48 | 21.2% | 87110.4 | 79414.95 | 7695.45 | 0 | 0 | 0 | 0 | 0 | 79414.95 | 4020.48 | 0 | 0% | NO | 0 | 4020 | 76064.95 | 0 | 0 | 0 | 4020.48 | 4020.48 | 0% | 21.2% | 0% | 0% |  | 41.88 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23560 | NJEWCS TAF202302 SM | Natalie Sinclair | 0 | COB | CHELTON LIMITED | EES | Level 2 | FIX |  |  |  |  | 97.96% | 50.1% | 50.1% | 0 | 11.94% | 81500 | 79836.44 | 1663.56 | 0 | 0 | 0 | 0 | 0 | 40000 | 174.22 | 39836.44 | 0% | NO | 39836.44 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 28% | 39.94% | 39.49% | 11.49% |  | 73.01 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P22885 | ME Support (Baxi) | Trevor Knox | 0 | HUV | BAXI HEATING UK LIMITED | ME | Level 3 | FIX | 2023-01-12 | 0 |  |  | 68.78% | 108.7% | 108.7% | 0 | 13.05% | 106632.96 | 73340.24 | 33292.72 | 0 | 0 | 0 | 0 | 0 | 79748.12 | 1531.35 | 1276.12 | 0% | NO | 1276.12 | 0 | 79748.12 | 0 | 0 | 0 | 0 | 0 | 15% | 28.05% | 0% | -15% |  | 44.37 | [5 empty] | 7684
1733 | 2024-04-10 23:28 | P23438 | A220 Spirit Shorts DTC - Stephen Corry | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 18.4139 | 85.55% | 78.54% | 49.23% | 0 | -7.3% | 95928.4 | 82068.6 | 13859.8 | 752.68 | 0 | 0 | 0 | 0 | 64459.8 | 341.41 | 17608.8 | 2339% | YES | 17608.8 | 28872 | 40399.8 | 0 | 28872.36 | 0 | 0 | 0 | 23% | 15.7% | 16.75% | -6.25% |  | 49.81 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23171 | Spirt Shorts Weights Eng | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 69.18% | 133.5% | 103.1% | 0 | 2.68% | 103113.14 | 71329.32 | 31783.82 | 0 | 71329.32 | 85975.13 | 0 | 0 | 95259.1 | 70.25 | -11659.78 | 0% | NO | 2986.03 | 26047 | 73553.2667 | 9273.05 | 0 | 16774.18 | 0 | 0 | 12% | 14.68% | 0% | -12% |  | 0 | [5 empty] | 12270
1733 | 2024-04-10 23:28 | P23335 | GKN S McConnell 2023 | Steven Lawton | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2023-12-31 | 1 |  |  | 96.61% | 100% | 91.76% | 0 | 0.74% | 87420 | 84459 | 2961 | 0 | 0 | 0 | 0 | 0 | 84459 | 8347.2 | 0 | 0% | NO | 0 | 8347 | 77503.1667 | 0 | 0 | 0 | 8347.2 | 0 | 15% | 15.74% | 0% | -15% |  | 47 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P22965 | Spirit 2022 - Design Man Serv (AH) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 1 |  |  | 106.7% | 96.66% | 92.02% | 4759.75 | 3.14% | 80079.56 | 85441.32 | -5361.76 | 0 | 0 | 0 | 0 | 5361.76 | 82588.96 | 8182.59 | 2852.36 | 0% | NO | 2852.36 | 4760 | 78622.2933 | 0 | 0 | 0 | 4759.75 | 4759.75 | 14% | 17.14% | 0% | -14% |  | 42.44 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23523 | Applique Armour Support | Dushan Fernando | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-18 | 1 |  |  | 72.43% | 138.1% | 98.47% | 0 | 3.42% | 118200 | 85606.5 | 32593.5 | 0 | 0 | 0 | 0 | 0 | 118200 | 1567.8 | -32593.5 | 0% | NO | -32593.5 | 40680 | 84300 | 0 | 40680 | 0 | 0 | 0 | 25% | 28.42% | 0% | -25% |  | 64.29 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P22964 | Spirit 2022 - MRB Man Serv (JC) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 100.6% | 97.95% | 97.95% | 0 | 1.91% | 85435.2 | 85960.26 | -525.06 | 0 | 0 | 0 | 0 | 525.06 | 84199.74 | 2112.62 | 1760.52 | 0% | NO | 1760.52 | 0 | 84199.74 | 0 | 0 | 0 | 0 | 0 | 16% | 17.91% | 0% | -16% |  | 42.69 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23342 | Spirit 2023 - Channapa Laxmeshwar | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 52.39% | 88.11% | 74.35% | 4036.8 | -3.69% | 158696.7 | 83134.33 | 75562.37 | 0 | 83134.33 | 94827 | 0 | 0 | 73251.1 | 106.52 | 12733.23 | 0% | NO | 24425.9 | 13725 | 61813.6 | 9688.32 | 0 | 0 | 4036.8 | 4036.8 | 7% | 3.31% | 0% | -7% |  | 0 | [5 empty] | 2850
1733 | 2024-04-10 23:28 | P23340 | Spirit 2023 - John Cole | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 44.867 | 57.5% | 91.71% | 64.29% | 8831.16 | -0.01% | 150129.72 | 86322.6 | 63807.12 | 1422.14 | 0 | 0 | 0 | 0 | 79162.2 | 150.69 | 7160.4 | 503.5% | YES | 7160.4 | 28403 | 55493.0333 | 14750.42 | 4821.34 | 0 | 8831.16 | 8831.16 | 7% | 6.99% | 6.99% | -0.01% |  | 39.78 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P22963 | Spirit 2022 - Design Man Serv (PC) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 1 |  |  | 108.6% | 104% | 94.46% | 9938.48 | 3.18% | 80079.56 | 86926.74 | -6847.18 | 0 | 0 | 0 | 0 | 6847.18 | 90389.95 | 5782.63 | -3463.21 | 0% | NO | -3463.21 | 9938 | 82108.2833 | 0 | 0 | 0 | 9938.48 | 9938.48 | 13% | 16.18% | 0% | -13% |  | 42.39 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23465 | A220 ToW Design Offload (Wing) | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 39.3889 | 66.79% | 91.36% | 63.25% | 0 | -4.71% | 132000 | 88168 | 43832 | 1112.8 | 0 | 0 | 0 | 0 | 80549.6 | 96.89 | 7618.4 | 684.6% | YES | 7618.4 | 29737 | 55768.7667 | 0 | 29737.44 | 0 | 0 | 0 | 20% | 15.29% | 13.92% | -6.08% |  | 42.8 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23079 | Spirit Shorts Nomenclature | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 0.036137 | 99.98% | 88.41% | 77.28% | 0 | 2.01% | 88455 | 88437.6 | 17.4 | 481.5 | 0 | 0 | 0 | 0 | 78185.2 | 237.36 | 10252.4 | 2129% | YES | 10252.4 | 11811 | 68342.7 | 0 | 11810.64 | 0 | 0 | 0 | 20% | 22.01% | 25.23% | 5.23% |  | 30.77 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23336 | Spirit 2023 - Neil Rampling | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 28.9357 | 67.22% | 91.62% | 53.17% | 21586.03 | -0.01% | 133901.52 | 90012.76 | 43888.76 | 1516.77 | 0 | 0 | 0 | 0 | 82473.26 | 197.46 | 7539.5 | 497.1% | YES | 7539.5 | 41533 | 47862.4267 | 15306.07 | 4640.79 | 0 | 21586.03 | 21586.03 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23586 | Project Management Support | Peter Bowen | 0 | BDX | MBDA UK LIMITED | MPE | Level NC | REIM |  |  |  | 41.8709 | 56.45% | 74.3% | 74.3% | 0 | -26.37% | 160000 | 90320.46 | 69679.54 | 1664.15 | 1277.2 | 1277.2 | 0 | 0 | 67103.86 | 65.82 | 23216.6 | 1395% | YES | 23216.6 | 0 | 67103.86 | 0 | 0 | 0 | 0 | 0 | 49% | 22.63% | 21.56% | -27.44% |  | 80 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23345 | Spirit 2023- Jonathan Escosio | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | -7.3639 | 119.3% | 75.5% | 56.57% | 15846.34 | -0.34% | 75970.62 | 90600.57 | -14629.95 | 1986.7 | 0 | 0 | 8938 | 14629.95 | 68401.74 | 215.41 | 22198.83 | 1117% | YES | 22198.83 | 20581 | 51250.9067 | 0 | 4734.58 | 0 | 15846.34 | 15846.34 | 7% | 6.66% | 25.2% | 18.2% |  | 43.01 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23375 | GKN Jaap Peters NL 2023 | Steven Lawton | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2024-03-01 | 2 |  |  | 93.37% | 105.3% | 85.02% | 0 | -15.93% | 97123.22 | 90686.41 | 6436.81 | 0 | 90686.41 | 90686.41 | 0 | 0 | 95456.72 | 108.86 | -920.31 | 0% | NO | -920.31 | 22027 | 77100.8867 | 0 | 0 | 8793.29 | 13234.06 | 0 | 20% | 4.07% | 0% | -20% |  | 0 | [5 empty] | 3850
1733 | 2024-04-10 23:28 | P23784 | Tempest Tooling Offload 2024 | Gary Kempster | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  | -13.8932 |  | 0% | 0% | 0 | -11.75% | 0 | 95087.45 | -95087.45 | 6844.15 | 0 | 0 | 107936.4 | 95087.45 | 0 | 91 | 95087.45 | 1389% | YES | 95087.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 18.25% | 18.25% | -11.75% |  | 54.82 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23551 | Ian Berry 2023 H2 | Natalie Sinclair | 0 | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  | -7.3356 | 126.2% | 70.23% | 70.23% | 0 | 13.46% | 75810 | 95705.12 | -19895.12 | 2712.15 | 0 | 0 | 24259.2 | 19895.12 | 67217.49 | 69.12 | 28487.63 | 1050% | YES | 28487.63 | 0 | 67217.49 | 0 | 0 | 0 | 0 | 0 | 22% | 35.46% | 37.71% | 15.71% |  | 77.6 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23753 | Tempest Composites Maturation | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 2.0951 | 78.49% | 30.98% | -0.0001993% | 0 | -10.67% | 127848.45 | 100352.75 | 27495.7 | 13123.78 | 0 | 0 | 0 | 0 | 31084.8 | 93.94 | 69267.95 | 527.8% | YES | 69267.95 | 37302 | -0.2 | 0 | 37301.76 | 0 | 0 | 0 | 32% | 21.33% | 21.33% | -10.67% |  | 64.66 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23583 | Castalla - Test Rig Design | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -22.4096 | 148.7% | 67.19% | 61% | 0 | -6.38% | 67520 | 100428.5 | -32908.5 | 1468.5 | 0 | 0 | 36106 | 32908.5 | 67482.1 | 135.59 | 32946.4 | 2244% | YES | 32946.4 | 7469 | 61257.9333 | 0 | 7469.4 | 0 | 0 | 0 | 21% | 14.62% | 16.88% | -4.12% |  | 42.79 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23545 | Ultra CSS continuation 2023 H2 | Natalie Sinclair | 0 | ULT | ULTRA SONAR SYSTEMS LIMITED | EES | Level NC | REIM |  |  |  | -33.0227 | 133% | 74.66% | 74.66% | 0 | 2.22% | 76000 | 101057.6 | -25057.6 | 758.8 | 0 | 0 | 24259.2 | 25057.6 | 75451.2 | 101.33 | 25606.4 | 3375% | YES | 25606.4 | 0 | 75451.2 | 0 | 0 | 0 | 0 | 0 | 23% | 25.22% | 25% | 2% |  | 80 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23754 | Tempest Composites WP4 | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 18.3726 | 35.15% | 0% | 0% | 0 | -1.38% | 310945.68 | 109282.7 | 201662.98 | 10976.31 | 1344.88 | 1344.88 | 0 | 0 | 0 | 91.78 | 109282.7 | 995.6% | YES | 109282.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36% | 34.62% | 34.62% | -1.38% |  | 62.63 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23353 | Spirit 2023 - MRB Man Serv (JC) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  | 54.6167 | 59.84% | 62.45% | 62.45% | 0 | 9.98% | 183600 | 109867.5 | 73732.5 | 1350 | 0 | 0 | 0 | 0 | 68615.25 | 190.9 | 41252.25 | 3056% | YES | 41252.25 | 0 | 68615.25 | 0 | 0 | 0 | 0 | 0 | 7% | 16.98% | 13.57% | 6.57% |  | 45 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23588 | BAE Typhoon MRB MC Shop Concessions | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 29.1881 | 65.44% | 97.87% | 70.09% | 14399.76 | -3.74% | 175060.5 | 114561.67 | 60498.83 | 2072.72 | 0 | 0 | 0 | 0 | 112121.71 | 98.39 | 2439.96 | 117.7% | NO | 2439.96 | 38191 | 80295.8767 | 10272.55 | 13518.34 | 14399.76 | 0 | 14399.76 | 31% | 27.26% | 29.27% | -1.73% |  | 55.51 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23352 | Spirit 2023 - Stress Approve Man Serv (CC) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  | -8.8125 | 117.3% | 60.88% | 60.88% | 0 | 6.65% | 97920 | 114840 | -16920 | 1920 | 0 | 0 | 29856 | 16920 | 69912 | 208.76 | 44928 | 2340% | YES | 44928 | 0 | 69912 | 0 | 0 | 0 | 0 | 0 | 7% | 13.65% | 4.69% | -2.31% |  | 48 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P22918 | Spirit Shorts Graduates | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 15.3479 | 88.73% | 92.54% | 60.99% | 0 | 9.47% | 130000 | 115343.39 | 14656.61 | 954.96 | 0 | 0 | 9900 | 0 | 106734.95 | 228.49 | 8608.44 | 901.4% | YES | 8608.44 | 43660 | 70351.6167 | 0 | 0 | 43659.95 | 0 | 0 | 7% | 16.47% | 17.17% | 10.17% |  | 23.3 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23664 | Tempest Composites WP3 | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 5.544 | 94.46% | 14.28% | 14.28% | 0 | -5.11% | 122455.49 | 115670.48 | 6785.01 | 1223.84 | 0 | 0 | 0 | 0 | 16518.7 | 240.48 | 99151.78 | 8102% | YES | 99151.78 | 0 | 16518.7 | 0 | 0 | 0 | 0 | 0 | 37% | 31.89% | 33.71% | -3.29% |  | 60.76 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P22736 | WoT Fixed Leading Edge - Industrial | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 106.7% | 93.42% | 91.32% | 3019.54 | 0.01% | 112196.27 | 119668.47 | -7472.2 | 0 | 0 | 0 | 0 | 7472.2 | 111796.68 | 12465.69 | 7871.79 | 0% | NO | 7871.79 | 3020 | 109280.0133 | 0 | 0 | 0 | 3019.54 | 3019.54 | 7% | 7.01% | 0% | -7% |  | 32.26 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P22883 | Spirit Shorts Evtol PMO C. Hatton | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 88.4947 | 65.16% | 89.99% | 89.99% | 0 | -11.75% | 185800 | 121066.15 | 64733.85 | 731.5 | 0 | 0 | 0 | 0 | 108946.73 | 99.66 | 12119.42 | 1657% | YES | 12119.42 | 0 | 108946.73 | 0 | 0 | 0 | 0 | 0 | 26% | 14.25% | 22.96% | -3.04% |  | 36.79 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23282 | Tooling Support (MBDA) | Dushan Fernando | 0 | BDV | MBDA UK LIMITED | ME | Level NC | REIM |  |  |  | 46.3338 | 63.07% | 98.06% | 84.12% | 0 | -8.37% | 195672.4 | 123406.1 | 72266.3 | 1559.69 | 0 | 0 | 0 | 0 | 121010.44 | 76.9 | 2395.66 | 153.6% | YES | 2395.66 | 20648 | 103803.7733 | 0 | 20647.76 | 0 | 0 | 0 | 30% | 21.63% | 30.37% | 0.37% |  | 49.72 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23270 | Shorts Project X | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 10.3132 | 88.11% | 92.51% | 70.13% | 0 | 0.55% | 142248 | 125331.08 | 16916.92 | 1640.31 | 0 | 0 | 0 | 0 | 115944.34 | 155.68 | 9386.74 | 572.3% | YES | 9386.74 | 33666 | 87889.34 | 10030.61 | 23635.49 | 0 | 0 | 0 | 13% | 13.55% | 10.99% | -2.01% |  | 45.34 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P22861 | WoT FLE Lifting & Handling Tools | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2023-06-14 | 1 |  |  | 65.17% | 101.6% | 101.6% | 0 | 12.01% | 173987.21 | 113381.75 | 60605.46 | 0 | 50078 | 58423.58 | 0 | 0 | 115203.5 | 12813.9 | 10678.25 | 0% | NO | 19023.83 | 0 | 115203.5 | 0 | 0 | 0 | 0 | 0 | 1% | 13.01% | 0% | -1% |  | 45 | [5 empty] | 12500
1733 | 2024-04-10 23:28 | P23810 | Strategic Enablement | Owain Jones | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -20.58% | 0 | 133060.2 | -133060.2 | 0 | 0 | 0 | 134000 | 133060.2 | 0 | 96.21 | 133060.2 | 0% | NO | 133060.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | -2.58% | -2.58% | -20.58% |  | 42 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23533 | External Stowage Design and Detail Support | Dushan Fernando | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 1 |  |  | 102.4% | 97.65% | 73.24% | 0 | 3.33% | 140000 | 143368.75 | -3368.75 | 0 | 0 | 0 | 12936 | 3368.75 | 140000 | 41999.7 | -0.25 | 0% | NO | -0.25 | 42000 | 105000 | 0 | 42000 | 0 | 0 | 0 | 27% | 30.33% | 0% | -27% |  | 60.04 | [5 empty] | -3369
1733 | 2024-04-10 23:28 | P23650 | MBDA Recruitment Management costs | Andrew Slaney | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM | 2024-02-01 | 0 |  |  |  | 0% | 0% | 0 | -20.2% | 0 | 240971.5 | -240971.5 | -25000 | 0 | 0 | 266000 | 240971.5 | 0 | 132.52 | 140971.5 | -563.9% | NO | 140971.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | -17.2% | -441% | -444% |  | 82.3 | [5 empty] | -100000
1733 | 2024-04-10 23:28 | P23741 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  | 43.4142 | 22.44% | 98.02% | -0.0001159% | 0 | 1.57% | 640812 | 143813.25 | 496998.75 | 11447.84 | 0 | 0 | 0 | 0 | 140959 | 92.27 | 4854.25 | 42.4% | NO | 4854.25 | 169151 | -0.16667 | 0 | 62626.8 | 52662 | 53862 | 0 | 28% | 29.57% | 29.57% | 1.57% |  | 38.84 | [5 empty] | 2000
1733 | 2024-04-10 23:28 | P22954 | Technical Support Step 1 | Owain Jones | 0 | HUV | HUARUI SPIRIT AEROSPACE MANUFACT | ME | Level 2 | REIM |  |  |  |  | 94.81% | 58.01% | 58.01% | 0 | 0.31% | 155501.18 | 147431.58 | 8069.6 | 0 | 23043 | 23043 | 0 | 0 | 85525.49 | 61906.09 | 61906.09 | 0% | NO | 61906.09 | 0 | 85525.49 | 0 | 0 | 0 | 0 | 0 | 30% | 30.31% | 0% | -30% |  | 60.79 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23386 | Software Development - BMS | Peter Bowen | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 98.78% | 100% | 100% | 0 | 4.31% | 149650 | 147823.35 | 1826.65 | 0 | 0 | 0 | 0 | 0 | 147823.35 | 0 | 0 | 0% | NO | 0 | 0 | 147823.35 | 0 | 0 | 0 | 0 | 0 | 18% | 22.31% | 22.61% | 4.61% |  | 78.5 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23437 | Embedded Software Engineer | Peter Bowen | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 2.6313 | 98.73% | 100% | 96.08% | 0 | -6.29% | 150150 | 148239.36 | 1910.64 | 726.13 | 737.86 | 737.86 | 0 | 0 | 148239.36 | 20.28 | 0 | 0% | NO | 0 | 6971 | 142430.1933 | 0 | 6970.8 | 0 | 0 | 0 | 22% | 15.71% | 16.24% | -5.76% |  | 78.5 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23550 | Tempest Composites | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -5.3077 | 100.9% | 99.13% | 99.13% | 0 | 5.11% | 149494.92 | 150812.24 | -1317.32 | 248.19 | 0 | 0 | 2396.12 | 1317.32 | 149494.92 | 6.52 | 1317.32 | 530.8% | YES | 1317.32 | 0 | 149494.92 | 0 | 0 | 0 | 0 | 0 | 26% | 31.11% | 34.17% | 8.17% |  | 61.59 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P22440 | Spirit Managed Service - F&DT and Static Approval | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 3 |  |  | 88.56% | 92.56% | 92.56% | 0 | 11.51% | 173500 | 153656.25 | 19843.75 | 0 | 52115 | 55720 | 0 | 0 | 142225.12 | 13717.36 | 11431.13 | 0% | NO | 15036.13 | 0 | 142225.12 | 0 | 0 | 0 | 0 | 0 | 0% | 11.51% | 0% | 0% |  | 44.73 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P22982 | Spirit 2022 - Hugh Sloan | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 83.8799 | 62.12% | 94.92% | 82.58% | 8217.17 | -0.52% | 247473 | 153727.18 | 93745.82 | 1117.62 | 0 | 0 | 0 | 0 | 145911.5 | 187.41 | 7815.68 | 699.3% | YES | 7815.68 | 22757 | 126947.3333 | 10239.53 | 4300.18 | 0 | 8217.17 | 8217.17 | 7% | 6.48% | 1.35% | -5.65% |  | 35.43 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23739 | Lifing Services DACs | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  | 50.6424 | 24.08% | 104.4% | 0.0002108% | 0 | 2.99% | 656508 | 158096.8 | 498411.2 | 9841.78 | 0 | 0 | 0 | 0 | 165127 | 91 | -7030.2 | -71.43% | NO | -7030.2 | 198152 | 0.33333 | 0 | 65650.8 | 65650.8 | 66850.8 | 0 | 28% | 30.99% | 30.99% | 2.99% |  | 37.75 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23518 | Systems Engineering support to FCAS | Peter Bowen | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 18.9889 | 82.02% | 94.17% | 89% | 0 | -3.95% | 193736.8 | 158893.25 | 34843.55 | 1834.94 | 3927.4 | 3927.4 | 0 | 0 | 149625.43 | 47.16 | 9267.82 | 505.1% | YES | 9267.82 | 9844 | 141422.0967 | 0 | 9843.9 | 0 | 0 | 0 | 30% | 26.05% | 3.5% | -26.5% |  | 67.99 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23667 | Safety Systems Engineer | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 62.614 | 40.3% | 95.61% | 85.46% | 0 | -9.96% | 398000 | 160380 | 237620 | 3795 | 0 | 0 | 0 | 0 | 153340 | 38.58 | 7040 | 185.5% | YES | 7040 | 19536 | 137060 | 0 | 19536 | 0 | 0 | 0 | 47% | 37.04% | 29.32% | -17.68% |  | 110 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23421 | A220 DTC | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 12.9335 | 75.45% | 73.42% | 65.38% | 0 | -28.37% | 217089.12 | 163793.13 | 53295.99 | 4120.78 | 0 | 0 | 0 | 0 | 120261.6 | 98.41 | 43531.53 | 1056% | YES | 43531.53 | 15801 | 107094.1 | 0 | 15800.9 | 0 | 0 | 0 | 29% | 0.63% | 6.45% | -22.55% |  | 46.05 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23464 | A220 Project X Design Offload | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 69.1576 | 51.68% | 100% | 64.09% | 27862.8 | -9.3% | 332340 | 171762.9 | 160577.1 | 2321.9 | 0 | 0 | 0 | 0 | 171762.9 | 153.64 | 0 | 0% | NO | 0 | 74010 | 110087.9 | 18361.2 | 27785.76 | 0 | 27862.8 | 27862.8 | 26% | 16.7% | 14.75% | -11.25% |  | 42.88 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23508 | Verification and Validation | Peter Bowen | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 100.5759 | 80.77% | 100% | 97.06% | 0 | 10.77% | 212950 | 171993.5 | 40956.5 | 407.22 | 0 | 0 | 0 | 0 | 171993.53 | 13.78 | -0.03 | -0.007367% | NO | -0.03 | 6076 | 166930.1967 | 0 | 6075.9 | 0 | 0 | 0 | 24% | 34.77% | 33.6% | 9.6% |  | 78.5 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23648 | EXP-032 Delivery of Datalink Eng support - FCAS AP | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 22.5878 | 49.78% | 82.4% | 73.59% | 0 | 5.61% | 371000 | 184692.95 | 186307.05 | 8248.13 | 1032.95 | 1032.95 | 0 | 0 | 152192.95 | 42.18 | 32500 | 394% | YES | 32500 | 19536 | 135912.95 | 0 | 19536 | 0 | 0 | 0 | 22% | 27.61% | 27.83% | 5.83% |  | 103.15 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23524 | Bombardier Regional Jets (BRJ) | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -2614.0777 | 130.8% | 56.87% | 55.26% | 3694.07 | -4.75% | 146287.84 | 191380.68 | -45092.84 | 17.25 | 0 | 0 | 46750 | 45092.84 | 108838.22 | 356.74 | 82542.46 | 478507% | YES | 82542.46 | 3694 | 105759.8867 | 0 | 0 | 0 | 3694.07 | 3694.07 | 18% | 13.25% | 15.01% | -2.99% |  | 43.92 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23506 | ASTER Mid-Life Refurbishment Project Manager | Peter Bowen | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 10.9425 | 86.35% | 96.01% | 89.97% | 0 | 1.04% | 224900 | 194206.41 | 30693.59 | 2805 | 2806.41 | 2806.41 | 0 | 0 | 186451.41 | 36.05 | 7755 | 276.5% | YES | 7755 | 14058 | 174736.41 | 14058 | 0 | 0 | 0 | 0 | 25% | 26.04% | 26.35% | 1.35% |  | 110 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23008 | Spirit Shorts Project Rachel | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 68.49% | 91.32% | 91.32% | 0 | -9.7% | 286960 | 196531.2 | 90428.8 | 0 | 0 | 0 | 0 | 0 | 179472.8 | 20470.08 | 17058.4 | 0% | NO | 17058.4 | 0 | 179472.8 | 0 | 0 | 0 | 0 | 0 | 15% | 5.3% | 0.31% | -14.69% |  | 46.04 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23505 | EXP-022 Meteor TBUS T&E support | Peter Bowen | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 17.0574 | 80.59% | 98.35% | 90.29% | 0 | -1.1% | 246744.4 | 198861.16 | 47883.24 | 2807.19 | 0 | 0 | 0 | 0 | 195582.38 | 37.07 | 3278.78 | 116.8% | NO | 3278.78 | 19242 | 179547.38 | 0 | 19241.59 | 0 | 0 | 0 | 20% | 18.9% | 15.67% | -4.33% |  | 89.83 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23019 | EXP034-B Actuator Development | Peter Bowen | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 103.1% | 89.91% | 89.91% | 0 | -16.68% | 215541.2 | 222215.54 | -6674.34 | -1261 | 12297.9 | 12297.9 | 0 | 6674.34 | 199796.76 | 91.24 | 397.78 | -31.54% | NO | 397.78 | 0 | 199796.76 | 0 | 0 | 0 | 0 | 0 | 34% | 17.32% | 79.64% | 45.64% |  | 58.45 | [5 empty] | -22021
1733 | 2024-04-10 23:28 | P23242 | Physical Architecture & System Engineering Support | Peter Bowen | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 36.5908 | 67.21% | 97.03% | 91.29% | 0 | 7.91% | 305459 | 205291.71 | 100167.29 | 2737.5 | 775.55 | 775.55 | 0 | 0 | 199187.05 | 42.12 | 5750.66 | 210.1% | YES | 5750.66 | 14130 | 187412.05 | 0 | 14130 | 0 | 0 | 0 | 15% | 22.91% | 7% | -8% |  | 78.2 | [5 empty] | -354
1733 | 2024-04-10 23:28 | P23373 | Raytheon Michael Bellini | Natalie Sinclair | 0 | RAS | RAYTHEON UNITED KINGDOM LIMITED | EES | Level NC | REIM |  |  |  | 2.3943 | 96.83% | 92.37% | 82.44% | 24734.7 | -7.85% | 214367.4 | 207567.79 | 6799.61 | 2839.91 | 0 | 0 | 0 | 0 | 191739.73 | 68.43 | 15828.06 | 557.3% | YES | 15828.06 | 24735 | 171127.23 | 0 | 24734.7 | 0 | 0 | 24734.7 | 45% | 37.15% | 38.63% | -6.37% |  | 91.61 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23677 | ME Managed Service - Phase 1 | Paul Watson | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  | 21.6424 | 39.43% | 98.04% | -0.0001906% | 0 | -16.7% | 554400 | 218577.6 | 335822.4 | 15516.9 | 0 | 0 | 0 | 0 | 214301.25 | 114.31 | 4276.35 | 27.56% | NO | 4276.35 | 257162 | -0.41667 | 120379.5 | 136782 | 0 | 0 | 0 | 33% | 16.3% | 19.34% | -13.66% |  | 43.78 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23743 | EHM Cloud Migration | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 36.3245 | 19.86% | 126.9% | 0.0001652% | 0 | 6.03% | 1016000 | 201766.5 | 814233.5 | 22415.56 | 0 | 0 | 0 | 0 | 256032 | 99.12 | -36265.5 | -161.8% | NO | -36265.5 | 307238 | 0.33333 | 0 | 102336 | 102412.8 | 102489.6 | 0 | 28% | 34.03% | 34.03% | 6.03% |  | 53.82 | [5 empty] | 18000
1733 | 2024-04-10 23:28 | P23629 | F35 FTI | Christopher McCarthy | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level NC | REIM |  |  |  | -26.3429 |  | 87.7% | 87.7% | 0 | -1.04% | 0 | 233440.84 | -233440.84 | 8861.61 | 0 | 0 | 0 | 233440.84 | 204738.05 | 22.39 | 28702.79 | 323.9% | YES | 28702.79 | 0 | 204738.05 | 0 | 0 | 0 | 0 | 0 | 31% | 29.96% | 28.72% | -2.28% |  | 61.82 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23816 | Typhoon FTI Works - 2024 Fixed Price Element | Christopher McCarthy | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 5.1848 | 60.71% | 0% | 0% | 0 | -3.67% | 404176.65 | 245389.11 | 158787.54 | 30625.39 | 0 | 0 | 0 | 0 | 0 | 70 | 245389.11 | 801.3% | YES | 245389.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 26.33% | 26.33% | -3.67% |  | 53.27 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23472 | Tempest Wing Design | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 21.2018 | 49.4% | 127.5% | 107.7% | 0 | -11.02% | 483869.78 | 239054.61 | 244815.17 | 11546.88 | 223175 | 356900 | 0 | 0 | 304757.78 | 10.21 | -40703.18 | -352.5% | NO | 93021.82 | 56671 | 257531.9467 | 32716.75 | 23954.72 | 0 | 0 | 0 | 23% | 11.98% | 33.99% | 10.99% |  | 46.74 | [5 empty] | 25000
1733 | 2024-04-10 23:28 | P23603 | Typhoon IMDLR | Christopher McCarthy | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 11.5705 | 87.37% | 44.95% | 0.0001276% | 0 | 5.44% | 305067.09 | 266544.12 | 38522.97 | 3329.41 | 0 | 0 | 61083.75 | 0 | 119807.84 | 355.78 | 146736.28 | 4407% | YES | 146736.28 | 143769 | 0.34 | 0 | 143769.41 | 0 | 0 | 0 | 26% | 31.44% | 33.04% | 7.04% |  | 57.1 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23007 | EXP-006A - Brimstone 3 | Peter Bowen | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 62.5072 | 67.18% | 98.64% | 90.56% | 0 | -2.77% | 406450 | 273045.91 | 133404.09 | 2134.22 | 0 | 0 | 0 | 0 | 269336.75 | 69.02 | 3679.16 | 172.4% | YES | 3679.16 | 26470 | 247278.4167 | 11492.4 | 0 | 14977.8 | 0 | 0 | 25% | 22.23% | 29.94% | 4.94% |  | 69.83 | [5 empty] | -30
1733 | 2024-04-10 23:28 | P21463 | Safety & Monitoring Systems at DM Beith & Gosport | Harry James Kellett | 0 | BXW | MOD | EES | Level 2 | FIX |  |  |  | 31.0847 | 80.09% | 124.9% | 124.9% | 0 | -27.49% | 349404.99 | 279825.42 | 69579.57 | 2238.39 | 65353.08 | 77379.59 | 21721 | 0 | 349386.99 | 0 | -69561.57 | -3108% | NO | -57535.06 | 0 | 349386.99 | 0 | 0 | 0 | 0 | 0 | 48% | 20.51% | 27.05% | -20.95% |  | 53 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23308 | NATO JEWCS | Natalie Sinclair | 0 | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  | 141.4837 | 81.94% | 93.6% | 93.6% | 0 | -3.63% | 356307 | 291951.72 | 64355.28 | 454.86 | 613.89 | 613.89 | 0 | 0 | 273254.06 | 70 | 18697.66 | 4111% | YES | 18697.66 | 0 | 273254.06 | 0 | 0 | 0 | 0 | 0 | 24% | 20.37% | 11.83% | -12.17% |  | 75.81 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23617 | Tempest Composites WP2 | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -16.3946 | 131.7% | 25.62% | 17.97% | 29536.68 | 11.7% | 244405.26 | 321867.9 | -77462.64 | 4724.9 | 0 | 0 | 77669.2 | 77462.64 | 82447.45 | 295.97 | 239420.45 | 5067% | YES | 239420.45 | 29537 | 57833.2833 | 0 | 0 | 0 | 29536.68 | 29536.68 | 22% | 33.7% | 33.41% | 11.41% |  | 62.17 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P22953 | Spirit Shorts eVTOL | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-05-08 | 2 |  |  | 103.1% | 80.83% | 79.36% | 0 | -9.51% | 324272 | 334483.6 | -10211.6 | -2500 | 66696.6 | 67387.9 | 0 | 10211.6 | 270366 | 70861.92 | 54117.6 | -2165% | NO | 54808.9 | 5921 | 265431.8333 | 0 | 5920.8 | 0 | 0 | 0 | 17% | 7.49% | 100% | 83% |  | 46.19 | [5 empty] | -10000
1733 | 2024-04-10 23:28 | P22515 | Shorts A220 100/300 ALI Phase III | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 50.995 | 81.43% | 98.3% | 91.19% | 0 | 0.76% | 400628.76 | 326213.75 | 74415.01 | 1459.26 | 3450.98 | 3450.98 | 0 | 0 | 320671.89 | 110.25 | 5541.86 | 379.8% | YES | 5541.86 | 27848 | 297465.2233 | 9461.23 | 18386.68 | 0 | 0 | 0 | 10% | 10.76% | 7.64% | -2.36% |  | 40.47 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23699 | A220 Stress Checkers | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -20.07 |  | 0% | 0% | 0 | -1.99% | 0 | 342248.61 | -342248.61 | 17052.76 | 12000 | 12000 | 321520 | 342248.61 | 0 | 110.78 | 342248.61 | 2007% | YES | 342248.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22% | 20.01% | 20.04% | -1.96% |  | 61.88 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P22842 | ME Support (Aim Altitude) | Trevor Knox | 0 | AVI | AIM ALTITUDE UK LIMITED | ME | Level 3 | FIX | 2023-06-14 | 4 |  |  | 99.31% | 100.5% | 86.63% | 57290.84 | 0.49% | 346293.67 | 343918.08 | 2375.59 | 0 | 2909.86 | 2909.86 | 0 | 0 | 345673.01 | 55184.93 | -1754.93 | 0% | NO | -1754.93 | 57291 | 297930.51 | 0 | 0 | 0 | 57290.84 | 57290.84 | 13% | 13.49% | 0% | -13% |  | 46.3 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P22391 | GE System Engineering support | Vinayakumar Sugur | 0 | GEE | EXPERIS LIMITED | EES | Level NC | REIM | 2024-04-08 | 0 |  |  | 82.01% | 100.7% | 100.7% | 0 | 0.13% | 434434.25 | 356260.63 | 78173.62 | 0 | 0 | 0 | 0 | 0 | 358805.6 | 0 | -2544.97 | 0% | NO | -2544.97 | 0 | 358805.6 | 0 | 0 | 0 | 0 | 0 | 6% | 6.13% | 6.09% | 0.09% |  | 57.33 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23045 | Shotgun Adaptors - 10 Sets | Harry James Kellett | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | FIX | 2024-02-27 | 4 |  | 4.3339 | 74.76% | 133.8% | 106.6% | 0 | 2.29% | 399276.11 | 298512.88 | 100763.23 | 23250 | 214550.47 | 214550.47 | 0 | 0 | 399276.11 | 32324.4 | -7763.23 | -33.39% | NO | -7763.23 | 97440 | 318076.11 | 0 | 0 | 97440 | 0 | 0 | 29% | 31.29% | 99.78% | 70.78% |  | 55.76 | [5 empty] | 93000
1733 | 2024-04-10 23:28 | P23432 | Spirit Belfast MRB On-Site Support (Mon & Clear) | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 65.77% | 128.6% | 103.8% | 0 | -11.53% | 449545 | 295665.27 | 153879.73 | 0 | 295665.27 | 451827.33 | 0 | 0 | 380234.75 | 120831.02 | 27430.52 | 0% | NO | 183592.58 | 87914 | 306973.0833 | 0 | 87914.4 | 0 | 0 | 0 | 39% | 27.47% | 0% | -39% |  | 0 | [5 empty] | 112000
1733 | 2024-04-10 23:28 | P23023 | Spirit Shorts R Foster/M Gourley | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 18.7331 | 84.82% | 103.2% | 89.81% | 0 | -20.82% | 480221.04 | 407302.38 | 72918.66 | 3892.51 | 237621.5 | 267726 | 0 | 0 | 420217.26 | 73.83 | 1596.12 | 41% | NO | 31700.62 | 65296 | 365803.9267 | 24971.11 | 19120.72 | 21204.59 | 0 | 0 | 27% | 6.18% | 3.11% | -23.89% |  | 29.62 | [5 empty] | 14511
1733 | 2024-04-10 23:28 | P23685 | DAC LUC Support and Recompliance | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 43.8184 | 17.99% | 183.5% | 0% | 0 | 2.41% | 2180000 | 392274.84 | 1787725.16 | 40798.5 | 0 | 0 | 0 | 0 | 720000 | 102.17 | -294961.16 | -723% | NO | -294961.16 | 864000 | 0 | 0 | 274286.4 | 288001.2 | 301712.4 | 0 | 30% | 32.41% | 32.41% | 2.41% |  | 58.69 | [5 empty] | 32764
1733 | 2024-04-10 23:28 | P23372 | BAE Carbon Tooling Off-load | Gary Kempster | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  |  | 100.5% | 95.27% | 56.3% | 0 | -1.13% | 454982.37 | 457433.31 | -2450.94 | 0 | 0 | 0 | 19196.43 | 2450.94 | 435785.94 | 12934.58 | 21647.37 | 0% | NO | 21647.37 | 213917 | 257521.7733 | 0 | 213917.24 | 0 | 0 | 0 | 24% | 22.87% | 20.74% | -3.26% |  | 53.57 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P22906 | Spirit Shorts - MRB JD Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 11.706 | 93.42% | 85.92% | 67.51% | 99451.32 | -7.8% | 481714 | 450031.68 | 31682.32 | 2706.5 | 0 | 0 | 0 | 0 | 386687.62 | 307.76 | 71344.06 | 2636% | YES | 71344.06 | 99451 | 303811.7867 | 0 | 0 | 0 | 99451.32 | 99451.32 | 13% | 5.2% | 2.61% | -10.39% |  | 36.91 | [5 empty] | 8000
1733 | 2024-04-10 23:28 | P23554 | Dornier Seawings 328 2023 H2 Support | Steven Lawton | 0 | DAX | EXPLEO GERMANY GMBH (EC) | MPE | Level 2 | REIM |  |  |  | 11.4014 | 90.78% | 92.78% | 83.83% | 21955.08 | 6.31% | 508481.81 | 461587.25 | 46894.56 | 4113.04 | 4046.44 | 4046.44 | 0 | 0 | 428252.8 | 71.02 | 33334.45 | 810.5% | YES | 33334.45 | 49568 | 386946.1333 | 27612.8 | 21955.08 | 0 | 0 | 21955.08 | 21% | 27.31% | 24.12% | 3.12% |  | 66.41 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23531 | BAe Systems F35 MRB Support | Richard Brook | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | -46.4196 |  | 92.68% | 92.68% | 0 | 3.12% | 0 | 467236.19 | -467236.19 | 10065.49 | 287.44 | 287.44 | 0 | 467236.19 | 433032.73 | 20.65 | 34203.46 | 339.8% | YES | 34203.46 | 0 | 433032.73 | 0 | 0 | 0 | 0 | 0 | 25% | 28.12% | 31.45% | 6.45% |  | 59.83 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23520 | FCAS AP Portfolio Systems | Peter Bowen | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 29.9542 | 60.06% | 95.6% | 84.95% | 0 | -6.89% | 810821 | 486954.55 | 323866.45 | 10812.06 | 423 | 423 | 0 | 0 | 465538.44 | 41.46 | 17133.11 | 158.5% | YES | 17133.11 | 62232 | 413678.44 | 0 | 62232.16 | 0 | 0 | 0 | 22% | 15.11% | 15.65% | -6.35% |  | 80.57 | [5 empty] | -4283
1733 | 2024-04-10 23:28 | P23140 | Spirit Shorts A220 MLG Stress Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  | 30.2641 | 73.25% | 79.6% | 70.95% | 0 | -12.13% | 636032.4 | 465889.89 | 170142.51 | 5621.92 | 20870.3 | 87811.88 | 0 | 0 | 370857.4 | 224.54 | 120032.49 | 2135% | YES | 186974.07 | 48343 | 330571.5667 | 0 | 48343.2 | 0 | 0 | 0 | 25% | 12.87% | -11.38% | -36.38% |  | 46.2 | [5 empty] | 25000
1733 | 2024-04-10 23:28 | P22652 | L3 - Saftey Engineering | Sean Simmons | 0 | LHW | L3HARRIS MAPPS LIMITED | EES | Level NC | FIX |  |  |  |  | 95.63% | 86.69% | 86.69% | 0 | 5.66% | 523390 | 500497.5 | 22892.5 | 0 | 0 | 0 | 0 | 0 | 433882.5 | 79938 | 66615 | 0% | NO | 66615 | 0 | 433882.5 | 0 | 0 | 0 | 0 | 0 | 21% | 26.66% | 25.88% | 4.88% |  | 83.05 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23694 | Systems Portfolio EXP-011a | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 6.722 | 77.24% | 85.32% | 74.44% | -12096 | 2.17% | 648492.8 | 500890.88 | 147601.92 | 21957.97 | 157.75 | 157.75 | 0 | 0 | 427384.31 | 40.16 | 73506.57 | 334.8% | YES | 73506.57 | 65431 | 372858.4767 | 77526.61 | 0 | -12096 | 0 | -12096 | 21% | 23.17% | 19.59% | -1.41% |  | 88.88 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23281 | Systems Portfolio | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM | 2024-02-28 | 0 |  |  | 44.43% | 97.31% | 97.31% | 0 | -17.25% | 1177697.24 | 523236.96 | 654460.28 | -202 | 2133.28 | 2133.28 | 0 | 0 | 509179.87 | 15792.1 | 13160.09 | -6515% | NO | 13160.09 | 0 | 509179.87 | 0 | 0 | 0 | 0 | 0 | 25% | 7.75% | 100% | 75% |  | 70.48 | [5 empty] | -897
1733 | 2024-04-10 23:28 | P23473 | Tempest Vertical Tail | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 17.5031 | 73.36% | 104.5% | 83.22% | 0 | -4.8% | 723866.48 | 530998.48 | 192868 | 11019.1 | 99775 | 112425 | 12000 | 0 | 554989.62 | 55.41 | -23991.14 | -217.7% | NO | -11341.14 | 135686 | 441917.9533 | 74168.03 | 61517.7 | 0 | 0 | 0 | 26% | 21.2% | 22.84% | -3.16% |  | 62.37 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23001 | Spirit Shorts A220 Design | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -27.2917 | 115.3% | 74.64% | 68.6% | 0 | -4.3% | 463100 | 533769.2 | -70669.2 | 2589.4 | 0 | 0 | 65953.2 | 70669.2 | 398429.7 | 375.63 | 135339.5 | 5227% | YES | 135339.5 | 38738 | 366148.0333 | 9501.6 | 29236.68 | 0 | 0 | 0 | 25% | 20.7% | 11.63% | -13.37% |  | 43.59 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23366 | Business Analyst Support | Peter Williams | 0 | BDZ | MBDA UK LIMITED | DET | Level 3 | REIM |  |  |  | 50.066 | 20.97% | 206.6% | 181.6% | 0 | 6.81% | 1302200 | 273075.23 | 1029124.77 | 20555.35 | 247149.55 | 416921.86 | 0 | 0 | 564160 | 40.42 | -7949.77 | -38.67% | NO | 161822.54 | 81792 | 496000 | 0 | 81792 | 0 | 0 | 0 | 43% | 49.81% | 26.39% | -16.61% |  | 37.78 | [5 empty] | 283135
1733 | 2024-04-10 23:28 | P23323 | CNC-CMM Programming Support | Stephen Young | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | 4.7712 | 93.6% | 94.43% | 73.88% | 0 | -2.69% | 617809.74 | 578243.15 | 39566.59 | 8292.79 | 15941.56 | 15941.56 | 0 | 0 | 546032.59 | 111.99 | 32210.56 | 388.4% | YES | 32210.56 | 142591 | 427206.7567 | 40305.01 | 102286.46 | 0 | 0 | 0 | 32% | 29.31% | 36.95% | 4.95% |  | 57.25 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23219 | Tornado Air 800 Engineering Support | Richard Brook | 0 | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 3 | REIM |  |  |  |  | 99.96% | 94.07% | 94.07% | 0 | -0.68% | 615046 | 614829.8 | 216.2 | -6685.94 | 459.21 | 459.21 | 0 | 0 | 578373.17 | 91 | 27731.63 | -414.8% | NO | 27731.63 | 0 | 578373.17 | 0 | 0 | 0 | 0 | 0 | 31% | 30.32% | -35.65% | -66.65% |  | 82.38 | [5 empty] | -8725
1733 | 2024-04-10 23:28 | P23605 | Typhoon Work Package 2 Continuation | Christopher McCarthy | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM |  |  |  | -534.8672 | 119.8% | 83.38% | 4.179% | 70906.73 | 5.19% | 545536.01 | 653621.97 | -108085.96 | 202.08 | 4054 | 4054 | 81999.09 | 108085.96 | 544986.65 | 402.05 | 108635.32 | 53759% | YES | 108635.32 | 621210 | 27311.65 | 18432.36 | 602777.85 | 0 | 0 | 70906.73 | 23% | 28.19% | 28.93% | 5.93% |  | 55.82 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P22790 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | REIM | 2024-03-18 | 0 |  |  | 194.5% | 90.44% | 90.44% | 0 | 1.37% | 352240 | 685262.25 | -333022.25 | 0 | 1611.52 | 1611.52 | 515246 | 333022.25 | 619743.88 | 41098.04 | 34248.37 | 0% | NO | 34248.37 | 0 | 619743.88 | 0 | 0 | 0 | 0 | 0 | 13% | 14.37% | 0% | -13% |  | 45.06 | [5 empty] | -31270
1733 | 2024-04-10 23:28 | P23426 | BAE Tempest WP 3 Harness Maturation | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 9.3872 | 79.78% | 96.64% | 74.16% | 0 | -6.08% | 884012.04 | 705293.3 | 178718.74 | 19038.48 | 213.34 | 213.34 | 0 | 0 | 681568.4 | 73.55 | 23724.9 | 124.6% | NO | 23724.9 | 190206 | 523063.4 | 107757.52 | 82448.95 | 0 | 0 | 0 | 33% | 26.92% | 27.52% | -5.48% |  | 51.55 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23602 | EXP-025 Portfolio Software Engineering Support | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 19.109 | 57.02% | 91.83% | 76.08% | 0 | -0.89% | 1327080 | 756698.39 | 570381.61 | 29848.92 | 2542.8 | 3006.91 | 0 | 0 | 694893.55 | 43.32 | 61804.84 | 207.1% | YES | 62268.95 | 143049 | 575686.05 | 0 | 143049.25 | 0 | 0 | 0 | 24% | 23.11% | 22.84% | -1.16% |  | 83.24 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23451 | BAE Tempest - DFM-ASO Planning | Stephen Young | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | 6.464 | 87.17% | 75.19% | 33.85% | 27224.9 | -3.16% | 953905.42 | 831558.23 | 122347.19 | 18927.58 | 0 | 0 | 0 | 0 | 625210.17 | 182.58 | 206348.06 | 1090% | YES | 206348.06 | 412472 | 281483.5033 | 57003.88 | 328243.6 | 0 | 27224.9 | 27224.9 | 28% | 24.84% | 26.68% | -1.32% |  | 53.66 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23105 | Raytheon Supply Engineering Support | Natalie Sinclair | 0 | RAY | RAYTHEON UNITED KINGDOM LIMITED | MPE | Level 3A | REIM | 2023-07-13 | 2 |  |  | 76.96% | 94.49% | 90.07% | 49156.8 | -2.02% | 1205008 | 927395.25 | 277612.75 | 0 | 0 | 0 | 0 | 0 | 876291.5 | 107644.5 | 48739.75 | 0% | NO | 48739.75 | 49157 | 835327.3333 | 0 | 0 | 49156.8 | 0 | 49156.8 | 26% | 23.98% | 100% | 74% |  | 48.97 | [5 empty] | -2364
1733 | 2024-04-10 23:28 | P22350 | EMP 2020-2021 | Natalie Sinclair | 0 | ARY | GUIDANT GROUP (trading name) | PCPR | Level NC | REIM |  |  |  | 4.8472 | 97.17% | 98.18% | 94.48% | 0 | -2.19% | 1017579.76 | 988786.18 | 28793.58 | 5940.2 | 400 | 400 | 0 | 0 | 970748.2 | 59.45 | 18037.98 | 303.7% | YES | 18037.98 | 43839 | 934215.7 | 12097.2 | 21769.52 | 9972.02 | 0 | 0 | 32% | 29.81% | 26.35% | -5.65% |  | 44.12 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23117 | BAE Typhoon Eng Support | Christopher McCarthy | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | 2024-03-12 | 11 |  |  | 107.6% | 92.94% | 88.52% | 0 | -1.44% | 950771.99 | 1022826.17 | -72054.18 | 0 | 19090.01 | 21165.02 | 69773.84 | 72054.18 | 950609.41 | 108434.62 | 45120.76 | 0% | NO | 47195.77 | 54290 | 905367.7433 | 0 | 54289.71 | 0 | 0 | 0 | 30% | 28.56% | 0% | -30% |  | 52.3 | [5 empty] | -27096
1733 | 2024-04-10 23:28 | P22671 | Spirit Shorts Pylon and Fairing Package | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX | 2023-05-03 | 0 |  |  | 105% | 95.26% | 95.26% | 0 | -7.21% | 1198494.77 | 1258071.09 | -59576.32 | 0 | 106494.89 | 106494.89 | 0 | 59576.32 | 1198494.77 | 2544.39 | 2120.32 | 0% | NO | 2120.32 | 0 | 1198494.77 | 0 | 0 | 0 | 0 | 0 | 20% | 12.79% | 0% | -20% |  | 45.4 | [5 empty] | -57456
1733 | 2024-04-10 23:28 | P23292 | BAE Tempest WP 4 AV Trays | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 10.9737 | 84.01% | 105.9% | 81.89% | 0 | 1.73% | 1498284.22 | 1258672.15 | 239612.07 | 21835.19 | 0 | 0 | 0 | 0 | 1332801.4 | 70.29 | -74129.25 | -339.5% | NO | -74129.25 | 362500 | 1030718.0667 | 245826.2 | 116674.18 | 0 | 0 | 0 | 32% | 33.73% | 32.44% | 0.44% |  | 53.45 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23152 | Project Aragon - Design and Stress Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 4.9549 | 96.35% | 79.22% | 56.76% | 0 | -9.55% | 1333452.21 | 1284832.56 | 48619.65 | 9812.42 | 0 | 0 | 0 | 0 | 1017835.58 | 323.88 | 266996.98 | 2721% | YES | 266996.98 | 346248 | 729295.58 | 346247.55 | 0 | 0 | 0 | 0 | 39% | 29.45% | 29.13% | -9.87% |  | 51.94 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23519 | Mechanical and Electrical Design Eng Support | Dushan Fernando | 0 | BAX | SAFRAN SEATS GB LIMITED | MPE | Level 2 | REIM |  |  |  | 16.3736 | 73.11% | 96.55% | 84.26% | 0 | -1.62% | 1807261.3 | 1321245.15 | 486016.15 | 29682.9 | 1004.45 | 1504.45 | 0 | 0 | 1275630.3 | 44.45 | 45614.85 | 153.7% | YES | 46114.85 | 194809 | 1113289.4667 | 194808.9 | 0 | 0 | 0 | 0 | 33% | 31.38% | 31.3% | -1.7% |  | 56.63 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23411 | Agile & Scrum Delivery Service | Peter Williams | 0 | BDZ | MBDA UK LIMITED | DET | Level 2 | REIM | 2023-08-14 | 0 |  |  | 36.3% | 170.5% | 170.5% | 0 | 13.08% | 2487000 | 902903.79 | 1584096.21 | 0 | 894178.59 | 894178.59 | 0 | 0 | 1539600 | 19368.95 | 16140.79 | 0% | NO | 16140.79 | 0 | 1539600 | 0 | 0 | 0 | 0 | 0 | 29% | 42.08% | 0% | -29% |  | 74.57 | [5 empty] | 652837
1733 | 2024-04-10 23:28 | P23315 | DAC LUC BAU and Service Workbench | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX | 2024-02-16 | 0 |  | 70.5463 | 85.17% | 117.4% | 117.4% | 0 | 3.84% | 1573630 | 1340192.3 | 233437.7 | 3309 | 180.3 | 180.3 | 0 | 0 | 1573630 | 0 | 0.3 | 0.009066% | NO | 0.3 | 0 | 1573630 | 0 | 0 | 0 | 0 | 0 | 28% | 31.84% | 47.26% | 19.26% |  | 52.35 | [5 empty] | 233438
1733 | 2024-04-10 23:28 | P22278 | TAI Supply Engineers to Ankara | Natalie Sinclair | 0 | TAI | TUSAS-TURK HAVACILIK VE UZAY | MPE | Level 3A | REIM |  |  |  | 403.9409 | 19.56% | 463.9% | 463.9% | 0 | -15.67% | 2105282 | 411860.91 | 1693421.09 | 4192.25 | 49400.29 | 49400.29 | 0 | 0 | 1910696.33 | 40.75 | 6224.58 | 148.5% | YES | 6224.58 | 0 | 1910696.33 | 0 | 0 | 0 | 0 | 0 | 95% | 79.33% | 68.85% | -26.15% |  | 34.18 | [5 empty] | 1505060
1733 | 2024-04-10 23:28 | P23006 | Spirit Shorts A350 Freighter Toulouse | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -43.5076 | 155.8% | 105.1% | 76.54% | 0 | 19.48% | 1035745.92 | 1613588.16 | -577842.24 | 13281.4 | 1086670.26 | 2010741.94 | 0 | 577842.24 | 1695787.93 | 313.02 | 229074.23 | 1725% | YES | 1153145.91 | 552824 | 1235101.2633 | 140525.66 | 412298.62 | 0 | 0 | 0 | 5% | 24.48% | 35.62% | 30.62% |  | 48.03 | [5 empty] | 311274
1733 | 2024-04-10 23:28 | P23435 | Andy Baker Portfolio | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 45.9365 | 49.02% | 96.09% | 69.06% | 0 | -7.21% | 4023207.4 | 1972040.54 | 2051166.86 | 44652.26 | 2352.57 | 2352.57 | 0 | 0 | 1894945.09 | 87.35 | 77095.45 | 172.7% | YES | 77095.45 | 639550 | 1361986.7567 | 0 | 489604.46 | 149945.57 | 0 | 0 | 25% | 17.79% | 20.01% | -4.99% |  | 80.37 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23175 | BAe Aero Typhoon Package 2 | Christopher McCarthy | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM | 2024-03-12 | 2 |  |  | 103.8% | 96.32% | 96.32% | 0 | -1.63% | 1984265.09 | 2060011.83 | -75746.74 | 0 | 57677.87 | 86030.82 | 15444.64 | 75746.74 | 1984257.03 | 84731.75 | 70609.8 | 0% | NO | 98962.75 | 0 | 1984257.03 | 0 | 0 | 0 | 0 | 0 | 29% | 27.37% | 0% | -29% |  | 51.76 | [5 empty] | -5145
1733 | 2024-04-10 23:28 | P23257 | BAE Tempest WP 5 Centre Fuselage | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | -2.1136 | 101.4% | 97.43% | 93.12% | 0 | -5.77% | 2106860.71 | 2136453.94 | -29593.23 | 14001.01 | 78100 | 78100 | 0 | 29593.23 | 2081529.48 | 58.61 | 54924.46 | 392.3% | YES | 54924.46 | 110362 | 1989561.1467 | 0 | 110362.14 | 0 | 0 | 0 | 33% | 27.23% | 27.95% | -5.05% |  | 61.04 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P19020 | Spirit Concessions - 2018 | Carl Warren | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2024-01-23 | 3 |  |  | 90.82% | 111.8% | 107% | 99792.83 | 2.09% | 1914846.83 | 1739018.14 | 175828.69 | 0 | 44317.61 | 44317.61 | 15178.88 | 0 | 1944710.76 | 10448.15 | 196987.38 | 0% | NO | 196987.38 | 99793 | 1861549.9267 | 0 | 0 | 0 | 99792.83 | 99792.83 | 25% | 27.09% | 9.32% | -15.68% |  | 40.87 | [5 empty] | 402680
1733 | 2024-04-10 23:28 | P23207 | A350 Approvers - Design and Stress Support | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  | 4.4486 | 90.86% | 99.18% | 62.12% | 91686.78 | -5.02% | 2728308 | 2478835.57 | 249472.43 | 56079.26 | 34683.19 | 35497.33 | 0 | 0 | 2458482.23 | 112.1 | 20353.34 | 36.29% | NO | 21167.48 | 1102381 | 1539831.3967 | 342017.26 | 253420.79 | 506942.78 | 0 | 91686.78 | 23% | 17.98% | 17.17% | -5.83% |  | 54.6 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P23179 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX |  |  |  | -286.7812 | 127.3% | 94.88% | 82.14% | 0 | -9.33% | 1996985.84 | 2542500.98 | -545515.14 | 1902.2 | 156991.12 | 248243.92 | 100000 | 545515.14 | 2412235.69 | 564.7 | 130265.29 | 6848% | YES | 221518.09 | 388547 | 2088446.5233 | 0 | 248280.21 | 140266.99 | 0 | 0 | 22% | 12.67% | 16.7% | -5.3% |  | 44.4 | [5 empty] | 0
1733 | 2024-04-10 23:28 | P19731 | Hapri HPC Rear Bearing Housing PDR & CDR | Steven Lawton | 0 | ATC | AECC Hunan Aviation Powerplant | MPE | Level 1 | FIX |  |  |  | -0.64966 | 100% | 99.97% | 87.47% | 447000 | -15.41% | 2980000 | 2980907.27 | -907.27 | 1396.53 | 366232.13 | 500332.13 | 0 | 907.27 | 2980000 | 841.03 | -224092.73 | -16046% | NO | -89992.73 | 447000 | 2607500 | 0 | 0 | 0 | 447000 | 447000 | 38% | 22.59% | 13.07% | -24.93% |  | 64.85 | [5 empty] | -225000
1733 | 2024-04-10 23:28 | P23487 | Tornado Air 800 Engineering Support | Richard Brook | 0 | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 2 | FIX |  |  |  | 0.60773 | 98.51% | 87.09% | 75.45% | 38732.48 | -3.44% | 3049066.2 | 3003749.08 | 45317.12 | 74568.31 | 0 | 0 | 0 | 0 | 2616021.67 | 90.99 | 414727.41 | 556.2% | YES | 414727.41 | 419489 | 2266447.5033 | 0 | 380756.59 | 8658.1 | 30074.38 | 38732.48 | 40% | 36.56% | 40.38% | 0.38% |  | 78.71 | [5 empty] | 27000
Extend Table

## AP4-2
WIP No | Date Created | Project ID | Project Description | Project Manager | Agency (1=yes, 0=no) | Department Id | Client | CBU | Complexity | Type | Stop Booking Hrs | Closing Project: Action(s) to close | RAG | Approx. PO Burndown (weeks) | Turnover vs Contract Value | Invoice To Date vs Turnover | Cash in vs Turnover | Open Amount Overdue | Actual PM% to Baseline PM% delta | Contract Value | Total Project Turnover | Contract Value - Total Turnover | Run Rate (based on total turnover) | Total BOI Spend to Date | Total Committed PO (supplier/best shore) | Current AA in PT3 | Exposure (turnover - contract value) | Invoiced To Date | DSO | Unbilled (WIP) | WIP / Run rate | WIP / Run rate >1.3 | WIP + Remaining Committed PO for BOI | Total Open Amount | Cash in (Invoiced - (Open amount -VAT)) | Debt <=30 Days | Debt 31 - 60 Days | Debt 61 - 90 Days | Debt >= 90 Days | Open Amount Overdue2 | Baseline Project Margin | Project To Date (PTD) PM | Year to Date (YTD) PM | YTD Delta Actual PM% to BPM% | Forecast PM at Completion (Manual input from PTT) | Average Sale Rate | CSat score for last quarter (Manual input from PTT) | Comments and Actions | Judged income adjustment at completion | Profit to take now | Provision required now | Fully Traded | Last Months Comments and Actions
1734 | 2024-04-17 23:33 | P23864 | REACH Coordinator | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -27% | 52920 | 0 | 52920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27% | 0% | 0% | -27% |  | 0 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23543 | EXP-024 FCAS AP Transformation & Change Enablers | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -26% | 385921 | 0 | 385921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26% | 0% | 0% | -26% |  | 0 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23637 | MBSE Proposal | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 | 0 | 0 | 0 | 49980 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23552 | FCAS AP Product Technology Development | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -25% | 597871 | 0 | 597871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0% | -25% |  | 0 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23711 | DO NOT USE - RAISED IN ERROR | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23585 | Systems Design - Missile Systems, Meteor,Brimstone | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 | 0 | 0 | 0 | 49500 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23717 | GKN Ted Tomblin 2024 | Matthew Tweed | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 10047 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23730 | FLE Project | Carl Warren | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -18.03% | 0 | 1120 | -1120 | 0 | 0 | 0 | 24000 | 1120 | 0 | 104 | 1120 | 0% | NO | 1120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | -18.03% | -18.03% | -18.03% |  | 35 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23463 | A220 Wing MaMo Design Checking | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-03-07 | 0 |  |  |  | 0% | 0% | 0 | 7.85% | 0 | 1628 | -1628 | 0 | 0 | 0 | 15000 | 1628 | 0 | 1953.6 | 1628 | 0% | NO | 1628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | 10.85% | 0% | -3% |  | 44 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23843 | EXP-035 FT15 Exemplar information set | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 293.8307 | 1.343% | 0% | 0% | 0 | -13.58% | 175985.16 | 2363.56 | 173621.6 | 590.89 | 0 | 0 | 0 | 0 | 0 | 28 | 2363.56 | 400% | YES | 2363.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 6.42% | 6.42% | -13.58% |  | 63.88 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P21028 | Rebate Collection (BACC) | David Catchpole | 0 | TOO | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | [5 empty] | 0% | 0% | 0 | 0% | 0 | 2680 | -2680 | 0 | 2680 | 2680 | 0 | 2680 | 0 | 3216 | 2680 | 0% | NO | 2680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23578 | ESN Work Package | Hannah Mead | 0 | COZ | CHELTON LIMITED | DET | Level 3 | FIX | 2024-01-01 | 0 |  |  | 86.17% | 116.1% | 116.1% | 0 | 35.86% | 4410 | 3800 | 610 | 0 | 0 | 0 | 0 | 0 | 4410 | 0 | -610 | 0% | NO | -610 | 0 | 4410 | 0 | 0 | 0 | 0 | 0 | 24% | 59.86% | 0% | -24% |  | 95 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23628 | Design Assurance | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -6.67% | 0 | 3909.24 | -3909.24 | 0 | 0 | 0 | 4454.8 | 3909.24 | 0 | 4691.09 | 3909.24 | 0% | NO | 3909.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 0.33% | 0% | -7% |  | 15.05 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23002 | WoT MAJ Transit Flag Stress | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2024-04-03 | 1 |  | 4.7688 | 62.41% | 160.2% | 160.2% | 0 | 38.54% | 4735 | 2955.29 | 1779.71 | 373.2 | 1492.79 | 2242.5 | 0 | 0 | 4735 | 1791.95 | 1493.29 | 400.1% | YES | 2243 | 0 | 4735 | 0 | 0 | 0 | 0 | 0 | 10% | 48.54% | 0% | -10% |  | 45 | [5 empty] | 3273
1734 | 2024-04-17 23:33 | P23842 | Tranche 1 Evolution Package Step 2 | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -4 |  | 0% | 0% | 0 | -15.03% | 0 | 7582.37 | -7582.37 | 1895.59 | 1000 | 1000 | 67488.9 | 7582.37 | 0 | 32.25 | 7582.37 | 400% | YES | 7582.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31% | 15.97% | 15.97% | -15.03% |  | 56.07 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23607 | SAFRAN - A330neo Turnover Frame | Gary Kempster | 0 | TOO | SAFRAN SEATS GB LIMITED | MPE | Level 3 | FIX |  |  |  | 37695 | 95.69% | 104.5% | 104.5% | 0 | -19.52% | 8736 | 8359.05 | 376.95 | 0.01 | 0 | 0 | 0 | 0 | 8736 | 0.06 | 0.05 | 500% | YES | 0.05 | 0 | 8736 | 0 | 0 | 0 | 0 | 0 | 23% | 3.48% | 8.5% | -14.5% |  | 50.46 | [5 empty] | 377
1734 | 2024-04-17 23:33 | P23274 | ME Support (Aim Altitude - Cambridge) | Trevor Knox | 0 | AVI | AVIC CABIN SYSTEMS (UK) LIMITED | ME | Level 3 | FIX | 2023-08-18 | 0 |  |  | 51.88% | 56.3% | 56.3% | 0 | -0.17% | 17280 | 8964 | 8316 | 0 | 0 | 0 | 0 | 0 | 5046.3 | 4701.24 | 3917.7 | 0% | NO | 3917.7 | 0 | 5046.3 | 0 | 0 | 0 | 0 | 0 | 21% | 20.83% | 0% | -21% |  | 48 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23283 | Spirit Tooling Audit | Charidimos Valadakis | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-05-03 | 0 |  |  | 97.22% | 48.57% | 48.57% | 0 | -7.99% | 9910.08 | 9634.8 | 275.28 | 0 | 0 | 0 | 0 | 0 | 4679.76 | 5946.05 | 4955.04 | 0% | NO | 4955.04 | 0 | 4679.76 | 0 | 0 | 0 | 0 | 0 | 7% | -0.99% | 0% | -7% |  | 34.41 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23127 | Loft Hall Design Support | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 101% | 99.06% | 99.06% | 0 | -9.55% | 9680 | 9772 | -92 | 0 | 0 | 0 | 0 | 92 | 9680 | 110.4 | 92 | 0% | NO | 92 | 0 | 9680 | 0 | 0 | 0 | 0 | 0 | 41% | 31.45% | 0% | -41% |  | 44 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23630 | 2Excel CFD Analysis Support | Dushan Fernando | 0 | BAX | STIRLING DYNAMICS LTD | MPE | Level NC | FIX |  |  |  |  | 61.2% | 100% | 100% | 0 | -1.87% | 16195.49 | 9911.34 | 6284.15 | 0 | 0 | 0 | 0 | 0 | 9911.63 | 0 | -0.29 | 0% | NO | -0.29 | 0 | 9911.63 | 0 | 0 | 0 | 0 | 0 | 26% | 24.13% | 0% | -26% |  | 64.78 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23718 | Requalification of EJ200 GSS ESS EHM SW module | Vijayakumara Nanjundappa | 0 | ARZ | MTU AERO ENGINES AG | DET | Level 3 | FIX |  |  |  | 76.6993 | 11.42% | 213.2% | 213.2% | 0 | 12.44% | 74463 | 8501.57 | 65961.43 | 860 | 991.93 | 991.93 | 0 | 0 | 18125 | 0 | -7623.43 | -886.4% | NO | -7623.43 | 0 | 18125 | 0 | 0 | 0 | 0 | 0 | 28% | 40.44% | 40.44% | 12.44% |  | 80 | [5 empty] | 2000
1734 | 2024-04-17 23:33 | P23313 | Laser Trim Fixtures | Gary Kempster | 0 | TOO | ALKEN ENGINEERING LIMITED | MPE | Level 3 | FIX | 2023-11-20 | 0 |  |  | 89.87% | 111.3% | 111.3% | 0 | 0.53% | 13770 | 12375 | 1395 | 0 | 0 | 0 | 0 | 0 | 13770 | 0 | -1395 | 0% | NO | -1395 | 0 | 13770 | 0 | 0 | 0 | 0 | 0 | 17% | 17.53% | 0% | -17% |  | 45 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P22761 | Red Bull Chassis Spit | Trevor Knox | 0 | TOO | MANUFAX ENGINEERING LTD | MPE | Level 3 | FIX | 2022-11-15 | 0 |  |  | 72.18% | 96.98% | 96.98% | 0 | 7.92% | 12961.2 | 9355.5 | 3605.7 | 0 | 0 | 0 | 0 | 0 | 9072.84 | 4666.39 | 3888.66 | 0% | NO | 3888.66 | 0 | 9072.84 | 0 | 0 | 0 | 0 | 0 | 23% | 30.92% | 0% | -23% |  | 42.19 | [5 empty] | 3606
1734 | 2024-04-17 23:33 | P23350 | Spirit 2023 - Stress Approve Man Serv (DH) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 14.15% | 72.64% | 72.64% | 0 | -0.29% | 97920 | 13860 | 84060 | 0 | 0 | 0 | 0 | 0 | 10068 | 4550.4 | 3792 | 0% | NO | 3792 | 0 | 10068 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23344 | Spirit A320 Spoilers Support 2023 | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 38.75% | 100% | 100% | 0 | 5.82% | 35786.4 | 13867.23 | 21919.17 | 0 | 0 | 0 | 0 | 0 | 13867.23 | 0 | 0 | 0% | NO | 0 | 0 | 13867.23 | 0 | 0 | 0 | 0 | 0 | 7% | 12.82% | 0% | -7% |  | 34.41 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23337 | Spirit 2023 - Steve Grimley | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 25.28% | 100% | 100% | 0 | 0.01% | 56812.9 | 14362.47 | 42450.43 | 0 | 0 | 0 | 0 | 0 | 14362.47 | 0 | 0 | 0% | NO | 0 | 0 | 14362.47 | 0 | 0 | 0 | 0 | 0 | 7% | 7.01% | 0% | -7% |  | 30.11 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23597 | MRB Onsite support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-02-16 | 1 |  |  |  | 0% | 0% | 0 | -10.04% | 0 | 15100.57 | -15100.57 | 0 | 9448.07 | 17381.62 | 24200 | 15100.57 | 0 | 102.4 | 15100.57 | 0% | NO | 23034.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 7.96% | 8.95% | -9.05% |  | 42.5 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23635 | Engineering Services: FAI Support | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 49.9% | 68.33% | 0.001436% | 0 | -3.4% | 37230 | 18576 | 18654 | 0 | 0 | 0 | 0 | 0 | 12693.6 | 390 | 5882.4 | 0% | NO | 5882.4 | 15232 | 0.26667 | 0 | 15232.32 | 0 | 0 | 0 | 8% | 4.6% | 5.04% | -2.96% |  | 38.7 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23343 | Spirit 2023 - John Agnew | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-08-09 | 0 |  |  | 28.56% | 86.27% | 86.27% | 0 | -0.02% | 65120.37 | 18600.89 | 46519.48 | 0 | 0 | 0 | 0 | 0 | 16047.15 | 3064.49 | 2553.74 | 0% | NO | 2553.74 | 0 | 16047.15 | 0 | 0 | 0 | 0 | 0 | 7% | 6.98% | 0% | -7% |  | 34.51 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23839 | Stirling Dynamics - ST002-GFEM | Matthew Dodd | 0 | BAX | STIRLING DYNAMICS LTD | MPE | Level NC | FIX |  |  |  | -4 |  | 0% | 0% | 0 | -5.68% | 0 | 18628.7 | -18628.7 | 4657.18 | 0 | 0 | 19985.76 | 18628.7 | 0 | 84 | 18628.7 | 400% | YES | 18628.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 1.32% | 1.32% | -5.68% |  | 43.32 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23663 | Spirit Tooling Verification and Inspection | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 1.25 | 94.79% | 35.16% | 0.0002839% | 0 | -7.43% | 19820.16 | 18787.86 | 1032.3 | 825.84 | 0 | 0 | 7392 | 0 | 6606.72 | 160.8 | 12181.14 | 1475% | YES | 12181.14 | 7928 | 0.053333 | 0 | 7928.06 | 0 | 0 | 0 | 12% | 4.57% | 4.82% | -7.18% |  | 34.41 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23742 | Cyber Security Support | Hannah Mead | 0 | COZ | CHELTON LIMITED | DET | Level 3 | FIX |  |  |  | -13.4 |  | 0% | 0% | 0 | 31.04% | 0 | 20100 | -20100 | 1500 | 0 | 0 | 27500 | 20100 | 0 | 93.8 | 20100 | 1340% | YES | 20100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 31.04% | 31.04% | 31.04% |  | 100 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23355 | Spirit Tooling Support 2023 | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-23 | 0 |  |  | 22.93% | 89.02% | 89.02% | 0 | -0.82% | 91800 | 21053.34 | 70746.66 | 0 | 0 | 0 | 0 | 0 | 18742.5 | 2773.01 | 2310.84 | 0% | NO | 2310.84 | 0 | 18742.5 | 0 | 0 | 0 | 0 | 0 | 20% | 19.18% | 0% | -20% |  | 44.46 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23351 | Spirit 2023 - Design Man Serv (KL) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 26.47% | 93.15% | 93.15% | 0 | 0.09% | 93840 | 24840 | 69000 | 0 | 0 | 0 | 0 | 0 | 23138 | 2042.4 | 1702 | 0% | NO | 1702 | 0 | 23138 | 0 | 0 | 0 | 0 | 0 | 26% | 26.09% | 0% | -26% |  | 46 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23356 | Spirit 2023 - Design Man Serv (AH) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX | 2023-08-09 | 1 |  |  |  | 76.66% | 0.001332% | 23018.4 | 0.48% | 0 | 25023.08 | -25023.08 | 0 | 0 | 0 | 25300 | 25023.08 | 19182 | 30027.7 | 5841.08 | 0% | NO | 5841.08 | 23018 | 0.33333 | 0 | 0 | 0 | 23018.4 | 23018.4 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23831 | Contract DM/00113 for maintenance, repair and post | Harry James Kellett | 0 | BXW | MOD | EES | Level 2 | FIX |  |  |  | 6.0263 | 61.77% | 0% | 0% | 0 | 14.67% | 40800 | 25201.64 | 15598.36 | 2588.39 | 0 | 0 | 0 | 0 | 0 | 91 | 25201.64 | 973.6% | YES | 25201.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37% | 51.67% | 51.67% | 14.67% |  | 80.26 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23740 | Phase 2 - EJ200 ESS EHM Platform Migration | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 3 | FIX |  |  |  | 53.0854 | 12.4% | 230.4% | -0.001528% | 30166.8 | 11.96% | 175971 | 21817.5 | 154153.5 | 2903.88 | 0 | 0 | 0 | 0 | 50278 | 116.9 | -24460.5 | -842.3% | NO | -24460.5 | 60334 | -0.33333 | 0 | 30166.8 | 0 | 30166.8 | 30166.8 | 28% | 39.96% | 39.96% | 11.96% |  | 44.66 | [5 empty] | 4000
1734 | 2024-04-17 23:33 | P22884 | Spirit Shorts Config Eng | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 66.3% | 100.1% | 100.1% | 0 | 0.56% | 38976 | 25841.9 | 13134.1 | 0 | 0 | 0 | 0 | 0 | 25863.2 | 0 | -0.3 | 0% | NO | -0.3 | 0 | 25863.2 | 0 | 0 | 0 | 0 | 0 | 7% | 7.56% | 0% | -7% |  | 20.3 | [5 empty] | 21
1734 | 2024-04-17 23:33 | P23354 | Spirit 2023 - Design Man Serv (PC) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 27.97% | 99.36% | 99.36% | 0 | 0.48% | 93840 | 26248.98 | 67591.02 | 0 | 0 | 0 | 0 | 0 | 26082 | 200.38 | 166.98 | 0% | NO | 166.98 | 0 | 26082 | 0 | 0 | 0 | 0 | 0 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23433 | Cavendish | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 5.0561 | 62.49% | 52.51% | 52.51% | 0 | -0.41% | 42240 | 26394.8 | 15845.2 | 3133.9 | 0 | 0 | 0 | 0 | 13859.2 | 91 | 12535.6 | 400% | YES | 12535.6 | 0 | 13859.2 | 0 | 0 | 0 | 0 | 0 | 7% | 6.59% | 6.51% | -0.49% |  | 45.94 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23724 | GKN S McConnell 2024 | Matthew Tweed | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  | 13.8073 | 53.4% | 53.93% | -0.0006515% | 0 | 0.69% | 49820 | 26603.91 | 23216.09 | 1681.43 | 0 | 0 | 0 | 0 | 14348.16 | 103.83 | 12255.75 | 728.9% | YES | 12255.75 | 17218 | -0.17333 | 0 | 8848.03 | 8369.76 | 0 | 0 | 19% | 19.69% | 19.69% | 0.69% |  | 49.54 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23811 | Spirit T300 MRB Concessions | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -9.2602 |  | 0% | 0% | 0 | -7.17% | 0 | 26757.06 | -26757.06 | 2889.46 | 0 | 0 | 34639 | 26757.06 | 0 | 63 | 26757.06 | 926% | YES | 26757.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21% | 13.83% | 13.83% | -7.17% |  | 46.81 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23823 | EXP-034 Spear 3 Test Equip Requirement Authority | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 18.2984 | 32.63% | 64.45% | -0.001024% | 0 | -0.19% | 85825 | 28002.63 | 57822.37 | 3159.97 | 1000 | 1000 | 0 | 0 | 18048.88 | 65.33 | 9953.75 | 315% | YES | 9953.75 | 21659 | -0.28667 | 0 | 21658.66 | 0 | 0 | 0 | 14% | 13.81% | 13.81% | -0.19% |  | 94.25 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23651 | PMO Spirit | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 78.2373 | 57.85% | 82.26% | -0.0005845% | 0 | -19.16% | 49284 | 28512 | 20772 | 265.5 | 0 | 0 | 0 | 0 | 23454 | 250.25 | 5058 | 1905% | YES | 5058 | 28145 | -0.16667 | 0 | 28144.8 | 0 | 0 | 0 | 43% | 23.84% | 23.17% | -19.83% |  | 36 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P22756 | A350 FLE Design Checker | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2022-03-23 | 1 |  |  | 68.39% | 119.7% | 119.7% | 0 | 16.46% | 34898.4 | 23867.15 | 11031.25 | 0 | 23867.15 | 24342.3 | 0 | 0 | 28571.1 | 0.06 | 0.05 | 0% | NO | 475.2 | 0 | 28571.1 | 0 | 0 | 0 | 0 | 0 | 0% | 16.46% | 0% | 0% |  | 0 | [5 empty] | 4704
1734 | 2024-04-17 23:33 | P23458 | Spirit Belfast Tooling Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-08-11 | 0 |  |  | 101.3% | 94.65% | 94.65% | 0 | 8.64% | 30384 | 30784.9 | -400.9 | 0 | 0 | 0 | 0 | 400.9 | 29139.1 | 1974.96 | 1645.8 | 0% | NO | 1645.8 | 0 | 29139.1 | 0 | 0 | 0 | 0 | 0 | 7% | 15.64% | 0% | -7% |  | 42.2 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23338 | Spirit 2023 - Blair Hainey | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 2.4844 | 95.79% | 54.61% | 54.61% | 0 | 5.35% | 34494.36 | 33041.1 | 1453.26 | 584.96 | 0 | 0 | 0 | 0 | 18042.36 | 167.41 | 14998.74 | 2564% | YES | 14998.74 | 0 | 18042.36 | 0 | 0 | 0 | 0 | 0 | 7% | 12.35% | 19.31% | 12.31% |  | 18.28 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23365 | GKN 777x Lip Skin Fixture | Steven Lawton | 0 | TOO | GKN AEROSPACE SERVICES LTD | MPE | Level 3 | FIX | 2023-10-12 | 0 |  |  | 41.91% | 113.2% | 113.2% | 0 | -9.26% | 79161.46 | 33175.67 | 45985.79 | 0 | 5109.88 | 5109.88 | 0 | 0 | 37544.22 | 0 | -4368.55 | 0% | NO | -4368.55 | 0 | 37544.22 | 0 | 0 | 0 | 0 | 0 | 22% | 12.74% | 0% | -22% |  | 56 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23821 | Supply of Safety Engineer | Dinna Elkhalifa | 0 | BXW | STIRLING DYNAMICS LTD | EES | Level NC | REIM |  |  |  | 0.023823 | 99.71% | 55.95% | -0.0003441% | 0 | 45.1% | 34006.44 | 33906.6 | 99.84 | 4190.82 | 0 | 0 | 0 | 0 | 18971.55 | 103.86 | 14935.05 | 356.4% | YES | 14935.05 | 22766 | -0.11667 | 0 | 22765.86 | 0 | 0 | 0 | 0% | 45.1% | 45.1% | 45.1% |  | 80.73 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P22768 | MRB Onsite Support - Spirit Belfast | Trevor Knox | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2023-07-27 | 0 |  |  |  | 0% | 0% | 0 | -17.07% | 0 | 34614 | -34614 | 0 | 0 | 0 | 36800 | 34614 | 0 | 41536.8 | 34614 | 0% | NO | 34614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | -7.07% | 0% | -10% |  | 36 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23347 | WoT Fixed Leading Edge - Industrial 2023 | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 112.8% | 42.03% | 42.03% | 0 | -0.41% | 31034.12 | 35002.1 | -3967.98 | 0 | 0 | 0 | 10500 | 3967.98 | 14710.56 | 24349.85 | 20291.54 | 0% | NO | 20291.54 | 0 | 14710.56 | 0 | 0 | 0 | 0 | 0 | 7% | 6.59% | 0% | -7% |  | 32.26 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23598 | MRB Onsite support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 47.6728 | 28.62% | 0% | 0% | 0 | -11.62% | 133056 | 38082.67 | 94973.33 | 1992.19 | 8736.42 | 14079.58 | 0 | 0 | 0 | 93.15 | 38082.67 | 1912% | YES | 43425.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 16.38% | 16.77% | -11.23% |  | 42.5 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23051 | Spirit Shorts A350 PAX Door | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3A | REIM |  |  |  |  | 205.9% | 105.4% | 105.4% | 0 | -0.63% | 18216 | 37513 | -19297 | 0 | 0 | 0 | 0 | 19297 | 39537 | 0 | 0 | 0% | NO | 0 | 0 | 39537 | 0 | 0 | 0 | 0 | 0 | 30% | 29.37% | 0% | -30% |  | 46 | [5 empty] | 2024
1734 | 2024-04-17 23:33 | P23760 | EXP-033 Systems Engineering Support | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 40.9356 | 29.43% | 82.38% | 56.89% | 0 | -0.02% | 142300 | 41879.75 | 100420.25 | 2453.13 | 0 | 0 | 0 | 0 | 34500.75 | 44.48 | 7379 | 300.8% | YES | 7379 | 12811 | 23824.9167 | 0 | 12811.2 | 0 | 0 | 0 | 29% | 28.98% | 28.98% | -0.02% |  | 78.5 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P22752 | Tooling WoT - 2021 (Spirit) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | REIM | 2023-05-03 | 0 |  |  | 101.1% | 74.02% | 74.02% | 0 | -8.5% | 41525.1 | 41982.28 | -457.18 | 0 | 0 | 0 | 0 | 457.18 | 31076.1 | 13087.42 | 10906.18 | 0% | NO | 10906.18 | 0 | 31076.1 | 0 | 0 | 0 | 0 | 0 | 0% | -8.5% | 0% | 0% |  | 39.09 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23642 | MRB Belfast Support | Carl Warren | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -29.6205 |  | 0% | 0% | 0 | -43.93% | 0 | 46600.97 | -46600.97 | 1573.27 | 3135.3 | 3135.3 | 42350 | 46600.97 | 0 | 176.26 | 46600.97 | 2962% | YES | 46600.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22% | -21.93% | -24.55% | -46.55% |  | 38.52 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23339 | Spirit 2023 - Stewart Russell | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 64.51% | 100% | 100% | 0 | 0.62% | 72766.8 | 46941.72 | 25825.08 | 0 | 0 | 0 | 0 | 0 | 46941.74 | 0 | -0.02 | 0% | NO | -0.02 | 0 | 46941.74 | 0 | 0 | 0 | 0 | 0 | 7% | 7.62% | 0% | -7% |  | 35.67 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P22760 | SA Leading Edge Transport Media ('A' Frames) | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-11-15 | 1 |  |  | 85.99% | 110.7% | 116.3% | -3082.8 | 3.97% | 53480.8 | 45985.5 | 7495.3 | 0 | 42804 | 42804 | 0 | 0 | 50911.8 | 0 | -0.3 | 0% | NO | -0.3 | -3083 | 53480.9667 | 0 | 0 | 0 | -3082.8 | -3082.8 | 6% | 9.97% | 0% | -6% |  | 42 | [5 empty] | 4926
1734 | 2024-04-17 23:33 | P23349 | Spirit 2023 - Stress Approve Man Serv (SB) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 58.24% | 80.05% | 80.05% | 0 | -0.29% | 97920 | 57024 | 40896 | 0 | 0 | 0 | 0 | 0 | 45648 | 13651.2 | 11376 | 0% | NO | 11376 | 0 | 45648 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23322 | GKN T Tomblin 2023 | Steven Lawton | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2024-04-15 | 3 |  |  | 99.66% | 100% | 83.41% | 0 | -0.33% | 58952 | 58752 | 200 | 0 | 0 | 0 | 0 | 0 | 58752 | 91 | 0 | 0% | NO | 0 | 11693 | 49007.8333 | 0 | 8121.6 | 3571.2 | 0 | 0 | 17% | 16.67% | 16.67% | -0.33% |  | 48 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23700 | IPDT Leads | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 31.5169 | 35.38% | 41.63% | -0.0006346% | 0 | -1.99% | 169263.9 | 59883.3 | 109380.6 | 3470.54 | 0 | 0 | 0 | 0 | 24932.12 | 119.54 | 34951.18 | 1007% | YES | 34951.18 | 29919 | -0.38 | 0 | 29918.54 | 0 | 0 | 0 | 26% | 24.01% | 21.81% | -4.19% |  | 50.45 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23106 | ME Support to NPD - Bobby Haggart | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  |  | 95.79% | 97.03% | 97.03% | 0 | 0.3% | 65675 | 62912.11 | 2762.89 | 0 | 0 | 0 | 0 | 0 | 61042.75 | 2243.24 | 1869.36 | 0% | NO | 1869.36 | 0 | 61042.75 | 0 | 0 | 0 | 0 | 0 | 15% | 15.3% | 0% | -15% |  | 35.65 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P22967 | Spirit 2022 - Channapa Laxmeshwar | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2023-01-26 | 2 |  |  | 69.69% | 121.3% | 121.3% | 0 | 9.53% | 75159.1 | 52376.15 | 22782.95 | 0 | 52376.15 | 54898.1 | 0 | 0 | 63508.8 | 0.42 | 0.35 | 0% | NO | 2522.3 | 0 | 63508.8 | 0 | 0 | 0 | 0 | 0 | 8% | 17.53% | 0% | -8% |  | 0 | [5 empty] | 11133
1734 | 2024-04-17 23:33 | P23193 | Spirit Shorts Stephen Greer | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -6.889 | 105.7% | 93.48% | 84.15% | 0 | 8.63% | 61472 | 64949.35 | -3477.35 | 504.77 | 0 | 0 | 10878 | 3477.35 | 60712.78 | 113.68 | 4236.57 | 839.3% | YES | 4236.57 | 7269 | 54655.28 | 0 | 7268.72 | 0 | 0 | 0 | 23% | 31.63% | 34.03% | 11.03% |  | 35.1 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23341 | Spirit 2023 - Tom McFarlane | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 41.9342 | 61.06% | 90.98% | 64.83% | 7110.19 | -0.01% | 108666.4 | 66356.47 | 42309.93 | 1008.96 | 0 | 0 | 0 | 0 | 60369.22 | 153.08 | 5987.25 | 593.4% | YES | 5987.25 | 20820 | 43019.22 | 11378.44 | 2331.04 | 0 | 7110.19 | 7110.19 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23561 | SAAB | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2024-01-01 | 0 |  |  | 82.46% | 121.1% | 121.1% | 0 | 8.77% | 67485 | 55649.23 | 11835.77 | 0 | 0 | 0 | 0 | 0 | 67399.4 | 0 | -0.17 | 0% | NO | -0.17 | 0 | 67399.4 | 0 | 0 | 0 | 0 | 0 | 16% | 24.77% | 100% | 84% |  | 36.82 | [5 empty] | 11750
1734 | 2024-04-17 23:33 | P23729 | Honda Tooling | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | FIX |  |  |  | 9.1165 | 61.66% | 46.31% | 0% | 0 | 3.45% | 113610 | 70056 | 43554 | 4777.5 | 0 | 0 | 0 | 0 | 32445 | 97.71 | 37611 | 787.3% | YES | 37611 | 38934 | 0 | 0 | 38934 | 0 | 0 | 0 | 10% | 13.45% | 13.45% | 3.45% |  | 42 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23744 | Model Factory | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 40.0179 | 26.5% | 95.77% | -0.0002398% | 27429.6 | 9.19% | 262300 | 69511.25 | 192788.75 | 4817.56 | 0 | 0 | 0 | 0 | 66574 | 102.66 | 5937.25 | 123.2% | NO | 5937.25 | 79889 | -0.16667 | 0 | 26229.6 | 26229.6 | 27429.6 | 27429.6 | 28% | 37.19% | 37.19% | 9.19% |  | 50.61 | [5 empty] | 3000
1734 | 2024-04-17 23:33 | P23600 | MBDA EXP-EE-023 Bristone Certification | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 59.65% | 100% | 100% | 0 | 0.4% | 126600 | 75517 | 51083 | 0 | 0 | 0 | 0 | 0 | 75517 | 0 | 0 | 0% | NO | 0 | 0 | 75517 | 0 | 0 | 0 | 0 | 0 | 41% | 41.4% | 0% | -41% |  | 78.5 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23080 | Spirit Shorts DManagement Cairan Cullen | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 491.6255 | 50.77% | 97.69% | 91.01% | 3787.8 | -1.23% | 149600 | 75954.5 | 73645.5 | 149.8 | 0 | 0 | 0 | 0 | 74199.7 | 186.68 | 1754.8 | 1171% | YES | 1754.8 | 6086 | 69128.0333 | 0 | 2298.36 | 0 | 3787.8 | 3787.8 | 24% | 22.77% | 13.03% | -10.97% |  | 44.39 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P22505 | Spirit MRB Engineering Support 2021 | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 1 |  |  | 91.17% | 100% | 95.78% | 4020.48 | 21.2% | 87110.4 | 79414.95 | 7695.45 | 0 | 0 | 0 | 0 | 0 | 79414.95 | 4020.48 | 0 | 0% | NO | 0 | 4020 | 76064.95 | 0 | 0 | 0 | 4020.48 | 4020.48 | 0% | 21.2% | 0% | 0% |  | 41.88 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23560 | NJEWCS TAF202302 SM | Natalie Sinclair | 0 | COB | CHELTON LIMITED | EES | Level 2 | FIX |  |  |  |  | 97.96% | 100.2% | 50.1% | 0 | 11.94% | 81500 | 79836.44 | 1663.56 | 0 | 0 | 0 | 0 | 0 | 80000 | 200.62 | -163.57 | 0% | NO | -163.57 | 48000 | 40000 | 48000 | 0 | 0 | 0 | 0 | 28% | 39.94% | 39.49% | 11.49% |  | 73.01 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P22885 | ME Support (Baxi) | Trevor Knox | 0 | HUV | BAXI HEATING UK LIMITED | ME | Level 3 | FIX | 2023-01-12 | 0 |  |  | 68.78% | 108.7% | 108.7% | 0 | 13.05% | 106632.96 | 73340.24 | 33292.72 | 0 | 0 | 0 | 0 | 0 | 79748.12 | 1531.35 | 1276.12 | 0% | NO | 1276.12 | 0 | 79748.12 | 0 | 0 | 0 | 0 | 0 | 15% | 28.05% | 0% | -15% |  | 44.37 | [5 empty] | 7684
1734 | 2024-04-17 23:33 | P23438 | A220 Spirit Shorts DTC - Stephen Corry | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 29.2167 | 85.55% | 78.54% | 49.23% | 0 | -7.3% | 95928.4 | 82068.6 | 13859.8 | 474.38 | 0 | 0 | 0 | 0 | 64459.8 | 341.41 | 17608.8 | 3712% | YES | 17608.8 | 28872 | 40399.8 | 0 | 28872.36 | 0 | 0 | 0 | 23% | 15.7% | 16.75% | -6.25% |  | 49.81 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23822 | FCASW Requirements Management | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | -9.0707 |  | 0% | 0% | 0 | -8.45% | 0 | 83917.15 | -83917.15 | 9251.46 | 0 | 0 | 98262.3 | 83917.15 | 0 | 70 | 83917.15 | 907.1% | YES | 83917.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 11.55% | 11.55% | -8.45% |  | 75.16 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23335 | GKN S McConnell 2023 | Steven Lawton | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2023-12-31 | 1 |  |  | 96.61% | 100% | 91.76% | 0 | 0.74% | 87420 | 84459 | 2961 | 0 | 0 | 0 | 0 | 0 | 84459 | 8347.2 | 0 | 0% | NO | 0 | 8347 | 77503.1667 | 0 | 0 | 0 | 8347.2 | 0 | 15% | 15.74% | 0% | -15% |  | 47 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P22965 | Spirit 2022 - Design Man Serv (AH) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 1 |  |  | 106.7% | 96.66% | 92.02% | 4759.75 | 3.14% | 80079.56 | 85441.32 | -5361.76 | 0 | 0 | 0 | 0 | 5361.76 | 82588.96 | 8182.59 | 2852.36 | 0% | NO | 2852.36 | 4760 | 78622.2933 | 0 | 0 | 0 | 4759.75 | 4759.75 | 14% | 17.14% | 0% | -14% |  | 42.44 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23523 | Applique Armour Support | Dushan Fernando | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-18 | 1 |  |  | 72.43% | 138.1% | 98.47% | 0 | 3.42% | 118200 | 85606.5 | 32593.5 | 0 | 0 | 0 | 0 | 0 | 118200 | 1567.8 | -32593.5 | 0% | NO | -32593.5 | 40680 | 84300 | 0 | 40680 | 0 | 0 | 0 | 25% | 28.42% | 0% | -25% |  | 64.29 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P22964 | Spirit 2022 - MRB Man Serv (JC) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 100.6% | 97.95% | 97.95% | 0 | 1.91% | 85435.2 | 85960.26 | -525.06 | 0 | 0 | 0 | 0 | 525.06 | 84199.74 | 2112.62 | 1760.52 | 0% | NO | 1760.52 | 0 | 84199.74 | 0 | 0 | 0 | 0 | 0 | 16% | 17.91% | 0% | -16% |  | 42.69 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P22963 | Spirit 2022 - Design Man Serv (PC) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 1 |  |  | 108.6% | 104% | 94.46% | 9938.48 | 3.18% | 80079.56 | 86926.74 | -6847.18 | 0 | 0 | 0 | 0 | 6847.18 | 90389.95 | 5782.63 | -3463.21 | 0% | NO | -3463.21 | 9938 | 82108.2833 | 0 | 0 | 0 | 9938.48 | 9938.48 | 13% | 16.18% | 0% | -13% |  | 42.39 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23342 | Spirit 2023 - Channapa Laxmeshwar | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 237.5059 | 53.17% | 86.8% | 73.25% | 4036.8 | -3.73% | 158696.7 | 84385.85 | 74310.85 | 312.88 | 84385.85 | 94827 | 0 | 0 | 73251.1 | 112.03 | 13984.75 | 4470% | YES | 24425.9 | 13725 | 61813.6 | 9688.32 | 0 | 0 | 4036.8 | 4036.8 | 7% | 3.27% | 0% | -7% |  | 0 | [5 empty] | 2850
1734 | 2024-04-17 23:33 | P23340 | Spirit 2023 - John Cole | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 43.832 | 58.48% | 90.17% | 63.21% | 8831.16 | -0.01% | 150129.72 | 87794.46 | 62335.26 | 1422.14 | 0 | 0 | 0 | 0 | 79162.2 | 157.89 | 8632.26 | 607% | YES | 8632.26 | 28403 | 55493.0333 | 14750.42 | 4821.34 | 0 | 8831.16 | 8831.16 | 7% | 6.99% | 6.99% | -0.01% |  | 39.78 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23465 | A220 ToW Design Offload (Wing) | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 61.141 | 66.79% | 91.36% | 63.25% | 0 | -4.71% | 132000 | 88168 | 43832 | 716.9 | 0 | 0 | 0 | 0 | 80549.6 | 106.97 | 7618.4 | 1063% | YES | 7618.4 | 29737 | 55768.7667 | 0 | 29737.44 | 0 | 0 | 0 | 20% | 15.29% | 13.92% | -6.08% |  | 42.8 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23079 | Spirit Shorts Nomenclature | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -1.2972 | 100.7% | 87.77% | 76.72% | 0 | 2.03% | 88455 | 89079.6 | -624.6 | 481.5 | 0 | 0 | 0 | 624.6 | 78185.2 | 244.94 | 10894.4 | 2263% | YES | 10894.4 | 11811 | 68342.7 | 0 | 11810.64 | 0 | 0 | 0 | 20% | 22.03% | 25.23% | 5.23% |  | 30.78 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23336 | Spirit 2023 - Neil Rampling | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 28.0586 | 68.31% | 90.17% | 52.33% | 21586.03 | -0.01% | 133901.52 | 91467.44 | 42434.08 | 1512.34 | 0 | 0 | 0 | 0 | 82473.26 | 204.27 | 8994.18 | 594.7% | YES | 8994.18 | 41533 | 47862.4267 | 15306.07 | 4640.79 | 0 | 21586.03 | 21586.03 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23345 | Spirit 2023- Jonathan Escosio | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 24.6433 | 61.61% | 73.07% | 54.75% | 15846.34 | -0.38% | 151941.24 | 93611.27 | 58329.97 | 2366.97 | 0 | 0 | 0 | 0 | 68401.74 | 213.65 | 25209.53 | 1065% | YES | 25209.53 | 20581 | 51250.9067 | 0 | 4734.58 | 0 | 15846.34 | 15846.34 | 7% | 6.62% | 22.81% | 15.81% |  | 43.01 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23375 | GKN Jaap Peters NL 2023 | Steven Lawton | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2024-03-01 | 2 |  |  | 93.37% | 105.3% | 85.02% | 0 | -15.93% | 97123.22 | 90686.41 | 6436.81 | 0 | 90686.41 | 90686.41 | 0 | 0 | 95456.72 | 108.86 | -920.31 | 0% | NO | -920.31 | 22027 | 77100.8867 | 0 | 0 | 8793.29 | 13234.06 | 0 | 20% | 4.07% | 0% | -20% |  | 0 | [5 empty] | 3850
1734 | 2024-04-17 23:33 | P23171 | Spirt Shorts Weights Eng | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 10.9035 | 69.18% | 133.5% | 103.1% | 0 | 13.12% | 103113.14 | 71329.32 | 31783.82 | 2915 | 71329.32 | 85975.13 | 0 | 0 | 95259.1 | 151.79 | 0.22 | 0.007547% | NO | 14646.03 | 26047 | 73553.2667 | 9273.05 | 0 | 16774.18 | 0 | 0 | 12% | 25.12% | 47.26% | 35.26% |  | 0 | [5 empty] | 23930
1734 | 2024-04-17 23:33 | P23586 | Project Management Support | Dushan Fernando | 0 | BDX | MBDA UK LIMITED | MPE | Level NC | REIM |  |  |  | 29.5948 | 59.6% | 70.37% | 70.37% | 0 | -26.42% | 160000 | 95360.46 | 64639.54 | 2184.15 | 1277.2 | 1277.2 | 0 | 0 | 67103.86 | 75.24 | 28256.6 | 1294% | YES | 28256.6 | 0 | 67103.86 | 0 | 0 | 0 | 0 | 0 | 49% | 22.58% | 21.58% | -27.42% |  | 80 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23551 | Ian Berry 2023 H2 | Natalie Sinclair | 0 | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  | -10.1569 | 126.2% | 70.23% | 70.23% | 0 | 13.46% | 75810 | 95705.12 | -19895.12 | 1958.78 | 0 | 0 | 24259.2 | 19895.12 | 67217.49 | 75.15 | 28487.63 | 1454% | YES | 28487.63 | 0 | 67217.49 | 0 | 0 | 0 | 0 | 0 | 22% | 35.46% | 37.71% | 15.71% |  | 77.6 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23545 | Ultra CSS continuation 2023 H2 | Natalie Sinclair | 0 | ULT | ULTRA SONAR SYSTEMS LIMITED | EES | Level NC | REIM |  |  |  |  | 133% | 74.66% | 74.66% | 0 | 2.22% | 76000 | 101057.6 | -25057.6 | 0 | 0 | 0 | 24259.2 | 25057.6 | 75451.2 | 114.15 | 25606.4 | 0% | NO | 25606.4 | 0 | 75451.2 | 0 | 0 | 0 | 0 | 0 | 23% | 25.22% | 25% | 2% |  | 80 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23583 | Castalla - Test Rig Design | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -23.5182 | 151.2% | 66.12% | 60.02% | 0 | -6.38% | 67520 | 102056.5 | -34536.5 | 1468.5 | 0 | 0 | 36106 | 34536.5 | 67482.1 | 141.22 | 34574.4 | 2354% | YES | 34574.4 | 7469 | 61257.9333 | 0 | 7469.4 | 0 | 0 | 0 | 21% | 14.62% | 16.76% | -4.24% |  | 42.81 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23784 | Tempest Tooling Offload 2024 | Gary Kempster | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  | -14.35 |  | 0% | 0% | 0 | -11.73% | 0 | 102162.19 | -102162.19 | 7119.34 | 0 | 0 | 107936.4 | 102162.19 | 0 | 100.02 | 102162.19 | 1435% | YES | 102162.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 18.27% | 18.27% | -11.73% |  | 54.81 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23753 | Tempest Composites Maturation | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 1.3829 | 85.13% | 28.56% | -0.0001838% | 0 | -10.48% | 127848.45 | 108837.64 | 19010.81 | 13747.43 | 0 | 0 | 0 | 0 | 31084.8 | 96.67 | 77752.84 | 565.6% | YES | 77752.84 | 37302 | -0.2 | 0 | 37301.76 | 0 | 0 | 0 | 32% | 21.52% | 21.52% | -10.48% |  | 64.61 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23353 | Spirit 2023 - MRB Man Serv (JC) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  | 31.17 | 61.8% | 60.47% | 60.47% | 0 | 9.8% | 183600 | 113467.5 | 70132.5 | 2250 | 0 | 0 | 0 | 0 | 68615.25 | 190.15 | 44852.25 | 1993% | YES | 44852.25 | 0 | 68615.25 | 0 | 0 | 0 | 0 | 0 | 7% | 16.8% | 13.21% | 6.21% |  | 45 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P22918 | Spirit Shorts Graduates | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 20.0216 | 88.73% | 92.54% | 60.99% | 0 | 9.47% | 130000 | 115343.39 | 14656.61 | 732.04 | 0 | 0 | 9900 | 0 | 106734.95 | 253.75 | 8608.44 | 1176% | YES | 8608.44 | 43660 | 70351.6167 | 0 | 0 | 43659.95 | 0 | 0 | 7% | 16.47% | 17.17% | 10.17% |  | 23.3 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23352 | Spirit 2023 - Stress Approve Man Serv (CC) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  | -8.0526 | 118.8% | 60.12% | 60.12% | 0 | 6.54% | 97920 | 116280 | -18360 | 2280 | 0 | 0 | 29856 | 18360 | 69912 | 225.4 | 46368 | 2034% | YES | 46368 | 0 | 69912 | 0 | 0 | 0 | 0 | 0 | 7% | 13.54% | 4.69% | -2.31% |  | 48 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23588 | BAE Typhoon MRB MC Shop Concessions | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 27.9313 | 66.87% | 95.77% | 68.59% | 14399.76 | -3.7% | 175060.5 | 117071.15 | 57989.35 | 2076.14 | 0 | 0 | 0 | 0 | 112121.71 | 105.86 | 4949.44 | 238.4% | YES | 4949.44 | 38191 | 80295.8767 | 10272.55 | 13518.34 | 14399.76 | 0 | 14399.76 | 31% | 27.3% | 29.27% | -1.73% |  | 55.52 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23664 | Tempest Composites WP3 | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 2.5125 | 97.51% | 72.12% | 13.83% | 0 | -5.11% | 122455.49 | 119400.61 | 3054.88 | 1215.86 | 0 | 0 | 14830.4 | 0 | 86110.38 | 253.81 | 33290.23 | 2738% | YES | 33290.23 | 83510 | 16518.7133 | 83510.02 | 0 | 0 | 0 | 0 | 37% | 31.89% | 33.56% | -3.44% |  | 60.63 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P22736 | WoT Fixed Leading Edge - Industrial | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 106.7% | 93.42% | 91.32% | 3019.54 | 0.01% | 112196.27 | 119668.47 | -7472.2 | 0 | 0 | 0 | 0 | 7472.2 | 111796.68 | 12465.69 | 7871.79 | 0% | NO | 7871.79 | 3020 | 109280.0133 | 0 | 0 | 0 | 3019.54 | 3019.54 | 7% | 7.01% | 0% | -7% |  | 32.26 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P22883 | Spirit Shorts Evtol PMO C. Hatton | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 199.488 | 65.16% | 89.99% | 89.99% | 0 | -11.75% | 185800 | 121066.15 | 64733.85 | 324.5 | 0 | 0 | 0 | 0 | 108946.73 | 116.85 | 12119.42 | 3735% | YES | 12119.42 | 0 | 108946.73 | 0 | 0 | 0 | 0 | 0 | 26% | 14.25% | 22.96% | -3.04% |  | 36.79 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23282 | Tooling Support (MBDA) | Dushan Fernando | 0 | BDV | MBDA UK LIMITED | ME | Level NC | REIM |  |  |  | 45.4898 | 64.03% | 96.58% | 82.85% | 0 | -8.24% | 195672.4 | 125290.2 | 70382.2 | 1547.21 | 0 | 0 | 0 | 0 | 121010.44 | 84.48 | 4279.76 | 276.6% | YES | 4279.76 | 20648 | 103803.7733 | 0 | 20647.76 | 0 | 0 | 0 | 30% | 21.76% | 30.37% | 0.37% |  | 49.72 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P22861 | WoT FLE Lifting & Handling Tools | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2023-06-14 | 1 |  |  | 65.17% | 101.6% | 101.6% | 0 | 12.01% | 173987.21 | 113381.75 | 60605.46 | 0 | 50078 | 58423.58 | 0 | 0 | 115203.5 | 12813.9 | 10678.25 | 0% | NO | 19023.83 | 0 | 115203.5 | 0 | 0 | 0 | 0 | 0 | 1% | 13.01% | 0% | -1% |  | 45 | [5 empty] | 12500
1734 | 2024-04-17 23:33 | P23270 | Shorts Project X | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 9.1198 | 89.34% | 91.23% | 69.16% | 0 | 0.51% | 142248 | 127083.74 | 15164.26 | 1662.78 | 0 | 0 | 0 | 0 | 115944.34 | 163.3 | 11139.4 | 669.9% | YES | 11139.4 | 33666 | 87889.34 | 10030.61 | 23635.49 | 0 | 0 | 0 | 13% | 13.51% | 10.99% | -2.01% |  | 45.33 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23754 | Tempest Composites WP4 | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 14.0569 | 42.31% | 0% | 0% | 0 | -1.12% | 310945.68 | 131561.23 | 179384.45 | 12761.3 | 1344.88 | 1344.88 | 0 | 0 | 0 | 92.26 | 131561.23 | 1031% | YES | 131561.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36% | 34.88% | 34.88% | -1.12% |  | 62.54 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23810 | Strategic Enablement | Owain Jones | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -848.8267 |  | 0% | 0% | 0 | -20.63% | 0 | 133690.2 | -133690.2 | 157.5 | 0 | 0 | 134000 | 133690.2 | 0 | 106.4 | 133690.2 | 84883% | YES | 133690.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | -2.63% | -2.63% | -20.63% |  | 42 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23533 | External Stowage Design and Detail Support | Dushan Fernando | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 1 |  |  | 102.4% | 97.65% | 73.24% | 0 | 3.33% | 140000 | 143368.75 | -3368.75 | 0 | 0 | 0 | 12936 | 3368.75 | 140000 | 41999.7 | -0.25 | 0% | NO | -0.25 | 42000 | 105000 | 0 | 42000 | 0 | 0 | 0 | 27% | 30.33% | 0% | -27% |  | 60.04 | [5 empty] | -3369
1734 | 2024-04-17 23:33 | P23650 | MBDA Recruitment Management costs | Andrew Slaney | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM | 2024-02-01 | 0 |  |  |  | 0% | 0% | 0 | -20.2% | 0 | 240971.5 | -240971.5 | 0 | 0 | 0 | 266000 | 240971.5 | 0 | 171.72 | 140971.5 | 0% | NO | 140971.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | -17.2% | -441% | -444% |  | 82.3 | [5 empty] | -100000
1734 | 2024-04-17 23:33 | P22954 | Technical Support Step 1 | Owain Jones | 0 | HUV | HUARUI SPIRIT AEROSPACE MANUFACT | ME | Level 2 | REIM |  |  |  |  | 94.81% | 58.01% | 58.01% | 0 | 0.31% | 155501.18 | 147431.58 | 8069.6 | 0 | 23043 | 23043 | 0 | 0 | 85525.49 | 61906.09 | 61906.09 | 0% | NO | 61906.09 | 0 | 85525.49 | 0 | 0 | 0 | 0 | 0 | 30% | 30.31% | 0% | -30% |  | 60.79 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23386 | Software Development - BMS | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 98.78% | 100% | 100% | 0 | 4.31% | 149650 | 147823.35 | 1826.65 | 0 | 0 | 0 | 0 | 0 | 147823.35 | 0 | 0 | 0% | NO | 0 | 0 | 147823.35 | 0 | 0 | 0 | 0 | 0 | 18% | 22.31% | 22.61% | 4.61% |  | 78.5 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23437 | Embedded Software Engineer | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 98.73% | 100% | 96.08% | 0 | -6.29% | 150150 | 148239.36 | 1910.64 | 0 | 737.86 | 737.86 | 0 | 0 | 148239.36 | 22.83 | 0 | 0% | NO | 0 | 6971 | 142430.1933 | 0 | 6970.8 | 0 | 0 | 0 | 22% | 15.71% | 16.24% | -5.76% |  | 78.5 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23550 | Tempest Composites | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -4.6319 | 102.5% | 97.57% | 97.57% | 0 | 5.14% | 149494.92 | 153217.46 | -3722.54 | 803.68 | 0 | 0 | 2396.12 | 3722.54 | 149494.92 | 19.17 | 3722.54 | 463.2% | YES | 3722.54 | 0 | 149494.92 | 0 | 0 | 0 | 0 | 0 | 26% | 31.14% | 34.01% | 8.01% |  | 61.6 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P22440 | Spirit Managed Service - F&DT and Static Approval | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 3 |  |  | 88.56% | 92.56% | 92.56% | 0 | 11.51% | 173500 | 153656.25 | 19843.75 | 0 | 52115 | 55720 | 0 | 0 | 142225.12 | 13717.36 | 11431.13 | 0% | NO | 15036.13 | 0 | 142225.12 | 0 | 0 | 0 | 0 | 0 | 0% | 11.51% | 0% | 0% |  | 44.73 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P22982 | Spirit 2022 - Hugh Sloan | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 83.0227 | 62.51% | 94.33% | 82.07% | 8217.17 | -0.55% | 247473 | 154685.14 | 92787.86 | 1117.62 | 0 | 0 | 0 | 0 | 145911.5 | 194.11 | 8773.64 | 785% | YES | 8773.64 | 22757 | 126947.3333 | 10239.53 | 4300.18 | 0 | 8217.17 | 8217.17 | 7% | 6.45% | 1.35% | -5.65% |  | 35.43 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23741 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  | 41.0913 | 24.44% | 90.02% | -0.0001064% | 53862 | 2.4% | 640812 | 156586.2 | 484225.8 | 11784.15 | 0 | 0 | 0 | 0 | 140959 | 99.83 | 19627.2 | 166.6% | YES | 19627.2 | 169151 | -0.16667 | 0 | 62626.8 | 52662 | 53862 | 53862 | 28% | 30.4% | 30.4% | 2.4% |  | 38.81 | [5 empty] | 4000
1734 | 2024-04-17 23:33 | P23518 | Systems Engineering support to FCAS | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 12.471 | 83.51% | 92.48% | 87.41% | 0 | -4.35% | 193736.8 | 161797.75 | 31939.05 | 2561.06 | 3927.4 | 3927.4 | 0 | 0 | 149625.43 | 54.99 | 12172.32 | 475.3% | YES | 12172.32 | 9844 | 141422.0967 | 0 | 9843.9 | 0 | 0 | 0 | 30% | 25.65% | 3.5% | -26.5% |  | 68.16 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23667 | Safety Systems Engineer | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 61.5415 | 41.32% | 93.24% | 83.34% | 0 | -10.15% | 398000 | 164450 | 233550 | 3795 | 0 | 0 | 0 | 0 | 153340 | 45.68 | 11110 | 292.8% | YES | 11110 | 19536 | 137060 | 0 | 19536 | 0 | 0 | 0 | 47% | 36.85% | 29.32% | -17.68% |  | 110 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23421 | A220 DTC | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 10.7776 | 78.72% | 70.37% | 62.67% | 0 | -28.53% | 217089.12 | 170893.65 | 46195.47 | 4286.26 | 0 | 0 | 0 | 0 | 120261.6 | 103.55 | 50632.05 | 1181% | YES | 50632.05 | 15801 | 107094.1 | 0 | 15800.9 | 0 | 0 | 0 | 29% | 0.47% | 5.34% | -23.66% |  | 46 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23464 | A220 Project X Design Offload | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 104.9455 | 51.68% | 100% | 64.09% | 27862.8 | -9.3% | 332340 | 171762.9 | 160577.1 | 1530.1 | 0 | 0 | 0 | 0 | 171762.9 | 168.22 | 0 | 0% | NO | 0 | 74010 | 110087.9 | 18361.2 | 27785.76 | 0 | 27862.8 | 27862.8 | 26% | 16.7% | 14.75% | -11.25% |  | 42.88 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23508 | Verification and Validation | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 80.77% | 100% | 97.06% | 0 | 10.77% | 212950 | 171993.5 | 40956.5 | 0 | 0 | 0 | 0 | 0 | 171993.53 | 16.08 | -0.03 | 0% | NO | -0.03 | 6076 | 166930.1967 | 0 | 6075.9 | 0 | 0 | 0 | 24% | 34.77% | 33.6% | 9.6% |  | 78.5 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23739 | Lifing Services DACs | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  | 43.1208 | 25.92% | 97.03% | 0.0001959% | 66850.8 | 5% | 656508 | 170179.6 | 486328.4 | 11278.28 | 0 | 0 | 0 | 0 | 165127 | 101.94 | 10052.6 | 89.13% | NO | 10052.6 | 198152 | 0.33333 | 0 | 65650.8 | 65650.8 | 66850.8 | 66850.8 | 28% | 33% | 33% | 5% |  | 37.77 | [5 empty] | 5000
1734 | 2024-04-17 23:33 | P23524 | Bombardier Regional Jets (BRJ) | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -2614.0777 | 130.8% | 56.87% | 55.26% | 3694.07 | -4.75% | 146287.84 | 191380.68 | -45092.84 | 17.25 | 0 | 0 | 46750 | 45092.84 | 108838.22 | 548.49 | 82542.46 | 478507% | YES | 82542.46 | 3694 | 105759.8867 | 0 | 0 | 0 | 3694.07 | 3694.07 | 18% | 13.25% | 15.01% | -2.99% |  | 43.92 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23648 | EXP-032 Delivery of Datalink Eng support - FCAS AP | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 19.0055 | 52.94% | 77.49% | 69.2% | 0 | 5.97% | 371000 | 196410.45 | 174589.55 | 9186.25 | 1032.95 | 1032.95 | 0 | 0 | 152192.95 | 50.51 | 44217.5 | 481.3% | YES | 44217.5 | 19536 | 135912.95 | 0 | 19536 | 0 | 0 | 0 | 22% | 27.97% | 28.32% | 6.32% |  | 102.94 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23008 | Spirit Shorts Project Rachel | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 68.49% | 91.32% | 91.32% | 0 | -9.7% | 286960 | 196531.2 | 90428.8 | 0 | 0 | 0 | 0 | 0 | 179472.8 | 20470.08 | 17058.4 | 0% | NO | 17058.4 | 0 | 179472.8 | 0 | 0 | 0 | 0 | 0 | 15% | 5.3% | 0.31% | -14.69% |  | 46.04 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23019 | EXP034-B Actuator Development | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 103.1% | 89.91% | 89.91% | 0 | -16.68% | 215541.2 | 222215.54 | -6674.34 | 0 | 12297.9 | 12297.9 | 0 | 6674.34 | 199796.76 | 91.24 | 397.78 | 0% | NO | 397.78 | 0 | 199796.76 | 0 | 0 | 0 | 0 | 0 | 34% | 17.32% | 79.64% | 45.64% |  | 58.45 | [5 empty] | -22021
1734 | 2024-04-17 23:33 | P23506 | ASTER Mid-Life Refurbishment Project Manager | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 6.0224 | 89.73% | 92.4% | 86.59% | 0 | 1.06% | 224900 | 201796.41 | 23103.59 | 3836.25 | 2806.41 | 2806.41 | 0 | 0 | 186451.41 | 46.8 | 15345 | 400% | YES | 15345 | 14058 | 174736.41 | 14058 | 0 | 0 | 0 | 0 | 25% | 26.06% | 26.38% | 1.38% |  | 110 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23505 | EXP-022 Meteor TBUS T&E support | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 15.5242 | 82.23% | 96.39% | 88.49% | 0 | -1.17% | 246744.4 | 202903.51 | 43840.89 | 2824.03 | 0 | 0 | 0 | 0 | 195582.38 | 44.75 | 7321.13 | 259.2% | YES | 7321.13 | 19242 | 179547.38 | 0 | 19241.59 | 0 | 0 | 0 | 20% | 18.83% | 15.67% | -4.33% |  | 89.83 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23242 | Physical Architecture & System Engineering Support | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 37.0712 | 67.97% | 95.94% | 90.27% | 0 | 7.74% | 305459 | 207607.46 | 97851.54 | 2639.56 | 775.55 | 775.55 | 0 | 0 | 199187.05 | 48.44 | 8066.41 | 305.6% | YES | 8066.41 | 14130 | 187412.05 | 0 | 14130 | 0 | 0 | 0 | 15% | 22.74% | 7.06% | -7.94% |  | 78.2 | [5 empty] | -354
1734 | 2024-04-17 23:33 | P23373 | Raytheon Michael Bellini | Natalie Sinclair | 0 | RAS | RAYTHEON UNITED KINGDOM LIMITED | EES | Level NC | REIM |  |  |  | 0.95559 | 98.37% | 90.93% | 81.15% | 24734.7 | -7.82% | 214367.4 | 210865.75 | 3501.65 | 3664.4 | 0 | 0 | 13558.28 | 0 | 191739.73 | 75.91 | 19126.02 | 521.9% | YES | 19126.02 | 24735 | 171127.23 | 0 | 24734.7 | 0 | 0 | 24734.7 | 45% | 37.18% | 38.65% | -6.35% |  | 91.61 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23677 | ME Managed Service - Phase 1 | Paul Watson | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  | 19.4537 | 43.37% | 89.13% | -0.0001733% | 0 | -16.25% | 554400 | 240447.6 | 313952.4 | 16138.46 | 0 | 38000 | 0 | 0 | 214301.25 | 115 | 26146.35 | 162% | YES | 64146.35 | 257162 | -0.41667 | 120379.5 | 136782 | 0 | 0 | 0 | 33% | 16.75% | 19.54% | -13.46% |  | 43.89 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23629 | F35 FTI | Christopher McCarthy | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level NC | REIM |  |  |  | -28.7939 |  | 91.29% | 84.85% | 0 | -1.3% | 0 | 241280.45 | -241280.45 | 8379.57 | 0 | 0 | 0 | 241280.45 | 220259.41 | 28.93 | 21021.04 | 250.9% | YES | 21021.04 | 18626 | 204737.7433 | 18625.64 | 0 | 0 | 0 | 0 | 31% | 29.7% | 28.32% | -2.68% |  | 61.87 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23743 | EHM Cloud Migration | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 41.562 | 21.93% | 114.9% | 0.0001496% | 102489.6 | 6.43% | 1016000 | 222846.25 | 793153.75 | 19083.63 | 0 | 0 | 0 | 0 | 256032 | 100.54 | -13185.75 | -69.09% | NO | -13185.75 | 307238 | 0.33333 | 0 | 102336 | 102412.8 | 102489.6 | 102489.6 | 28% | 34.43% | 34.43% | 6.43% |  | 54.2 | [5 empty] | 20000
1734 | 2024-04-17 23:33 | P23472 | Tempest Wing Design | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 41.1569 | 49.9% | 126.2% | 106.7% | 0 | -11.12% | 483869.78 | 241429.61 | 242440.17 | 5890.63 | 225550 | 356900 | 0 | 0 | 304757.78 | 14.25 | -38328.18 | -650.7% | NO | 93021.82 | 56671 | 257531.9467 | 32716.75 | 23954.72 | 0 | 0 | 0 | 23% | 11.88% | 33.11% | 10.11% |  | 46.74 | [5 empty] | 25000
1734 | 2024-04-17 23:33 | P23816 | Typhoon FTI Works - 2024 Fixed Price Element | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 5.2068 | 64.56% | 0% | 0% | 0 | -1% | 404176.65 | 260931.54 | 143245.11 | 27511.36 | 0 | 0 | 0 | 0 | 0 | 79.95 | 270931.54 | 984.8% | YES | 270931.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 29% | 29% | -1% |  | 52.82 | [5 empty] | 10000
1734 | 2024-04-17 23:33 | P23603 | Typhoon IMDLR | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 7.6073 | 89.94% | 43.66% | 0.0001239% | 0 | 5.31% | 305067.09 | 274391.68 | 30675.41 | 4032.37 | 1500 | 1500 | 0 | 0 | 119807.84 | 371.52 | 154583.84 | 3834% | YES | 154583.84 | 143769 | 0.34 | 0 | 143769.41 | 0 | 0 | 0 | 26% | 31.31% | 32.43% | 6.43% |  | 56.95 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23007 | EXP-006A - Brimstone 3 | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 67.5432 | 67.63% | 97.98% | 89.96% | 0 | -2.72% | 406450 | 274890.66 | 131559.34 | 1947.78 | 0 | 0 | 0 | 0 | 269336.75 | 76.36 | 5523.91 | 283.6% | YES | 5523.91 | 26470 | 247278.4167 | 11492.4 | 0 | 14977.8 | 0 | 0 | 25% | 22.28% | 29.94% | 4.94% |  | 69.88 | [5 empty] | -30
1734 | 2024-04-17 23:33 | P21463 | Safety & Monitoring Systems at DM Beith & Gosport | Harry James Kellett | 0 | BXW | MOD | EES | Level 2 | FIX |  |  |  | 15.6977 | 82.15% | 121.7% | 121.7% | 0 | -28% | 349404.99 | 287025.79 | 62379.2 | 3973.79 | 72553.45 | 77420.74 | 21721 | 0 | 349386.99 | 0 | -62361.2 | -1569% | NO | -57493.91 | 0 | 349386.99 | 0 | 0 | 0 | 0 | 0 | 48% | 20% | 21.05% | -26.95% |  | 53 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23308 | NATO JEWCS | Natalie Sinclair | 0 | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  | 92.1008 | 82.61% | 92.95% | 92.84% | 0 | -3.7% | 356307 | 294339.74 | 61967.26 | 672.82 | 613.89 | 613.89 | 0 | 0 | 273576.49 | 80.32 | 20763.25 | 3086% | YES | 20763.25 | 387 | 273253.99 | 386.92 | 0 | 0 | 0 | 0 | 24% | 20.3% | 11.84% | -12.16% |  | 75.81 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P22953 | Spirit Shorts eVTOL | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-05-08 | 2 |  |  | 103.1% | 80.83% | 79.36% | 0 | -9.51% | 324272 | 334483.6 | -10211.6 | 0 | 66696.6 | 67387.9 | 0 | 10211.6 | 270366 | 70861.92 | 54117.6 | 0% | NO | 54808.9 | 5921 | 265431.8333 | 0 | 5920.8 | 0 | 0 | 0 | 17% | 7.49% | 100% | 83% |  | 46.19 | [5 empty] | -10000
1734 | 2024-04-17 23:33 | P22515 | Shorts A220 100/300 ALI Phase III | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 44.6801 | 81.9% | 97.73% | 90.65% | 0 | 0.73% | 400628.76 | 328130.39 | 72498.37 | 1622.61 | 3450.98 | 3450.98 | 0 | 0 | 320671.89 | 116.21 | 7458.5 | 459.7% | YES | 7458.5 | 27848 | 297465.2233 | 9461.23 | 18386.68 | 0 | 0 | 0 | 10% | 10.73% | 7.4% | -2.6% |  | 40.49 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23617 | Tempest Composites WP2 | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -23.4124 | 136.1% | 30.41% | 17.39% | 29536.68 | 11.7% | 244405.26 | 332615.92 | -88210.66 | 3767.69 | 0 | 0 | 120669.84 | 88210.66 | 101150.9 | 302.84 | 231465.02 | 6143% | YES | 231465.02 | 51981 | 57833.4 | 22444.14 | 0 | 0 | 29536.68 | 29536.68 | 22% | 33.7% | 33.45% | 11.45% |  | 62.06 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23699 | A220 Stress Checkers | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -31.517 |  | 0% | 0% | 0 | -1.99% | 0 | 342248.61 | -342248.61 | 10859.17 | 12000 | 12000 | 321520 | 342248.61 | 0 | 120.24 | 342248.61 | 3152% | YES | 342248.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22% | 20.01% | 20.04% | -1.96% |  | 61.88 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P22842 | ME Support (Aim Altitude) | Trevor Knox | 0 | AVI | AIM ALTITUDE UK LIMITED | ME | Level 3 | FIX | 2023-06-14 | 4 |  |  | 99.31% | 100.5% | 86.63% | 57290.84 | 0.49% | 346293.67 | 343918.08 | 2375.59 | 0 | 2909.86 | 2909.86 | 0 | 0 | 345673.01 | 55184.93 | -1754.93 | 0% | NO | -1754.93 | 57291 | 297930.51 | 0 | 0 | 0 | 57290.84 | 57290.84 | 13% | 13.49% | 0% | -13% |  | 46.3 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P22391 | GE System Engineering support | Vinayakumar Sugur | 0 | GEE | EXPERIS LIMITED | EES | Level NC | REIM | 2024-04-08 | 0 |  |  | 82.01% | 100.7% | 100.7% | 0 | 0.13% | 434434.25 | 356260.63 | 78173.62 | 0 | 0 | 0 | 0 | 0 | 358805.6 | 0 | -2544.97 | 0% | NO | -2544.97 | 0 | 358805.6 | 0 | 0 | 0 | 0 | 0 | 6% | 6.13% | 6.09% | 0.09% |  | 57.33 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23045 | Shotgun Adaptors - 10 Sets | Harry James Kellett | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | FIX | 2024-02-27 | 4 |  |  | 74.76% | 133.8% | 106.6% | 0 | 2.29% | 399276.11 | 298512.88 | 100763.23 | 0 | 214550.47 | 214550.47 | 0 | 0 | 399276.11 | 32324.4 | -7763.23 | 0% | NO | -7763.23 | 97440 | 318076.11 | 0 | 0 | 97440 | 0 | 0 | 29% | 31.29% | 99.78% | 70.78% |  | 55.76 | [5 empty] | 93000
1734 | 2024-04-17 23:33 | P23432 | Spirit Belfast MRB On-Site Support (Mon & Clear) | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 65.77% | 128.6% | 103.8% | 0 | -11.53% | 449545 | 295665.27 | 153879.73 | 0 | 295665.27 | 451827.33 | 0 | 0 | 380234.75 | 120831.02 | 27430.52 | 0% | NO | 183592.58 | 87914 | 306973.0833 | 0 | 87914.4 | 0 | 0 | 0 | 39% | 27.47% | 0% | -39% |  | 0 | [5 empty] | 112000
1734 | 2024-04-17 23:33 | P23023 | Spirit Shorts R Foster/M Gourley | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 12.0583 | 85.3% | 102.6% | 89.3% | 0 | -19.11% | 480221.04 | 409648.86 | 70572.18 | 5852.58 | 237621.5 | 267726 | 0 | 0 | 420217.26 | 87.32 | 11797.6 | 201.6% | YES | 41902.1 | 65296 | 365803.9267 | 24971.11 | 19120.72 | 21204.59 | 0 | 0 | 27% | 7.89% | 11.73% | -15.27% |  | 29.63 | [5 empty] | 22366
1734 | 2024-04-17 23:33 | P23372 | BAE Carbon Tooling Off-load | Gary Kempster | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  |  | 100.5% | 95.27% | 56.3% | 0 | -1.13% | 454982.37 | 457433.31 | -2450.94 | 0 | 0 | 0 | 19196.43 | 2450.94 | 435785.94 | 239894.09 | 21647.37 | 0% | NO | 21647.37 | 213917 | 257521.7733 | 0 | 213917.24 | 0 | 0 | 0 | 24% | 22.87% | 20.74% | -3.26% |  | 53.57 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P22906 | Spirit Shorts - MRB JD Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 9.0803 | 94.47% | 84.97% | 66.76% | 99451.32 | -7.84% | 481714 | 455065.68 | 26648.32 | 2934.75 | 0 | 0 | 0 | 0 | 386687.62 | 310.79 | 76378.06 | 2603% | YES | 76378.06 | 99451 | 303811.7867 | 0 | 0 | 0 | 99451.32 | 99451.32 | 13% | 5.16% | 2.51% | -10.49% |  | 36.92 | [5 empty] | 8000
1734 | 2024-04-17 23:33 | P23554 | Dornier Seawings 328 2023 H2 Support | Steven Lawton | 0 | DAX | EXPLEO GERMANY GMBH (EC) | MPE | Level 2 | REIM |  |  |  | 12.6184 | 92.36% | 91.18% | 82.39% | 49567.88 | 6.18% | 508481.81 | 469654.99 | 38826.82 | 3076.99 | 4046.44 | 4046.44 | 0 | 0 | 428252.8 | 78.03 | 41402.19 | 1346% | YES | 41402.19 | 49568 | 386946.1333 | 27612.8 | 21955.08 | 0 | 0 | 49567.88 | 21% | 27.18% | 23.83% | 2.83% |  | 66.33 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23531 | BAe Systems F35 MRB Support | Richard Brook | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | -50.5599 |  | 94.39% | 90.87% | 0 | 3.22% | 0 | 476545.22 | -476545.22 | 9425.36 | 287.44 | 287.44 | 0 | 476545.22 | 449807.52 | 26.87 | 26737.7 | 283.7% | YES | 26737.7 | 20130 | 433032.52 | 20129.74 | 0 | 0 | 0 | 0 | 25% | 28.22% | 31.54% | 6.54% |  | 59.88 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23685 | DAC LUC Support and Recompliance | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 48.1574 | 19.72% | 167.5% | 0% | 301712.4 | 4.52% | 2180000 | 429953.34 | 1750046.66 | 36340.13 | 0 | 0 | 0 | 0 | 720000 | 109.76 | -241282.66 | -664% | NO | -241282.66 | 864000 | 0 | 0 | 274286.4 | 288001.2 | 301712.4 | 301712.4 | 30% | 34.52% | 34.52% | 4.52% |  | 58.67 | [5 empty] | 48764
1734 | 2024-04-17 23:33 | P23520 | FCAS AP Portfolio Systems | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 26.7059 | 61.56% | 93.27% | 82.88% | 0 | -6.81% | 810821 | 499149.3 | 311671.7 | 11670.5 | 423 | 423 | 0 | 0 | 465538.44 | 47.64 | 29327.86 | 251.3% | YES | 29327.86 | 62232 | 413678.44 | 0 | 62232.16 | 0 | 0 | 0 | 22% | 15.19% | 15.84% | -6.16% |  | 80.72 | [5 empty] | -4283
1734 | 2024-04-17 23:33 | P23140 | Spirit Shorts A220 MLG Stress Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  | 30.4037 | 74.03% | 78.77% | 70.21% | 0 | -12.75% | 636032.4 | 470823.69 | 165208.71 | 5433.84 | 20870.3 | 87811.88 | 0 | 0 | 370857.4 | 225.73 | 124966.29 | 2300% | YES | 191907.87 | 48343 | 330571.5667 | 0 | 48343.2 | 0 | 0 | 0 | 25% | 12.25% | -13.91% | -38.91% |  | 45.99 | [5 empty] | 25000
1734 | 2024-04-17 23:33 | P22652 | L3 - Saftey Engineering | Sean Simmons | 0 | LHW | L3HARRIS MAPPS LIMITED | EES | Level NC | FIX |  |  |  |  | 95.63% | 86.69% | 86.69% | 0 | 5.66% | 523390 | 500497.5 | 22892.5 | 0 | 0 | 0 | 0 | 0 | 433882.5 | 79938 | 66615 | 0% | NO | 66615 | 0 | 433882.5 | 0 | 0 | 0 | 0 | 0 | 21% | 26.66% | 25.88% | 4.88% |  | 83.05 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23281 | Systems Portfolio | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM | 2024-02-28 | 0 |  |  | 44.43% | 97.31% | 97.31% | 0 | -17.25% | 1177697.24 | 523236.96 | 654460.28 | 0 | 2133.28 | 2133.28 | 0 | 0 | 509179.87 | 15792.1 | 13160.09 | 0% | NO | 13160.09 | 0 | 509179.87 | 0 | 0 | 0 | 0 | 0 | 25% | 7.75% | 100% | 75% |  | 70.48 | [5 empty] | -897
1734 | 2024-04-17 23:33 | P23694 | Systems Portfolio EXP-011a | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 5.1659 | 81.61% | 80.76% | 70.46% | -12096 | 2.19% | 648492.8 | 529205.78 | 119287.02 | 23091.38 | 444.4 | 444.4 | 0 | 0 | 427384.31 | 48.57 | 101821.47 | 441% | YES | 101821.47 | 65431 | 372858.4767 | 77526.61 | 0 | -12096 | 0 | -12096 | 21% | 23.19% | 19.94% | -1.06% |  | 88.96 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23001 | Spirit Shorts A220 Design | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -28.5149 | 115.9% | 74.2% | 68.19% | 0 | -4.35% | 463100 | 536936.4 | -73836.4 | 2589.4 | 0 | 0 | 65953.2 | 73836.4 | 398429.7 | 380.12 | 138506.7 | 5349% | YES | 138506.7 | 38738 | 366148.0333 | 9501.6 | 29236.68 | 0 | 0 | 0 | 25% | 20.65% | 11.6% | -13.4% |  | 43.58 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23473 | Tempest Vertical Tail | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 14.873 | 74.78% | 102.5% | 81.64% | 0 | -4.03% | 723866.48 | 541306.76 | 182559.72 | 12274.55 | 100175 | 112425 | 12000 | 0 | 554989.62 | 65.12 | -8682.86 | -70.74% | NO | 3567.14 | 135686 | 441917.9533 | 74168.03 | 61517.7 | 0 | 0 | 0 | 26% | 21.97% | 25.14% | -0.86% |  | 62.42 | [5 empty] | 5000
1734 | 2024-04-17 23:33 | P23366 | Business Analyst Support | Peter Williams | 0 | BDZ | MBDA UK LIMITED | DET | Level 3 | REIM |  |  |  | 62.5603 | 21.23% | 204.1% | 179.4% | 0 | 7.43% | 1302200 | 276439.23 | 1025760.77 | 16396.35 | 247149.55 | 416921.86 | 0 | 0 | 564160 | 48.19 | 5414.23 | 33.02% | NO | 175186.54 | 81792 | 496000 | 0 | 81792 | 0 | 0 | 0 | 43% | 50.43% | 29.63% | -13.37% |  | 38.27 | [5 empty] | 293135
1734 | 2024-04-17 23:33 | P23323 | CNC-CMM Programming Support | Stephen Young | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | 3.3401 | 95.26% | 92.78% | 72.59% | 0 | -2.56% | 617809.74 | 588535.55 | 29274.19 | 8764.37 | 15941.56 | 15941.56 | 0 | 0 | 546032.59 | 118.04 | 42502.96 | 485% | YES | 42502.96 | 142591 | 427206.7567 | 40305.01 | 102286.46 | 0 | 0 | 0 | 32% | 29.44% | 36.94% | 4.94% |  | 57.31 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23219 | Tornado Air 800 Engineering Support | Richard Brook | 0 | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 3 | REIM |  |  |  | -3.0414 | 103.3% | 91.05% | 91.05% | 0 | -2.57% | 615046 | 635207.71 | -20161.71 | 6629.01 | 459.21 | 459.21 | 0 | 20161.71 | 578373.17 | 60.39 | 31927.54 | 481.6% | YES | 31927.54 | 0 | 578373.17 | 0 | 0 | 0 | 0 | 0 | 31% | 28.43% | -73.36% | -104.4% |  | 82.41 | [5 empty] | -24907
1734 | 2024-04-17 23:33 | P22790 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | REIM | 2024-03-18 | 0 |  |  | 194.5% | 90.44% | 90.44% | 0 | 1.37% | 352240 | 685262.25 | -333022.25 | 0 | 1611.52 | 1611.52 | 515246 | 333022.25 | 619743.88 | 41098.04 | 34248.37 | 0% | NO | 34248.37 | 0 | 619743.88 | 0 | 0 | 0 | 0 | 0 | 13% | 14.37% | 0% | -13% |  | 45.06 | [5 empty] | -31270
1734 | 2024-04-17 23:33 | P23605 | Typhoon Work Package 2 Continuation | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM |  |  |  | -508.4117 | 119.9% | 83.29% | 4.174% | 70906.73 | 5.12% | 545536.01 | 654331.04 | -108795.03 | 213.99 | 5554 | 5554 | 81999.09 | 108795.03 | 544986.65 | 513.34 | 109344.39 | 51098% | YES | 109344.39 | 621210 | 27311.65 | 18432.36 | 602777.85 | 0 | 0 | 70906.73 | 23% | 28.12% | 28.66% | 5.66% |  | 55.82 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23426 | BAE Tempest WP 3 Harness Maturation | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 9.4213 | 81.39% | 94.73% | 72.7% | 0 | -6.18% | 884012.04 | 719522.48 | 164489.56 | 17459.34 | 213.34 | 213.34 | 0 | 0 | 681568.4 | 80.02 | 37954.08 | 217.4% | YES | 37954.08 | 190206 | 523063.4 | 107757.52 | 82448.95 | 0 | 0 | 0 | 33% | 26.82% | 27.18% | -5.82% |  | 51.6 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23602 | EXP-025 Portfolio Software Engineering Support | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 19.4211 | 58.94% | 88.84% | 73.6% | 0 | -0.92% | 1327080 | 782165.73 | 544914.27 | 28057.88 | 2542.8 | 3251.04 | 0 | 0 | 694893.55 | 49.51 | 87272.18 | 311% | YES | 87980.42 | 143049 | 575686.05 | 0 | 143049.25 | 0 | 0 | 0 | 24% | 23.08% | 22.81% | -1.19% |  | 83.31 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23451 | BAE Tempest - DFM-ASO Planning | Stephen Young | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | 5.6287 | 89.17% | 73.51% | 33.09% | 27224.9 | -3.23% | 953905.42 | 850566.34 | 103339.08 | 18359.44 | 0 | 0 | 0 | 0 | 625210.17 | 190.15 | 224273.17 | 1222% | YES | 224273.17 | 412472 | 281483.5033 | 57003.88 | 328243.6 | 0 | 27224.9 | 27224.9 | 28% | 24.77% | 26.38% | -1.62% |  | 53.69 | [5 empty] | -1083
1734 | 2024-04-17 23:33 | P23105 | Raytheon Supply Engineering Support | Natalie Sinclair | 0 | RAY | RAYTHEON UNITED KINGDOM LIMITED | MPE | Level 3A | REIM | 2023-07-13 | 2 |  |  | 76.96% | 94.49% | 90.07% | 49156.8 | -2.02% | 1205008 | 927395.25 | 277612.75 | 0 | 0 | 0 | 0 | 0 | 876291.5 | 107644.5 | 48739.75 | 0% | NO | 48739.75 | 49157 | 835327.3333 | 0 | 0 | 49156.8 | 0 | 49156.8 | 26% | 23.98% | 100% | 74% |  | 48.97 | [5 empty] | -2364
1734 | 2024-04-17 23:33 | P22350 | EMP 2020-2021 | Natalie Sinclair | 0 | ARY | GUIDANT GLOBAL UK LIMITED | PCPR | Level NC | REIM |  |  |  | 4.303 | 97.67% | 98.58% | 94% | 0 | -2.18% | 1017579.76 | 993826.69 | 23753.07 | 5520.16 | 400 | 400 | 0 | 0 | 979705.34 | 66.27 | 14121.35 | 255.8% | YES | 14121.35 | 54587 | 934216.1733 | 22845.77 | 21769.52 | 9972.02 | 0 | 0 | 32% | 29.82% | 26.62% | -5.38% |  | 44.12 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23117 | BAE Typhoon Eng Support | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | 2024-03-12 | 11 |  |  | 107.6% | 92.94% | 88.52% | 0 | -1.44% | 950771.99 | 1022826.17 | -72054.18 | 0 | 19090.01 | 21165.02 | 69773.84 | 72054.18 | 950609.41 | 108434.62 | 45120.76 | 0% | NO | 47195.77 | 54290 | 905367.7433 | 0 | 54289.71 | 0 | 0 | 0 | 30% | 28.56% | 0% | -30% |  | 52.3 | [5 empty] | -27096
1734 | 2024-04-17 23:33 | P22671 | Spirit Shorts Pylon and Fairing Package | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX | 2023-05-03 | 0 |  |  | 105% | 95.26% | 95.26% | 0 | -7.21% | 1198494.77 | 1258071.09 | -59576.32 | 0 | 106494.89 | 106494.89 | 0 | 59576.32 | 1198494.77 | 2544.39 | 2120.32 | 0% | NO | 2120.32 | 0 | 1198494.77 | 0 | 0 | 0 | 0 | 0 | 20% | 12.79% | 0% | -20% |  | 45.4 | [5 empty] | -57456
1734 | 2024-04-17 23:33 | P23292 | BAE Tempest WP 4 AV Trays | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 9.7954 | 85.57% | 104% | 80.39% | 0 | 1.67% | 1498284.22 | 1282126.88 | 216157.34 | 22067.19 | 0 | 0 | 0 | 0 | 1332801.4 | 77.81 | -50674.52 | -229.6% | NO | -50674.52 | 362500 | 1030718.0667 | 245826.2 | 116674.18 | 0 | 0 | 0 | 32% | 33.67% | 32.32% | 0.32% |  | 53.53 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23152 | Project Aragon - Design and Stress Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 3.5964 | 97.36% | 78.4% | 56.18% | 0 | -9.55% | 1333452.21 | 1298247.99 | 35204.22 | 9788.74 | 0 | 0 | 0 | 0 | 1017835.58 | 331.22 | 280412.41 | 2865% | YES | 280412.41 | 346248 | 729295.58 | 346247.55 | 0 | 0 | 0 | 0 | 39% | 29.45% | 29.16% | -9.84% |  | 51.95 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23519 | Mechanical and Electrical Design Eng Support | Dushan Fernando | 0 | BAX | SAFRAN SEATS GB LIMITED | MPE | Level 2 | REIM |  |  |  | 15.837 | 74.82% | 94.33% | 82.33% | 0 | -1.59% | 1807261.3 | 1352253.4 | 455007.9 | 28730.71 | 1004.45 | 1504.45 | 0 | 0 | 1275630.3 | 51.2 | 76623.1 | 266.7% | YES | 77123.1 | 194809 | 1113289.4667 | 194808.9 | 0 | 0 | 0 | 0 | 33% | 31.41% | 31.4% | -1.6% |  | 56.64 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23411 | Agile & Scrum Delivery Service | Peter Williams | 0 | BDZ | MBDA UK LIMITED | DET | Level 2 | REIM | 2023-08-14 | 0 |  |  | 36.3% | 170.5% | 170.5% | 0 | 13.08% | 2487000 | 902903.79 | 1584096.21 | 0 | 894178.59 | 894178.59 | 0 | 0 | 1539600 | 19368.95 | 16140.79 | 0% | NO | 16140.79 | 0 | 1539600 | 0 | 0 | 0 | 0 | 0 | 29% | 42.08% | 0% | -29% |  | 74.57 | [5 empty] | 652837
1734 | 2024-04-17 23:33 | P23315 | DAC LUC BAU and Service Workbench | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX | 2024-02-16 | 0 |  |  | 85.17% | 117.4% | 117.4% | 0 | 3.84% | 1573630 | 1340192.3 | 233437.7 | 0 | 180.3 | 180.3 | 0 | 0 | 1573630 | 0 | 0.3 | 0% | NO | 0.3 | 0 | 1573630 | 0 | 0 | 0 | 0 | 0 | 28% | 31.84% | 47.26% | 19.26% |  | 52.35 | [5 empty] | 233438
1734 | 2024-04-17 23:33 | P22278 | TAI Supply Engineers to Ankara | Natalie Sinclair | 0 | TAI | TUSAS-TURK HAVACILIK VE UZAY | MPE | Level 3A | REIM |  |  |  | 822.5482 | 19.56% | 463.9% | 463.9% | 0 | -15.61% | 2105282 | 411860.91 | 1693421.09 | 2058.75 | 49400.29 | 49400.29 | 0 | 0 | 1910696.33 | 82.27 | 11564.58 | 561.7% | YES | 11564.58 | 0 | 1910696.33 | 0 | 0 | 0 | 0 | 0 | 95% | 79.39% | 72.38% | -22.62% |  | 34.18 | [5 empty] | 1510400
1734 | 2024-04-17 23:33 | P23435 | Andy Baker Portfolio | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 46.6161 | 50.1% | 94.02% | 67.58% | 0 | -7.16% | 4023207.4 | 2015473.39 | 2007734.01 | 43069.54 | 2352.57 | 2352.57 | 0 | 0 | 1894945.09 | 93.87 | 120528.3 | 279.8% | YES | 120528.3 | 639550 | 1361986.7567 | 0 | 489604.46 | 149945.57 | 0 | 0 | 25% | 17.84% | 20.03% | -4.97% |  | 80.54 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23006 | Spirit Shorts A350 Freighter Toulouse | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -15.8015 | 157.1% | 104.2% | 75.89% | 0 | 23.27% | 1035745.92 | 1627382.16 | -591636.24 | 37441.72 | 1086670.26 | 2010741.94 | 0 | 591636.24 | 1695787.93 | 370.23 | 342868.23 | 915.7% | YES | 1266939.91 | 552824 | 1235101.2633 | 140525.66 | 412298.62 | 0 | 0 | 0 | 5% | 28.27% | 55.36% | 50.36% |  | 48.07 | [5 empty] | 411274
1734 | 2024-04-17 23:33 | P23175 | BAe Aero Typhoon Package 2 | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM | 2024-03-12 | 2 |  |  | 103.8% | 96.32% | 96.32% | 0 | -1.63% | 1984265.09 | 2060011.83 | -75746.74 | 0 | 57677.87 | 86030.82 | 15444.64 | 75746.74 | 1984257.03 | 84731.75 | 70609.8 | 0% | NO | 98962.75 | 0 | 1984257.03 | 0 | 0 | 0 | 0 | 0 | 29% | 27.37% | 0% | -29% |  | 51.76 | [5 empty] | -5145
1734 | 2024-04-17 23:33 | P19020 | Spirit Concessions - 2018 | Carl Warren | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2024-01-23 | 3 |  |  | 90.82% | 111.8% | 107% | 99792.83 | 2.09% | 1914846.83 | 1739018.14 | 175828.69 | 0 | 44317.61 | 44317.61 | 15178.88 | 0 | 1944710.76 | 22762.03 | 196987.38 | 0% | NO | 196987.38 | 99793 | 1861549.9267 | 0 | 0 | 0 | 99792.83 | 99792.83 | 25% | 27.09% | 9.32% | -15.68% |  | 40.87 | [5 empty] | 402680
1734 | 2024-04-17 23:33 | P23257 | BAE Tempest WP 5 Centre Fuselage | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | -3.4239 | 102.6% | 96.29% | 92.04% | 0 | -5.76% | 2106860.71 | 2161711.44 | -54850.73 | 16019.9 | 78100 | 78100 | 158540.8 | 54850.73 | 2081529.48 | 66.87 | 80181.96 | 500.5% | YES | 80181.96 | 110362 | 1989561.1467 | 0 | 110362.14 | 0 | 0 | 0 | 33% | 27.24% | 28% | -5% |  | 61.05 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23207 | A350 Approvers - Design and Stress Support | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  | 3.6564 | 92.77% | 97.14% | 63.86% | 0 | -5.08% | 2728308 | 2530972.91 | 197335.09 | 53970.21 | 34897.19 | 35711.33 | 0 | 0 | 2458482.23 | 110.13 | 72490.68 | 134.3% | YES | 73304.82 | 1010694 | 1616237.23 | 342017.26 | 253420.79 | 415256 | 0 | 0 | 23% | 17.92% | 17.06% | -5.94% |  | 54.58 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P23179 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX |  |  |  | -295.7202 | 127.3% | 94.88% | 82.14% | 0 | -9.33% | 1996985.84 | 2542500.98 | -545515.14 | 1844.7 | 156991.12 | 248243.92 | 100000 | 545515.14 | 2412235.69 | 684 | 130265.29 | 7062% | YES | 221518.09 | 388547 | 2088446.5233 | 0 | 248280.21 | 140266.99 | 0 | 0 | 22% | 12.67% | 16.7% | -5.3% |  | 44.4 | [5 empty] | 0
1734 | 2024-04-17 23:33 | P19731 | Hapri HPC Rear Bearing Housing PDR & CDR | Steven Lawton | 0 | ATC | AECC Hunan Aviation Powerplant | MPE | Level 1 | FIX |  |  |  | -1.5536 | 100.1% | 99.9% | 87.41% | 447000 | -15.41% | 2980000 | 2982971.27 | -2971.27 | 1912.53 | 366232.13 | 500332.13 | 0 | 2971.27 | 2980000 | 828.92 | -222028.73 | -11609% | NO | -87928.73 | 447000 | 2607500 | 0 | 0 | 0 | 447000 | 447000 | 38% | 22.59% | 13.64% | -24.36% |  | 64.85 | [5 empty] | -225000
1734 | 2024-04-17 23:33 | P23487 | Tornado Air 800 Engineering Support | Richard Brook | 0 | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 2 | FIX |  |  |  | 2.7443 | 95.31% | 85.49% | 74.07% | 38732.48 | -2.46% | 3210579.12 | 3059928.35 | 150650.77 | 54895.31 | 0 | 0 | 0 | 0 | 2616021.67 | 97.66 | 470906.68 | 857.8% | YES | 470906.68 | 419489 | 2266447.5033 | 0 | 380756.59 | 8658.1 | 30074.38 | 38732.48 | 39% | 36.54% | 40.09% | 1.09% |  | 78.71 | [5 empty] | 27000
Extend Table

## AP4-3
WIP No | Date Created | Project ID | Project Description | Project Manager | Agency (1=yes, 0=no) | Department Id | Client | CBU | Complexity | Type | Stop Booking Hrs | Closing Project: Action(s) to close | RAG | Approx. PO Burndown (weeks) | Turnover vs Contract Value | Invoice To Date vs Turnover | Cash in vs Turnover | Open Amount Overdue | Actual PM% to Baseline PM% delta | Contract Value | Total Project Turnover | Contract Value - Total Turnover | Run Rate (based on total turnover) | Total BOI Spend to Date | Total Committed PO (supplier/best shore) | Current AA in PT3 | Exposure (turnover - contract value) | Invoiced To Date | DSO | Unbilled (WIP) | WIP / Run rate | WIP / Run rate >1.3 | WIP + Remaining Committed PO for BOI | Total Open Amount | Cash in (Invoiced - (Open amount -VAT)) | Debt <=30 Days | Debt 31 - 60 Days | Debt 61 - 90 Days | Debt >= 90 Days | Open Amount Overdue2 | Baseline Project Margin | Project To Date (PTD) PM | Year to Date (YTD) PM | YTD Delta Actual PM% to BPM% | Forecast PM at Completion (Manual input from PTT) | Average Sale Rate | CSat score for last quarter (Manual input from PTT) | Comments and Actions | Judged income adjustment at completion | Profit to take now | Provision required now | Fully Traded | Last Months Comments and Actions
1735 | 2024-04-24 23:37 | P23637 | MBSE Proposal | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 | 0 | 0 | 0 | 49980 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23552 | FCAS AP Product Technology Development | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -25% | 597871 | 0 | 597871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0% | -25% |  | 0 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23543 | EXP-024 FCAS AP Transformation & Change Enablers | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -26% | 385921 | 0 | 385921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26% | 0% | 0% | -26% |  | 0 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23711 | DO NOT USE - RAISED IN ERROR | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23585 | Systems Design - Missile Systems, Meteor,Brimstone | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 | 0 | 0 | 0 | 49500 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23717 | GKN Ted Tomblin 2024 | Matthew Tweed | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 10047 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23869 | EXP-037 Land Ceptor Development Hardware Test Def | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -26% | 162694 | 0 | 162694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26% | 0% | 0% | -26% |  | 0 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23730 | FLE Project | Carl Warren | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -18.03% | 0 | 1120 | -1120 | 0 | 0 | 0 | 24000 | 1120 | 0 | 104 | 1120 | 0% | NO | 1120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | -18.03% | -18.03% | -18.03% |  | 35 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23463 | A220 Wing MaMo Design Checking | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-03-07 | 0 |  |  |  | 0% | 0% | 0 | 7.85% | 0 | 1628 | -1628 | 0 | 0 | 0 | 15000 | 1628 | 0 | 1953.6 | 1628 | 0% | NO | 1628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | 10.85% | 0% | -3% |  | 44 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23843 | EXP-035 FT15 Exemplar information set | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 293.8307 | 1.343% | 0% | 0% | 0 | -13.58% | 175985.16 | 2363.56 | 173621.6 | 590.89 | 0 | 0 | 0 | 0 | 0 | 35 | 2363.56 | 400% | YES | 2363.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 6.42% | 6.42% | -13.58% |  | 63.88 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P21028 | Rebate Collection (BACC) | David Catchpole | 0 | TOO | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | [5 empty] | 0% | 0% | 0 | 0% | 0 | 2680 | -2680 | 0 | 2680 | 2680 | 0 | 2680 | 0 | 3216 | 2680 | 0% | NO | 2680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23873 | FCAS Systems Engineering Support | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | -1 |  | 0% | 0% | 0 | 8.28% | 0 | 2904.5 | -2904.5 | 2904.5 | 0 | 0 | 26604 | 2904.5 | 0 | 7 | 2904.5 | 100% | NO | 2904.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 8.28% | 8.28% | 8.28% |  | 78.5 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23578 | ESN Work Package | Hannah Mead | 0 | COZ | CHELTON LIMITED | DET | Level 3 | FIX | 2024-01-01 | 0 |  |  | 86.17% | 116.1% | 116.1% | 0 | 35.86% | 4410 | 3800 | 610 | 0 | 0 | 0 | 0 | 0 | 4410 | 0 | -610 | 0% | NO | -610 | 0 | 4410 | 0 | 0 | 0 | 0 | 0 | 24% | 59.86% | 0% | -24% |  | 95 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23864 | REACH Coordinator | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 25.7795 | 7.2% | 0% | 0% | 0 | -10.24% | 52920 | 3810 | 49110 | 1905 | 0 | 0 | 0 | 0 | 0 | 35 | 3810 | 200% | YES | 3810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27% | 16.76% | 16.76% | -10.24% |  | 30 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23628 | Design Assurance | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -6.67% | 0 | 3909.24 | -3909.24 | 0 | 0 | 0 | 4454.8 | 3909.24 | 0 | 4691.09 | 3909.24 | 0% | NO | 3909.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 0.33% | 0% | -7% |  | 15.05 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23002 | WoT MAJ Transit Flag Stress | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2024-04-03 | 1 |  | 4.7688 | 62.41% | 160.2% | 160.2% | 0 | 38.54% | 4735 | 2955.29 | 1779.71 | 373.2 | 1492.79 | 2242.5 | 0 | 0 | 4735 | 91.03 | 1493.29 | 400.1% | YES | 2243 | 0 | 4735 | 0 | 0 | 0 | 0 | 0 | 10% | 48.54% | 0% | -10% |  | 45 | [5 empty] | 3273
1735 | 2024-04-24 23:37 | P23607 | SAFRAN - A330neo Turnover Frame | Gary Kempster | 0 | TOO | SAFRAN SEATS GB LIMITED | MPE | Level 3 | FIX |  |  |  | 37695 | 95.69% | 104.5% | 104.5% | 0 | -19.52% | 8736 | 8359.05 | 376.95 | 0.01 | 0 | 0 | 0 | 0 | 8736 | 0.06 | 0.05 | 500% | YES | 0.05 | 0 | 8736 | 0 | 0 | 0 | 0 | 0 | 23% | 3.48% | 8.5% | -14.5% |  | 50.46 | [5 empty] | 377
1735 | 2024-04-24 23:37 | P23874 | Environmental Engineering (Sea Venom/ANL) | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | -1 |  | 0% | 0% | 0 | 18.31% | 0 | 8949 | -8949 | 8949 | 0 | 0 | 27140.5 | 8949 | 0 | 14 | 8949 | 100% | NO | 8949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 18.31% | 18.31% | 18.31% |  | 78.5 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23274 | ME Support (Aim Altitude - Cambridge) | Trevor Knox | 0 | AVI | AVIC CABIN SYSTEMS (UK) LIMITED | ME | Level 3 | FIX | 2023-08-18 | 0 |  |  | 51.88% | 56.3% | 56.3% | 0 | -0.17% | 17280 | 8964 | 8316 | 0 | 0 | 0 | 0 | 0 | 5046.3 | 4701.24 | 3917.7 | 0% | NO | 3917.7 | 0 | 5046.3 | 0 | 0 | 0 | 0 | 0 | 21% | 20.83% | 0% | -21% |  | 48 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23283 | Spirit Tooling Audit | Charidimos Valadakis | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-05-03 | 0 |  |  | 97.22% | 48.57% | 48.57% | 0 | -7.99% | 9910.08 | 9634.8 | 275.28 | 0 | 0 | 0 | 0 | 0 | 4679.76 | 5946.05 | 4955.04 | 0% | NO | 4955.04 | 0 | 4679.76 | 0 | 0 | 0 | 0 | 0 | 7% | -0.99% | 0% | -7% |  | 34.41 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23127 | Loft Hall Design Support | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-04-19 | 0 |  |  | 101% | 99.06% | 99.06% | 0 | -9.55% | 9680 | 9772 | -92 | 0 | 0 | 0 | 0 | 92 | 9680 | 110.4 | 92 | 0% | NO | 92 | 0 | 9680 | 0 | 0 | 0 | 0 | 0 | 41% | 31.45% | 0% | -41% |  | 44 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23630 | 2Excel CFD Analysis Support | Dushan Fernando | 0 | BAX | STIRLING DYNAMICS LTD | MPE | Level NC | FIX |  |  |  |  | 61.2% | 100% | 100% | 0 | -1.87% | 16195.49 | 9911.34 | 6284.15 | 0 | 0 | 0 | 0 | 0 | 9911.63 | 0 | -0.29 | 0% | NO | -0.29 | 0 | 9911.63 | 0 | 0 | 0 | 0 | 0 | 26% | 24.13% | 0% | -26% |  | 64.78 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23842 | Tranche 1 Evolution Package Step 2 | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -4 |  | 0% | 0% | 0 | -15.35% | 0 | 9927.77 | -9927.77 | 2481.94 | 1000 | 1000 | 67488.9 | 9927.77 | 0 | 35 | 9927.77 | 400% | YES | 9927.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31% | 15.65% | 15.65% | -15.35% |  | 54.97 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23718 | Requalification of EJ200 GSS ESS EHM SW module | Vijayakumara Nanjundappa | 0 | ARZ | MTU AERO ENGINES AG | DET | Level 3 | FIX |  |  |  | 74.5925 | 11.85% | 205.5% | 205.5% | 0 | 12.18% | 74463 | 8821.57 | 65641.43 | 880 | 991.93 | 991.93 | 0 | 0 | 18125 | 0 | -7303.43 | -829.9% | NO | -7303.43 | 0 | 18125 | 0 | 0 | 0 | 0 | 0 | 28% | 40.18% | 40.18% | 12.18% |  | 80 | [5 empty] | 2000
1735 | 2024-04-24 23:37 | P23313 | Laser Trim Fixtures | Gary Kempster | 0 | TOO | ALKEN ENGINEERING LIMITED | MPE | Level 3 | FIX | 2023-11-20 | 0 |  |  | 89.87% | 111.3% | 111.3% | 0 | 0.53% | 13770 | 12375 | 1395 | 0 | 0 | 0 | 0 | 0 | 13770 | 0 | -1395 | 0% | NO | -1395 | 0 | 13770 | 0 | 0 | 0 | 0 | 0 | 17% | 17.53% | 0% | -17% |  | 45 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P22761 | Red Bull Chassis Spit | Trevor Knox | 0 | TOO | MANUFAX ENGINEERING LTD | MPE | Level 3 | FIX | 2022-11-15 | 0 |  |  | 72.18% | 96.98% | 96.98% | 0 | 7.92% | 12961.2 | 9355.5 | 3605.7 | 0 | 0 | 0 | 0 | 0 | 9072.84 | 4666.39 | 3888.66 | 0% | NO | 3888.66 | 0 | 9072.84 | 0 | 0 | 0 | 0 | 0 | 23% | 30.92% | 0% | -23% |  | 42.19 | [5 empty] | 3606
1735 | 2024-04-24 23:37 | P23350 | Spirit 2023 - Stress Approve Man Serv (DH) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 14.15% | 72.64% | 72.64% | 0 | -0.29% | 97920 | 13860 | 84060 | 0 | 0 | 0 | 0 | 0 | 10068 | 4550.4 | 3792 | 0% | NO | 3792 | 0 | 10068 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23344 | Spirit A320 Spoilers Support 2023 | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 38.75% | 100% | 100% | 0 | 5.82% | 35786.4 | 13867.23 | 21919.17 | 0 | 0 | 0 | 0 | 0 | 13867.23 | 0 | 0 | 0% | NO | 0 | 0 | 13867.23 | 0 | 0 | 0 | 0 | 0 | 7% | 12.82% | 0% | -7% |  | 34.41 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23337 | Spirit 2023 - Steve Grimley | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 25.28% | 100% | 100% | 0 | 0.01% | 56812.9 | 14362.47 | 42450.43 | 0 | 0 | 0 | 0 | 0 | 14362.47 | 0 | 0 | 0% | NO | 0 | 0 | 14362.47 | 0 | 0 | 0 | 0 | 0 | 7% | 7.01% | 0% | -7% |  | 30.11 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23597 | MRB Onsite support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-02-16 | 1 |  |  |  | 0% | 0% | 0 | -10.04% | 0 | 15100.57 | -15100.57 | 0 | 9448.07 | 17381.62 | 24200 | 15100.57 | 0 | 110.07 | 15100.57 | 0% | NO | 23034.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 7.96% | 8.95% | -9.05% |  | 42.5 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23635 | Engineering Services: FAI Support | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 49.9% | 68.33% | 0.001436% | 0 | -3.4% | 37230 | 18576 | 18654 | 0 | 0 | 0 | 0 | 0 | 12693.6 | 496.36 | 5882.4 | 0% | NO | 5882.4 | 15232 | 0.26667 | 0 | 15232.32 | 0 | 0 | 0 | 8% | 4.6% | 5.04% | -2.96% |  | 38.7 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23343 | Spirit 2023 - John Agnew | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-08-09 | 0 |  |  | 28.56% | 86.27% | 86.27% | 0 | -0.02% | 65120.37 | 18600.89 | 46519.48 | 0 | 0 | 0 | 0 | 0 | 16047.15 | 3064.49 | 2553.74 | 0% | NO | 2553.74 | 0 | 16047.15 | 0 | 0 | 0 | 0 | 0 | 7% | 6.98% | 0% | -7% |  | 34.51 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23839 | Stirling Dynamics - ST002-GFEM | Matthew Dodd | 0 | BAX | STIRLING DYNAMICS LTD | MPE | Level NC | FIX |  |  |  | -18.6564 |  | 0% | 0% | 0 | -4.97% | 0 | 19132.33 | -19132.33 | 1025.51 | 0 | 0 | 19985.76 | 19132.33 | 0 | 91 | 19132.33 | 1866% | YES | 19132.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 2.03% | 2.03% | -4.97% |  | 43.63 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23663 | Spirit Tooling Verification and Inspection | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 0.25 | 98.96% | 33.68% | 0.0002719% | 0 | -7.42% | 19820.16 | 19613.7 | 206.46 | 825.84 | 0 | 0 | 7392 | 0 | 6606.72 | 167.86 | 13006.98 | 1575% | YES | 13006.98 | 7928 | 0.053333 | 0 | 7928.06 | 0 | 0 | 0 | 12% | 4.58% | 4.82% | -7.18% |  | 34.41 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23355 | Spirit Tooling Support 2023 | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-23 | 0 |  |  | 22.93% | 89.02% | 89.02% | 0 | -0.82% | 91800 | 21053.34 | 70746.66 | 0 | 0 | 0 | 0 | 0 | 18742.5 | 2773.01 | 2310.84 | 0% | NO | 2310.84 | 0 | 18742.5 | 0 | 0 | 0 | 0 | 0 | 20% | 19.18% | 0% | -20% |  | 44.46 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23742 | Cyber Security Support | Hannah Mead | 0 | COZ | CHELTON LIMITED | DET | Level 3 | FIX |  |  |  | 3.9333 | 78.55% | 0% | 0% | 0 | -0.96% | 27500 | 21600 | 5900 | 1500 | 0 | 0 | 0 | 0 | 0 | 100.8 | 21600 | 1440% | YES | 21600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32% | 31.04% | 31.04% | -0.96% |  | 100 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23351 | Spirit 2023 - Design Man Serv (KL) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 26.47% | 93.15% | 93.15% | 0 | 0.09% | 93840 | 24840 | 69000 | 0 | 0 | 0 | 0 | 0 | 23138 | 2042.4 | 1702 | 0% | NO | 1702 | 0 | 23138 | 0 | 0 | 0 | 0 | 0 | 26% | 26.09% | 0% | -26% |  | 46 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23356 | Spirit 2023 - Design Man Serv (AH) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX | 2023-08-09 | 1 |  |  |  | 76.66% | 0.001332% | 23018.4 | 0.48% | 0 | 25023.08 | -25023.08 | 0 | 0 | 0 | 25300 | 25023.08 | 19182 | 30027.7 | 5841.08 | 0% | NO | 5841.08 | 23018 | 0.33333 | 0 | 0 | 0 | 23018.4 | 23018.4 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P22884 | Spirit Shorts Config Eng | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 66.3% | 100.1% | 100.1% | 0 | 0.56% | 38976 | 25841.9 | 13134.1 | 0 | 0 | 0 | 0 | 0 | 25863.2 | 0 | -0.3 | 0% | NO | -0.3 | 0 | 25863.2 | 0 | 0 | 0 | 0 | 0 | 7% | 7.56% | 0% | -7% |  | 20.3 | [5 empty] | 21
1735 | 2024-04-24 23:37 | P23354 | Spirit 2023 - Design Man Serv (PC) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 27.97% | 99.36% | 99.36% | 0 | 0.48% | 93840 | 26248.98 | 67591.02 | 0 | 0 | 0 | 0 | 0 | 26082 | 200.38 | 166.98 | 0% | NO | 166.98 | 0 | 26082 | 0 | 0 | 0 | 0 | 0 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23831 | Contract DM/00113 for maintenance, repair and post | Harry James Kellett | 0 | BXW | MOD | EES | Level 2 | FIX |  |  |  | 3.9593 | 68.36% | 0% | 0% | 0 | 14.16% | 40800 | 27890.35 | 12909.65 | 3260.56 | 0 | 0 | 0 | 0 | 0 | 91 | 27890.35 | 855.4% | YES | 27890.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37% | 51.16% | 51.16% | 14.16% |  | 80.26 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23433 | Cavendish | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 3.9241 | 66.73% | 49.17% | 49.17% | 0 | -0.41% | 42240 | 28185.6 | 14054.4 | 3581.6 | 0 | 0 | 0 | 0 | 13859.2 | 91 | 14326.4 | 400% | YES | 14326.4 | 0 | 13859.2 | 0 | 0 | 0 | 0 | 0 | 7% | 6.59% | 6.51% | -0.49% |  | 46.09 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23724 | GKN S McConnell 2024 | Matthew Tweed | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  | 12.7111 | 57.1% | 81.96% | -0.0002578% | 0 | 0.75% | 49820 | 28447.25 | 21372.75 | 1681.43 | 0 | 0 | 0 | 0 | 23315.76 | 111.03 | 5131.49 | 305.2% | YES | 5131.49 | 27979 | -0.073333 | 10761.12 | 8848.03 | 8369.76 | 0 | 0 | 19% | 19.75% | 19.75% | 0.75% |  | 49.56 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P22756 | A350 FLE Design Checker | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2022-03-23 | 1 |  |  | 68.39% | 119.7% | 119.7% | 0 | 16.46% | 34898.4 | 23867.15 | 11031.25 | 0 | 23867.15 | 24342.3 | 0 | 0 | 28571.1 | 0.06 | 0.05 | 0% | NO | 475.2 | 0 | 28571.1 | 0 | 0 | 0 | 0 | 0 | 0% | 16.46% | 0% | 0% |  | 0 | [5 empty] | 4704
1735 | 2024-04-24 23:37 | P23740 | Phase 2 - EJ200 ESS EHM Platform Migration | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 3 | FIX |  |  |  | 48.8973 | 14.37% | 198.8% | 99.41% | 0 | 11.03% | 175971 | 25287.5 | 150683.5 | 3081.63 | 0 | 0 | 0 | 0 | 50278 | 16.1 | -20990.5 | -681.1% | NO | -20990.5 | 30167 | 25138.8333 | 0 | 30166.8 | 0 | 0 | 0 | 28% | 39.03% | 39.03% | 11.03% |  | 44.09 | [5 empty] | 4000
1735 | 2024-04-24 23:37 | P23811 | Spirit T300 MRB Concessions | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -10.3616 |  | 0% | 0% | 0 | -7.2% | 0 | 29675.2 | -29675.2 | 2863.95 | 0 | 0 | 34639 | 29675.2 | 0 | 70 | 29675.2 | 1036% | YES | 29675.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21% | 13.8% | 13.8% | -7.2% |  | 46.81 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23458 | Spirit Belfast Tooling Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-08-11 | 0 |  |  | 101.3% | 94.65% | 94.65% | 0 | 8.64% | 30384 | 30784.9 | -400.9 | 0 | 0 | 0 | 0 | 400.9 | 29139.1 | 1974.96 | 1645.8 | 0% | NO | 1645.8 | 0 | 29139.1 | 0 | 0 | 0 | 0 | 0 | 7% | 15.64% | 0% | -7% |  | 42.2 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23651 | PMO Spirit | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 26.5695 | 63.37% | 75.1% | -0.0005337% | 0 | -19.23% | 49284 | 31230 | 18054 | 679.5 | 0 | 0 | 0 | 0 | 23454 | 241.78 | 7776 | 1144% | YES | 7776 | 28145 | -0.16667 | 0 | 28144.8 | 0 | 0 | 0 | 43% | 23.77% | 23.15% | -19.85% |  | 36 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23821 | Supply of Safety Engineer | Dinna Elkhalifa | 0 | BXW | STIRLING DYNAMICS LTD | EES | Level NC | REIM |  |  |  | 2.9183 | 92.47% | 60.33% | -0.000371% | 22765.86 | 45.1% | 34006.44 | 31444.34 | 2562.1 | 877.94 | 0 | 0 | 0 | 0 | 18971.55 | 113.06 | 12472.79 | 1421% | YES | 12472.79 | 22766 | -0.11667 | 0 | 22765.86 | 0 | 0 | 22765.86 | 0% | 45.1% | 45.1% | 45.1% |  | 80.73 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23823 | EXP-034 Spear 3 Test Equip Requirement Authority | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 15.4868 | 37.24% | 56.47% | -0.0008969% | 0 | -0.12% | 85825 | 31961.13 | 53863.87 | 3478.06 | 1000 | 1000 | 0 | 0 | 18048.88 | 70 | 13912.25 | 400% | YES | 13912.25 | 21659 | -0.28667 | 0 | 21658.66 | 0 | 0 | 0 | 14% | 13.88% | 13.88% | -0.12% |  | 94.25 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23365 | GKN 777x Lip Skin Fixture | Steven Lawton | 0 | TOO | GKN AEROSPACE SERVICES LTD | MPE | Level 3 | FIX | 2023-10-12 | 0 |  |  | 41.91% | 113.2% | 113.2% | 0 | -9.26% | 79161.46 | 33175.67 | 45985.79 | 0 | 5109.88 | 5109.88 | 0 | 0 | 37544.22 | 0 | -4368.55 | 0% | NO | -4368.55 | 0 | 37544.22 | 0 | 0 | 0 | 0 | 0 | 22% | 12.74% | 0% | -22% |  | 56 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23338 | Spirit 2023 - Blair Hainey | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 1.3281 | 97.75% | 53.51% | 53.51% | 0 | 5.49% | 34494.36 | 33717.46 | 776.9 | 584.96 | 0 | 0 | 0 | 0 | 18042.36 | 174.96 | 15675.1 | 2680% | YES | 15675.1 | 0 | 18042.36 | 0 | 0 | 0 | 0 | 0 | 7% | 12.49% | 19.31% | 12.31% |  | 18.28 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P22768 | MRB Onsite Support - Spirit Belfast | Trevor Knox | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2023-07-27 | 0 |  |  |  | 0% | 0% | 0 | -17.07% | 0 | 34614 | -34614 | 0 | 0 | 0 | 36800 | 34614 | 0 | 41536.8 | 34614 | 0% | NO | 34614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | -7.07% | 0% | -10% |  | 36 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23347 | WoT Fixed Leading Edge - Industrial 2023 | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 112.8% | 42.03% | 42.03% | 0 | -0.41% | 31034.12 | 35002.1 | -3967.98 | 0 | 0 | 0 | 10500 | 3967.98 | 14710.56 | 24349.85 | 20291.54 | 0% | NO | 20291.54 | 0 | 14710.56 | 0 | 0 | 0 | 0 | 0 | 7% | 6.59% | 0% | -7% |  | 32.26 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23051 | Spirit Shorts A350 PAX Door | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3A | REIM |  |  |  |  | 205.9% | 105.4% | 105.4% | 0 | -0.63% | 18216 | 37513 | -19297 | 0 | 0 | 0 | 0 | 19297 | 39537 | 0 | 0 | 0% | NO | 0 | 0 | 39537 | 0 | 0 | 0 | 0 | 0 | 30% | 29.37% | 0% | -30% |  | 46 | [5 empty] | 2024
1735 | 2024-04-24 23:37 | P23598 | MRB Onsite support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 53.1157 | 29.8% | 0% | 0% | 0 | -11.43% | 133056 | 39655.17 | 93400.83 | 1758.44 | 8736.42 | 14079.58 | 0 | 0 | 0 | 95.36 | 39655.17 | 2255% | YES | 44998.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 16.57% | 16.95% | -11.05% |  | 42.5 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P22752 | Tooling WoT - 2021 (Spirit) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | REIM | 2023-05-03 | 0 |  |  | 101.1% | 74.02% | 74.02% | 0 | -8.5% | 41525.1 | 41982.28 | -457.18 | 0 | 0 | 0 | 0 | 457.18 | 31076.1 | 13087.42 | 10906.18 | 0% | NO | 10906.18 | 0 | 31076.1 | 0 | 0 | 0 | 0 | 0 | 0% | -8.5% | 0% | 0% |  | 39.09 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23877 | Strategic Enablement | Owain Jones | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -1 |  | 0% | 0% | 0 | -15.82% | 0 | 43081.5 | -43081.5 | 43081.5 | 0 | 0 | 67200 | 43081.5 | 0 | 91 | 43081.5 | 100% | NO | 43081.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 2.18% | 2.18% | -15.82% |  | 42 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23760 | EXP-033 Systems Engineering Support | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 37.7715 | 31.5% | 76.97% | 53.15% | 0 | -0.02% | 142300 | 44823.5 | 97476.5 | 2580.69 | 0 | 0 | 0 | 0 | 34500.75 | 51.74 | 10322.75 | 400% | YES | 10322.75 | 12811 | 23824.9167 | 0 | 12811.2 | 0 | 0 | 0 | 29% | 28.98% | 28.98% | -0.02% |  | 78.5 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23642 | MRB Belfast Support | Carl Warren | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -39.0659 |  | 0% | 0% | 0 | -43.93% | 0 | 46600.97 | -46600.97 | 1192.88 | 3135.3 | 3135.3 | 42350 | 46600.97 | 0 | 190.44 | 46600.97 | 3907% | YES | 46600.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22% | -21.93% | -24.55% | -46.55% |  | 38.52 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23339 | Spirit 2023 - Stewart Russell | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 64.51% | 100% | 100% | 0 | 0.62% | 72766.8 | 46941.72 | 25825.08 | 0 | 0 | 0 | 0 | 0 | 46941.74 | 0 | -0.02 | 0% | NO | -0.02 | 0 | 46941.74 | 0 | 0 | 0 | 0 | 0 | 7% | 7.62% | 0% | -7% |  | 35.67 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P22760 | SA Leading Edge Transport Media ('A' Frames) | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-11-15 | 1 |  |  | 85.99% | 110.7% | 116.3% | -3082.8 | 3.97% | 53480.8 | 45985.5 | 7495.3 | 0 | 42804 | 42804 | 0 | 0 | 50911.8 | 0 | -0.3 | 0% | NO | -0.3 | -3083 | 53480.9667 | 0 | 0 | 0 | -3082.8 | -3082.8 | 6% | 9.97% | 0% | -6% |  | 42 | [5 empty] | 4926
1735 | 2024-04-24 23:37 | P23349 | Spirit 2023 - Stress Approve Man Serv (SB) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 58.24% | 80.05% | 80.05% | 0 | -0.29% | 97920 | 57024 | 40896 | 0 | 0 | 0 | 0 | 0 | 45648 | 13651.2 | 11376 | 0% | NO | 11376 | 0 | 45648 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23322 | GKN T Tomblin 2023 | Steven Lawton | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2024-04-15 | 1 |  |  | 99.66% | 100% | 95.06% | 0 | -0.33% | 58952 | 58752 | 200 | 0 | 0 | 0 | 0 | 0 | 58752 | 33.57 | 0 | 0% | NO | 0 | 3485 | 55847.8333 | 0 | 3484.8 | 0 | 0 | 0 | 17% | 16.67% | 16.67% | -0.33% |  | 48 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23106 | ME Support to NPD - Bobby Haggart | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  |  | 95.79% | 97.03% | 97.03% | 0 | 0.3% | 65675 | 62912.11 | 2762.89 | 0 | 0 | 0 | 0 | 0 | 61042.75 | 2243.24 | 1869.36 | 0% | NO | 1869.36 | 0 | 61042.75 | 0 | 0 | 0 | 0 | 0 | 15% | 15.3% | 0% | -15% |  | 35.65 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P22967 | Spirit 2022 - Channapa Laxmeshwar | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2023-01-26 | 2 |  |  | 69.69% | 121.3% | 121.3% | 0 | 9.53% | 75159.1 | 52376.15 | 22782.95 | 0 | 52376.15 | 54898.1 | 0 | 0 | 63508.8 | 0.42 | 0.35 | 0% | NO | 2522.3 | 0 | 63508.8 | 0 | 0 | 0 | 0 | 0 | 8% | 17.53% | 0% | -8% |  | 0 | [5 empty] | 11133
1735 | 2024-04-24 23:37 | P23193 | Spirit Shorts Stephen Greer | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -8.3245 | 107% | 92.34% | 83.13% | 0 | 8.66% | 61472 | 65749.71 | -4277.71 | 513.87 | 0 | 0 | 10878 | 4277.71 | 60712.78 | 121.98 | 5036.93 | 980.2% | YES | 5036.93 | 7269 | 54655.28 | 0 | 7268.72 | 0 | 0 | 0 | 23% | 31.66% | 34.03% | 11.03% |  | 35.12 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23700 | IPDT Leads | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 29.0032 | 39.48% | 37.31% | -0.0005686% | 0 | -1.88% | 169263.9 | 66825.35 | 102438.55 | 3531.97 | 0 | 0 | 0 | 0 | 24932.12 | 124.82 | 41893.23 | 1186% | YES | 41893.23 | 29919 | -0.38 | 0 | 29918.54 | 0 | 0 | 0 | 26% | 24.12% | 22.2% | -3.8% |  | 50.38 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23341 | Spirit 2023 - Tom McFarlane | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 41.55 | 61.93% | 89.71% | 63.92% | 7110.19 | -0.01% | 108666.4 | 67296.69 | 41369.71 | 995.66 | 0 | 0 | 0 | 0 | 60369.22 | 160.27 | 6927.47 | 695.8% | YES | 6927.47 | 20820 | 43019.22 | 11378.44 | 2331.04 | 0 | 7110.19 | 7110.19 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23561 | SAAB | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2024-01-01 | 0 |  |  | 82.46% | 121.1% | 121.1% | 0 | 8.77% | 67485 | 55649.23 | 11835.77 | 0 | 0 | 0 | 0 | 0 | 67399.4 | 0 | -0.17 | 0% | NO | -0.17 | 0 | 67399.4 | 0 | 0 | 0 | 0 | 0 | 16% | 24.77% | 100% | 84% |  | 36.82 | [5 empty] | 11750
1735 | 2024-04-24 23:37 | P23600 | MBDA EXP-EE-023 Bristone Certification | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 59.65% | 100% | 100% | 0 | 0.4% | 126600 | 75517 | 51083 | 0 | 0 | 0 | 0 | 0 | 75517 | 0 | 0 | 0% | NO | 0 | 0 | 75517 | 0 | 0 | 0 | 0 | 0 | 41% | 41.4% | 0% | -41% |  | 78.5 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23729 | Honda Tooling | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | FIX |  |  |  | 7.7804 | 66.6% | 42.88% | 0% | 0 | 3.16% | 113610 | 75663 | 37947 | 4877.25 | 0 | 0 | 0 | 0 | 32445 | 104.05 | 43218 | 886.1% | YES | 43218 | 38934 | 0 | 0 | 38934 | 0 | 0 | 0 | 10% | 13.16% | 13.16% | 3.16% |  | 42 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23080 | Spirit Shorts DManagement Cairan Cullen | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 686.6757 | 50.89% | 97.47% | 90.81% | 3787.8 | -1.26% | 149600 | 76125.7 | 73474.3 | 107 | 0 | 0 | 0 | 0 | 74199.7 | 191.36 | 1926 | 1800% | YES | 1926 | 6086 | 69128.0333 | 0 | 2298.36 | 0 | 3787.8 | 3787.8 | 24% | 22.74% | 13.03% | -10.97% |  | 44.39 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23744 | Model Factory | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 34.9601 | 28.7% | 88.43% | 30.36% | 0 | 9.09% | 262300 | 75283.25 | 187016.75 | 5349.44 | 0 | 0 | 0 | 0 | 66574 | 78.31 | 11709.25 | 218.9% | YES | 11709.25 | 52459 | 22858.1667 | 0 | 26229.6 | 26229.6 | 0 | 0 | 28% | 37.09% | 37.09% | 9.09% |  | 50.71 | [5 empty] | 3000
1735 | 2024-04-24 23:37 | P22505 | Spirit MRB Engineering Support 2021 | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 1 |  |  | 91.17% | 100% | 95.78% | 4020.48 | 21.2% | 87110.4 | 79414.95 | 7695.45 | 0 | 0 | 0 | 0 | 0 | 79414.95 | 4020.48 | 0 | 0% | NO | 0 | 4020 | 76064.95 | 0 | 0 | 0 | 4020.48 | 4020.48 | 0% | 21.2% | 0% | 0% |  | 41.88 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23560 | NJEWCS TAF202302 SM | Natalie Sinclair | 0 | COB | CHELTON LIMITED | EES | Level 2 | FIX |  |  |  |  | 97.96% | 100.2% | 50.1% | 0 | 11.94% | 81500 | 79836.44 | 1663.56 | 0 | 0 | 0 | 0 | 0 | 80000 | 236.44 | -163.57 | 0% | NO | -163.57 | 48000 | 40000 | 48000 | 0 | 0 | 0 | 0 | 28% | 39.94% | 39.49% | 11.49% |  | 73.01 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P22885 | ME Support (Baxi) | Trevor Knox | 0 | HUV | BAXI HEATING UK LIMITED | ME | Level 3 | FIX | 2023-01-12 | 0 |  |  | 68.78% | 108.7% | 108.7% | 0 | 13.05% | 106632.96 | 73340.24 | 33292.72 | 0 | 0 | 0 | 0 | 0 | 79748.12 | 1531.35 | 1276.12 | 0% | NO | 1276.12 | 0 | 79748.12 | 0 | 0 | 0 | 0 | 0 | 15% | 28.05% | 0% | -15% |  | 44.37 | [5 empty] | 7684
1735 | 2024-04-24 23:37 | P23438 | A220 Spirit Shorts DTC - Stephen Corry | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 85.55% | 78.54% | 49.23% | 0 | -7.3% | 95928.4 | 82068.6 | 13859.8 | 0 | 0 | 0 | 0 | 0 | 64459.8 | 341.41 | 17608.8 | 0% | NO | 17608.8 | 28872 | 40399.8 | 0 | 28872.36 | 0 | 0 | 0 | 23% | 15.7% | 16.75% | -6.25% |  | 49.81 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23335 | GKN S McConnell 2023 | Steven Lawton | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2023-12-31 | 0 |  |  | 96.61% | 100% | 100% | 0 | 0.74% | 87420 | 84459 | 2961 | 0 | 0 | 0 | 0 | 0 | 84459 | 0 | 0 | 0% | NO | 0 | 0 | 84459 | 0 | 0 | 0 | 0 | 0 | 15% | 15.74% | 0% | -15% |  | 47 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P22965 | Spirit 2022 - Design Man Serv (AH) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 106.7% | 96.66% | 96.66% | 0 | 3.14% | 80079.56 | 85441.32 | -5361.76 | 0 | 0 | 0 | 0 | 5361.76 | 82588.96 | 3422.84 | 2852.36 | 0% | NO | 2852.36 | 0 | 82588.96 | 0 | 0 | 0 | 0 | 0 | 14% | 17.14% | 0% | -14% |  | 42.44 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23523 | Applique Armour Support | Dushan Fernando | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-18 | 1 |  |  | 72.43% | 138.1% | 98.47% | 0 | 3.42% | 118200 | 85606.5 | 32593.5 | 0 | 0 | 0 | 0 | 0 | 118200 | 1567.8 | -32593.5 | 0% | NO | -32593.5 | 40680 | 84300 | 0 | 40680 | 0 | 0 | 0 | 25% | 28.42% | 0% | -25% |  | 64.29 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P22964 | Spirit 2022 - MRB Man Serv (JC) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 100.6% | 97.95% | 97.95% | 0 | 1.91% | 85435.2 | 85960.26 | -525.06 | 0 | 0 | 0 | 0 | 525.06 | 84199.74 | 2112.62 | 1760.52 | 0% | NO | 1760.52 | 0 | 84199.74 | 0 | 0 | 0 | 0 | 0 | 16% | 17.91% | 0% | -16% |  | 42.69 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P22963 | Spirit 2022 - Design Man Serv (PC) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 108.6% | 104% | 104% | 0 | 3.18% | 80079.56 | 86926.74 | -6847.18 | 0 | 0 | 0 | 0 | 6847.18 | 90389.95 | 0 | -3463.21 | 0% | NO | -3463.21 | 0 | 90389.95 | 0 | 0 | 0 | 0 | 0 | 13% | 16.18% | 0% | -13% |  | 42.39 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23342 | Spirit 2023 - Channapa Laxmeshwar | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 237.5059 | 53.17% | 86.8% | 73.25% | 4036.8 | -3.73% | 158696.7 | 84385.85 | 74310.85 | 312.88 | 84385.85 | 94827 | 0 | 0 | 73251.1 | 105.63 | 13984.75 | 4470% | YES | 24425.9 | 13725 | 61813.6 | 9688.32 | 0 | 0 | 4036.8 | 4036.8 | 7% | 3.27% | 0% | -7% |  | 0 | [5 empty] | 2850
1735 | 2024-04-24 23:37 | P23340 | Spirit 2023 - John Cole | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 42.7971 | 59.46% | 88.68% | 62.17% | 8831.16 | -0.01% | 150129.72 | 89266.32 | 60863.4 | 1422.14 | 0 | 0 | 0 | 0 | 79162.2 | 165.08 | 10104.12 | 710.5% | YES | 10104.12 | 28403 | 55493.0333 | 14750.42 | 4821.34 | 0 | 8831.16 | 8831.16 | 7% | 6.99% | 6.99% | -0.01% |  | 39.78 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23079 | Spirit Shorts Nomenclature | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -2.5327 | 101.3% | 87.27% | 76.28% | 0 | 2.05% | 88455 | 89593.2 | -1138.2 | 449.4 | 0 | 0 | 0 | 1138.2 | 78185.2 | 255.26 | 11408 | 2538% | YES | 11408 | 11811 | 68342.7 | 0 | 11810.64 | 0 | 0 | 0 | 20% | 22.05% | 25.23% | 5.23% |  | 30.79 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23465 | A220 ToW Design Offload (Wing) | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 42.0101 | 68.59% | 88.97% | 61.6% | 0 | -4.88% | 132000 | 90532.7 | 41467.3 | 987.08 | 0 | 0 | 0 | 0 | 80549.6 | 117.84 | 9983.1 | 1011% | YES | 9983.1 | 29737 | 55768.7667 | 0 | 29737.44 | 0 | 0 | 0 | 20% | 15.12% | 13.54% | -6.46% |  | 42.8 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23336 | Spirit 2023 - Neil Rampling | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 27.1765 | 69.4% | 88.76% | 51.51% | 21586.03 | -0.01% | 133901.52 | 92922.12 | 40979.4 | 1507.9 | 0 | 0 | 0 | 0 | 82473.26 | 211.47 | 10448.86 | 692.9% | YES | 10448.86 | 41533 | 47862.4267 | 15306.07 | 4640.79 | 0 | 21586.03 | 21586.03 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23375 | GKN Jaap Peters NL 2023 | Steven Lawton | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2024-03-01 | 1 |  |  | 93.37% | 105.3% | 97.18% | 0 | -15.93% | 97123.22 | 90686.41 | 6436.81 | 0 | 90686.41 | 90686.41 | 0 | 0 | 95456.72 | 40.01 | -920.31 | 0% | NO | -920.31 | 8793 | 88129.22 | 0 | 0 | 8793.29 | 0 | 0 | 20% | 4.07% | 0% | -20% |  | 0 | [5 empty] | 3850
1735 | 2024-04-24 23:37 | P23345 | Spirit 2023- Jonathan Escosio | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 21.8331 | 62.66% | 71.85% | 53.83% | 15846.34 | -0.41% | 151941.24 | 95202.64 | 56738.6 | 2598.74 | 0 | 0 | 0 | 0 | 68401.74 | 221.67 | 26800.9 | 1031% | YES | 26800.9 | 20581 | 51250.9067 | 0 | 4734.58 | 0 | 15846.34 | 15846.34 | 7% | 6.59% | 21.77% | 14.77% |  | 43.01 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23171 | Spirt Shorts Weights Eng | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 10.9035 | 69.18% | 133.5% | 103.1% | 7796.45 | 13.12% | 103113.14 | 71329.32 | 31783.82 | 2915 | 71329.32 | 85975.13 | 0 | 0 | 95259.1 | 151.79 | 0.22 | 0.007547% | NO | 14646.03 | 26047 | 73553.2667 | 9273.05 | 0 | 16774.18 | 0 | 7796.45 | 12% | 25.12% | 47.26% | 35.26% |  | 0 | [5 empty] | 23930
1735 | 2024-04-24 23:37 | P23551 | Ian Berry 2023 H2 | Natalie Sinclair | 0 | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  | -16.505 | 126.2% | 70.23% | 70.23% | 0 | 13.46% | 75810 | 95705.12 | -19895.12 | 1205.4 | 0 | 0 | 24259.2 | 19895.12 | 67217.49 | 82.35 | 28487.63 | 2363% | YES | 28487.63 | 0 | 67217.49 | 0 | 0 | 0 | 0 | 0 | 22% | 35.46% | 37.71% | 15.71% |  | 77.6 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23822 | FCASW Requirements Management | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | -8.4195 |  | 0% | 0% | 0 | -8.61% | 0 | 96547.68 | -96547.68 | 11467.09 | 0 | 0 | 98262.3 | 96547.68 | 0 | 77 | 96547.68 | 842% | YES | 96547.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 11.39% | 11.39% | -8.61% |  | 75.11 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23586 | Project Management Support | Dushan Fernando | 0 | BDX | MBDA UK LIMITED | MPE | Level NC | REIM |  |  |  | 28.2396 | 61.45% | 68.25% | 68.25% | 0 | -26.45% | 160000 | 98320.46 | 61679.54 | 2184.15 | 1277.2 | 1277.2 | 0 | 0 | 67103.86 | 83.12 | 31216.6 | 1429% | YES | 31216.6 | 0 | 67103.86 | 0 | 0 | 0 | 0 | 0 | 49% | 22.55% | 21.58% | -27.42% |  | 80 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23583 | Castalla - Test Rig Design | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -7.7141 | 113% | 65.08% | 59.08% | 0 | -6.38% | 91720 | 103684.5 | -11964.5 | 1551 | 0 | 0 | 13200 | 11964.5 | 67482.1 | 152.47 | 36202.4 | 2334% | YES | 36202.4 | 7469 | 61257.9333 | 0 | 7469.4 | 0 | 0 | 0 | 21% | 14.62% | 16.66% | -4.34% |  | 42.83 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23784 | Tempest Tooling Offload 2024 | Gary Kempster | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  | -17.9402 |  | 0% | 0% | 0 | -11.61% | 0 | 106853.87 | -106853.87 | 5956.11 | 0 | 0 | 107936.4 | 106853.87 | 0 | 109.28 | 106853.87 | 1794% | YES | 106853.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 18.39% | 18.39% | -11.61% |  | 54.8 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23545 | Ultra CSS continuation 2023 H2 | Natalie Sinclair | 0 | ULT | ULTRA SONAR SYSTEMS LIMITED | EES | Level NC | REIM |  |  |  | -12.9709 | 147.7% | 67.23% | 67.23% | 0 | 2.2% | 76000 | 112230.4 | -36230.4 | 2793.2 | 0 | 0 | 49859.2 | 36230.4 | 75451.2 | 116.14 | 36779.2 | 1317% | YES | 36779.2 | 0 | 75451.2 | 0 | 0 | 0 | 0 | 0 | 23% | 25.2% | 25% | 2% |  | 80 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23353 | Spirit 2023 - MRB Man Serv (JC) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  | 37.9625 | 62.78% | 59.53% | 59.53% | 0 | 9.71% | 183600 | 115267.5 | 68332.5 | 1800 | 0 | 0 | 0 | 0 | 68615.25 | 197.78 | 46652.25 | 2592% | YES | 46652.25 | 0 | 68615.25 | 0 | 0 | 0 | 0 | 0 | 7% | 16.71% | 13.06% | 6.06% |  | 45 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P22918 | Spirit Shorts Graduates | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 24.7378 | 89.34% | 91.9% | 60.58% | 0 | 9.48% | 130000 | 116138.69 | 13861.31 | 560.33 | 0 | 0 | 9900 | 0 | 106734.95 | 264.96 | 9403.74 | 1678% | YES | 9403.74 | 43660 | 70351.6167 | 0 | 0 | 43659.95 | 0 | 0 | 7% | 16.48% | 17.18% | 10.18% |  | 23.31 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23753 | Tempest Composites Maturation | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 0.617 | 93.26% | 26.07% | -0.0001677% | 0 | -10.3% | 127848.45 | 119231.5 | 8616.95 | 13965.96 | 0 | 0 | 0 | 0 | 31084.8 | 98.98 | 88146.7 | 631.2% | YES | 88146.7 | 37302 | -0.2 | 0 | 37301.76 | 0 | 0 | 0 | 32% | 21.7% | 21.7% | -10.3% |  | 64.58 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23588 | BAE Typhoon MRB MC Shop Concessions | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 26.1584 | 68.24% | 93.86% | 67.22% | 14399.76 | -3.68% | 175060.5 | 119459.23 | 55601.27 | 2125.56 | 0 | 0 | 0 | 0 | 112121.71 | 113.37 | 7337.52 | 345.2% | YES | 7337.52 | 38191 | 80295.8767 | 10272.55 | 13518.34 | 14399.76 | 0 | 14399.76 | 31% | 27.32% | 29.19% | -1.81% |  | 55.53 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P22736 | WoT Fixed Leading Edge - Industrial | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 106.7% | 93.42% | 91.32% | 3019.54 | 0.01% | 112196.27 | 119668.47 | -7472.2 | 0 | 0 | 0 | 0 | 7472.2 | 111796.68 | 12465.69 | 7871.79 | 0% | NO | 7871.79 | 3020 | 109280.0133 | 0 | 0 | 0 | 3019.54 | 3019.54 | 7% | 7.01% | 0% | -7% |  | 32.26 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23664 | Tempest Composites WP3 | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 2.1733 | 97.78% | 71.92% | 13.8% | 0 | -5.09% | 122455.49 | 119736.27 | 2719.22 | 1251.2 | 0 | 0 | 14830.4 | 0 | 86110.38 | 287.71 | 33625.89 | 2687% | YES | 33625.89 | 83510 | 16518.7133 | 83510.02 | 0 | 0 | 0 | 0 | 37% | 31.91% | 33.6% | -3.4% |  | 60.6 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23352 | Spirit 2023 - Stress Approve Man Serv (CC) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  | -8.7391 | 124.6% | 57.29% | 57.29% | 0 | 6.12% | 97920 | 122040 | -24120 | 2760 | 0 | 0 | 29856 | 24120 | 69912 | 210.27 | 52128 | 1889% | YES | 52128 | 0 | 69912 | 0 | 0 | 0 | 0 | 0 | 7% | 13.12% | 4.69% | -2.31% |  | 48 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P22883 | Spirit Shorts Evtol PMO C. Hatton | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 155.0512 | 66.04% | 88.8% | 88.8% | 0 | -11.64% | 185800 | 122694.15 | 63105.85 | 407 | 0 | 0 | 0 | 0 | 108946.73 | 113.05 | 13747.42 | 3378% | YES | 13747.42 | 0 | 108946.73 | 0 | 0 | 0 | 0 | 0 | 26% | 14.36% | 22.96% | -3.04% |  | 36.87 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P22861 | WoT FLE Lifting & Handling Tools | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2023-06-14 | 1 |  |  | 65.17% | 101.6% | 101.6% | 0 | 12.01% | 173987.21 | 113381.75 | 60605.46 | 0 | 50078 | 58423.58 | 0 | 0 | 115203.5 | 12813.9 | 10678.25 | 0% | NO | 19023.83 | 0 | 115203.5 | 0 | 0 | 0 | 0 | 0 | 1% | 13.01% | 0% | -1% |  | 45 | [5 empty] | 12500
1735 | 2024-04-24 23:37 | P23282 | Tooling Support (MBDA) | Dushan Fernando | 0 | BDV | MBDA UK LIMITED | ME | Level NC | REIM |  |  |  | 44.3372 | 65.01% | 95.13% | 81.6% | 0 | -8.11% | 195672.4 | 127211.74 | 68460.66 | 1544.09 | 0 | 0 | 0 | 0 | 121010.44 | 92.08 | 6201.3 | 401.6% | YES | 6201.3 | 20648 | 103803.7733 | 0 | 20647.76 | 0 | 0 | 0 | 30% | 21.89% | 30.37% | 0.37% |  | 49.72 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23270 | Shorts Project X | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 8.1198 | 90.51% | 90.06% | 68.27% | 0 | 0.48% | 142248 | 128746.52 | 13501.48 | 1662.78 | 0 | 0 | 0 | 0 | 115944.34 | 170.58 | 12802.18 | 769.9% | YES | 12802.18 | 33666 | 87889.34 | 10030.61 | 23635.49 | 0 | 0 | 0 | 13% | 13.48% | 10.99% | -2.01% |  | 45.33 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23810 | Strategic Enablement | Owain Jones | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -843.2318 |  | 0% | 0% | 0 | -20.63% | 0 | 133694.4 | -133694.4 | 158.55 | 0 | 0 | 134000 | 133694.4 | 0 | 127.3 | 133694.4 | 84323% | YES | 133694.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | -2.63% | -2.63% | -20.63% |  | 42 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23754 | Tempest Composites WP4 | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 13.4873 | 44.82% | 0% | 0% | 0 | -1.11% | 310945.68 | 139369.44 | 171576.24 | 12721.35 | 1344.88 | 1784.88 | 0 | 0 | 0 | 99.68 | 139369.44 | 1096% | YES | 139809.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36% | 34.89% | 34.89% | -1.11% |  | 61.93 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23533 | External Stowage Design and Detail Support | Dushan Fernando | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 1 |  |  | 102.4% | 97.65% | 73.24% | 0 | 3.33% | 140000 | 143368.75 | -3368.75 | 0 | 0 | 0 | 12936 | 3368.75 | 140000 | 41999.7 | -0.25 | 0% | NO | -0.25 | 42000 | 105000 | 0 | 42000 | 0 | 0 | 0 | 27% | 30.33% | 0% | -27% |  | 60.04 | [5 empty] | -3369
1735 | 2024-04-24 23:37 | P23650 | MBDA Recruitment Management costs | Andrew Slaney | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM | 2024-02-01 | 0 |  |  |  | 0% | 0% | 0 | -20.2% | 0 | 240971.5 | -240971.5 | 0 | 0 | 0 | 266000 | 240971.5 | 0 | 236.71 | 140971.5 | 0% | NO | 140971.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | -17.2% | -441% | -444% |  | 82.3 | [5 empty] | -100000
1735 | 2024-04-24 23:37 | P22954 | Technical Support Step 1 | Owain Jones | 0 | HUV | HUARUI SPIRIT AEROSPACE MANUFACT | ME | Level 2 | REIM |  |  |  |  | 94.81% | 58.01% | 58.01% | 0 | 0.31% | 155501.18 | 147431.58 | 8069.6 | 0 | 23043 | 23043 | 0 | 0 | 85525.49 | 61906.09 | 61906.09 | 0% | NO | 61906.09 | 0 | 85525.49 | 0 | 0 | 0 | 0 | 0 | 30% | 30.31% | 0% | -30% |  | 60.79 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23386 | Software Development - BMS | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 98.78% | 100% | 100% | 0 | 4.31% | 149650 | 147823.35 | 1826.65 | 0 | 0 | 0 | 0 | 0 | 147823.35 | 0 | 0 | 0% | NO | 0 | 0 | 147823.35 | 0 | 0 | 0 | 0 | 0 | 18% | 22.31% | 22.61% | 4.61% |  | 78.5 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23437 | Embedded Software Engineer | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 98.73% | 100% | 96.08% | 0 | -6.29% | 150150 | 148239.36 | 1910.64 | 0 | 737.86 | 737.86 | 0 | 0 | 148239.36 | 26.1 | 0 | 0% | NO | 0 | 6971 | 142430.1933 | 0 | 6970.8 | 0 | 0 | 0 | 22% | 15.71% | 16.24% | -5.76% |  | 78.5 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23550 | Tempest Composites | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -4.6319 | 102.5% | 97.57% | 97.57% | 0 | 5.14% | 149494.92 | 153217.46 | -3722.54 | 803.68 | 0 | 0 | 2396.12 | 3722.54 | 149494.92 | 20.35 | 3722.54 | 463.2% | YES | 3722.54 | 0 | 149494.92 | 0 | 0 | 0 | 0 | 0 | 26% | 31.14% | 34.01% | 8.01% |  | 61.6 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P22440 | Spirit Managed Service - F&DT and Static Approval | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 3 |  |  | 88.56% | 92.56% | 92.56% | 0 | 11.51% | 173500 | 153656.25 | 19843.75 | 0 | 52115 | 55720 | 0 | 0 | 142225.12 | 13717.36 | 11431.13 | 0% | NO | 15036.13 | 0 | 142225.12 | 0 | 0 | 0 | 0 | 0 | 0% | 11.51% | 0% | 0% |  | 44.73 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P22982 | Spirit 2022 - Hugh Sloan | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 82.1656 | 62.89% | 93.75% | 81.56% | 8217.17 | -0.58% | 247473 | 155643.1 | 91829.9 | 1117.62 | 0 | 0 | 0 | 0 | 145911.5 | 200.82 | 9731.6 | 870.7% | YES | 9731.6 | 22757 | 126947.3333 | 10239.53 | 4300.18 | 0 | 8217.17 | 8217.17 | 7% | 6.42% | 1.35% | -5.65% |  | 35.43 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23518 | Systems Engineering support to FCAS | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 12.8421 | 84.32% | 91.59% | 86.57% | 0 | -4.56% | 193736.8 | 163367.75 | 30369.05 | 2364.81 | 3927.4 | 3927.4 | 0 | 0 | 149625.43 | 62.05 | 13742.32 | 581.1% | YES | 13742.32 | 9844 | 141422.0967 | 0 | 9843.9 | 0 | 0 | 0 | 30% | 25.44% | 3.5% | -26.5% |  | 68.25 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23667 | Safety Systems Engineer | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 60.469 | 42.34% | 90.99% | 81.33% | 0 | -10.33% | 398000 | 168520 | 229480 | 3795 | 0 | 0 | 0 | 0 | 153340 | 53.88 | 15180 | 400% | YES | 15180 | 19536 | 137060 | 0 | 19536 | 0 | 0 | 0 | 47% | 36.67% | 29.32% | -17.68% |  | 110 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23464 | A220 Project X Design Offload | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 217.4957 | 51.68% | 100% | 64.09% | 27862.8 | -9.3% | 332340 | 171762.9 | 160577.1 | 738.3 | 0 | 0 | 0 | 0 | 171762.9 | 185.87 | 0 | 0% | NO | 0 | 74010 | 110087.9 | 18361.2 | 27785.76 | 0 | 27862.8 | 27862.8 | 26% | 16.7% | 14.75% | -11.25% |  | 42.88 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23508 | Verification and Validation | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 80.77% | 100% | 97.06% | 0 | 10.77% | 212950 | 171993.5 | 40956.5 | 0 | 0 | 0 | 0 | 0 | 171993.53 | 19.36 | -0.03 | 0% | NO | -0.03 | 6076 | 166930.1967 | 0 | 6075.9 | 0 | 0 | 0 | 24% | 34.77% | 33.6% | 9.6% |  | 78.5 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23421 | A220 DTC | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 9.7076 | 80.36% | 68.94% | 61.39% | 0 | -28.47% | 217089.12 | 174443.91 | 42645.21 | 4392.99 | 0 | 0 | 0 | 0 | 120261.6 | 109.13 | 54182.31 | 1233% | YES | 54182.31 | 15801 | 107094.1 | 0 | 15800.9 | 0 | 0 | 0 | 29% | 0.53% | 5.23% | -23.77% |  | 45.98 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23741 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  | 38.6696 | 26.67% | 82.47% | 26.26% | 0 | 2.3% | 640812 | 170927.4 | 469884.6 | 12151.28 | 0 | 0 | 0 | 0 | 140959 | 78.61 | 33968.4 | 279.5% | YES | 33968.4 | 115289 | 44884.8333 | 0 | 62626.8 | 52662 | 0 | 0 | 28% | 30.3% | 30.3% | 2.3% |  | 38.8 | [5 empty] | 4000
1735 | 2024-04-24 23:37 | P23739 | Lifing Services DACs | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  | 39.4071 | 27.93% | 90.05% | 30.38% | 0 | 4.86% | 656508 | 183378.65 | 473129.35 | 12006.19 | 0 | 0 | 0 | 0 | 165127 | 77.61 | 23251.65 | 193.7% | YES | 23251.65 | 131302 | 55708.6667 | 0 | 65650.8 | 65650.8 | 0 | 0 | 28% | 32.86% | 32.86% | 4.86% |  | 37.78 | [5 empty] | 5000
1735 | 2024-04-24 23:37 | P23008 | Spirit Shorts Project Rachel | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 68.49% | 91.32% | 91.32% | 0 | -9.7% | 286960 | 196531.2 | 90428.8 | 0 | 0 | 0 | 0 | 0 | 179472.8 | 20470.08 | 17058.4 | 0% | NO | 17058.4 | 0 | 179472.8 | 0 | 0 | 0 | 0 | 0 | 15% | 5.3% | 0.31% | -14.69% |  | 46.04 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23019 | EXP034-B Actuator Development | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 103.1% | 89.91% | 89.91% | 0 | -16.68% | 215541.2 | 222215.54 | -6674.34 | 0 | 12297.9 | 12297.9 | 0 | 6674.34 | 199796.76 | 122.03 | 397.78 | 0% | NO | 397.78 | 0 | 199796.76 | 0 | 0 | 0 | 0 | 0 | 34% | 17.32% | 79.64% | 45.64% |  | 58.45 | [5 empty] | -22021
1735 | 2024-04-24 23:37 | P23648 | EXP-032 Delivery of Datalink Eng support - FCAS AP | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 18.3606 | 54.99% | 74.6% | 66.62% | 0 | 6.41% | 371000 | 204010.45 | 166989.55 | 9095 | 1032.95 | 1032.95 | 0 | 0 | 152192.95 | 57.43 | 51817.5 | 569.7% | YES | 51817.5 | 19536 | 135912.95 | 0 | 19536 | 0 | 0 | 0 | 22% | 28.41% | 28.91% | 6.91% |  | 102.62 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23506 | ASTER Mid-Life Refurbishment Project Manager | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 4.3755 | 92% | 90.11% | 84.45% | 0 | 1.08% | 224900 | 206911.41 | 17988.59 | 4111.25 | 2806.41 | 2806.41 | 0 | 0 | 186451.41 | 53.79 | 20460 | 497.7% | YES | 20460 | 14058 | 174736.41 | 14058 | 0 | 0 | 0 | 0 | 25% | 26.08% | 26.4% | 1.4% |  | 110 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23505 | EXP-022 Meteor TBUS T&E support | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 14.0093 | 83.87% | 94.51% | 86.76% | 0 | -1.23% | 246744.4 | 206945.86 | 39798.54 | 2840.87 | 0 | 0 | 0 | 0 | 195582.38 | 52.49 | 11363.48 | 400% | YES | 11363.48 | 19242 | 179547.38 | 0 | 19241.59 | 0 | 0 | 0 | 20% | 18.77% | 15.67% | -4.33% |  | 89.83 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23242 | Physical Architecture & System Engineering Support | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 35.9708 | 68.92% | 94.62% | 89.03% | 0 | 7.54% | 305459 | 210511.96 | 94947.04 | 2639.56 | 775.55 | 775.55 | 0 | 0 | 199187.05 | 56.16 | 10970.91 | 415.6% | YES | 10970.91 | 14130 | 187412.05 | 0 | 14130 | 0 | 0 | 0 | 15% | 22.54% | 7.12% | -7.88% |  | 78.21 | [5 empty] | -354
1735 | 2024-04-24 23:37 | P23373 | Raytheon Michael Bellini | Natalie Sinclair | 0 | RAS | RAYTHEON UNITED KINGDOM LIMITED | EES | Level NC | REIM |  |  |  | -0.084476 | 100.2% | 89.28% | 79.68% | 24734.7 | -7.79% | 214367.4 | 214759.18 | -391.78 | 4637.76 | 0 | 0 | 13558.28 | 391.78 | 191739.73 | 83.75 | 23019.45 | 496.3% | YES | 23019.45 | 24735 | 171127.23 | 0 | 24734.7 | 0 | 0 | 24734.7 | 45% | 37.21% | 38.67% | -6.33% |  | 91.61 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23524 | Bombardier Regional Jets (BRJ) | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -10.5065 | 149.7% | 49.7% | 48.29% | 3694.07 | -3.99% | 146287.84 | 218990.96 | -72703.12 | 6919.82 | 0 | 0 | 113075 | 72703.12 | 108838.22 | 278.09 | 110152.74 | 1592% | YES | 110152.74 | 3694 | 105759.8867 | 0 | 0 | 0 | 3694.07 | 3694.07 | 18% | 14.01% | 17.1% | -0.9% |  | 43.78 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23629 | F35 FTI | Christopher McCarthy | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level NC | REIM |  |  |  | -31.7099 |  | 91.51% | 82.17% | 0 | -1.54% | 0 | 249151.86 | -249151.86 | 7857.22 | 0 | 0 | 0 | 249151.86 | 228001.02 | 35.12 | 21150.84 | 269.2% | YES | 21150.84 | 27916 | 204737.6867 | 27915.57 | 0 | 0 | 0 | 0 | 31% | 29.46% | 27.97% | -3.03% |  | 61.91 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23743 | EHM Cloud Migration | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 40.2513 | 24.02% | 104.9% | 35% | 0 | 6.25% | 1016000 | 244004.75 | 771995.25 | 19179.38 | 0 | 0 | 0 | 0 | 256032 | 68.97 | 7972.75 | 41.57% | NO | 7972.75 | 204749 | 85407.8333 | 0 | 102336 | 102412.8 | 0 | 0 | 28% | 34.25% | 34.25% | 6.25% |  | 54.54 | [5 empty] | 20000
1735 | 2024-04-24 23:37 | P23677 | ME Managed Service - Phase 1 | Paul Watson | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  | 17.4831 | 47.79% | 0% | 0% | 0 | -15.46% | 554400 | 264972.6 | 289427.4 | 16554.71 | 0 | 38000 | 0 | 0 | 0 | 116.67 | 264972.6 | 1601% | YES | 302972.6 | 0 | 0 | -136782 | 136782 | 0 | 0 | 0 | 33% | 17.54% | 20.17% | -12.83% |  | 43.99 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23472 | Tempest Wing Design | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 33.5976 | 50.87% | 123.8% | 104.6% | 0 | -11.33% | 483869.78 | 246167.11 | 237702.67 | 7075 | 230287.5 | 356900 | 0 | 0 | 304757.78 | 24.13 | -33590.68 | -474.8% | NO | 93021.82 | 56671 | 257531.9467 | 32716.75 | 23954.72 | 0 | 0 | 0 | 23% | 11.67% | 31.49% | 8.49% |  | 46.74 | [5 empty] | 25000
1735 | 2024-04-24 23:37 | P23007 | EXP-006A - Brimstone 3 | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 64.3291 | 68.24% | 97.11% | 89.15% | 0 | -2.65% | 406450 | 277363.41 | 129086.59 | 2006.66 | 0 | 0 | 0 | 0 | 269336.75 | 83.9 | 7996.66 | 398.5% | YES | 7996.66 | 26470 | 247278.4167 | 11492.4 | 0 | 14977.8 | 0 | 0 | 25% | 22.35% | 29.94% | 4.94% |  | 69.95 | [5 empty] | -30
1735 | 2024-04-24 23:37 | P23603 | Typhoon IMDLR | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 6.5307 | 91.43% | 42.95% | 0.0001219% | 0 | 5.31% | 305067.09 | 278921.22 | 26145.87 | 4003.55 | 1500 | 1500 | 0 | 0 | 119807.84 | 387.55 | 159113.38 | 3974% | YES | 159113.38 | 143769 | 0.34 | 0 | 143769.41 | 0 | 0 | 0 | 26% | 31.31% | 32.39% | 6.39% |  | 56.89 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P21463 | Safety & Monitoring Systems at DM Beith & Gosport | Harry James Kellett | 0 | BXW | MOD | EES | Level 2 | FIX |  |  |  | 19.1642 | 79.03% | 121.7% | 121.7% | 0 | -28% | 363180.15 | 287025.79 | 76154.36 | 3973.79 | 72553.45 | 77420.74 | 21721 | 0 | 349386.99 | 0 | -62361.2 | -1569% | NO | -57493.91 | 0 | 349386.99 | 0 | 0 | 0 | 0 | 0 | 48% | 20% | 21.05% | -26.95% |  | 53 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23308 | NATO JEWCS | Natalie Sinclair | 0 | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  | 43.0566 | 83.4% | 92.07% | 91.96% | 0 | -3.78% | 356307 | 297144.71 | 59162.29 | 1374.06 | 613.89 | 613.89 | 0 | 0 | 273576.49 | 92.06 | 23568.22 | 1715% | YES | 23568.22 | 387 | 273253.99 | 386.92 | 0 | 0 | 0 | 0 | 24% | 20.22% | 11.85% | -12.15% |  | 75.81 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23816 | Typhoon FTI Works - 2024 Fixed Price Element | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 3.5044 | 74.22% | 0% | 0% | 0 | -1.15% | 404176.65 | 299962.86 | 104213.79 | 29738.29 | 0 | 0 | 0 | 0 | 0 | 86.8 | 309962.86 | 1042% | YES | 309962.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 28.85% | 28.85% | -1.15% |  | 52.88 | [5 empty] | 10000
1735 | 2024-04-24 23:37 | P22953 | Spirit Shorts eVTOL | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-05-08 | 2 |  |  | 103.1% | 80.83% | 79.36% | 0 | -9.51% | 324272 | 334483.6 | -10211.6 | 0 | 66696.6 | 67387.9 | 0 | 10211.6 | 270366 | 70861.92 | 54117.6 | 0% | NO | 54808.9 | 5921 | 265431.8333 | 0 | 5920.8 | 0 | 0 | 0 | 17% | 7.49% | 100% | 83% |  | 46.19 | [5 empty] | -10000
1735 | 2024-04-24 23:37 | P22515 | Shorts A220 100/300 ALI Phase III | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 39.725 | 82.45% | 97.08% | 90.05% | 0 | 0.68% | 400628.76 | 330330.17 | 70298.59 | 1769.63 | 3450.98 | 3450.98 | 0 | 0 | 320671.89 | 122.66 | 9658.28 | 545.8% | YES | 9658.28 | 27848 | 297465.2233 | 9461.23 | 18386.68 | 0 | 0 | 0 | 10% | 10.68% | 7.13% | -2.87% |  | 40.51 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23699 | A220 Stress Checkers | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -56.814 |  | 0% | 0% | 0 | -1.99% | 0 | 342248.61 | -342248.61 | 6024.02 | 12000 | 12000 | 321520 | 342248.61 | 0 | 131.98 | 342248.61 | 5681% | YES | 342248.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22% | 20.01% | 20.04% | -1.96% |  | 61.88 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P22842 | ME Support (Aim Altitude) | Trevor Knox | 0 | AVI | AIM ALTITUDE UK LIMITED | ME | Level 3 | FIX | 2023-06-14 | 4 |  |  | 99.31% | 100.5% | 86.63% | 57290.84 | 0.49% | 346293.67 | 343918.08 | 2375.59 | 0 | 2909.86 | 2909.86 | 0 | 0 | 345673.01 | 55184.93 | -1754.93 | 0% | NO | -1754.93 | 57291 | 297930.51 | 0 | 0 | 0 | 57290.84 | 57290.84 | 13% | 13.49% | 0% | -13% |  | 46.3 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23617 | Tempest Composites WP2 | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -16.7459 | 141.6% | 29.22% | 16.71% | 29536.68 | 11.67% | 244405.26 | 346177.71 | -101772.45 | 6077.45 | 0 | 0 | 120669.84 | 101772.45 | 101150.9 | 299.84 | 245026.81 | 4032% | YES | 245026.81 | 51981 | 57833.4 | 22444.14 | 0 | 0 | 29536.68 | 29536.68 | 22% | 33.67% | 33.4% | 11.4% |  | 62.09 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P22391 | GE System Engineering support | Vinayakumar Sugur | 0 | GEE | EXPERIS LIMITED | EES | Level NC | REIM | 2024-04-08 | 0 |  |  | 82.01% | 100.7% | 100.7% | 0 | 0.13% | 434434.25 | 356260.63 | 78173.62 | 0 | 0 | 0 | 0 | 0 | 358805.6 | 0 | -2544.97 | 0% | NO | -2544.97 | 0 | 358805.6 | 0 | 0 | 0 | 0 | 0 | 6% | 6.13% | 6.09% | 0.09% |  | 57.33 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23045 | Shotgun Adaptors - 10 Sets | Harry James Kellett | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | FIX | 2024-02-27 | 3 |  |  | 74.76% | 133.8% | 133.8% | 0 | 2.29% | 399276.11 | 298512.88 | 100763.23 | 0 | 214550.47 | 214550.47 | 0 | 0 | 399276.11 | 0 | -7763.23 | 0% | NO | -7763.23 | 0 | 399276.11 | 0 | 0 | 0 | 0 | 0 | 29% | 31.29% | 99.78% | 70.78% |  | 55.76 | [5 empty] | 93000
1735 | 2024-04-24 23:37 | P23432 | Spirit Belfast MRB On-Site Support (Mon & Clear) | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 65.77% | 128.6% | 103.8% | 0 | -11.53% | 449545 | 295665.27 | 153879.73 | 0 | 295665.27 | 451827.33 | 0 | 0 | 380234.75 | 120831.02 | 27430.52 | 0% | NO | 183592.58 | 87914 | 306973.0833 | 0 | 87914.4 | 0 | 0 | 0 | 39% | 27.47% | 0% | -39% |  | 0 | [5 empty] | 112000
1735 | 2024-04-24 23:37 | P23023 | Spirit Shorts R Foster/M Gourley | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 11.3804 | 85.81% | 102% | 88.78% | 0 | -19.11% | 480221.04 | 412054.21 | 68166.83 | 5989.83 | 237621.5 | 267726 | 0 | 0 | 420217.26 | 80.52 | 14202.95 | 237.1% | YES | 44307.45 | 65296 | 365803.9267 | 24971.11 | 19120.72 | 21204.59 | 0 | 0 | 27% | 7.89% | 11.63% | -15.37% |  | 29.65 | [5 empty] | 22366
1735 | 2024-04-24 23:37 | P23372 | BAE Carbon Tooling Off-load | Gary Kempster | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  |  | 100.5% | 95.27% | 56.3% | 0 | -1.13% | 454982.37 | 457433.31 | -2450.94 | 0 | 0 | 0 | 19196.43 | 2450.94 | 435785.94 | 239894.09 | 21647.37 | 0% | NO | 21647.37 | 213917 | 257521.7733 | 0 | 213917.24 | 0 | 0 | 0 | 24% | 22.87% | 20.74% | -3.26% |  | 53.57 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P22906 | Spirit Shorts - MRB JD Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 7.6158 | 95.31% | 84.23% | 66.17% | 99451.32 | -7.86% | 481714 | 459111.18 | 22602.82 | 2967.88 | 0 | 0 | 0 | 0 | 386687.62 | 318.68 | 80423.56 | 2710% | YES | 80423.56 | 99451 | 303811.7867 | 0 | 0 | 0 | 99451.32 | 99451.32 | 13% | 5.14% | 2.51% | -10.49% |  | 36.93 | [5 empty] | 8000
1735 | 2024-04-24 23:37 | P23554 | Dornier Seawings 328 2023 H2 Support | Steven Lawton | 0 | DAX | EXPLEO GERMANY GMBH (EC) | MPE | Level 2 | REIM |  |  |  | 4.037 | 94.04% | 89.56% | 89.56% | 0 | 6.06% | 508481.81 | 478163.35 | 30318.46 | 7510.07 | 4046.44 | 4046.44 | 0 | 0 | 428252.8 | 42.52 | 49910.55 | 664.6% | YES | 49910.55 | 0 | 428252.8 | 0 | 0 | 0 | 0 | 0 | 21% | 27.06% | 23.61% | 2.61% |  | 66.24 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23531 | BAe Systems F35 MRB Support | Richard Brook | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | -55.4206 |  | 94.59% | 89.23% | 0 | 3.31% | 0 | 485273.86 | -485273.86 | 8756.2 | 287.44 | 287.44 | 0 | 485273.86 | 459000.19 | 33.13 | 26273.67 | 300.1% | YES | 26273.67 | 31161 | 433032.69 | 31160.95 | 0 | 0 | 0 | 0 | 25% | 28.31% | 31.62% | 6.62% |  | 59.93 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P22652 | L3 - Saftey Engineering | Sean Simmons | 0 | LHW | L3HARRIS MAPPS LIMITED | EES | Level NC | FIX |  |  |  |  | 95.63% | 86.69% | 86.69% | 0 | 5.66% | 523390 | 500497.5 | 22892.5 | 0 | 0 | 0 | 0 | 0 | 433882.5 | 79938 | 66615 | 0% | NO | 66615 | 0 | 433882.5 | 0 | 0 | 0 | 0 | 0 | 21% | 26.66% | 25.88% | 4.88% |  | 83.05 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23140 | Spirit Shorts A220 MLG Stress Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  | 42.7139 | 65.03% | 113.1% | 69.11% | 0 | -13.3% | 735573.4 | 478318.47 | 257254.93 | 6022.74 | 20870.3 | 87811.88 | 0 | 0 | 540939.4 | 225.66 | -37620.94 | -624.6% | NO | 29320.64 | 252442 | 330571.0667 | 204098.4 | 48343.2 | 0 | 0 | 0 | 25% | 11.7% | -14.83% | -39.83% |  | 45.78 | [5 empty] | 25000
1735 | 2024-04-24 23:37 | P23520 | FCAS AP Portfolio Systems | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 25.4879 | 63.19% | 90.86% | 80.74% | 0 | -6.74% | 810821 | 512364.55 | 298456.45 | 11709.75 | 423 | 423 | 0 | 0 | 465538.44 | 55.21 | 42543.11 | 363.3% | YES | 42543.11 | 62232 | 413678.44 | 0 | 62232.16 | 0 | 0 | 0 | 22% | 15.26% | 16.01% | -5.99% |  | 80.85 | [5 empty] | -4283
1735 | 2024-04-24 23:37 | P23685 | DAC LUC Support and Recompliance | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 46.3191 | 21.56% | 153.2% | 53.49% | 0 | 4.1% | 2180000 | 470001.59 | 1709998.41 | 36917.75 | 0 | 0 | 0 | 0 | 720000 | 58.49 | -201234.41 | -545.1% | NO | -201234.41 | 562288 | 251426.6667 | 0 | 274286.4 | 288001.2 | 0 | 0 | 30% | 34.1% | 34.1% | 4.1% |  | 58.32 | [5 empty] | 48764
1735 | 2024-04-24 23:37 | P23281 | Systems Portfolio | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM | 2024-02-28 | 0 |  |  | 44.43% | 97.31% | 97.31% | 0 | -17.25% | 1177697.24 | 523236.96 | 654460.28 | 0 | 2133.28 | 2133.28 | 0 | 0 | 509179.87 | 15792.1 | 13160.09 | 0% | NO | 13160.09 | 0 | 509179.87 | 0 | 0 | 0 | 0 | 0 | 25% | 7.75% | 100% | 75% |  | 70.48 | [5 empty] | -897
1735 | 2024-04-24 23:37 | P23001 | Spirit Shorts A220 Design | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -20.6471 | 111% | 73.77% | 67.79% | 0 | 11.59% | 486640 | 540103.6 | -53463.6 | 2589.4 | 0 | 0 | 65953.2 | 53463.6 | 398429.7 | 387.17 | 141673.9 | 5471% | YES | 141673.9 | 38738 | 366148.0333 | 9501.6 | 29236.68 | 0 | 0 | 0 | 9% | 20.59% | 11.58% | 2.58% |  | 43.58 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23694 | Systems Portfolio EXP-011a | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 4.6857 | 84.45% | 78.04% | 66.24% | 0 | 2.1% | 648492.8 | 547668.4 | 100824.4 | 21517.38 | 444.4 | 444.4 | 0 | 0 | 427384.31 | 58.72 | 120284.09 | 559% | YES | 120284.09 | 77527 | 362778.4767 | 77526.61 | 0 | 0 | 0 | 0 | 21% | 23.1% | 19.98% | -1.02% |  | 88.75 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23473 | Tempest Vertical Tail | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 14.0883 | 76.22% | 100.6% | 80.1% | 0 | -4.04% | 723866.48 | 551731.74 | 172134.74 | 12218.26 | 101825 | 112425 | 12000 | 0 | 554989.62 | 73.04 | 1742.12 | 14.26% | NO | 12342.12 | 135686 | 441917.9533 | 74168.03 | 61517.7 | 0 | 0 | 0 | 26% | 21.96% | 24.91% | -1.09% |  | 62.46 | [5 empty] | 5000
1735 | 2024-04-24 23:37 | P23366 | Business Analyst Support | Peter Williams | 0 | BDZ | MBDA UK LIMITED | DET | Level 3 | REIM |  |  |  | 50.716 | 22.32% | 194.1% | 170.7% | 0 | 6.41% | 1302200 | 290636.48 | 1011563.52 | 19945.66 | 247149.55 | 416921.86 | 0 | 0 | 564160 | 64.07 | 19611.48 | 98.32% | NO | 189383.79 | 81792 | 496000 | 0 | 81792 | 0 | 0 | 0 | 43% | 49.41% | 28.27% | -14.73% |  | 44.7 | [5 empty] | 293135
1735 | 2024-04-24 23:37 | P23323 | CNC-CMM Programming Support | Stephen Young | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | 2.1399 | 96.93% | 91.18% | 71.34% | 0 | -2.44% | 617809.74 | 598827.95 | 18981.79 | 8870.21 | 15941.56 | 15941.56 | 0 | 0 | 546032.59 | 124.29 | 52795.36 | 595.2% | YES | 52795.36 | 142591 | 427206.7567 | 40305.01 | 102286.46 | 0 | 0 | 0 | 32% | 29.56% | 36.92% | 4.92% |  | 57.36 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23219 | Tornado Air 800 Engineering Support | Richard Brook | 0 | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 3 | REIM |  |  |  | -2.6439 | 102% | 92.18% | 92.18% | 0 | -2.82% | 615046 | 627435.09 | -12389.09 | 4685.85 | 459.21 | 459.21 | 0 | 12389.09 | 578373.17 | 54.49 | 24154.92 | 515.5% | YES | 24154.92 | 0 | 578373.17 | 0 | 0 | 0 | 0 | 0 | 31% | 28.18% | -134.4% | -165.4% |  | 82.46 | [5 empty] | -24907
1735 | 2024-04-24 23:37 | P22790 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | REIM | 2024-03-18 | 0 |  |  | 194.5% | 90.44% | 90.44% | 0 | 1.37% | 352240 | 685262.25 | -333022.25 | 0 | 1611.52 | 1611.52 | 515246 | 333022.25 | 619743.88 | 41098.04 | 34248.37 | 0% | NO | 34248.37 | 0 | 619743.88 | 0 | 0 | 0 | 0 | 0 | 13% | 14.37% | 0% | -13% |  | 45.06 | [5 empty] | -31270
1735 | 2024-04-24 23:37 | P23605 | Typhoon Work Package 2 Continuation | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM |  |  |  | -677.1986 | 119.9% | 83.3% | 4.175% | 70906.73 | 5.13% | 545536.01 | 654246.7 | -108710.69 | 160.53 | 5554 | 5554 | 81999.09 | 108710.69 | 544986.65 | 708.15 | 109260.05 | 68062% | YES | 109260.05 | 621210 | 27311.65 | 18432.36 | 602777.85 | 0 | 0 | 70906.73 | 23% | 28.13% | 28.7% | 5.7% |  | 55.86 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23426 | BAE Tempest WP 3 Harness Maturation | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 8.8353 | 83.25% | 92.61% | 71.07% | 0 | -6.26% | 884012.04 | 735958.72 | 148053.32 | 16757.06 | 213.34 | 213.34 | 0 | 0 | 681568.4 | 86.84 | 54390.32 | 324.6% | YES | 54390.32 | 190206 | 523063.4 | 107757.52 | 82448.95 | 0 | 0 | 0 | 33% | 26.74% | 26.95% | -6.05% |  | 51.65 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23602 | EXP-025 Portfolio Software Engineering Support | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 17.68 | 61.65% | 84.93% | 70.36% | 0 | -0.95% | 1327080 | 818152.24 | 508927.76 | 28785.58 | 2542.8 | 3344.37 | 0 | 0 | 694893.55 | 56.84 | 123258.69 | 428.2% | YES | 124060.26 | 143049 | 575686.05 | 0 | 143049.25 | 0 | 0 | 0 | 24% | 23.05% | 22.76% | -1.24% |  | 83.29 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23451 | BAE Tempest - DFM-ASO Planning | Stephen Young | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | 4.9414 | 90.89% | 72.11% | 32.47% | 27224.9 | -3.2% | 953905.42 | 867020.04 | 86885.38 | 17583.02 | 0 | 0 | 0 | 0 | 625210.17 | 200.83 | 240726.87 | 1369% | YES | 240726.87 | 412472 | 281483.5033 | 57003.88 | 328243.6 | 0 | 27224.9 | 27224.9 | 28% | 24.8% | 26.38% | -1.62% |  | 53.72 | [5 empty] | -1083
1735 | 2024-04-24 23:37 | P23105 | Raytheon Supply Engineering Support | Natalie Sinclair | 0 | RAY | RAYTHEON UNITED KINGDOM LIMITED | MPE | Level 3A | REIM | 2023-07-13 | 2 |  |  | 76.96% | 94.49% | 90.07% | 49156.8 | -2.02% | 1205008 | 927395.25 | 277612.75 | 0 | 0 | 0 | 0 | 0 | 876291.5 | 107644.5 | 48739.75 | 0% | NO | 48739.75 | 49157 | 835327.3333 | 0 | 0 | 49156.8 | 0 | 49156.8 | 26% | 23.98% | 100% | 74% |  | 48.97 | [5 empty] | -2364
1735 | 2024-04-24 23:37 | P23117 | BAE Typhoon Eng Support | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | 2024-03-12 | 11 |  |  | 107.6% | 92.94% | 88.52% | 0 | -1.44% | 950771.99 | 1022826.17 | -72054.18 | 0 | 19090.01 | 21165.02 | 69773.84 | 72054.18 | 950609.41 | 108434.62 | 45120.76 | 0% | NO | 47195.77 | 54290 | 905367.7433 | 0 | 54289.71 | 0 | 0 | 0 | 30% | 28.56% | 0% | -30% |  | 52.3 | [5 empty] | -27096
1735 | 2024-04-24 23:37 | P22350 | EMP 2020-2021 | Natalie Sinclair | 0 | ARY | GUIDANT GLOBAL UK LIMITED | PCPR | Level NC | REIM |  |  |  | 4.2178 | 98.03% | 98.38% | 95.16% | 0 | -2.15% | 1017579.76 | 997504.9 | 20074.86 | 4759.54 | 400 | 400 | 0 | 0 | 981385.51 | 55.72 | 16119.39 | 338.7% | YES | 16119.39 | 38567 | 949246.3433 | 24861.97 | 13704.72 | 0 | 0 | 0 | 32% | 29.85% | 27.11% | -4.89% |  | 44.13 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P22671 | Spirit Shorts Pylon and Fairing Package | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX | 2023-05-03 | 0 |  |  | 105% | 95.26% | 95.26% | 0 | -7.21% | 1198494.77 | 1258071.09 | -59576.32 | 0 | 106494.89 | 106494.89 | 0 | 59576.32 | 1198494.77 | 2544.39 | 2120.32 | 0% | NO | 2120.32 | 0 | 1198494.77 | 0 | 0 | 0 | 0 | 0 | 20% | 12.79% | 0% | -20% |  | 45.4 | [5 empty] | -57456
1735 | 2024-04-24 23:37 | P23292 | BAE Tempest WP 4 AV Trays | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 8.8008 | 87.15% | 102.1% | 78.94% | 0 | 1.64% | 1498284.22 | 1305772.04 | 192512.18 | 21874.41 | 0 | 0 | 0 | 0 | 1332801.4 | 84.62 | -27029.36 | -123.6% | NO | -27029.36 | 362500 | 1030718.0667 | 245826.2 | 116674.18 | 0 | 0 | 0 | 32% | 33.64% | 32.28% | 0.28% |  | 53.64 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23152 | Project Aragon - Design and Stress Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 2.2618 | 98.29% | 77.66% | 55.65% | 0 | -9.55% | 1333452.21 | 1310607.67 | 22844.54 | 10100.09 | 0 | 0 | 0 | 0 | 1017835.58 | 341.86 | 292772.09 | 2899% | YES | 292772.09 | 346248 | 729295.58 | 346247.55 | 0 | 0 | 0 | 0 | 39% | 29.45% | 29.17% | -9.83% |  | 51.95 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23519 | Mechanical and Electrical Design Eng Support | Dushan Fernando | 0 | BAX | SAFRAN SEATS GB LIMITED | MPE | Level 2 | REIM |  |  |  | 14.8928 | 76.59% | 92.16% | 80.43% | 0 | -1.58% | 1807261.3 | 1384216.9 | 423044.4 | 28405.96 | 1004.45 | 1504.45 | 0 | 0 | 1275630.3 | 58.47 | 108586.6 | 382.3% | YES | 109086.6 | 194809 | 1113289.4667 | 194808.9 | 0 | 0 | 0 | 0 | 33% | 31.42% | 31.43% | -1.57% |  | 56.65 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23411 | Agile & Scrum Delivery Service | Peter Williams | 0 | BDZ | MBDA UK LIMITED | DET | Level 2 | REIM | 2023-08-14 | 0 |  |  | 36.3% | 170.5% | 170.5% | 0 | 13.08% | 2487000 | 902903.79 | 1584096.21 | 0 | 894178.59 | 894178.59 | 0 | 0 | 1539600 | 19368.95 | 16140.79 | 0% | NO | 16140.79 | 0 | 1539600 | 0 | 0 | 0 | 0 | 0 | 29% | 42.08% | 0% | -29% |  | 74.57 | [5 empty] | 652837
1735 | 2024-04-24 23:37 | P23315 | DAC LUC BAU and Service Workbench | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX | 2024-02-16 | 0 |  |  | 85.17% | 117.4% | 117.4% | 0 | 3.84% | 1573630 | 1340192.3 | 233437.7 | 0 | 180.3 | 180.3 | 0 | 0 | 1573630 | 0 | 0.3 | 0% | NO | 0.3 | 0 | 1573630 | 0 | 0 | 0 | 0 | 0 | 28% | 31.84% | 47.26% | 19.26% |  | 52.35 | [5 empty] | 233438
1735 | 2024-04-24 23:37 | P22278 | TAI Supply Engineers to Ankara | Natalie Sinclair | 0 | TAI | TUSAS-TURK HAVACILIK VE UZAY | MPE | Level 3A | REIM |  |  |  | 779.2106 | 19.64% | 462.2% | 462.2% | 0 | -15.66% | 2105282 | 413420.91 | 1691861.09 | 2171.25 | 49400.29 | 49400.29 | 0 | 0 | 1910696.33 | 90.2 | 13124.58 | 604.5% | YES | 13124.58 | 0 | 1910696.33 | 0 | 0 | 0 | 0 | 0 | 95% | 79.34% | 70.52% | -24.48% |  | 34.16 | [5 empty] | 1510400
1735 | 2024-04-24 23:37 | P23006 | Spirit Shorts A350 Freighter Toulouse | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -7.927 | 122.4% | 103.3% | 75.22% | 0 | 23.33% | 1341989.92 | 1642072.66 | -300082.74 | 37855.59 | 1086670.26 | 2010741.94 | 0 | 300082.74 | 1695787.93 | 376.42 | 357558.73 | 944.5% | YES | 1281630.41 | 552824 | 1235101.2633 | 140525.66 | 412298.62 | 0 | 0 | 0 | 5% | 28.33% | 54.57% | 49.57% |  | 48.11 | [5 empty] | 411274
1735 | 2024-04-24 23:37 | P23175 | BAe Aero Typhoon Package 2 | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM | 2024-03-12 | 2 |  |  | 103.8% | 96.32% | 96.32% | 0 | -1.63% | 1984265.09 | 2060011.83 | -75746.74 | 0 | 57677.87 | 86030.82 | 15444.64 | 75746.74 | 1984257.03 | 84731.75 | 70609.8 | 0% | NO | 98962.75 | 0 | 1984257.03 | 0 | 0 | 0 | 0 | 0 | 29% | 27.37% | 0% | -29% |  | 51.76 | [5 empty] | -5145
1735 | 2024-04-24 23:37 | P23435 | Andy Baker Portfolio | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 45.7639 | 51.35% | 91.72% | 71.97% | 0 | -7.12% | 4023207.4 | 2066013.78 | 1957193.62 | 42767.2 | 2596.25 | 2596.25 | 0 | 0 | 1894945.09 | 83.01 | 171068.69 | 400% | YES | 171068.69 | 489604 | 1486941.7567 | 0 | 489604.46 | 0 | 0 | 0 | 25% | 17.88% | 19.98% | -5.02% |  | 80.7 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P19020 | Spirit Concessions - 2018 | Carl Warren | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2024-01-23 | 3 |  |  | 90.82% | 111.8% | 107% | 99792.83 | 2.09% | 1914846.83 | 1739018.14 | 175828.69 | 0 | 44317.61 | 44317.61 | 15178.88 | 0 | 1944710.76 | 336177.69 | 196987.38 | 0% | NO | 196987.38 | 99793 | 1861549.9267 | 0 | 0 | 0 | 99792.83 | 99792.83 | 25% | 27.09% | 9.32% | -15.68% |  | 40.87 | [5 empty] | 402680
1735 | 2024-04-24 23:37 | P23257 | BAE Tempest WP 5 Centre Fuselage | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | -4.3678 | 103.3% | 99.04% | 91.44% | 0 | -5.74% | 2106860.71 | 2175748.76 | -68888.05 | 15771.81 | 78100 | 78100 | 158540.8 | 68888.05 | 2154862.7 | 73.63 | 20886.06 | 132.4% | YES | 20886.06 | 198362 | 1989561.0333 | 87999.86 | 110362.14 | 0 | 0 | 0 | 33% | 27.26% | 28.08% | -4.92% |  | 61.05 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23179 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX |  |  |  | -15.7912 | 100.6% | 94.74% | 82.03% | 140266.99 | -9.31% | 2531995.04 | 2546064.98 | -14069.94 | 891 | 156991.12 | 248243.92 | 0 | 14069.94 | 2412235.69 | 794.39 | 133829.29 | 15020% | YES | 225082.09 | 388547 | 2088446.5233 | 0 | 248280.21 | 140266.99 | 0 | 140266.99 | 22% | 12.69% | 17.1% | -4.9% |  | 44.4 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P23207 | A350 Approvers - Design and Stress Support | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  | 2.4971 | 95.03% | 94.82% | 62.34% | 275920.23 | -5.17% | 2728308 | 2592776.41 | 135531.59 | 54275.38 | 35048.69 | 36247.79 | 0 | 0 | 2458482.23 | 117.71 | 134294.18 | 247.4% | YES | 135493.28 | 1010694 | 1616237.23 | 342017.26 | 253420.79 | 415256 | 0 | 275920.23 | 23% | 17.83% | 16.86% | -6.14% |  | 54.56 | [5 empty] | 0
1735 | 2024-04-24 23:37 | P19731 | Hapri HPC Rear Bearing Housing PDR & CDR | Steven Lawton | 0 | ATC | AECC Hunan Aviation Powerplant | MPE | Level 1 | FIX |  |  |  | -2.622 | 100.3% | 99.73% | 87.27% | 447000 | -15.41% | 2980000 | 2987939.22 | -7939.22 | 3027.94 | 366232.13 | 500332.13 | 0 | 7939.22 | 2980000 | 719.46 | -217060.78 | -7169% | NO | -82960.78 | 447000 | 2607500 | 0 | 0 | 0 | 447000 | 447000 | 38% | 22.59% | 14.88% | -23.12% |  | 64.85 | [5 empty] | -225000
1735 | 2024-04-24 23:37 | P23487 | Tornado Air 800 Engineering Support | Richard Brook | 0 | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 2 | FIX |  |  |  | 13.7927 | 79.83% | 83.47% | 72.32% | 38732.48 | -6.42% | 3925502.05 | 3133907.76 | 791594.29 | 57392.35 | 0 | 0 | 0 | 0 | 2616021.67 | 105.11 | 544886.09 | 949.4% | YES | 544886.09 | 419489 | 2266447.5033 | 0 | 380756.59 | 8658.1 | 30074.38 | 38732.48 | 43% | 36.58% | 39.95% | -3.05% |  | 78.74 | [5 empty] | 27000
Extend Table

## AP4-4
WIP No | Date Created | Project ID | Project Description | Project Manager | Agency (1=yes, 0=no) | Department Id | Client | CBU | Complexity | Type | Stop Booking Hrs | Closing Project: Action(s) to close | RAG | Approx. PO Burndown (weeks) | Turnover vs Contract Value | Invoice To Date vs Turnover | Cash in vs Turnover | Open Amount Overdue | Actual PM% to Baseline PM% delta | Contract Value | Total Project Turnover | Contract Value - Total Turnover | Run Rate (based on total turnover) | Total BOI Spend to Date | Total Committed PO (supplier/best shore) | Current AA in PT3 | Exposure (turnover - contract value) | Invoiced To Date | DSO | Unbilled (WIP) | WIP / Run rate | WIP / Run rate >1.3 | WIP + Remaining Committed PO for BOI | Total Open Amount | Cash in (Invoiced - (Open amount -VAT)) | Debt <=30 Days | Debt 31 - 60 Days | Debt 61 - 90 Days | Debt >= 90 Days | Open Amount Overdue2 | Baseline Project Margin | Project To Date (PTD) PM | Year to Date (YTD) PM | YTD Delta Actual PM% to BPM% | Forecast PM at Completion (Manual input from PTT) | Average Sale Rate | CSat score for last quarter (Manual input from PTT) | Comments and Actions | Judged income adjustment at completion | Profit to take now | Provision required now | Fully Traded | Last Months Comments and Actions
1736 | 2024-05-01 23:36 | P23543 | EXP-024 FCAS AP Transformation & Change Enablers | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -26% | 385921 | 0 | 385921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26% | 0% | 0% | -26% |  | 0 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23637 | MBSE Proposal | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 | 0 | 0 | 0 | 49980 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23552 | FCAS AP Product Technology Development | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -25% | 597871 | 0 | 597871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0% | -25% |  | 0 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23711 | DO NOT USE - RAISED IN ERROR | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23585 | Systems Design - Missile Systems, Meteor,Brimstone | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -35% | 0 | 0 | 0 | 0 | 0 | 0 | 49500 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23717 | GKN Ted Tomblin 2024 | Matthew Tweed | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 10047 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23888 | HondaJet assembley Jig | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | FIX | [7 empty] | 0 | -10% | 0 | 0 | 0 | 0 | 0 | 0 | 31500 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 0% | 0% | -10% |  | 0 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23886 | A220 F&DT Support | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [7 empty] | 0 | -18% | 0 | 0 | 0 | 0 | 0 | 0 | 12199.2 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 0% | 0% | -18% |  | 0 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23887 | EXP-039 Future Systems Synthetic Test Support | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -18% | 156475 | 0 | 156475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 0% | 0% | -18% |  | 0 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23730 | FLE Project | Carl Warren | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -18.03% | 0 | 1120 | -1120 | 0 | 0 | 0 | 24000 | 1120 | 0 | 126.61 | 1120 | 0% | NO | 1120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | -18.03% | -18.03% | -18.03% |  | 35 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23463 | A220 Wing MaMo Design Checking | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-03-07 | 0 |  |  |  | 0% | 0% | 0 | 7.85% | 0 | 1628 | -1628 | 0 | 0 | 0 | 15000 | 1628 | 0 | 1953.6 | 1628 | 0% | NO | 1628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | 10.85% | 0% | -3% |  | 44 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23881 | Bulldog Fuel System Design | Trevin Fernandopulle | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM |  |  |  | 3 | 25% | 0% | 0% | 0 | 1.29% | 8288 | 2072 | 6216 | 2072 | 0 | 0 | 0 | 0 | 0 | 7 | 2072 | 100% | NO | 2072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13% | 14.29% | 14.29% | 1.29% |  | 56 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23843 | EXP-035 FT15 Exemplar information set | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 268.0607 | 1.47% | 0% | 0% | 0 | -14.14% | 175985.16 | 2587.42 | 173397.74 | 646.86 | 0 | 0 | 0 | 0 | 0 | 42 | 2587.42 | 400% | YES | 2587.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 5.86% | 5.86% | -14.14% |  | 63.88 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P21028 | Rebate Collection (BACC) | David Catchpole | 0 | TOO | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | [5 empty] | 0% | 0% | 0 | 0% | 0 | 2680 | -2680 | 0 | 2680 | 2680 | 0 | 2680 | 0 | 3216 | 2680 | 0% | NO | 2680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23880 | Warrior Crew Heater Design | Trevin Fernandopulle | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM |  |  |  | 0.92233 | 52.02% | 0% | 0% | 0 | 3.58% | 5544 | 2884 | 2660 | 2884 | 0 | 0 | 0 | 0 | 0 | 14 | 2884 | 100% | NO | 2884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32% | 35.58% | 35.58% | 3.58% |  | 56 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23578 | ESN Work Package | Hannah Mead | 0 | COZ | CHELTON LIMITED | DET | Level 3 | FIX | 2024-01-01 | 0 |  |  | 86.17% | 116.1% | 116.1% | 0 | 35.86% | 4410 | 3800 | 610 | 0 | 0 | 0 | 0 | 0 | 4410 | 0 | -610 | 0% | NO | -610 | 0 | 4410 | 0 | 0 | 0 | 0 | 0 | 24% | 59.86% | 0% | -24% |  | 95 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23628 | Design Assurance | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -6.67% | 0 | 3909.24 | -3909.24 | 0 | 0 | 0 | 4454.8 | 3909.24 | 0 | 4691.09 | 3909.24 | 0% | NO | 3909.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 0.33% | 0% | -7% |  | 15.05 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23864 | REACH Coordinator | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 29.2683 | 9.297% | 0% | 0% | 0 | -10.24% | 52920 | 4920 | 48000 | 1640 | 0 | 0 | 0 | 0 | 0 | 42 | 4920 | 300% | YES | 4920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27% | 16.76% | 16.76% | -10.24% |  | 30 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23873 | FCAS Systems Engineering Support | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | -2 |  | 0% | 0% | 0 | 8.28% | 0 | 5809 | -5809 | 2904.5 | 0 | 0 | 26604 | 5809 | 0 | 14 | 5809 | 200% | YES | 5809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 8.28% | 8.28% | 8.28% |  | 78.5 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23002 | WoT MAJ Transit Flag Stress | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2024-04-03 | 1 |  | 4.7688 | 62.41% | 160.2% | 160.2% | 0 | 38.54% | 4735 | 2955.29 | 1779.71 | 373.2 | 1492.79 | 2242.5 | 0 | 0 | 4735 | 91.03 | 1493.29 | 400.1% | YES | 2243 | 0 | 4735 | 0 | 0 | 0 | 0 | 0 | 10% | 48.54% | 0% | -10% |  | 45 | [5 empty] | 3273
1736 | 2024-05-01 23:36 | P23607 | SAFRAN - A330neo Turnover Frame | Gary Kempster | 0 | TOO | SAFRAN SEATS GB LIMITED | MPE | Level 3 | FIX |  |  |  |  | 95.69% | 104.5% | 104.5% | 0 | -19.52% | 8736 | 8359.05 | 376.95 | 0 | 0 | 0 | 0 | 0 | 8736 | 0.06 | 0.05 | 0% | NO | 0.05 | 0 | 8736 | 0 | 0 | 0 | 0 | 0 | 23% | 3.48% | 8.5% | -14.5% |  | 50.46 | [5 empty] | 377
1736 | 2024-05-01 23:36 | P23274 | ME Support (Aim Altitude - Cambridge) | Trevor Knox | 0 | AVI | AVIC CABIN SYSTEMS (UK) LIMITED | ME | Level 3 | FIX | 2023-08-18 | 0 |  |  | 51.88% | 56.3% | 56.3% | 0 | -0.17% | 17280 | 8964 | 8316 | 0 | 0 | 0 | 0 | 0 | 5046.3 | 4701.24 | 3917.7 | 0% | NO | 3917.7 | 0 | 5046.3 | 0 | 0 | 0 | 0 | 0 | 21% | 20.83% | 0% | -21% |  | 48 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23283 | Spirit Tooling Audit | Charidimos Valadakis | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-05-03 | 0 |  |  | 97.22% | 48.57% | 48.57% | 0 | -7.99% | 9910.08 | 9634.8 | 275.28 | 0 | 0 | 0 | 0 | 0 | 4679.76 | 5946.05 | 4955.04 | 0% | NO | 4955.04 | 0 | 4679.76 | 0 | 0 | 0 | 0 | 0 | 7% | -0.99% | 0% | -7% |  | 34.41 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23127 | Loft Hall Design Support | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-04-19 | 0 |  |  | 101% | 99.06% | 99.06% | 0 | -9.55% | 9680 | 9772 | -92 | 0 | 0 | 0 | 0 | 92 | 9680 | 110.4 | 92 | 0% | NO | 92 | 0 | 9680 | 0 | 0 | 0 | 0 | 0 | 41% | 31.45% | 0% | -41% |  | 44 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23630 | 2Excel CFD Analysis Support | Dushan Fernando | 0 | BAX | STIRLING DYNAMICS LTD | MPE | Level NC | FIX |  |  |  |  | 61.2% | 100% | 100% | 0 | -1.87% | 16195.49 | 9911.34 | 6284.15 | 0 | 0 | 0 | 0 | 0 | 9911.63 | 0 | -0.29 | 0% | NO | -0.29 | 0 | 9911.63 | 0 | 0 | 0 | 0 | 0 | 26% | 24.13% | 0% | -26% |  | 64.78 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23842 | Tranche 1 Evolution Package Step 2 | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -4.0947 |  | 0% | 0% | 0 | -15.35% | 0 | 9927.77 | -9927.77 | 2424.55 | 1000 | 1000 | 67488.9 | 9927.77 | 0 | 42 | 9927.77 | 409.5% | YES | 9927.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31% | 15.65% | 15.65% | -15.35% |  | 54.97 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23718 | Requalification of EJ200 GSS ESS EHM SW module | Vijayakumara Nanjundappa | 0 | ARZ | MTU AERO ENGINES AG | DET | Level 3 | FIX |  |  |  | 72.6683 | 12.17% | 200% | 200% | 0 | 11.99% | 74463 | 9061.57 | 65401.43 | 900 | 991.93 | 991.93 | 0 | 0 | 18125 | 0 | -7063.43 | -784.8% | NO | -7063.43 | 0 | 18125 | 0 | 0 | 0 | 0 | 0 | 28% | 39.99% | 39.99% | 11.99% |  | 80 | [5 empty] | 2000
1736 | 2024-05-01 23:36 | P23869 | EXP-037 Land Ceptor Development Hardware Test Def | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 24.7325 | 7.482% | 72.69% | -0.0006025% | 0 | 0.81% | 162694 | 12171.97 | 150522.03 | 6085.99 | 0 | 0 | 0 | 0 | 8848.26 | 35 | 3323.71 | 54.61% | NO | 3323.71 | 10618 | -0.073333 | 10617.91 | 0 | 0 | 0 | 0 | 26% | 26.81% | 26.81% | 0.81% |  | 89.83 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23313 | Laser Trim Fixtures | Gary Kempster | 0 | TOO | ALKEN ENGINEERING LIMITED | MPE | Level 3 | FIX | 2023-11-20 | 0 |  |  | 89.87% | 111.3% | 111.3% | 0 | 0.53% | 13770 | 12375 | 1395 | 0 | 0 | 0 | 0 | 0 | 13770 | 0 | -1395 | 0% | NO | -1395 | 0 | 13770 | 0 | 0 | 0 | 0 | 0 | 17% | 17.53% | 0% | -17% |  | 45 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P22761 | Red Bull Chassis Spit | Trevor Knox | 0 | TOO | MANUFAX ENGINEERING LTD | MPE | Level 3 | FIX | 2022-11-15 | 0 |  |  | 72.18% | 96.98% | 96.98% | 0 | 7.92% | 12961.2 | 9355.5 | 3605.7 | 0 | 0 | 0 | 0 | 0 | 9072.84 | 4666.39 | 3888.66 | 0% | NO | 3888.66 | 0 | 9072.84 | 0 | 0 | 0 | 0 | 0 | 23% | 30.92% | 0% | -23% |  | 42.19 | [5 empty] | 3606
1736 | 2024-05-01 23:36 | P23350 | Spirit 2023 - Stress Approve Man Serv (DH) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 14.15% | 72.64% | 72.64% | 0 | -0.29% | 97920 | 13860 | 84060 | 0 | 0 | 0 | 0 | 0 | 10068 | 4550.4 | 3792 | 0% | NO | 3792 | 0 | 10068 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23344 | Spirit A320 Spoilers Support 2023 | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 38.75% | 100% | 100% | 0 | 5.82% | 35786.4 | 13867.23 | 21919.17 | 0 | 0 | 0 | 0 | 0 | 13867.23 | 0 | 0 | 0% | NO | 0 | 0 | 13867.23 | 0 | 0 | 0 | 0 | 0 | 7% | 12.82% | 0% | -7% |  | 34.41 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23337 | Spirit 2023 - Steve Grimley | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 25.28% | 100% | 100% | 0 | 0.01% | 56812.9 | 14362.47 | 42450.43 | 0 | 0 | 0 | 0 | 0 | 14362.47 | 0 | 0 | 0% | NO | 0 | 0 | 14362.47 | 0 | 0 | 0 | 0 | 0 | 7% | 7.01% | 0% | -7% |  | 30.11 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23874 | Environmental Engineering (Sea Venom/ANL) | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | -2 |  | 0% | 0% | 0 | 18.72% | 0 | 14915 | -14915 | 7457.5 | 0 | 0 | 27140.5 | 14915 | 0 | 21 | 14915 | 200% | YES | 14915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 18.72% | 18.72% | 18.72% |  | 78.5 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23597 | MRB Onsite support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-02-16 | 1 |  |  |  | 0% | 0% | 0 | -10.04% | 0 | 15100.57 | -15100.57 | 0 | 9448.07 | 17381.62 | 24200 | 15100.57 | 0 | 125.94 | 15100.57 | 0% | NO | 23034.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 7.96% | 8.95% | -9.05% |  | 42.5 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23635 | Engineering Services: FAI Support | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 49.9% | 100% | 0.0008972% | 0 | -3.4% | 37230 | 18576 | 18654 | 0 | 0 | 0 | 0 | 0 | 18576 | 682.5 | 0 | 0% | NO | 0 | 22291 | 0.16667 | 7058.88 | 15232.32 | 0 | 0 | 0 | 8% | 4.6% | 5.04% | -2.96% |  | 38.7 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23343 | Spirit 2023 - John Agnew | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-08-09 | 0 |  |  | 28.56% | 86.27% | 86.27% | 0 | -0.02% | 65120.37 | 18600.89 | 46519.48 | 0 | 0 | 0 | 0 | 0 | 16047.15 | 3064.49 | 2553.74 | 0% | NO | 2553.74 | 0 | 16047.15 | 0 | 0 | 0 | 0 | 0 | 7% | 6.98% | 0% | -7% |  | 34.51 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23663 | Spirit Tooling Verification and Inspection | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | -0.75 | 103.1% | 83.84% | 0.001696% | 0 | -7.41% | 19820.16 | 20439.54 | -619.38 | 825.84 | 0 | 0 | 7392 | 619.38 | 17136.18 | 174.93 | 3303.36 | 400% | YES | 3303.36 | 20563 | 0.34667 | 12635.35 | 7928.06 | 0 | 0 | 0 | 12% | 4.59% | 4.82% | -7.18% |  | 34.41 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23839 | Stirling Dynamics - ST002-GFEM | Matthew Dodd | 0 | BAX | STIRLING DYNAMICS LTD | MPE | Level NC | FIX |  |  |  | -43.6938 |  | 0% | 0% | 0 | -4.93% | 0 | 20505.95 | -20505.95 | 469.31 | 1225.5 | 1225.5 | 19985.76 | 20505.95 | 0 | 91 | 20505.95 | 4369% | YES | 20505.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 2.07% | 2.07% | -4.93% |  | 43.72 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23355 | Spirit Tooling Support 2023 | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-23 | 0 |  |  | 22.93% | 89.02% | 89.02% | 0 | -0.82% | 91800 | 21053.34 | 70746.66 | 0 | 0 | 0 | 0 | 0 | 18742.5 | 2773.01 | 2310.84 | 0% | NO | 2310.84 | 0 | 18742.5 | 0 | 0 | 0 | 0 | 0 | 20% | 19.18% | 0% | -20% |  | 44.46 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23742 | Cyber Security Support | Hannah Mead | 0 | COZ | CHELTON LIMITED | DET | Level 3 | FIX |  |  |  | 2.9333 | 84% | 0% | 0% | 0 | -0.96% | 27500 | 23100 | 4400 | 1500 | 0 | 0 | 0 | 0 | 0 | 107.8 | 23100 | 1540% | YES | 23100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32% | 31.04% | 31.04% | -0.96% |  | 100 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23351 | Spirit 2023 - Design Man Serv (KL) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 26.47% | 93.15% | 93.15% | 0 | 0.09% | 93840 | 24840 | 69000 | 0 | 0 | 0 | 0 | 0 | 23138 | 2042.4 | 1702 | 0% | NO | 1702 | 0 | 23138 | 0 | 0 | 0 | 0 | 0 | 26% | 26.09% | 0% | -26% |  | 46 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23356 | Spirit 2023 - Design Man Serv (AH) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX | 2023-08-09 | 1 |  |  |  | 76.66% | 0.001332% | 23018.4 | 0.48% | 0 | 25023.08 | -25023.08 | 0 | 0 | 0 | 25300 | 25023.08 | 19182 | 30027.7 | 5841.08 | 0% | NO | 5841.08 | 23018 | 0.33333 | 0 | 0 | 0 | 23018.4 | 23018.4 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P22884 | Spirit Shorts Config Eng | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 66.3% | 100.1% | 100.1% | 0 | 0.56% | 38976 | 25841.9 | 13134.1 | 0 | 0 | 0 | 0 | 0 | 25863.2 | 0 | -0.3 | 0% | NO | -0.3 | 0 | 25863.2 | 0 | 0 | 0 | 0 | 0 | 7% | 7.56% | 0% | -7% |  | 20.3 | [5 empty] | 21
1736 | 2024-05-01 23:36 | P23354 | Spirit 2023 - Design Man Serv (PC) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 27.97% | 99.36% | 99.36% | 0 | 0.48% | 93840 | 26248.98 | 67591.02 | 0 | 0 | 0 | 0 | 0 | 26082 | 200.38 | 166.98 | 0% | NO | 166.98 | 0 | 26082 | 0 | 0 | 0 | 0 | 0 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P22756 | A350 FLE Design Checker | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2022-03-23 | 1 |  |  | 68.39% | 119.7% | 119.7% | 0 | 16.46% | 34898.4 | 23867.15 | 11031.25 | 0 | 23867.15 | 24342.3 | 0 | 0 | 28571.1 | 0.06 | 0.05 | 0% | NO | 475.2 | 0 | 28571.1 | 0 | 0 | 0 | 0 | 0 | 0% | 16.46% | 0% | 0% |  | 0 | [5 empty] | 4704
1736 | 2024-05-01 23:36 | P23433 | Cavendish | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 3.0436 | 70.97% | 46.23% | 46.23% | 0 | -0.42% | 42240 | 29976.4 | 12263.6 | 4029.3 | 0 | 0 | 0 | 0 | 13859.2 | 91 | 16117.2 | 400% | YES | 16117.2 | 0 | 13859.2 | 0 | 0 | 0 | 0 | 0 | 7% | 6.58% | 6.51% | -0.49% |  | 46.22 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23831 | Contract DM/00113 for maintenance, repair and post | Harry James Kellett | 0 | BXW | MOD | EES | Level 2 | FIX |  |  |  | 3.1233 | 73.97% | 0% | 0% | 0 | 14.02% | 40800 | 30177.76 | 10622.24 | 3401.02 | 0 | 0 | 0 | 0 | 0 | 91 | 30177.76 | 887.3% | YES | 30177.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37% | 51.02% | 51.02% | 14.02% |  | 80.26 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23724 | GKN S McConnell 2024 | Matthew Tweed | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  | 11.2 | 60.8% | 100% | -0.0009024% | 0 | 0.79% | 49820 | 30290.59 | 19529.41 | 1743.7 | 0 | 0 | 0 | 0 | 30290.56 | 118.22 | 0.03 | 0.00172% | NO | 0.03 | 36349 | -0.27333 | 19130.88 | 8848.03 | 8369.76 | 0 | 0 | 19% | 19.79% | 19.79% | 0.79% |  | 49.58 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23458 | Spirit Belfast Tooling Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-08-11 | 0 |  |  | 101.3% | 94.65% | 94.65% | 0 | 8.64% | 30384 | 30784.9 | -400.9 | 0 | 0 | 0 | 0 | 400.9 | 29139.1 | 1974.96 | 1645.8 | 0% | NO | 1645.8 | 0 | 29139.1 | 0 | 0 | 0 | 0 | 0 | 7% | 15.64% | 0% | -7% |  | 42.2 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23740 | Phase 2 - EJ200 ESS EHM Platform Migration | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 3 | FIX |  |  |  | 46.6406 | 16.07% | 266.7% | 88.9% | 0 | 10.4% | 175971 | 28277.5 | 147693.5 | 3166.63 | 0 | 0 | 0 | 0 | 75417 | 25.22 | -43139.5 | -1362% | NO | -43139.5 | 60334 | 25138.6667 | 30166.8 | 30166.8 | 0 | 0 | 0 | 28% | 38.4% | 38.4% | 10.4% |  | 43.34 | [5 empty] | 4000
1736 | 2024-05-01 23:36 | P23811 | Spirit T300 MRB Concessions | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -11.0828 |  | 0% | 0% | 0 | -7.18% | 0 | 33014.16 | -33014.16 | 2978.87 | 0 | 0 | 34639 | 33014.16 | 0 | 77 | 33014.16 | 1108% | YES | 33014.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21% | 13.82% | 13.82% | -7.18% |  | 46.81 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23365 | GKN 777x Lip Skin Fixture | Steven Lawton | 0 | TOO | GKN AEROSPACE SERVICES LTD | MPE | Level 3 | FIX | 2023-10-12 | 0 |  |  | 41.91% | 113.2% | 113.2% | 0 | -9.26% | 79161.46 | 33175.67 | 45985.79 | 0 | 5109.88 | 5109.88 | 0 | 0 | 37544.22 | 0 | -4368.55 | 0% | NO | -4368.55 | 0 | 37544.22 | 0 | 0 | 0 | 0 | 0 | 22% | 12.74% | 0% | -22% |  | 56 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23651 | PMO Spirit | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 11.3867 | 68.81% | 69.16% | -0.0004915% | 0 | -19.29% | 49284 | 33912 | 15372 | 1350 | 0 | 0 | 0 | 0 | 23454 | 232.94 | 10458 | 774.7% | YES | 10458 | 28145 | -0.16667 | 0 | 28144.8 | 0 | 0 | 0 | 43% | 23.71% | 23.13% | -19.87% |  | 36 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23338 | Spirit 2023 - Blair Hainey | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 0.14865 | 99.71% | 52.46% | 52.46% | 0 | 5.22% | 34494.36 | 34393.82 | 100.54 | 676.36 | 0 | 0 | 0 | 0 | 18042.36 | 182.51 | 16351.46 | 2418% | YES | 16351.46 | 0 | 18042.36 | 0 | 0 | 0 | 0 | 0 | 7% | 12.22% | 17.98% | 10.98% |  | 18.28 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P22768 | MRB Onsite Support - Spirit Belfast | Trevor Knox | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2023-07-27 | 0 |  |  |  | 0% | 0% | 0 | -17.07% | 0 | 34614 | -34614 | 0 | 0 | 0 | 36800 | 34614 | 0 | 41536.8 | 34614 | 0% | NO | 34614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | -7.07% | 0% | -10% |  | 36 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23347 | WoT Fixed Leading Edge - Industrial 2023 | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 112.8% | 42.03% | 42.03% | 0 | -0.41% | 31034.12 | 35002.1 | -3967.98 | 0 | 0 | 0 | 10500 | 3967.98 | 14710.56 | 24349.85 | 20291.54 | 0% | NO | 20291.54 | 0 | 14710.56 | 0 | 0 | 0 | 0 | 0 | 7% | 6.59% | 0% | -7% |  | 32.26 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23823 | EXP-034 Spear 3 Test Equip Requirement Authority | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 12.4143 | 41.85% | 86.2% | 0.0008259% | 0 | -0.08% | 85825 | 35919.63 | 49905.37 | 4020 | 1000 | 1000 | 0 | 0 | 30961.13 | 77 | 4958.5 | 123.3% | NO | 4958.5 | 37153 | 0.29667 | 15494.7 | 21658.66 | 0 | 0 | 0 | 14% | 13.92% | 13.92% | -0.08% |  | 94.25 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23821 | Supply of Safety Engineer | Dinna Elkhalifa | 0 | BXW | STIRLING DYNAMICS LTD | EES | Level NC | REIM |  |  |  | -3.8294 | 106.6% | 49% | -0.0006437% | 22765.86 | 45.1% | 34006.44 | 36247.77 | -2241.33 | 585.29 | 0 | 0 | 0 | 2241.33 | 17760.6 | 113.97 | 18487.17 | 3159% | YES | 18487.17 | 21313 | -0.23333 | -1453.14 | 22765.86 | 0 | 0 | 22765.86 | 0% | 45.1% | 45.1% | 45.1% |  | 80.73 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23051 | Spirit Shorts A350 PAX Door | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3A | REIM |  |  |  |  | 205.9% | 105.4% | 105.4% | 0 | -0.63% | 18216 | 37513 | -19297 | 0 | 0 | 0 | 0 | 19297 | 39537 | 0 | 0 | 0% | NO | 0 | 0 | 39537 | 0 | 0 | 0 | 0 | 0 | 30% | 29.37% | 0% | -30% |  | 46 | [5 empty] | 2024
1736 | 2024-05-01 23:36 | P22752 | Tooling WoT - 2021 (Spirit) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | REIM | 2023-05-03 | 0 |  |  | 101.1% | 74.02% | 74.02% | 0 | -8.5% | 41525.1 | 41982.28 | -457.18 | 0 | 0 | 0 | 0 | 457.18 | 31076.1 | 13087.42 | 10906.18 | 0% | NO | 10906.18 | 0 | 31076.1 | 0 | 0 | 0 | 0 | 0 | 0% | -8.5% | 0% | 0% |  | 39.09 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23598 | MRB Onsite support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 32.599 | 34.53% | 0% | 0% | 0 | -10.79% | 133056 | 45945.17 | 87110.83 | 2672.19 | 8736.42 | 14079.58 | 0 | 0 | 0 | 98.24 | 45945.17 | 1719% | YES | 51288.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 17.21% | 17.55% | -10.45% |  | 42.5 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23339 | Spirit 2023 - Stewart Russell | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 64.51% | 100% | 100% | 0 | 0.62% | 72766.8 | 46941.72 | 25825.08 | 0 | 0 | 0 | 0 | 0 | 46941.74 | 0 | -0.02 | 0% | NO | -0.02 | 0 | 46941.74 | 0 | 0 | 0 | 0 | 0 | 7% | 7.62% | 0% | -7% |  | 35.67 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23760 | EXP-033 Systems Engineering Support | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 34.6543 | 33.57% | 93.84% | 49.88% | 0 | -0.02% | 142300 | 47767.25 | 94532.75 | 2727.88 | 0 | 0 | 0 | 0 | 44823.5 | 59.18 | 2943.75 | 107.9% | NO | 2943.75 | 25199 | 23824.3333 | 12387.3 | 12811.2 | 0 | 0 | 0 | 29% | 28.98% | 28.98% | -0.02% |  | 78.5 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23642 | MRB Belfast Support | Carl Warren | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -28.0569 |  | 0% | 0% | 0 | -44.12% | 0 | 50845.27 | -50845.27 | 1812.22 | 3566.12 | 3566.12 | 48125 | 50845.27 | 0 | 187.46 | 50845.27 | 2806% | YES | 50845.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22% | -22.12% | -24.5% | -46.5% |  | 38.52 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P22760 | SA Leading Edge Transport Media ('A' Frames) | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-11-15 | 1 |  |  | 85.99% | 110.7% | 116.3% | -3082.8 | 3.97% | 53480.8 | 45985.5 | 7495.3 | 0 | 42804 | 42804 | 0 | 0 | 50911.8 | 0 | -0.3 | 0% | NO | -0.3 | -3083 | 53480.9667 | 0 | 0 | 0 | -3082.8 | -3082.8 | 6% | 9.97% | 0% | -6% |  | 42 | [5 empty] | 4926
1736 | 2024-05-01 23:36 | P23349 | Spirit 2023 - Stress Approve Man Serv (SB) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 58.24% | 80.05% | 80.05% | 0 | -0.29% | 97920 | 57024 | 40896 | 0 | 0 | 0 | 0 | 0 | 45648 | 13651.2 | 11376 | 0% | NO | 11376 | 0 | 45648 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23322 | GKN T Tomblin 2023 | Steven Lawton | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2024-04-15 | 1 |  |  | 99.66% | 100% | 95.06% | 0 | -0.33% | 58952 | 58752 | 200 | 0 | 0 | 0 | 0 | 0 | 58752 | 39.05 | 0 | 0% | NO | 0 | 3485 | 55847.8333 | 0 | 3484.8 | 0 | 0 | 0 | 17% | 16.67% | 16.67% | -0.33% |  | 48 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23106 | ME Support to NPD - Bobby Haggart | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  |  | 95.79% | 97.03% | 97.03% | 0 | 0.3% | 65675 | 62912.11 | 2762.89 | 0 | 0 | 0 | 0 | 0 | 61042.75 | 2243.24 | 1869.36 | 0% | NO | 1869.36 | 0 | 61042.75 | 0 | 0 | 0 | 0 | 0 | 15% | 15.3% | 0% | -15% |  | 35.65 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P22967 | Spirit 2022 - Channapa Laxmeshwar | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2023-01-26 | 2 |  |  | 69.69% | 121.3% | 121.3% | 0 | 9.53% | 75159.1 | 52376.15 | 22782.95 | 0 | 52376.15 | 54898.1 | 0 | 0 | 63508.8 | 0.42 | 0.35 | 0% | NO | 2522.3 | 0 | 63508.8 | 0 | 0 | 0 | 0 | 0 | 8% | 17.53% | 0% | -8% |  | 0 | [5 empty] | 11133
1736 | 2024-05-01 23:36 | P23193 | Spirit Shorts Stephen Greer | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -7.1528 | 108.2% | 91.28% | 82.17% | 0 | 8.69% | 61472 | 66513.69 | -5041.69 | 704.86 | 0 | 0 | 10878 | 5041.69 | 60712.78 | 130.1 | 5800.91 | 823% | YES | 5800.91 | 7269 | 54655.28 | 0 | 7268.72 | 0 | 0 | 0 | 23% | 31.69% | 34.03% | 11.03% |  | 35.13 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23341 | Spirit 2023 - Tom McFarlane | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 40.7876 | 62.79% | 94.19% | 63.04% | 7110.19 | -0.01% | 108666.4 | 68236.91 | 40429.49 | 991.22 | 0 | 0 | 0 | 0 | 64272.02 | 166.7 | 3964.89 | 400% | YES | 3964.89 | 25503 | 43019.52 | 16061.8 | 2331.04 | 0 | 7110.19 | 7110.19 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23877 | Strategic Enablement | Owain Jones | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -2 |  | 0% | 0% | 0 | -16.99% | 0 | 71017.3 | -71017.3 | 35508.65 | 4000 | 4000 | 67200 | 71017.3 | 0 | 93.04 | 71017.3 | 200% | YES | 71017.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 1.01% | 1.01% | -16.99% |  | 42 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23700 | IPDT Leads | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 18.2228 | 43.53% | 33.84% | -0.0005158% | 0 | -1.57% | 169263.9 | 73678.91 | 95584.99 | 5245.36 | 0 | 0 | 0 | 0 | 24932.12 | 129.41 | 48746.79 | 929.3% | YES | 48746.79 | 29919 | -0.38 | 0 | 29918.54 | 0 | 0 | 0 | 26% | 24.43% | 22.75% | -3.25% |  | 50.12 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23600 | MBDA EXP-EE-023 Bristone Certification | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 59.65% | 100% | 100% | 0 | 0.4% | 126600 | 75517 | 51083 | 0 | 0 | 0 | 0 | 0 | 75517 | 0 | 0 | 0% | NO | 0 | 0 | 75517 | 0 | 0 | 0 | 0 | 0 | 41% | 41.4% | 0% | -41% |  | 78.5 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23080 | Spirit Shorts DManagement Cairan Cullen | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 1525.5016 | 50.9% | 97.44% | 90.78% | 3787.8 | -1.26% | 149600 | 76147.1 | 73452.9 | 48.15 | 0 | 0 | 0 | 0 | 74199.7 | 203.74 | 1947.4 | 4044% | YES | 1947.4 | 6086 | 69128.0333 | 0 | 2298.36 | 0 | 3787.8 | 3787.8 | 24% | 22.74% | 13.03% | -10.97% |  | 44.39 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P22505 | Spirit MRB Engineering Support 2021 | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 1 |  |  | 91.17% | 100% | 95.78% | 4020.48 | 21.2% | 87110.4 | 79414.95 | 7695.45 | 0 | 0 | 0 | 0 | 0 | 79414.95 | 4020.48 | 0 | 0% | NO | 0 | 4020 | 76064.95 | 0 | 0 | 0 | 4020.48 | 4020.48 | 0% | 21.2% | 0% | 0% |  | 41.88 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23560 | NJEWCS TAF202302 SM | Natalie Sinclair | 0 | COB | CHELTON LIMITED | EES | Level 2 | FIX |  |  |  |  | 97.96% | 100.2% | 50.1% | 0 | 11.94% | 81500 | 79836.44 | 1663.56 | 0 | 0 | 0 | 0 | 0 | 80000 | 275.85 | -163.57 | 0% | NO | -163.57 | 48000 | 40000 | 48000 | 0 | 0 | 0 | 0 | 28% | 39.94% | 39.49% | 11.49% |  | 73.01 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23729 | Honda Tooling | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | FIX |  |  |  | 6.72 | 70.89% | 40.29% | 0% | 0 | 3.04% | 113610 | 80535 | 33075 | 4921.88 | 0 | 0 | 0 | 0 | 32445 | 111.19 | 48090 | 977.1% | YES | 48090 | 38934 | 0 | 0 | 38934 | 0 | 0 | 0 | 10% | 13.04% | 13.04% | 3.04% |  | 42 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P22885 | ME Support (Baxi) | Trevor Knox | 0 | HUV | BAXI HEATING UK LIMITED | ME | Level 3 | FIX | 2023-01-12 | 0 |  |  | 68.78% | 108.7% | 108.7% | 0 | 13.05% | 106632.96 | 73340.24 | 33292.72 | 0 | 0 | 0 | 0 | 0 | 79748.12 | 1531.35 | 1276.12 | 0% | NO | 1276.12 | 0 | 79748.12 | 0 | 0 | 0 | 0 | 0 | 15% | 28.05% | 0% | -15% |  | 44.37 | [5 empty] | 7684
1736 | 2024-05-01 23:36 | P23744 | Model Factory | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 32.3963 | 30.83% | 110.6% | 28.27% | 0 | 9.01% | 262300 | 80862.75 | 181437.25 | 5600.56 | 0 | 0 | 0 | 0 | 89432 | 86.28 | -5569.25 | -99.44% | NO | -5569.25 | 79889 | 22857.8333 | 27429.6 | 26229.6 | 26229.6 | 0 | 0 | 28% | 37.01% | 37.01% | 9.01% |  | 50.79 | [5 empty] | 3000
1736 | 2024-05-01 23:36 | P22965 | Spirit 2022 - Design Man Serv (AH) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 106.7% | 96.66% | 96.66% | 0 | 3.14% | 80079.56 | 85441.32 | -5361.76 | 0 | 0 | 0 | 0 | 5361.76 | 82588.96 | 3422.84 | 2852.36 | 0% | NO | 2852.36 | 0 | 82588.96 | 0 | 0 | 0 | 0 | 0 | 14% | 17.14% | 0% | -14% |  | 42.44 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23523 | Applique Armour Support | Dushan Fernando | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-18 | 1 |  |  | 72.43% | 138.1% | 98.47% | 40680 | 3.42% | 118200 | 85606.5 | 32593.5 | 0 | 0 | 0 | 0 | 0 | 118200 | 1567.8 | -32593.5 | 0% | NO | -32593.5 | 40680 | 84300 | 0 | 40680 | 0 | 0 | 40680 | 25% | 28.42% | 0% | -25% |  | 64.29 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P22964 | Spirit 2022 - MRB Man Serv (JC) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 100.6% | 97.95% | 97.95% | 0 | 1.91% | 85435.2 | 85960.26 | -525.06 | 0 | 0 | 0 | 0 | 525.06 | 84199.74 | 2112.62 | 1760.52 | 0% | NO | 1760.52 | 0 | 84199.74 | 0 | 0 | 0 | 0 | 0 | 16% | 17.91% | 0% | -16% |  | 42.69 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P22963 | Spirit 2022 - Design Man Serv (PC) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 108.6% | 104% | 104% | 0 | 3.18% | 80079.56 | 86926.74 | -6847.18 | 0 | 0 | 0 | 0 | 6847.18 | 90389.95 | 0 | -3463.21 | 0% | NO | -3463.21 | 0 | 90389.95 | 0 | 0 | 0 | 0 | 0 | 13% | 16.18% | 0% | -13% |  | 42.39 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23342 | Spirit 2023 - Channapa Laxmeshwar | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 237.5059 | 53.17% | 109.3% | 73.25% | 4036.8 | -3.73% | 158696.7 | 84385.85 | 74310.85 | 312.88 | 84385.85 | 94827 | 0 | 0 | 92257.7 | 105.63 | -5021.85 | -1605% | NO | 5419.3 | 36533 | 61813.5333 | 32496.24 | 0 | 0 | 4036.8 | 4036.8 | 7% | 3.27% | 0% | -7% |  | 0 | [5 empty] | 2850
1736 | 2024-05-01 23:36 | P23438 | A220 Spirit Shorts DTC - Stephen Corry | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 4.207 | 92.59% | 72.57% | 45.48% | 0 | -7.18% | 95928.4 | 88823.7 | 7104.7 | 1688.78 | 0 | 0 | 0 | 0 | 64459.8 | 246.71 | 24363.9 | 1443% | YES | 24363.9 | 28872 | 40399.8 | 0 | 28872.36 | 0 | 0 | 0 | 23% | 15.82% | 16.95% | -6.05% |  | 49.87 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23340 | Spirit 2023 - John Cole | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 40.3514 | 60.44% | 93.51% | 61.16% | 8831.16 | -0.01% | 150129.72 | 90738.18 | 59391.54 | 1471.86 | 0 | 0 | 0 | 0 | 84850.74 | 172.28 | 5887.44 | 400% | YES | 5887.44 | 35229 | 55493.24 | 21576.67 | 4821.34 | 0 | 8831.16 | 8831.16 | 7% | 6.99% | 6.99% | -0.01% |  | 39.78 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23079 | Spirit Shorts Nomenclature | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -3.9742 | 103% | 85.79% | 74.99% | 0 | 15.1% | 88455 | 91134 | -2679 | 674.1 | 0 | 0 | 5136 | 2679 | 78185.2 | 244.73 | 12948.8 | 1921% | YES | 12948.8 | 11811 | 68342.7 | 0 | 11810.64 | 0 | 0 | 0 | 7% | 22.1% | 25.23% | 18.23% |  | 30.81 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23336 | Spirit 2023 - Neil Rampling | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 29.5474 | 70.15% | 94.24% | 50.95% | 21586.03 | -0.01% | 133901.52 | 93933.3 | 39968.22 | 1352.68 | 0 | 0 | 0 | 0 | 88522.6 | 220.87 | 5410.7 | 400% | YES | 5410.7 | 48792 | 47862.6 | 22565.28 | 4640.79 | 0 | 21586.03 | 21586.03 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23375 | GKN Jaap Peters NL 2023 | Steven Lawton | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2024-03-01 | 1 |  |  | 93.37% | 105.3% | 97.18% | 0 | -15.93% | 97123.22 | 90686.41 | 6436.81 | 0 | 90686.41 | 90686.41 | 0 | 0 | 95456.72 | 40.01 | -920.31 | 0% | NO | -920.31 | 8793 | 88129.22 | 0 | 0 | 8793.29 | 0 | 0 | 20% | 4.07% | 0% | -20% |  | 0 | [5 empty] | 3850
1736 | 2024-05-01 23:36 | P23171 | Spirt Shorts Weights Eng | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 10.9035 | 69.18% | 141.4% | 122.7% | 0 | 13.12% | 103113.14 | 71329.32 | 31783.82 | 2915 | 71329.32 | 85975.13 | 0 | 0 | 100870.18 | 54.04 | -5610.86 | -192.5% | NO | 9034.95 | 16006 | 87531.8467 | 16006.35 | 0 | 0 | 0 | 0 | 12% | 25.12% | 47.26% | 35.26% |  | 0 | [5 empty] | 23930
1736 | 2024-05-01 23:36 | P23465 | A220 ToW Design Offload (Wing) | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 16.8829 | 72.18% | 97.52% | 58.53% | 0 | -5.21% | 132000 | 95283.5 | 36716.5 | 2174.78 | 0 | 0 | 0 | 0 | 92918.8 | 127.06 | 2364.7 | 108.7% | NO | 2364.7 | 44580 | 55768.8 | 14843.04 | 29737.44 | 0 | 0 | 0 | 20% | 14.79% | 12.92% | -7.08% |  | 42.8 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23345 | Spirit 2023- Jonathan Escosio | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 35.6165 | 63.7% | 84.75% | 52.95% | 15846.34 | -0.43% | 151941.24 | 96794.01 | 55147.23 | 1548.36 | 0 | 0 | 0 | 0 | 82035.91 | 229.7 | 14758.1 | 953.1% | YES | 14758.1 | 36942 | 51250.91 | 16361 | 4734.58 | 0 | 15846.34 | 15846.34 | 7% | 6.57% | 20.85% | 13.85% |  | 43.01 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23583 | Castalla - Test Rig Design | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 106.8% | 68.92% | 62.56% | 0 | -7.01% | 91720 | 97920.5 | -6200.5 | -627 | 0 | 0 | 13200 | 6200.5 | 67482.1 | 176.54 | 30438.4 | -4855% | NO | 30438.4 | 7469 | 61257.9333 | 0 | 7469.4 | 0 | 0 | 0 | 21% | 13.99% | 14.71% | -6.29% |  | 42.76 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23551 | Ian Berry 2023 H2 | Natalie Sinclair | 0 | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  | -9.7605 | 133.7% | 66.32% | 66.32% | 0 | 13.59% | 75810 | 101350.41 | -25540.41 | 2616.72 | 0 | 0 | 24259.2 | 25540.41 | 67217.49 | 91.05 | 34132.92 | 1304% | YES | 34132.92 | 0 | 67217.49 | 0 | 0 | 0 | 0 | 0 | 22% | 35.59% | 37.71% | 15.71% |  | 77.75 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23586 | Project Management Support | Dushan Fernando | 0 | BDX | MBDA UK LIMITED | MPE | Level NC | REIM |  |  |  | 20.5536 | 63.54% | 96.57% | 66% | 0 | -26.56% | 160000 | 101671.86 | 58328.14 | 2837.85 | 1668.6 | 1668.6 | 0 | 0 | 98183.86 | 91 | 3488 | 122.9% | NO | 3488 | 37296 | 67103.86 | 37296 | 0 | 0 | 0 | 0 | 49% | 22.44% | 21.39% | -27.61% |  | 80 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23753 | Tempest Composites Maturation | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 1.8556 | 87.45% | 63.53% | 27.8% | 0 | -11.72% | 127848.45 | 111801.62 | 16046.83 | 8647.91 | 0 | 0 | 0 | 0 | 71025.53 | 74.23 | 40776.09 | 471.5% | YES | 40776.09 | 47929 | 31084.6967 | 47928.88 | 0 | 0 | 0 | 0 | 32% | 20.28% | 20.28% | -11.72% |  | 64.51 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23545 | Ultra CSS continuation 2023 H2 | Natalie Sinclair | 0 | ULT | ULTRA SONAR SYSTEMS LIMITED | EES | Level NC | REIM |  |  |  | -12.9709 | 147.7% | 67.23% | 67.23% | 0 | 2.2% | 76000 | 112230.4 | -36230.4 | 2793.2 | 0 | 0 | 49859.2 | 36230.4 | 75451.2 | 130.35 | 36779.2 | 1317% | YES | 36779.2 | 0 | 75451.2 | 0 | 0 | 0 | 0 | 0 | 23% | 25.2% | 25% | 2% |  | 80 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23353 | Spirit 2023 - MRB Man Serv (JC) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  | 37.9625 | 62.78% | 59.53% | 59.53% | 0 | 9.71% | 183600 | 115267.5 | 68332.5 | 1800 | 0 | 0 | 0 | 0 | 68615.25 | 215.88 | 46652.25 | 2592% | YES | 46652.25 | 0 | 68615.25 | 0 | 0 | 0 | 0 | 0 | 7% | 16.71% | 13.06% | 6.06% |  | 45 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23784 | Tempest Tooling Offload 2024 | Gary Kempster | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  | -16.7602 |  | 0% | 0% | 0 | -6.97% | 0 | 116978.57 | -116978.57 | 6979.53 | 0 | 0 | 159270 | 116978.57 | 0 | 116.26 | 116978.57 | 1676% | YES | 116978.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 18.03% | 18.03% | -6.97% |  | 54.91 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P22918 | Spirit Shorts Graduates | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 21.2087 | 90.51% | 90.71% | 90.71% | 0 | 9.49% | 130000 | 117669.04 | 12330.96 | 581.41 | 0 | 0 | 19800 | 0 | 106734.95 | 64.31 | 10934.09 | 1881% | YES | 10934.09 | 0 | 106734.95 | 0 | 0 | 0 | 0 | 0 | 7% | 16.49% | 17.18% | 10.18% |  | 23.32 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P22736 | WoT Fixed Leading Edge - Industrial | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 106.7% | 93.42% | 91.32% | 3019.54 | 0.01% | 112196.27 | 119668.47 | -7472.2 | 0 | 0 | 0 | 0 | 7472.2 | 111796.68 | 12465.69 | 7871.79 | 0% | NO | 7871.79 | 3020 | 109280.0133 | 0 | 0 | 0 | 3019.54 | 3019.54 | 7% | 7.01% | 0% | -7% |  | 32.26 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23588 | BAE Typhoon MRB MC Shop Concessions | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 22.917 | 69.59% | 92.03% | 65.91% | 38190.65 | -3.65% | 175060.5 | 121827.07 | 53233.43 | 2322.88 | 0 | 0 | 0 | 0 | 112121.71 | 121.84 | 9705.36 | 417.8% | YES | 9705.36 | 38191 | 80295.8767 | 10272.55 | 13518.34 | 14399.76 | 0 | 38190.65 | 31% | 27.35% | 29.17% | -1.83% |  | 55.55 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23352 | Spirit 2023 - Stress Approve Man Serv (CC) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  | 32.3684 | 62.32% | 57.29% | 57.29% | 0 | 6.12% | 195840 | 122040 | 73800 | 2280 | 0 | 0 | 0 | 0 | 69912 | 229.83 | 52128 | 2286% | YES | 52128 | 0 | 69912 | 0 | 0 | 0 | 0 | 0 | 7% | 13.12% | 4.69% | -2.31% |  | 48 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23822 | FCASW Requirements Management | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 26.2889 | 20.59% | 0% | 0% | 0 | -5.9% | 595703 | 122655.98 | 473047.02 | 17994.17 | 0 | 0 | 0 | 0 | 0 | 84 | 122655.98 | 681.6% | YES | 122655.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17% | 11.1% | 11.1% | -5.9% |  | 75.4 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P22861 | WoT FLE Lifting & Handling Tools | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2023-06-14 | 1 |  |  | 65.17% | 101.6% | 101.6% | 0 | 12.01% | 173987.21 | 113381.75 | 60605.46 | 0 | 50078 | 58423.58 | 0 | 0 | 115203.5 | 12813.9 | 10678.25 | 0% | NO | 19023.83 | 0 | 115203.5 | 0 | 0 | 0 | 0 | 0 | 1% | 13.01% | 0% | -1% |  | 45 | [5 empty] | 12500
1736 | 2024-05-01 23:36 | P23664 | Tempest Composites WP3 | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -1.8138 | 104.6% | 67.23% | 12.9% | 0 | -5.15% | 122455.49 | 128084.79 | -5629.3 | 3103.58 | 0 | 0 | 14830.4 | 5629.3 | 86110.38 | 277.98 | 41974.41 | 1352% | YES | 41974.41 | 83510 | 16518.7133 | 83510.02 | 0 | 0 | 0 | 0 | 37% | 31.85% | 33.18% | -3.82% |  | 60.84 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23282 | Tooling Support (MBDA) | Dushan Fernando | 0 | BDV | MBDA UK LIMITED | ME | Level NC | REIM |  |  |  | 41.4114 | 66% | 98.48% | 80.38% | 0 | -7.98% | 195672.4 | 129145.75 | 66526.65 | 1606.48 | 0 | 0 | 0 | 0 | 127186.8 | 99.47 | 1958.95 | 121.9% | NO | 1958.95 | 28059 | 103804.3 | 7411.63 | 20647.76 | 0 | 0 | 0 | 30% | 22.02% | 30.37% | 0.37% |  | 49.72 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23270 | Shorts Project X | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 7.1198 | 91.68% | 94.01% | 67.4% | 0 | 0.45% | 142248 | 130409.3 | 11838.7 | 1662.78 | 0 | 0 | 0 | 0 | 122595.46 | 177.53 | 7813.84 | 469.9% | YES | 7813.84 | 41647 | 87889.6267 | 18011.95 | 23635.49 | 0 | 0 | 0 | 13% | 13.45% | 10.99% | -2.01% |  | 45.32 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P22883 | Spirit Shorts Evtol PMO C. Hatton | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 20.3177 | 70.89% | 82.71% | 82.71% | 0 | -11.05% | 185800 | 131714.15 | 54085.85 | 2662 | 0 | 0 | 0 | 0 | 108946.73 | 118.46 | 22767.42 | 855.3% | YES | 22767.42 | 0 | 108946.73 | 0 | 0 | 0 | 0 | 0 | 26% | 14.95% | 22.96% | -3.04% |  | 37.29 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23810 | Strategic Enablement | Owain Jones | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -843.2318 |  | 0% | 0% | 0 | -20.63% | 0 | 133694.4 | -133694.4 | 158.55 | 0 | 0 | 134000 | 133694.4 | 0 | 155.03 | 133694.4 | 84323% | YES | 133694.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | -2.63% | -2.63% | -20.63% |  | 42 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23533 | External Stowage Design and Detail Support | Dushan Fernando | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 1 |  |  | 102.4% | 97.65% | 73.24% | 42000 | 3.33% | 140000 | 143368.75 | -3368.75 | 0 | 0 | 0 | 12936 | 3368.75 | 140000 | 41999.7 | -0.25 | 0% | NO | -0.25 | 42000 | 105000 | 0 | 42000 | 0 | 0 | 42000 | 27% | 30.33% | 0% | -27% |  | 60.04 | [5 empty] | -3369
1736 | 2024-05-01 23:36 | P23650 | MBDA Recruitment Management costs | Andrew Slaney | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM | 2024-02-01 | 0 |  |  |  | 0% | 0% | 0 | -20.2% | 0 | 240971.5 | -240971.5 | 0 | 0 | 0 | 266000 | 240971.5 | 0 | 421.29 | 140971.5 | 0% | NO | 140971.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | -17.2% | -441% | -444% |  | 82.3 | [5 empty] | -100000
1736 | 2024-05-01 23:36 | P22954 | Technical Support Step 1 | Owain Jones | 0 | HUV | HUARUI SPIRIT AEROSPACE MANUFACT | ME | Level 2 | REIM |  |  |  |  | 94.81% | 58.01% | 58.01% | 0 | 0.31% | 155501.18 | 147431.58 | 8069.6 | 0 | 23043 | 23043 | 0 | 0 | 85525.49 | 61906.09 | 61906.09 | 0% | NO | 61906.09 | 0 | 85525.49 | 0 | 0 | 0 | 0 | 0 | 30% | 30.31% | 0% | -30% |  | 60.79 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23386 | Software Development - BMS | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 98.78% | 100% | 100% | 0 | 4.31% | 149650 | 147823.35 | 1826.65 | 0 | 0 | 0 | 0 | 0 | 147823.35 | 0 | 0 | 0% | NO | 0 | 0 | 147823.35 | 0 | 0 | 0 | 0 | 0 | 18% | 22.31% | 22.61% | 4.61% |  | 78.5 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23437 | Embedded Software Engineer | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 98.73% | 100% | 96.08% | 0 | -6.29% | 150150 | 148239.36 | 1910.64 | 0 | 737.86 | 737.86 | 0 | 0 | 148239.36 | 30.33 | 0 | 0% | NO | 0 | 6971 | 142430.1933 | 0 | 6970.8 | 0 | 0 | 0 | 22% | 15.71% | 16.24% | -5.76% |  | 78.5 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23550 | Tempest Composites | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -4.6319 | 102.5% | 97.57% | 97.57% | 0 | 5.11% | 149494.92 | 153217.46 | -3722.54 | 803.68 | 0 | 0 | 2396.12 | 3722.54 | 149494.92 | 30.19 | 3722.54 | 463.2% | YES | 3722.54 | 0 | 149494.92 | 0 | 0 | 0 | 0 | 0 | 26% | 31.11% | 33.8% | 7.8% |  | 61.6 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P22440 | Spirit Managed Service - F&DT and Static Approval | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 3 |  |  | 88.56% | 92.56% | 92.56% | 0 | 11.51% | 173500 | 153656.25 | 19843.75 | 0 | 52115 | 55720 | 0 | 0 | 142225.12 | 13717.36 | 11431.13 | 0% | NO | 15036.13 | 0 | 142225.12 | 0 | 0 | 0 | 0 | 0 | 0% | 11.51% | 0% | 0% |  | 44.73 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P22982 | Spirit 2022 - Hugh Sloan | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 94.8598 | 63.28% | 96.03% | 81.06% | 8217.17 | -0.62% | 247473 | 156601.06 | 90871.94 | 957.96 | 0 | 0 | 0 | 0 | 150381.98 | 207.52 | 6219.08 | 649.2% | YES | 6219.08 | 28121 | 126947.8133 | 15604.11 | 4300.18 | 0 | 8217.17 | 8217.17 | 7% | 6.38% | 1.35% | -5.65% |  | 35.43 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23754 | Tempest Composites WP4 | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 9.4532 | 51.4% | 0% | 0% | 0 | -1.27% | 310945.68 | 159835.13 | 151110.55 | 15985.13 | 1784.87 | 1784.87 | 0 | 0 | 0 | 108.31 | 159835.13 | 999.9% | YES | 159835.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36% | 34.73% | 34.73% | -1.27% |  | 61.61 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23518 | Systems Engineering support to FCAS | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 11.3317 | 85.82% | 95.68% | 85.05% | 0 | -4.95% | 193736.8 | 166272.25 | 27464.55 | 2423.69 | 3927.4 | 3927.4 | 0 | 0 | 159084.68 | 70.26 | 7187.57 | 296.6% | YES | 7187.57 | 21195 | 141422.18 | 11351.1 | 9843.9 | 0 | 0 | 0 | 30% | 25.05% | 3.5% | -26.5% |  | 68.41 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23508 | Verification and Validation | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 80.77% | 100% | 97.06% | 0 | 10.77% | 212950 | 171993.5 | 40956.5 | 0 | 0 | 0 | 0 | 0 | 171993.53 | 24.18 | -0.03 | 0% | NO | -0.03 | 6076 | 166930.1967 | 0 | 6075.9 | 0 | 0 | 0 | 24% | 34.77% | 33.6% | 9.6% |  | 78.5 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23667 | Safety Systems Engineer | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 57.3198 | 43.36% | 97.64% | 79.41% | 0 | -10.51% | 398000 | 172590 | 225410 | 3932.5 | 0 | 0 | 0 | 0 | 168520 | 62.41 | 4070 | 103.5% | NO | 4070 | 37752 | 137060 | 18216 | 19536 | 0 | 0 | 0 | 47% | 36.49% | 29.32% | -17.68% |  | 110 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23464 | A220 Project X Design Offload | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 401.6002 | 52.16% | 100% | 63.51% | 27862.8 | -9.42% | 332340 | 173346.5 | 158993.5 | 395.9 | 0 | 0 | 0 | 0 | 173346.5 | 196.92 | 0 | 0% | NO | 0 | 75910 | 110088.1667 | 20261.52 | 27785.76 | 0 | 27862.8 | 27862.8 | 26% | 16.58% | 14.31% | -11.69% |  | 42.88 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23421 | A220 DTC | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 8.9846 | 81.95% | 73.41% | 60.2% | 0 | -28.43% | 217089.12 | 177904.29 | 39184.83 | 4361.35 | 0 | 0 | 0 | 0 | 130597.8 | 114.92 | 47306.49 | 1085% | YES | 47306.49 | 28204 | 107094.4667 | 12403.44 | 15800.9 | 0 | 0 | 0 | 29% | 0.57% | 5.12% | -23.88% |  | 45.96 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23741 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  | 34.7126 | 28.88% | 107.2% | 24.26% | 0 | 2.23% | 640812 | 185037.6 | 455774.4 | 13129.95 | 0 | 0 | 0 | 0 | 198299 | 85.61 | -9261.4 | -70.54% | NO | -9261.4 | 184097 | 44884.8333 | 68808 | 62626.8 | 52662 | 0 | 0 | 28% | 30.23% | 30.23% | 2.23% |  | 38.81 | [5 empty] | 4000
1736 | 2024-05-01 23:36 | P23008 | Spirit Shorts Project Rachel | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 68.49% | 91.32% | 91.32% | 0 | -9.7% | 286960 | 196531.2 | 90428.8 | 0 | 0 | 0 | 0 | 0 | 179472.8 | 20470.08 | 17058.4 | 0% | NO | 17058.4 | 0 | 179472.8 | 0 | 0 | 0 | 0 | 0 | 15% | 5.3% | 0.31% | -14.69% |  | 46.04 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23019 | EXP034-B Actuator Development | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 103.1% | 89.91% | 89.91% | 0 | -16.68% | 215541.2 | 222215.54 | -6674.34 | 0 | 12297.9 | 12297.9 | 0 | 6674.34 | 199796.76 | 122.03 | 397.78 | 0% | NO | 397.78 | 0 | 199796.76 | 0 | 0 | 0 | 0 | 0 | 34% | 17.32% | 79.64% | 45.64% |  | 58.45 | [5 empty] | -22021
1736 | 2024-05-01 23:36 | P23739 | Lifing Services DACs | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  | 35.3111 | 29.92% | 112.4% | 28.36% | 0 | 4.73% | 656508 | 196418.3 | 460089.7 | 13029.6 | 0 | 0 | 0 | 0 | 220836 | 85.78 | -19417.7 | -149% | NO | -19417.7 | 198152 | 55709.3333 | 66850.8 | 65650.8 | 65650.8 | 0 | 0 | 28% | 32.73% | 32.73% | 4.73% |  | 37.78 | [5 empty] | 5000
1736 | 2024-05-01 23:36 | P23505 | EXP-022 Meteor TBUS T&E support | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 11.1341 | 85.51% | 98.08% | 85.1% | 0 | -1.29% | 246744.4 | 210988.21 | 35756.19 | 3211.42 | 0 | 0 | 0 | 0 | 206945.88 | 60.24 | 4042.33 | 125.9% | NO | 4042.33 | 32878 | 179547.5467 | 13636.2 | 19241.59 | 0 | 0 | 0 | 20% | 18.71% | 15.67% | -4.33% |  | 89.83 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23506 | ASTER Mid-Life Refurbishment Project Manager | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 27.2312 | 64.61% | 97.97% | 82.73% | 0 | 1.09% | 326900 | 211201.41 | 115698.59 | 4248.75 | 2806.41 | 2806.41 | 0 | 0 | 206911.41 | 62.09 | 4290 | 101% | NO | 4290 | 38610 | 174736.41 | 38610 | 0 | 0 | 0 | 0 | 25% | 26.09% | 26.41% | 1.41% |  | 110 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23242 | Physical Architecture & System Engineering Support | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 34.4858 | 69.87% | 98.28% | 87.82% | 0 | 7.34% | 305459 | 213416.46 | 92042.54 | 2669 | 775.55 | 775.55 | 0 | 0 | 209745.3 | 63.33 | 3317.16 | 124.3% | NO | 3317.16 | 26800 | 187411.9667 | 12669.9 | 14130 | 0 | 0 | 0 | 15% | 22.34% | 7.17% | -7.83% |  | 78.21 | [5 empty] | -354
1736 | 2024-05-01 23:36 | P23373 | Raytheon Michael Bellini | Natalie Sinclair | 0 | RAS | RAYTHEON UNITED KINGDOM LIMITED | EES | Level NC | REIM |  |  |  | -0.21792 | 100.2% | 89.28% | 79.68% | 24734.7 | -7.79% | 214367.4 | 214759.18 | -391.78 | 1797.85 | 0 | 0 | 13558.28 | 391.78 | 191739.73 | 91.73 | 23019.45 | 1280% | YES | 23019.45 | 24735 | 171127.23 | 0 | 24734.7 | 0 | 0 | 24734.7 | 45% | 37.21% | 38.67% | -6.33% |  | 91.61 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23648 | EXP-032 Delivery of Datalink Eng support - FCAS AP | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 15.0443 | 58.22% | 75.61% | 62.93% | 0 | 6.68% | 371000 | 215977.95 | 155022.05 | 10304.38 | 1032.95 | 1032.95 | 0 | 0 | 163302.95 | 64.99 | 52675 | 511.2% | YES | 52675 | 32868 | 135912.95 | 13332 | 19536 | 0 | 0 | 0 | 22% | 28.68% | 29.24% | 7.24% |  | 102.48 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23524 | Bombardier Regional Jets (BRJ) | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -9.8466 | 151.8% | 49% | 47.61% | 3694.07 | -3.92% | 146287.84 | 222115.36 | -75827.52 | 7700.92 | 0 | 0 | 113075 | 75827.52 | 108838.22 | 285.77 | 113277.14 | 1471% | YES | 113277.14 | 3694 | 105759.8867 | 0 | 0 | 0 | 3694.07 | 3694.07 | 18% | 14.08% | 17.21% | -0.79% |  | 43.76 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23629 | F35 FTI | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level NC | REIM |  |  |  | -38.0865 |  | 93.24% | 80.96% | 0 | -1.62% | 0 | 252875.54 | -252875.54 | 6639.51 | 0 | 0 | 0 | 252875.54 | 235774.05 | 40.25 | 17101.49 | 257.6% | YES | 17101.49 | 37243 | 204738.2167 | 37243.2 | 0 | 0 | 0 | 0 | 31% | 29.38% | 27.87% | -3.13% |  | 61.79 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23472 | Tempest Wing Design | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 60.7434 | 51.83% | 121.5% | 110.7% | 0 | -11.53% | 483869.78 | 250767.11 | 233102.67 | 3837.5 | 234887.5 | 356900 | 0 | 0 | 304757.78 | 0 | -28990.68 | -755.5% | NO | 93021.82 | 32717 | 277493.6133 | 32716.75 | 0 | 0 | 0 | 0 | 23% | 11.47% | 30.06% | 7.06% |  | 46.74 | [5 empty] | 25000
1736 | 2024-05-01 23:36 | P23007 | EXP-006A - Brimstone 3 | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 79.6066 | 68.39% | 99.79% | 88.96% | 14977.8 | -2.64% | 406450 | 277952.16 | 128497.84 | 1614.16 | 0 | 0 | 0 | 0 | 277363.38 | 90.91 | 558.78 | 34.62% | NO | 558.78 | 36102 | 247278.38 | 21124.36 | 0 | 14977.8 | 0 | 14977.8 | 25% | 22.36% | 29.94% | 4.94% |  | 69.96 | [5 empty] | -30
1736 | 2024-05-01 23:36 | P23743 | EHM Cloud Migration | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 36.9798 | 26.12% | 129% | 32.19% | 0 | 6.11% | 1016000 | 265330.13 | 750669.87 | 20299.47 | 0 | 0 | 0 | 0 | 342376 | 73.24 | -57045.88 | -281% | NO | -57045.88 | 308362 | 85407.6667 | 103612.8 | 102336 | 102412.8 | 0 | 0 | 28% | 34.11% | 34.11% | 6.11% |  | 54.82 | [5 empty] | 20000
1736 | 2024-05-01 23:36 | P23677 | ME Managed Service - Phase 1 | Paul Watson | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  | 15.5316 | 51.82% | 62.33% | -0.000145% | 0 | -15.04% | 554400 | 287281.35 | 267118.65 | 17198.44 | 0 | 38000 | 0 | 0 | 179066.25 | 117.96 | 108215.1 | 629.2% | YES | 146215.1 | 214880 | -0.41667 | 78097.5 | 136782 | 0 | 0 | 0 | 33% | 17.96% | 20.43% | -12.57% |  | 44.07 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P21463 | Safety & Monitoring Systems at DM Beith & Gosport | Harry James Kellett | 0 | BXW | MOD | EES | Level 2 | FIX |  |  |  | 16.2479 | 79.82% | 125.3% | 120.5% | 0 | -28.2% | 363180.15 | 289875.79 | 73304.36 | 4511.61 | 75403.45 | 77420.74 | 21721 | 0 | 363162.15 | 0 | -73286.36 | -1624% | NO | -71269.07 | 16530 | 349387.15 | 16530.2 | 0 | 0 | 0 | 0 | 48% | 19.8% | 19.35% | -28.65% |  | 53 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23308 | NATO JEWCS | Natalie Sinclair | 0 | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  | 28.569 | 84.08% | 91.32% | 91.21% | 0 | -3.85% | 356307 | 299589.58 | 56717.42 | 1985.28 | 613.89 | 613.89 | 0 | 0 | 273576.49 | 100.12 | 26013.09 | 1310% | YES | 26013.09 | 387 | 273253.99 | 386.92 | 0 | 0 | 0 | 0 | 24% | 20.15% | 11.86% | -12.14% |  | 75.81 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23603 | Typhoon IMDLR | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | -0.056216 | 100.2% | 39.2% | 0.0001112% | 143769.41 | 3.9% | 305067.09 | 305642.41 | -575.32 | 10234.12 | 1500 | 1500 | 0 | 575.32 | 119807.84 | 445.62 | 185834.57 | 1816% | YES | 185834.57 | 143769 | 0.34 | 0 | 143769.41 | 0 | 0 | 143769.41 | 26% | 29.9% | 28.36% | 2.36% |  | 56.46 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P22953 | Spirit Shorts eVTOL | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-05-08 | 2 |  |  | 103.1% | 80.83% | 79.36% | 0 | -9.51% | 324272 | 334483.6 | -10211.6 | 0 | 66696.6 | 67387.9 | 0 | 10211.6 | 270366 | 70861.92 | 54117.6 | 0% | NO | 54808.9 | 5921 | 265431.8333 | 0 | 5920.8 | 0 | 0 | 0 | 17% | 7.49% | 100% | 83% |  | 46.19 | [5 empty] | -10000
1736 | 2024-05-01 23:36 | P22515 | Shorts A220 100/300 ALI Phase III | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 38.9373 | 82.8% | 98.96% | 89.67% | 0 | 0.66% | 400628.76 | 331724.09 | 68904.67 | 1769.63 | 3450.98 | 3450.98 | 0 | 0 | 328273.11 | 134.85 | 3450.98 | 195% | YES | 3450.98 | 36969 | 297465.61 | 18582.69 | 18386.68 | 0 | 0 | 0 | 10% | 10.66% | 7.05% | -2.95% |  | 40.52 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23816 | Typhoon FTI Works - 2024 Fixed Price Element | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 2.5495 | 81.55% | 55.67% | 5.056e-05% | 0 | -1.24% | 404176.65 | 329613.75 | 74562.9 | 29246.37 | 0 | 0 | 0 | 0 | 183496 | 93.76 | 156117.75 | 533.8% | YES | 156117.75 | 220195 | 0.16667 | 220195.2 | 0 | 0 | 0 | 0 | 30% | 28.76% | 28.76% | -1.24% |  | 52.78 | [5 empty] | 10000
1736 | 2024-05-01 23:36 | P23699 | A220 Stress Checkers | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -234.4811 |  | 0% | 0% | 0 | -1.99% | 0 | 342248.61 | -342248.61 | 1459.6 | 12000 | 12000 | 321520 | 342248.61 | 0 | 145.81 | 342248.61 | 23448% | YES | 342248.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22% | 20.01% | 20.04% | -1.96% |  | 61.88 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P22842 | ME Support (Aim Altitude) | Trevor Knox | 0 | AVI | AIM ALTITUDE UK LIMITED | ME | Level 3 | FIX | 2023-06-14 | 4 |  |  | 99.31% | 100.5% | 86.63% | 57290.84 | 0.49% | 346293.67 | 343918.08 | 2375.59 | 0 | 2909.86 | 2909.86 | 0 | 0 | 345673.01 | 55184.93 | -1754.93 | 0% | NO | -1754.93 | 57291 | 297930.51 | 0 | 0 | 0 | 57290.84 | 57290.84 | 13% | 13.49% | 0% | -13% |  | 46.3 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P22391 | GE System Engineering support | Vinayakumar Sugur | 0 | GEE | EXPERIS LIMITED | EES | Level NC | REIM | 2024-04-08 | 0 |  |  | 82.01% | 100.7% | 100.7% | 0 | 0.13% | 434434.25 | 356260.63 | 78173.62 | 0 | 0 | 0 | 0 | 0 | 358805.6 | 0 | -2544.97 | 0% | NO | -2544.97 | 0 | 358805.6 | 0 | 0 | 0 | 0 | 0 | 6% | 6.13% | 6.09% | 0.09% |  | 57.33 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23617 | Tempest Composites WP2 | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -11.6356 | 148.3% | 27.91% | 15.96% | 29536.68 | 11.64% | 244405.26 | 362447.55 | -118042.29 | 10144.91 | 0 | 0 | 120669.84 | 118042.29 | 101150.9 | 289.61 | 261296.65 | 2576% | YES | 261296.65 | 51981 | 57833.4 | 22444.14 | 0 | 0 | 29536.68 | 29536.68 | 22% | 33.64% | 33.33% | 11.33% |  | 62.15 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23045 | Shotgun Adaptors - 10 Sets | Harry James Kellett | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | FIX | 2024-02-27 | 3 |  |  | 74.76% | 133.8% | 133.8% | 0 | 2.29% | 399276.11 | 298512.88 | 100763.23 | 0 | 214550.47 | 214550.47 | 0 | 0 | 399276.11 | 0 | -7763.23 | 0% | NO | -7763.23 | 0 | 399276.11 | 0 | 0 | 0 | 0 | 0 | 29% | 31.29% | 99.78% | 70.78% |  | 55.76 | [5 empty] | 93000
1736 | 2024-05-01 23:36 | P23432 | Spirit Belfast MRB On-Site Support (Mon & Clear) | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 65.77% | 128.6% | 103.8% | 0 | -11.53% | 449545 | 295665.27 | 153879.73 | 0 | 295665.27 | 451827.33 | 0 | 0 | 380234.75 | 120831.02 | 27430.52 | 0% | NO | 183592.58 | 87914 | 306973.0833 | 0 | 87914.4 | 0 | 0 | 0 | 39% | 27.47% | 0% | -39% |  | 0 | [5 empty] | 112000
1736 | 2024-05-01 23:36 | P23023 | Spirit Shorts R Foster/M Gourley | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 10.7884 | 86.29% | 105.5% | 92.54% | 0 | -19.1% | 480221.04 | 414400.69 | 65820.35 | 6101.01 | 237621.5 | 267726 | 0 | 0 | 437064.88 | 62.57 | -298.19 | -4.888% | NO | 29806.31 | 64309 | 383474.0467 | 45188.25 | 19120.72 | 0 | 0 | 0 | 27% | 7.9% | 11.55% | -15.45% |  | 29.66 | [5 empty] | 22366
1736 | 2024-05-01 23:36 | P23372 | BAE Carbon Tooling Off-load | Gary Kempster | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  |  | 100.5% | 95.27% | 95.27% | 0 | -1.13% | 454982.37 | 457433.31 | -2450.94 | 0 | 0 | 0 | 1285.68 | 2450.94 | 435785.94 | 25976.85 | 21647.37 | 0% | NO | 21647.37 | 0 | 435785.94 | 0 | 0 | 0 | 0 | 0 | 24% | 22.87% | 20.74% | -3.26% |  | 53.57 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P22906 | Spirit Shorts - MRB JD Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 5.9682 | 95.89% | 83.72% | 65.77% | 99451.32 | -7.88% | 481714 | 461903.18 | 19810.82 | 3319.38 | 0 | 0 | 0 | 0 | 386687.62 | 334.2 | 83215.56 | 2507% | YES | 83215.56 | 99451 | 303811.7867 | 0 | 0 | 0 | 99451.32 | 99451.32 | 13% | 5.12% | 2.49% | -10.51% |  | 36.94 | [5 empty] | 8000
1736 | 2024-05-01 23:36 | P23554 | Dornier Seawings 328 2023 H2 Support | Steven Lawton | 0 | DAX | EXPLEO GERMANY GMBH (EC) | MPE | Level 2 | REIM |  |  |  | 2.6723 | 95.83% | 87.89% | 87.89% | 0 | 5.91% | 508481.81 | 487261.47 | 21220.34 | 7940.89 | 4046.44 | 4046.44 | 0 | 0 | 428252.8 | 50.04 | 59008.67 | 743.1% | YES | 59008.67 | 0 | 428252.8 | 0 | 0 | 0 | 0 | 0 | 21% | 26.91% | 23.32% | 2.32% |  | 66.13 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23531 | BAe Systems F35 MRB Support | Richard Brook | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | -56.9613 |  | 94.52% | 87.54% | 0 | 3.4% | 0 | 494645.8 | -494645.8 | 8683.9 | 287.44 | 287.44 | 0 | 494645.8 | 467545.66 | 39.81 | 27100.14 | 312.1% | YES | 27100.14 | 41416 | 433032.3267 | 41415.52 | 0 | 0 | 0 | 0 | 25% | 28.4% | 31.7% | 6.7% |  | 59.97 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P22652 | L3 - Saftey Engineering | Sean Simmons | 0 | LHW | L3HARRIS MAPPS LIMITED | EES | Level NC | FIX |  |  |  |  | 95.63% | 95.66% | 86.69% | 0 | 5.66% | 523390 | 500497.5 | 22892.5 | 0 | 0 | 0 | 0 | 0 | 478783.75 | 79938 | 21713.75 | 0% | NO | 21713.75 | 53882 | 433882.0833 | 53881.5 | 0 | 0 | 0 | 0 | 21% | 26.66% | 25.88% | 4.88% |  | 83.05 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23520 | FCAS AP Portfolio Systems | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 24.0138 | 64.81% | 97.5% | 78.72% | 0 | -6.66% | 810821 | 525501.3 | 285319.7 | 11881.47 | 423 | 423 | 0 | 0 | 512377.44 | 60.74 | 8840.86 | 74.41% | NO | 8840.86 | 118439 | 413678.2733 | 56206.8 | 62232.16 | 0 | 0 | 0 | 22% | 15.34% | 16.16% | -5.84% |  | 80.97 | [5 empty] | -4283
1736 | 2024-05-01 23:36 | P23281 | Systems Portfolio | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM | 2024-02-28 | 0 |  |  | 44.43% | 97.31% | 97.31% | 0 | -17.25% | 1177697.24 | 523236.96 | 654460.28 | 0 | 2133.28 | 2133.28 | 0 | 0 | 509179.87 | 15792.1 | 13160.09 | 0% | NO | 13160.09 | 0 | 509179.87 | 0 | 0 | 0 | 0 | 0 | 25% | 7.75% | 100% | 75% |  | 70.48 | [5 empty] | -897
1736 | 2024-05-01 23:36 | P23140 | Spirit Shorts A220 MLG Stress Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  | 26.2542 | 67.8% | 108.5% | 66.28% | 0 | -13.37% | 735573.4 | 498746.42 | 236826.98 | 9020.54 | 20870.3 | 87811.88 | 0 | 0 | 540939.4 | 208.76 | -17192.98 | -190.6% | NO | 49748.6 | 252442 | 330571.0667 | 204098.4 | 48343.2 | 0 | 0 | 0 | 25% | 11.63% | -9.97% | -34.97% |  | 45.69 | [5 empty] | 25000
1736 | 2024-05-01 23:36 | P23001 | Spirit Shorts A220 Design | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -21.8702 | 111.6% | 76.7% | 67.4% | 0 | 11.54% | 486640 | 543270.8 | -56630.8 | 2589.4 | 0 | 0 | 65953.2 | 56630.8 | 416705.3 | 394.22 | 126565.5 | 4888% | YES | 126565.5 | 60669 | 366147.8 | 31432.32 | 29236.68 | 0 | 0 | 0 | 9% | 20.54% | 11.56% | 2.56% |  | 43.57 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23685 | DAC LUC Support and Recompliance | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 41.0216 | 23.59% | 188.2% | 48.89% | 0 | 3.74% | 2180000 | 514270.65 | 1665729.35 | 40606.14 | 0 | 0 | 0 | 0 | 967868 | 64.74 | -404833.35 | -997% | NO | -404833.35 | 859729 | 251427.1667 | 297441.6 | 274286.4 | 288001.2 | 0 | 0 | 30% | 33.74% | 33.74% | 3.74% |  | 58.06 | [5 empty] | 48764
1736 | 2024-05-01 23:36 | P23473 | Tempest Vertical Tail | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 25.9039 | 66.38% | 98.83% | 87.82% | 0 | -7.06% | 846017.62 | 561564.24 | 284453.38 | 10981.1 | 103562.5 | 112425 | 12000 | 0 | 554989.62 | 47.02 | 11574.62 | 105.4% | NO | 20437.12 | 74168 | 493182.9533 | 74168.03 | 0 | 0 | 0 | 0 | 29% | 21.94% | 24.71% | -4.29% |  | 62.5 | [5 empty] | 5000
1736 | 2024-05-01 23:36 | P23694 | Systems Portfolio EXP-011a | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 3.2456 | 88.6% | 95.08% | 63.14% | 0 | 2.07% | 648492.8 | 574580.03 | 73912.77 | 22773.07 | 444.4 | 444.4 | 0 | 0 | 546332.19 | 64.86 | 28247.84 | 124% | NO | 28247.84 | 220264 | 362778.8567 | 220264.07 | 0 | 0 | 0 | 0 | 21% | 23.07% | 20.15% | -0.85% |  | 88.74 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23366 | Business Analyst Support | Peter Williams | 0 | BDZ | MBDA UK LIMITED | DET | Level 3 | REIM |  |  |  | 115.5524 | 22.65% | 191.3% | 168.1% | 0 | 6.06% | 1302200 | 294979.11 | 1007220.89 | 8716.57 | 247149.55 | 900687.4 | 0 | 0 | 564160 | 64.98 | 23954.11 | 274.8% | YES | 677491.96 | 81792 | 496000 | 0 | 81792 | 0 | 0 | 0 | 43% | 49.06% | 27.76% | -15.24% |  | 44.7 | [5 empty] | 293135
1736 | 2024-05-01 23:36 | P23219 | Tornado Air 800 Engineering Support | Richard Brook | 0 | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 3 | REIM |  |  |  | -13.1578 | 102.3% | 91.93% | 91.93% | 0 | -2.8% | 615046 | 629166.71 | -14120.71 | 1073.18 | 459.21 | 459.21 | 0 | 14120.71 | 578373.17 | 56 | 25886.54 | 2412% | YES | 25886.54 | 0 | 578373.17 | 0 | 0 | 0 | 0 | 0 | 31% | 28.2% | -117.3% | -148.3% |  | 82.45 | [5 empty] | -24907
1736 | 2024-05-01 23:36 | P23323 | CNC-CMM Programming Support | Stephen Young | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  | 0.66878 | 98.9% | 94.02% | 83.87% | 40305.01 | -2.35% | 617809.74 | 611013.77 | 6795.97 | 10161.69 | 15941.56 | 15941.56 | 49744.45 | 0 | 574493.52 | 70.77 | 36520.25 | 359.4% | YES | 36520.25 | 74458 | 512445.1867 | 74458.13 | 0 | 0 | 0 | 40305.01 | 32% | 29.65% | 36.72% | 4.72% |  | 57.46 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23605 | Typhoon Work Package 2 Continuation | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM |  |  |  | -696.0603 | 119.9% | 83.3% | 29.79% | 401637.33 | 5.13% | 545536.01 | 654246.7 | -108710.69 | 156.18 | 5554 | 5554 | 81999.09 | 108710.69 | 544986.65 | 820.02 | 109260.05 | 69958% | YES | 109260.05 | 420070 | 194928.3167 | 18432.36 | 401637.33 | 0 | 0 | 401637.33 | 23% | 28.13% | 28.7% | 5.7% |  | 55.86 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P22790 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | REIM |  |  |  | -134.62 | 197.4% | 89.11% | 89.11% | 0 | 1.11% | 352240 | 695460.45 | -343220.45 | 2549.55 | 1611.52 | 1611.52 | 515246 | 343220.45 | 619743.88 | 396.6 | 44446.57 | 1743% | YES | 44446.57 | 0 | 619743.88 | 0 | 0 | 0 | 0 | 0 | 13% | 14.11% | -2.72% | -15.72% |  | 45.08 | [5 empty] | -31270
1736 | 2024-05-01 23:36 | P23426 | BAE Tempest WP 3 Harness Maturation | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 6.535 | 86.23% | 89.41% | 68.61% | 82448.95 | -6.23% | 884012.04 | 762316.74 | 121695.3 | 18621.94 | 213.34 | 213.34 | 0 | 0 | 681568.4 | 93.45 | 80748.34 | 433.6% | YES | 80748.34 | 190206 | 523063.4 | 107757.52 | 82448.95 | 0 | 0 | 82448.95 | 33% | 26.77% | 27% | -6% |  | 51.88 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23602 | EXP-025 Portfolio Software Engineering Support | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 15.3225 | 64.38% | 95.3% | 67.39% | 0 | -1.01% | 1327080 | 854322.5 | 472757.5 | 30853.81 | 3624.28 | 3868.41 | 0 | 0 | 814204.07 | 63.91 | 40118.43 | 130% | YES | 40362.56 | 286222 | 575685.7367 | 143172.62 | 143049.25 | 0 | 0 | 0 | 24% | 22.99% | 22.68% | -1.32% |  | 83.32 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23451 | BAE Tempest - DFM-ASO Planning | Stephen Young | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | 3.8276 | 92.94% | 74.52% | 66.79% | 39715.08 | -3.17% | 953905.42 | 886525.14 | 67380.28 | 17603.63 | 0 | 0 | 0 | 0 | 660614.46 | 102 | 224827.68 | 1277% | YES | 224827.68 | 82200 | 592114.46 | 99489.03 | -44513.7 | 0 | 27224.9 | 39715.08 | 28% | 24.83% | 26.38% | -1.62% |  | 53.75 | [5 empty] | -1083
1736 | 2024-05-01 23:36 | P23105 | Raytheon Supply Engineering Support | Natalie Sinclair | 0 | RAY | RAYTHEON UNITED KINGDOM LIMITED | MPE | Level 3A | REIM | 2023-07-13 | 2 |  |  | 76.96% | 94.49% | 90.07% | 49156.8 | -2.02% | 1205008 | 927395.25 | 277612.75 | 0 | 0 | 0 | 0 | 0 | 876291.5 | 107644.5 | 48739.75 | 0% | NO | 48739.75 | 49157 | 835327.3333 | 0 | 0 | 49156.8 | 0 | 49156.8 | 26% | 23.98% | 100% | 74% |  | 48.97 | [5 empty] | -2364
1736 | 2024-05-01 23:36 | P23117 | BAE Typhoon Eng Support | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | 2024-03-12 | 11 |  |  | 105.2% | 95.01% | 90.49% | 54289.71 | -1.06% | 950771.99 | 1000558.49 | -49786.5 | -5566.92 | 19090.01 | 21165.02 | 69773.84 | 49786.5 | 950609.41 | 81713.4 | 22853.08 | -410.5% | NO | 24928.09 | 54290 | 905367.7433 | 0 | 54289.71 | 0 | 0 | 54289.71 | 30% | 28.94% | 12.07% | -17.93% |  | 52.3 | [5 empty] | -27096
1736 | 2024-05-01 23:36 | P22350 | EMP 2020-2021 | Natalie Sinclair | 0 | ARY | GUIDANT GLOBAL UK LIMITED | PCPR | Level NC | REIM |  |  |  | 3.4601 | 98.46% | 97.95% | 94.75% | 0 | -2.14% | 1017579.76 | 1001886.96 | 15692.8 | 4535.32 | 400 | 400 | 0 | 0 | 981385.51 | 62.64 | 20501.45 | 452% | YES | 20501.45 | 38567 | 949246.3433 | 24861.97 | 13704.72 | 0 | 0 | 0 | 32% | 29.86% | 27.33% | -4.67% |  | 44.13 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P22671 | Spirit Shorts Pylon and Fairing Package | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX | 2023-05-03 | 0 |  |  | 105% | 95.26% | 95.26% | 0 | -7.21% | 1198494.77 | 1258071.09 | -59576.32 | 0 | 106494.89 | 106494.89 | 0 | 59576.32 | 1198494.77 | 2544.39 | 2120.32 | 0% | NO | 2120.32 | 0 | 1198494.77 | 0 | 0 | 0 | 0 | 0 | 20% | 12.79% | 0% | -20% |  | 45.4 | [5 empty] | -57456
1736 | 2024-05-01 23:36 | P23152 | Project Aragon - Design and Stress Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 0.91555 | 99.27% | 76.89% | 55.09% | 0 | -9.55% | 1333452.21 | 1323715.17 | 9737.04 | 10635.23 | 0 | 0 | 0 | 0 | 1017835.58 | 351.32 | 305879.59 | 2876% | YES | 305879.59 | 346248 | 729295.58 | 346247.55 | 0 | 0 | 0 | 0 | 39% | 29.45% | 29.2% | -9.8% |  | 51.96 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23292 | BAE Tempest WP 4 AV Trays | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 8.0308 | 88.42% | 100.6% | 77.81% | 155584.85 | 1.52% | 1498284.22 | 1324741.72 | 173542.5 | 21609.67 | 0 | 0 | 0 | 0 | 1332801.4 | 91.02 | -8059.68 | -37.3% | NO | -8059.68 | 362500 | 1030718.0667 | 245826.2 | 116674.18 | 0 | 0 | 155584.85 | 32% | 33.52% | 31.95% | -0.05% |  | 53.73 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23519 | Mechanical and Electrical Design Eng Support | Dushan Fernando | 0 | BAX | SAFRAN SEATS GB LIMITED | MPE | Level 2 | REIM |  |  |  | 13.2116 | 78.44% | 98.28% | 78.53% | 0 | -1.56% | 1807261.3 | 1417594.15 | 389667.15 | 29494.28 | 1004.45 | 1504.45 | 0 | 0 | 1393199.8 | 65.91 | 24394.35 | 82.71% | NO | 24894.35 | 335892 | 1113289.8 | 335892.3 | 0 | 0 | 0 | 0 | 33% | 31.44% | 31.46% | -1.54% |  | 56.65 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23411 | Agile & Scrum Delivery Service | Peter Williams | 0 | BDZ | MBDA UK LIMITED | DET | Level 2 | REIM | 2023-08-14 | 0 |  |  | 36.3% | 170.5% | 170.5% | 0 | 13.08% | 2487000 | 902903.79 | 1584096.21 | 0 | 894178.59 | 894178.59 | 0 | 0 | 1539600 | 19368.95 | 16140.79 | 0% | NO | 16140.79 | 0 | 1539600 | 0 | 0 | 0 | 0 | 0 | 29% | 42.08% | 0% | -29% |  | 74.57 | [5 empty] | 652837
1736 | 2024-05-01 23:36 | P22278 | TAI Supply Engineers to Ankara | Natalie Sinclair | 0 | TAI | TUSAS-TURK HAVACILIK VE UZAY | MPE | Level 3A | REIM |  |  |  | 869.2928 | 19.64% | 462.2% | 462.2% | 0 | -15.66% | 2105282 | 413420.91 | 1691861.09 | 1946.25 | 49400.29 | 49400.29 | 0 | 0 | 1910696.33 | 98.45 | 13124.58 | 674.4% | YES | 13124.58 | 0 | 1910696.33 | 0 | 0 | 0 | 0 | 0 | 95% | 79.34% | 70.52% | -24.48% |  | 34.16 | [5 empty] | 1510400
1736 | 2024-05-01 23:36 | P23175 | BAe Aero Typhoon Package 2 | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM | 2024-03-12 | 2 |  |  | 103.8% | 96.32% | 96.32% | 0 | -1.63% | 1984265.09 | 2060011.83 | -75746.74 | 0 | 57677.87 | 86030.82 | 15444.64 | 75746.74 | 1984257.03 | 84731.75 | 70609.8 | 0% | NO | 98962.75 | 0 | 1984257.03 | 0 | 0 | 0 | 0 | 0 | 29% | 27.37% | 0% | -29% |  | 51.76 | [5 empty] | -5145
1736 | 2024-05-01 23:36 | P23006 | Spirit Shorts A350 Freighter Toulouse | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -8.2039 | 123.4% | 102.4% | 74.55% | 0 | 23.39% | 1341989.92 | 1656668.34 | -314678.42 | 38357.19 | 1086670.26 | 2010741.94 | 0 | 314678.42 | 1695787.93 | 385.68 | 372154.41 | 970.2% | YES | 1296226.09 | 552824 | 1235101.2633 | 140525.66 | 412298.62 | 0 | 0 | 0 | 5% | 28.39% | 53.8% | 48.8% |  | 48.15 | [5 empty] | 411274
1736 | 2024-05-01 23:36 | P23435 | Andy Baker Portfolio | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 41.0171 | 52.69% | 97.45% | 70.15% | 0 | -7.12% | 4023207.4 | 2119764.47 | 1903442.93 | 46406.04 | 2596.25 | 2596.25 | 0 | 0 | 2065770.21 | 90.11 | 53994.26 | 116.4% | NO | 53994.26 | 694595 | 1486941.0433 | 204990.14 | 489604.46 | 0 | 0 | 0 | 25% | 17.88% | 19.85% | -5.15% |  | 80.83 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P19020 | Spirit Concessions - 2018 | Carl Warren | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2024-01-23 | 3 |  |  | 90.82% | 111.8% | 107% | 99792.83 | 2.09% | 1914846.83 | 1739018.14 | 175828.69 | 0 | 44317.61 | 44317.61 | 15178.88 | 0 | 1944710.76 | 336177.69 | 196987.38 | 0% | NO | 196987.38 | 99793 | 1861549.9267 | 0 | 0 | 0 | 99792.83 | 99792.83 | 25% | 27.09% | 9.32% | -15.68% |  | 40.87 | [5 empty] | 402680
1736 | 2024-05-01 23:36 | P23257 | BAE Tempest WP 5 Centre Fuselage | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 4.408 | 96.73% | 98.33% | 90.79% | 110362.14 | -5.74% | 2265401.51 | 2191433.09 | 73968.42 | 16780.37 | 78100 | 78100 | 0 | 0 | 2154862.7 | 81.67 | 36570.39 | 217.9% | YES | 36570.39 | 198362 | 1989561.0333 | 87999.86 | 110362.14 | 0 | 0 | 110362.14 | 33% | 27.26% | 28.05% | -4.95% |  | 61.06 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23179 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX |  |  |  | -7.8875 | 100.8% | 94.47% | 86.37% | 0 | -9.28% | 2531995.04 | 2553310.9 | -21315.86 | 2702.48 | 156991.12 | 248243.92 | 0 | 21315.86 | 2412235.69 | 645.79 | 141075.21 | 5220% | YES | 232328.01 | 248280 | 2205335.69 | 0 | 248280.21 | 0 | 0 | 0 | 22% | 12.72% | 17.44% | -4.56% |  | 44.4 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P23207 | A350 Approvers - Design and Stress Support | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  | 1.2557 | 97.43% | 95.69% | 73.82% | 63762.48 | -5.25% | 2728308 | 2658296.59 | 70011.41 | 55756.34 | 36201.43 | 36766.42 | 0 | 0 | 2543608.88 | 83.39 | 114687.71 | 205.7% | YES | 115252.7 | 697590 | 1962283.88 | 444169.24 | 253420.79 | 0 | 0 | 63762.48 | 23% | 17.75% | 16.71% | -6.29% |  | 54.53 | [5 empty] | 0
1736 | 2024-05-01 23:36 | P19731 | Hapri HPC Rear Bearing Housing PDR & CDR | Steven Lawton | 0 | ATC | AECC Hunan Aviation Powerplant | MPE | Level 1 | FIX |  |  |  | -3.4259 | 100.3% | 99.67% | 87.21% | 447000 | -15.41% | 2980000 | 2989767.41 | -9767.41 | 2851.04 | 366282.13 | 500382.13 | 0 | 9767.41 | 2980000 | 695.18 | -215232.59 | -7549% | NO | -81132.59 | 447000 | 2607500 | 0 | 0 | 0 | 447000 | 447000 | 38% | 22.59% | 15.47% | -22.53% |  | 64.85 | [5 empty] | -225000
1736 | 2024-05-01 23:36 | P23487 | Tornado Air 800 Engineering Support | Richard Brook | 0 | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 2 | FIX |  |  |  | 11.7355 | 81.63% | 81.63% | 80.4% | 47390.58 | 2.56% | 3925502.05 | 3204542 | 720960.05 | 61434.08 | 0 | 0 | 0 | 0 | 2616021.67 | 76.02 | 615520.33 | 1002% | YES | 615520.33 | 47391 | 2576529.17 | 0 | 8658.1 | 8658.1 | 30074.38 | 47390.58 | 34% | 36.56% | 39.66% | 5.66% |  | 78.77 | [5 empty] | 27000
Extend Table

## AP5-1
WIP No | Date Created | Project ID | Project Description | Project Manager | Agency (1=yes, 0=no) | Department Id | Client | CBU | Complexity | Type | Stop Booking Hrs | Closing Project: Action(s) to close | RAG | Approx. PO Burndown (weeks) | Turnover vs Contract Value | Invoice To Date vs Turnover | Cash in vs Turnover | Open Amount Overdue | Actual PM% to Baseline PM% delta | Contract Value | Total Project Turnover | Contract Value - Total Turnover | Run Rate (based on total turnover) | Total BOI Spend to Date | Total Committed PO (supplier/best shore) | Current AA in PT3 | Exposure (turnover - contract value) | Invoiced To Date | DSO | Unbilled (WIP) | WIP / Run rate | WIP / Run rate >1.3 | WIP + Remaining Committed PO for BOI | Total Open Amount | Cash in (Invoiced - (Open amount -VAT)) | Debt <=30 Days | Debt 31 - 60 Days | Debt 61 - 90 Days | Debt >= 90 Days | Open Amount Overdue2 | Baseline Project Margin | Project To Date (PTD) PM | Year to Date (YTD) PM | YTD Delta Actual PM% to BPM% | Forecast PM at Completion (Manual input from PTT) | Average Sale Rate | CSat score for last quarter (Manual input from PTT) | Comments and Actions | Judged income adjustment at completion | Profit to take now | Provision required now | Fully Traded | Last Months Comments and Actions
1737 | 2024-05-08 23:31 | P23637 | MBSE Proposal | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM | 2024-04-28 | 0 | [5 empty] | 0 | -35% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23543 | EXP-024 FCAS AP Transformation & Change Enablers | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -26% | 385921 | 0 | 385921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26% | 0% | 0% | -26% |  | 0 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23552 | FCAS AP Product Technology Development | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -25% | 597871 | 0 | 597871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0% | -25% |  | 0 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23711 | DO NOT USE - RAISED IN ERROR | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23628 | Design Assurance | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | -7% | 0 | 0 | 0 | -977.31 | 0 | 0 | 4454.8 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 0% | 0.33% | -6.67% |  | 0 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23585 | Systems Design - Missile Systems, Meteor,Brimstone | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM | 2024-04-28 | 0 | [5 empty] | 0 | -35% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23717 | GKN Ted Tomblin 2024 | Matthew Tweed | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2024-04-28 | 0 | [5 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23886 | A220 F&DT Support | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [7 empty] | 0 | -18% | 0 | 0 | 0 | 0 | 0 | 0 | 12199.2 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 0% | 0% | -18% |  | 0 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23891 | A220 FLE Support | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [7 empty] | 0 | -7% | 0 | 0 | 0 | 0 | 0 | 0 | 36633.6 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 0% | 0% | -7% |  | 0 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23887 | EXP-039 Future Systems Synthetic Test Support | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -18% | 156475 | 0 | 156475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 0% | 0% | -18% |  | 0 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23892 | Warrior Environmental Control Unit | Trevin Fernandopulle | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -32% | 3920 | 0 | 3920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32% | 0% | 0% | -32% |  | 0 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23730 | FLE Project | Carl Warren | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -18.03% | 0 | 1120 | -1120 | 0 | 0 | 0 | 24000 | 1120 | 0 | 194.13 | 1120 | 0% | NO | 1120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | -18.03% | -18.03% | -18.03% |  | 35 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23463 | A220 Wing MaMo Design Checking | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-03-07 | 0 |  |  |  | 0% | 0% | 0 | 7.85% | 0 | 1628 | -1628 | 0 | 0 | 0 | 15000 | 1628 | 0 | 1953.6 | 1628 | 0% | NO | 1628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | 10.85% | 0% | -3% |  | 44 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23894 | EE Test and Integration Lead | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | -1 |  | 0% | 0% | 0 | 10.6% | 0 | 2363.56 | -2363.56 | 2363.56 | 0 | 0 | 15430 | 2363.56 | 0 | 7 | 2363.56 | 100% | NO | 2363.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23% | 33.6% | 33.6% | 10.6% |  | 63.88 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P21028 | Rebate Collection (BACC) | David Catchpole | 0 | TOO | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | [5 empty] | 0% | 0% | 0 | 0% | 0 | 2680 | -2680 | 0 | 2680 | 2680 | 0 | 2680 | 0 | 3216 | 2680 | 0% | NO | 2680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23888 | HondaJet FWD Assy Jig Tool Design | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX |  |  |  | 16.0723 | 11.07% | 0% | 0% | 0 | 4.29% | 31500 | 3486 | 28014 | 1743 | 0 | 0 | 0 | 0 | 0 | 21 | 3486 | 200% | YES | 3486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 14.29% | 14.29% | 4.29% |  | 42 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23578 | ESN Work Package | Hannah Mead | 0 | COZ | CHELTON LIMITED | DET | Level 3 | FIX | 2024-01-01 | 0 |  |  | 86.17% | 116.1% | 116.1% | 0 | 35.86% | 4410 | 3800 | 610 | 0 | 0 | 0 | 0 | 0 | 4410 | 0 | -610 | 0% | NO | -610 | 0 | 4410 | 0 | 0 | 0 | 0 | 0 | 24% | 59.86% | 0% | -24% |  | 95 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23880 | Warrior Crew Heater Design | Trevin Fernandopulle | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM |  |  |  | 0.67568 | 74.75% | 0% | 0% | 0 | 3.58% | 5544 | 4144 | 1400 | 2072 | 0 | 0 | 0 | 0 | 0 | 21 | 4144 | 200% | YES | 4144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32% | 35.58% | 35.58% | 3.58% |  | 56 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23881 | Bulldog Fuel System Design | Trevin Fernandopulle | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM |  |  |  | 1.8442 | 52.03% | 0% | 0% | 0 | 1.29% | 8288 | 4312 | 3976 | 2156 | 0 | 0 | 0 | 0 | 0 | 14 | 4312 | 200% | YES | 4312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13% | 14.29% | 14.29% | 1.29% |  | 56 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23864 | REACH Coordinator | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 31.3684 | 11.31% | 0% | 0% | 0 | -10.24% | 52920 | 5985 | 46935 | 1496.25 | 0 | 0 | 0 | 0 | 0 | 49 | 5985 | 400% | YES | 5985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27% | 16.76% | 16.76% | -10.24% |  | 30 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23002 | WoT MAJ Transit Flag Stress | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2024-04-03 | 1 |  | 4.7688 | 62.41% | 160.2% | 160.2% | 0 | 38.54% | 4735 | 2955.29 | 1779.71 | 373.2 | 1492.79 | 2242.5 | 0 | 0 | 4735 | 91.03 | 1493.29 | 400.1% | YES | 2243 | 0 | 4735 | 0 | 0 | 0 | 0 | 0 | 10% | 48.54% | 0% | -10% |  | 45 | [5 empty] | 3273
1737 | 2024-05-08 23:31 | P23843 | EXP-035 FT15 Exemplar information set | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 166.0389 | 3.664% | 0% | 0% | 0 | -11.8% | 175985.16 | 6447.82 | 169537.34 | 1021.07 | 0 | 0 | 0 | 0 | 0 | 49 | 6447.82 | 631.5% | YES | 6447.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 8.2% | 8.2% | -11.8% |  | 69.74 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23873 | FCAS Systems Engineering Support | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | -3 |  | 0% | 0% | 0 | 8.28% | 0 | 8713.5 | -8713.5 | 2904.5 | 0 | 0 | 26604 | 8713.5 | 0 | 21 | 8713.5 | 300% | YES | 8713.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 8.28% | 8.28% | 8.28% |  | 78.5 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23607 | SAFRAN - A330neo Turnover Frame | Gary Kempster | 0 | TOO | SAFRAN SEATS GB LIMITED | MPE | Level 3 | FIX |  |  |  |  | 95.69% | 104.5% | 104.5% | 0 | -19.52% | 8736 | 8359.05 | 376.95 | 0 | 0 | 0 | 0 | 0 | 8736 | 0.06 | 0.05 | 0% | NO | 0.05 | 0 | 8736 | 0 | 0 | 0 | 0 | 0 | 23% | 3.48% | 8.5% | -14.5% |  | 50.46 | [5 empty] | 377
1737 | 2024-05-08 23:31 | P23274 | ME Support (Aim Altitude - Cambridge) | Trevor Knox | 0 | AVI | AVIC CABIN SYSTEMS (UK) LIMITED | ME | Level 3 | FIX | 2023-08-18 | 0 |  |  | 51.88% | 56.3% | 56.3% | 0 | -0.17% | 17280 | 8964 | 8316 | 0 | 0 | 0 | 0 | 0 | 5046.3 | 4701.24 | 3917.7 | 0% | NO | 3917.7 | 0 | 5046.3 | 0 | 0 | 0 | 0 | 0 | 21% | 20.83% | 0% | -21% |  | 48 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23283 | Spirit Tooling Audit | Charidimos Valadakis | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-05-03 | 0 |  |  | 97.22% | 48.57% | 48.57% | 0 | -7.99% | 9910.08 | 9634.8 | 275.28 | 0 | 0 | 0 | 0 | 0 | 4679.76 | 5946.05 | 4955.04 | 0% | NO | 4955.04 | 0 | 4679.76 | 0 | 0 | 0 | 0 | 0 | 7% | -0.99% | 0% | -7% |  | 34.41 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23127 | Loft Hall Design Support | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-04-19 | 0 |  |  | 101% | 99.06% | 99.06% | 0 | -9.55% | 9680 | 9772 | -92 | 0 | 0 | 0 | 0 | 92 | 9680 | 110.4 | 92 | 0% | NO | 92 | 0 | 9680 | 0 | 0 | 0 | 0 | 0 | 41% | 31.45% | 0% | -41% |  | 44 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23630 | 2Excel CFD Analysis Support | Dushan Fernando | 0 | BAX | STIRLING DYNAMICS LTD | MPE | Level NC | FIX |  |  |  |  | 61.2% | 100% | 100% | 0 | -1.87% | 16195.49 | 9911.34 | 6284.15 | 0 | 0 | 0 | 0 | 0 | 9911.63 | 0 | -0.29 | 0% | NO | -0.29 | 0 | 9911.63 | 0 | 0 | 0 | 0 | 0 | 26% | 24.13% | 0% | -26% |  | 64.78 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23718 | Requalification of EJ200 GSS ESS EHM SW module | Vijayakumara Nanjundappa | 0 | ARZ | MTU AERO ENGINES AG | DET | Level 3 | FIX |  |  |  | 66.1647 | 12.92% | 188.4% | 188.4% | 0 | 11.59% | 74463 | 9621.57 | 64841.43 | 980 | 991.93 | 991.93 | 0 | 0 | 18125 | 0 | -6503.43 | -663.6% | NO | -6503.43 | 0 | 18125 | 0 | 0 | 0 | 0 | 0 | 28% | 39.59% | 39.59% | 11.59% |  | 80 | [5 empty] | 2000
1737 | 2024-05-08 23:31 | P23869 | EXP-037 Land Ceptor Development Hardware Test Def | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 37.0989 | 7.482% | 72.69% | -0.0006025% | 0 | 0.81% | 162694 | 12171.97 | 150522.03 | 4057.32 | 0 | 0 | 0 | 0 | 8848.26 | 42 | 3323.71 | 81.92% | NO | 3323.71 | 10618 | -0.073333 | 10617.91 | 0 | 0 | 0 | 0 | 26% | 26.81% | 26.81% | 0.81% |  | 89.83 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23313 | Laser Trim Fixtures | Gary Kempster | 0 | TOO | ALKEN ENGINEERING LIMITED | MPE | Level 3 | FIX | 2023-11-20 | 0 |  |  | 89.87% | 111.3% | 111.3% | 0 | 0.53% | 13770 | 12375 | 1395 | 0 | 0 | 0 | 0 | 0 | 13770 | 0 | -1395 | 0% | NO | -1395 | 0 | 13770 | 0 | 0 | 0 | 0 | 0 | 17% | 17.53% | 0% | -17% |  | 45 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P22761 | Red Bull Chassis Spit | Trevor Knox | 0 | TOO | MANUFAX ENGINEERING LTD | MPE | Level 3 | FIX | 2022-11-15 | 0 |  |  | 72.18% | 96.98% | 96.98% | 0 | 7.92% | 12961.2 | 9355.5 | 3605.7 | 0 | 0 | 0 | 0 | 0 | 9072.84 | 4666.39 | 3888.66 | 0% | NO | 3888.66 | 0 | 9072.84 | 0 | 0 | 0 | 0 | 0 | 23% | 30.92% | 0% | -23% |  | 42.19 | [5 empty] | 3606
1737 | 2024-05-08 23:31 | P23350 | Spirit 2023 - Stress Approve Man Serv (DH) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 14.15% | 72.64% | 72.64% | 0 | -0.29% | 97920 | 13860 | 84060 | 0 | 0 | 0 | 0 | 0 | 10068 | 4550.4 | 3792 | 0% | NO | 3792 | 0 | 10068 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23344 | Spirit A320 Spoilers Support 2023 | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 38.75% | 100% | 100% | 0 | 5.82% | 35786.4 | 13867.23 | 21919.17 | 0 | 0 | 0 | 0 | 0 | 13867.23 | 0 | 0 | 0% | NO | 0 | 0 | 13867.23 | 0 | 0 | 0 | 0 | 0 | 7% | 12.82% | 0% | -7% |  | 34.41 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23337 | Spirit 2023 - Steve Grimley | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 25.28% | 100% | 100% | 0 | 0.01% | 56812.9 | 14362.47 | 42450.43 | 0 | 0 | 0 | 0 | 0 | 14362.47 | 0 | 0 | 0% | NO | 0 | 0 | 14362.47 | 0 | 0 | 0 | 0 | 0 | 7% | 7.01% | 0% | -7% |  | 30.11 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23597 | MRB Onsite support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-02-16 | 1 |  |  |  | 0% | 0% | 0 | -10.04% | 0 | 15100.57 | -15100.57 | 0 | 9448.07 | 17381.62 | 24200 | 15100.57 | 0 | 147.14 | 15100.57 | 0% | NO | 23034.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 7.96% | 8.95% | -9.05% |  | 42.5 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23343 | Spirit 2023 - John Agnew | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-08-09 | 0 |  |  | 24.64% | 100% | 100% | 0 | -0.02% | 65120.37 | 16047.15 | 49073.22 | -638.44 | 0 | 0 | 0 | 0 | 16047.15 | 0 | 0 | 0% | NO | 0 | 0 | 16047.15 | 0 | 0 | 0 | 0 | 0 | 7% | 6.98% | 6.98% | -0.02% |  | 34.51 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23842 | Tranche 1 Evolution Package Step 2 | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -4.6726 |  | 0% | 0% | 0 | -14.52% | 0 | 17340.05 | -17340.05 | 3710.97 | 1000 | 1000 | 67488.9 | 17340.05 | 0 | 49 | 17340.05 | 467.3% | YES | 17340.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31% | 16.48% | 16.48% | -14.52% |  | 55.31 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23635 | Engineering Services: FAI Support | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 49.9% | 100% | 0.0008972% | 0 | -3.4% | 37230 | 18576 | 18654 | 0 | 0 | 0 | 0 | 0 | 18576 | 910 | 0 | 0% | NO | 0 | 22291 | 0.16667 | 0 | 7058.88 | 15232.32 | 0 | 0 | 8% | 4.6% | 5.04% | -2.96% |  | 38.7 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23839 | Stirling Dynamics - ST002-GFEM | Matthew Dodd | 0 | BAX | STIRLING DYNAMICS LTD | MPE | Level NC | FIX |  |  |  | -73.6776 |  | 0% | 0% | 0 | -4.93% | 0 | 20505.95 | -20505.95 | 278.32 | 1225.5 | 1225.5 | 19985.76 | 20505.95 | 0 | 91 | 20505.95 | 7368% | YES | 20505.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 2.07% | 2.07% | -4.93% |  | 43.72 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23874 | Environmental Engineering (Sea Venom/ANL) | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | -3 |  | 0% | 0% | 0 | 18.9% | 0 | 20881 | -20881 | 6960.33 | 0 | 0 | 27140.5 | 20881 | 0 | 28 | 20881 | 300% | YES | 20881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 18.9% | 18.9% | 18.9% |  | 78.5 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23355 | Spirit Tooling Support 2023 | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-23 | 0 |  |  | 22.93% | 89.02% | 89.02% | 0 | -0.82% | 91800 | 21053.34 | 70746.66 | 0 | 0 | 0 | 0 | 0 | 18742.5 | 2773.01 | 2310.84 | 0% | NO | 2310.84 | 0 | 18742.5 | 0 | 0 | 0 | 0 | 0 | 20% | 19.18% | 0% | -20% |  | 44.46 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23663 | Spirit Tooling Verification and Inspection | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 1 | FIX |  |  |  | 2.4516 | 91.52% | 80.98% | 0.001638% | 0 | -6.4% | 23123.52 | 21162.15 | 1961.37 | 800.03 | 0 | 0 | 0 | 0 | 17136.18 | 182.89 | 4025.97 | 503.2% | YES | 4025.97 | 20563 | 0.34667 | 0 | 12635.35 | 7928.06 | 0 | 0 | 11% | 4.6% | 4.82% | -6.18% |  | 34.41 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23742 | Cyber Security Support | Hannah Mead | 0 | COZ | CHELTON LIMITED | DET | Level 3 | FIX |  |  |  | 1.9333 | 89.45% | 111.8% | 0% | 0 | -0.96% | 27500 | 24600 | 2900 | 1500 | 0 | 0 | 0 | 0 | 27500 | 114.8 | -2900 | -193.3% | NO | -2900 | 33000 | 0 | 33000 | 0 | 0 | 0 | 0 | 32% | 31.04% | 31.04% | -0.96% |  | 100 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23351 | Spirit 2023 - Design Man Serv (KL) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 26.47% | 93.15% | 93.15% | 0 | 0.09% | 93840 | 24840 | 69000 | 0 | 0 | 0 | 0 | 0 | 23138 | 2042.4 | 1702 | 0% | NO | 1702 | 0 | 23138 | 0 | 0 | 0 | 0 | 0 | 26% | 26.09% | 0% | -26% |  | 46 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23356 | Spirit 2023 - Design Man Serv (AH) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX | 2023-08-09 | 1 |  |  |  | 76.66% | 0.001332% | 23018.4 | 0.48% | 0 | 25023.08 | -25023.08 | 0 | 0 | 0 | 25300 | 25023.08 | 19182 | 30027.7 | 5841.08 | 0% | NO | 5841.08 | 23018 | 0.33333 | 0 | 0 | 0 | 23018.4 | 23018.4 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P22884 | Spirit Shorts Config Eng | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 66.3% | 100.1% | 100.1% | 0 | 0.56% | 38976 | 25841.9 | 13134.1 | 0 | 0 | 0 | 0 | 0 | 25863.2 | 0 | -0.3 | 0% | NO | -0.3 | 0 | 25863.2 | 0 | 0 | 0 | 0 | 0 | 7% | 7.56% | 0% | -7% |  | 20.3 | [5 empty] | 21
1737 | 2024-05-08 23:31 | P23354 | Spirit 2023 - Design Man Serv (PC) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 27.97% | 99.36% | 99.36% | 0 | 0.48% | 93840 | 26248.98 | 67591.02 | 0 | 0 | 0 | 0 | 0 | 26082 | 200.38 | 166.98 | 0% | NO | 166.98 | 0 | 26082 | 0 | 0 | 0 | 0 | 0 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P22756 | A350 FLE Design Checker | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2022-03-23 | 1 |  |  | 68.39% | 119.7% | 119.7% | 0 | 16.46% | 34898.4 | 23867.15 | 11031.25 | 0 | 23867.15 | 24342.3 | 0 | 0 | 28571.1 | 0.06 | 0.05 | 0% | NO | 475.2 | 0 | 28571.1 | 0 | 0 | 0 | 0 | 0 | 0% | 16.46% | 0% | 0% |  | 0 | [5 empty] | 4704
1737 | 2024-05-08 23:31 | P23831 | Contract DM/00113 for maintenance, repair and post | Harry James Kellett | 0 | BXW | MOD | EES | Level 2 | FIX |  |  |  | 3.3719 | 73.97% | 0% | 0% | 0 | 14.02% | 40800 | 30177.76 | 10622.24 | 3150.21 | 0 | 0 | 0 | 0 | 0 | 91 | 30177.76 | 958% | YES | 30177.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37% | 51.02% | 51.02% | 14.02% |  | 80.26 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23458 | Spirit Belfast Tooling Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-08-11 | 0 |  |  | 101.3% | 94.65% | 94.65% | 0 | 8.64% | 30384 | 30784.9 | -400.9 | 0 | 0 | 0 | 0 | 400.9 | 29139.1 | 1974.96 | 1645.8 | 0% | NO | 1645.8 | 0 | 29139.1 | 0 | 0 | 0 | 0 | 0 | 7% | 15.64% | 0% | -7% |  | 42.2 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23433 | Cavendish | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 5.8481 | 75.21% | 43.63% | 43.63% | 0 | -0.42% | 42240 | 31767.2 | 10472.8 | 1790.8 | 0 | 0 | 0 | 0 | 13859.2 | 91 | 17908 | 1000% | YES | 17908 | 0 | 13859.2 | 0 | 0 | 0 | 0 | 0 | 7% | 6.58% | 6.51% | -0.49% |  | 46.34 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23724 | GKN S McConnell 2024 | Matthew Tweed | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  | 9.5946 | 64.5% | 94.26% | -0.0008506% | 0 | 0.84% | 49820 | 32133.93 | 17686.07 | 1843.34 | 0 | 0 | 0 | 0 | 30290.56 | 125.42 | 1843.37 | 100% | NO | 1843.37 | 36349 | -0.27333 | 8369.76 | 10761.12 | 8848.03 | 8369.76 | 0 | 19% | 19.84% | 19.84% | 0.84% |  | 49.59 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23365 | GKN 777x Lip Skin Fixture | Steven Lawton | 0 | TOO | GKN AEROSPACE SERVICES LTD | MPE | Level 3 | FIX | 2023-10-12 | 0 |  |  | 41.91% | 113.2% | 113.2% | 0 | -9.26% | 79161.46 | 33175.67 | 45985.79 | 0 | 5109.88 | 5109.88 | 0 | 0 | 37544.22 | 0 | -4368.55 | 0% | NO | -4368.55 | 0 | 37544.22 | 0 | 0 | 0 | 0 | 0 | 22% | 12.74% | 0% | -22% |  | 56 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23811 | Spirit T300 MRB Concessions | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -13.1303 |  | 0% | 0% | 0 | -7.05% | 0 | 34294.88 | -34294.88 | 2611.88 | 0 | 0 | 34639 | 34294.88 | 0 | 84 | 34294.88 | 1313% | YES | 34294.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21% | 13.95% | 13.95% | -7.05% |  | 46.81 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P22768 | MRB Onsite Support - Spirit Belfast | Trevor Knox | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2023-07-27 | 0 |  |  |  | 0% | 0% | 0 | -17.07% | 0 | 34614 | -34614 | 0 | 0 | 0 | 36800 | 34614 | 0 | 41536.8 | 34614 | 0% | NO | 34614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | -7.07% | 0% | -10% |  | 36 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23651 | PMO Spirit | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 9.1136 | 70.71% | 67.3% | -0.0004783% | 0 | -19.31% | 49284 | 34848 | 14436 | 1584 | 0 | 0 | 0 | 0 | 23454 | 246.75 | 11394 | 719.3% | YES | 11394 | 28145 | -0.16667 | 0 | 0 | 28144.8 | 0 | 0 | 43% | 23.69% | 23.12% | -19.88% |  | 36 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23740 | Phase 2 - EJ200 ESS EHM Platform Migration | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 3 | FIX |  |  |  | 43.8253 | 17.81% | 240.6% | 80.19% | 0 | 9.85% | 175971 | 31347.5 | 144623.5 | 3300 | 0 | 0 | 0 | 0 | 75417 | 32.5 | -40069.5 | -1214% | NO | -40069.5 | 60334 | 25138.6667 | 30166.8 | 30166.8 | 0 | 0 | 0 | 28% | 37.85% | 37.85% | 9.85% |  | 42.8 | [5 empty] | 4000
1737 | 2024-05-08 23:31 | P23821 | Supply of Safety Engineer | Dinna Elkhalifa | 0 | BXW | STIRLING DYNAMICS LTD | EES | Level NC | REIM |  |  |  | -3.8294 | 106.6% | 49% | -0.0006437% | 22765.86 | 45.1% | 34006.44 | 36247.77 | -2241.33 | 585.29 | 0 | 0 | 0 | 2241.33 | 17760.6 | 126.3 | 18487.17 | 3159% | YES | 18487.17 | 21313 | -0.23333 | 0 | 21312.72 | -15645.36 | 15645.36 | 22765.86 | 0% | 45.1% | 45.1% | 45.1% |  | 80.73 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23347 | WoT Fixed Leading Edge - Industrial 2023 | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | -10.6486 | 120.5% | 39.34% | 39.34% | 0 | -0.38% | 31034.12 | 37389.34 | -6355.22 | 596.81 | 0 | 0 | 10500 | 6355.22 | 14710.56 | 27214.54 | 22678.78 | 3800% | YES | 22678.78 | 0 | 14710.56 | 0 | 0 | 0 | 0 | 0 | 7% | 6.62% | 7.01% | 0.01% |  | 32.26 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23051 | Spirit Shorts A350 PAX Door | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3A | REIM |  |  |  |  | 205.9% | 105.4% | 105.4% | 0 | -0.63% | 18216 | 37513 | -19297 | 0 | 0 | 0 | 0 | 19297 | 39537 | 0 | 0 | 0% | NO | 0 | 0 | 39537 | 0 | 0 | 0 | 0 | 0 | 30% | 29.37% | 0% | -30% |  | 46 | [5 empty] | 2024
1737 | 2024-05-08 23:31 | P23338 | Spirit 2023 - Blair Hainey | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 12.3733 | 63.32% | 45.31% | 45.31% | 0 | 5.93% | 62893.71 | 39822.98 | 23070.73 | 1864.56 | 0 | 0 | 0 | 0 | 18042.36 | 242.97 | 21780.62 | 1168% | YES | 21780.62 | 0 | 18042.36 | 0 | 0 | 0 | 0 | 0 | 7% | 12.93% | 17.81% | 10.81% |  | 18.28 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23823 | EXP-034 Spear 3 Test Equip Requirement Authority | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 10.9176 | 46.46% | 77.64% | 9.218% | 0 | -0.04% | 85825 | 39878.13 | 45946.87 | 4208.5 | 1000 | 1000 | 0 | 0 | 30961.13 | 76.26 | 8917 | 211.9% | YES | 8917 | 32742 | 3676.13 | 15494.7 | 17247.76 | 0 | 0 | 0 | 14% | 13.96% | 13.96% | -0.04% |  | 94.25 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P22752 | Tooling WoT - 2021 (Spirit) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | REIM | 2023-05-03 | 0 |  |  | 101.1% | 74.02% | 74.02% | 0 | -8.5% | 41525.1 | 41982.28 | -457.18 | 0 | 0 | 0 | 0 | 457.18 | 31076.1 | 13087.42 | 10906.18 | 0% | NO | 10906.18 | 0 | 31076.1 | 0 | 0 | 0 | 0 | 0 | 0% | -8.5% | 0% | 0% |  | 39.09 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23339 | Spirit 2023 - Stewart Russell | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 64.51% | 100% | 100% | 0 | 0.62% | 72766.8 | 46941.72 | 25825.08 | 0 | 0 | 0 | 0 | 0 | 46941.74 | 0 | -0.02 | 0% | NO | -0.02 | 0 | 46941.74 | 0 | 0 | 0 | 0 | 0 | 7% | 7.62% | 0% | -7% |  | 35.67 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23598 | MRB Onsite support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 24.2785 | 36.89% | 0% | 0% | 0 | -10.53% | 133056 | 49090.17 | 83965.83 | 3458.44 | 8736.42 | 14079.58 | 0 | 0 | 0 | 101.23 | 49090.17 | 1419% | YES | 54433.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 17.47% | 17.79% | -10.21% |  | 42.5 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23760 | EXP-033 Systems Engineering Support | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 32.0753 | 35.64% | 88.39% | 46.98% | 0 | -0.02% | 142300 | 50711 | 91589 | 2855.44 | 0 | 0 | 0 | 0 | 44823.5 | 67.83 | 5887.5 | 206.2% | YES | 5887.5 | 25199 | 23824.3333 | 12387.3 | 0 | 12811.2 | 0 | 0 | 29% | 28.98% | 28.98% | -0.02% |  | 78.5 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P22760 | SA Leading Edge Transport Media ('A' Frames) | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-11-15 | 1 |  |  | 85.99% | 110.7% | 116.3% | -3082.8 | 3.97% | 53480.8 | 45985.5 | 7495.3 | 0 | 42804 | 42804 | 0 | 0 | 50911.8 | 0 | -0.3 | 0% | NO | -0.3 | -3083 | 53480.9667 | 0 | 0 | 0 | -3082.8 | -3082.8 | 6% | 9.97% | 0% | -6% |  | 42 | [5 empty] | 4926
1737 | 2024-05-08 23:31 | P23642 | MRB Belfast Support | Carl Warren | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -26.529 |  | 0% | 0% | 0 | -44.28% | 0 | 52674.97 | -52674.97 | 1985.56 | 3566.12 | 3566.12 | 48125 | 52674.97 | 0 | 194.05 | 52674.97 | 2653% | YES | 52674.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22% | -22.28% | -24.62% | -46.62% |  | 38.52 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23349 | Spirit 2023 - Stress Approve Man Serv (SB) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 58.24% | 80.05% | 80.05% | 0 | -0.29% | 97920 | 57024 | 40896 | 0 | 0 | 0 | 0 | 0 | 45648 | 13651.2 | 11376 | 0% | NO | 11376 | 0 | 45648 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23322 | GKN T Tomblin 2023 | Steven Lawton | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2024-04-15 | 1 |  |  | 99.66% | 100% | 95.06% | 0 | -0.33% | 58952 | 58752 | 200 | 0 | 0 | 0 | 0 | 0 | 58752 | 46.86 | 0 | 0% | NO | 0 | 3485 | 55847.8333 | 0 | 0 | 3484.8 | 0 | 0 | 17% | 16.67% | 16.67% | -0.33% |  | 48 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23106 | ME Support to NPD - Bobby Haggart | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  |  | 95.79% | 97.03% | 97.03% | 0 | 0.3% | 65675 | 62912.11 | 2762.89 | 0 | 0 | 0 | 0 | 0 | 61042.75 | 2243.24 | 1869.36 | 0% | NO | 1869.36 | 0 | 61042.75 | 0 | 0 | 0 | 0 | 0 | 15% | 15.3% | 0% | -15% |  | 35.65 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P22967 | Spirit 2022 - Channapa Laxmeshwar | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2023-01-26 | 2 |  |  | 69.69% | 121.3% | 121.3% | 0 | 9.53% | 75159.1 | 52376.15 | 22782.95 | 0 | 52376.15 | 54898.1 | 0 | 0 | 63508.8 | 0.42 | 0.35 | 0% | NO | 2522.3 | 0 | 63508.8 | 0 | 0 | 0 | 0 | 0 | 8% | 17.53% | 0% | -8% |  | 0 | [5 empty] | 11133
1737 | 2024-05-08 23:31 | P23193 | Spirit Shorts Stephen Greer | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -7.4584 | 109.7% | 90.02% | 81.04% | 0 | 8.72% | 61472 | 67441.38 | -5969.38 | 800.36 | 0 | 0 | 10878 | 5969.38 | 60712.78 | 135.23 | 6728.6 | 840.7% | YES | 6728.6 | 7269 | 54655.28 | 0 | 0 | 7268.72 | 0 | 0 | 23% | 31.72% | 34.03% | 11.03% |  | 35.15 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23341 | Spirit 2023 - Tom McFarlane | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 40.0179 | 63.66% | 92.91% | 62.19% | 7110.19 | -0.01% | 108666.4 | 69177.13 | 39489.27 | 986.79 | 0 | 0 | 0 | 0 | 64272.02 | 175.17 | 4905.11 | 497.1% | YES | 4905.11 | 25503 | 43019.52 | 0 | 16061.8 | 2331.04 | 7110.19 | 7110.19 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23877 | Strategic Enablement | Owain Jones | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -3 |  | 0% | 0% | 0 | -16.99% | 0 | 71017.3 | -71017.3 | 23672.43 | 4000 | 4000 | 67200 | 71017.3 | 0 | 97.39 | 71017.3 | 300% | YES | 71017.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 1.01% | 1.01% | -16.99% |  | 42 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23600 | MBDA EXP-EE-023 Bristone Certification | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 59.65% | 100% | 100% | 0 | 0.4% | 126600 | 75517 | 51083 | 0 | 0 | 0 | 0 | 0 | 75517 | 0 | 0 | 0% | NO | 0 | 0 | 75517 | 0 | 0 | 0 | 0 | 0 | 41% | 41.4% | 0% | -41% |  | 78.5 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23080 | Spirit Shorts DManagement Cairan Cullen | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 1143.1262 | 50.94% | 97.36% | 94.85% | 0 | -1.27% | 149600 | 76211.3 | 73388.7 | 64.2 | 0 | 0 | 0 | 0 | 74199.7 | 118.43 | 2011.6 | 3133% | YES | 2011.6 | 2298 | 72284.7 | 0 | 0 | 2298.36 | 0 | 0 | 24% | 22.73% | 13.03% | -10.97% |  | 44.39 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23700 | IPDT Leads | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 15.799 | 46.61% | 31.6% | -0.0004817% | 0 | -1.65% | 169263.9 | 78888.71 | 90375.19 | 5720.3 | 0 | 0 | 0 | 0 | 24932.12 | 134.8 | 53956.59 | 943.2% | YES | 53956.59 | 29919 | -0.38 | 0 | 0 | 29918.54 | 0 | 0 | 26% | 24.35% | 22.8% | -3.2% |  | 50.07 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P22505 | Spirit MRB Engineering Support 2021 | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 1 |  |  | 91.17% | 100% | 95.78% | 4020.48 | 21.2% | 87110.4 | 79414.95 | 7695.45 | 0 | 0 | 0 | 0 | 0 | 79414.95 | 4020.48 | 0 | 0% | NO | 0 | 4020 | 76064.95 | 0 | 0 | 0 | 4020.48 | 4020.48 | 0% | 21.2% | 0% | 0% |  | 41.88 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P22885 | ME Support (Baxi) | Trevor Knox | 0 | HUV | BAXI HEATING UK LIMITED | ME | Level 3 | FIX | 2023-01-12 | 0 |  |  | 68.78% | 108.7% | 108.7% | 0 | 13.05% | 106632.96 | 73340.24 | 33292.72 | 0 | 0 | 0 | 0 | 0 | 79748.12 | 1531.35 | 1276.12 | 0% | NO | 1276.12 | 0 | 79748.12 | 0 | 0 | 0 | 0 | 0 | 15% | 28.05% | 0% | -15% |  | 44.37 | [5 empty] | 7684
1737 | 2024-05-08 23:31 | P22965 | Spirit 2022 - Design Man Serv (AH) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 106.7% | 96.66% | 96.66% | 0 | 3.14% | 80079.56 | 85441.32 | -5361.76 | 0 | 0 | 0 | 0 | 5361.76 | 82588.96 | 3422.84 | 2852.36 | 0% | NO | 2852.36 | 0 | 82588.96 | 0 | 0 | 0 | 0 | 0 | 14% | 17.14% | 0% | -14% |  | 42.44 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23523 | Applique Armour Support | Dushan Fernando | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-18 | 1 |  |  | 72.43% | 138.1% | 98.47% | 40680 | 3.42% | 118200 | 85606.5 | 32593.5 | 0 | 0 | 0 | 0 | 0 | 118200 | 1567.8 | -32593.5 | 0% | NO | -32593.5 | 40680 | 84300 | 0 | 0 | 40680 | 0 | 40680 | 25% | 28.42% | 0% | -25% |  | 64.29 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P22964 | Spirit 2022 - MRB Man Serv (JC) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 100.6% | 97.95% | 97.95% | 0 | 1.91% | 85435.2 | 85960.26 | -525.06 | 0 | 0 | 0 | 0 | 525.06 | 84199.74 | 2112.62 | 1760.52 | 0% | NO | 1760.52 | 0 | 84199.74 | 0 | 0 | 0 | 0 | 0 | 16% | 17.91% | 0% | -16% |  | 42.69 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P22963 | Spirit 2022 - Design Man Serv (PC) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 108.6% | 104% | 104% | 0 | 3.18% | 80079.56 | 86926.74 | -6847.18 | 0 | 0 | 0 | 0 | 6847.18 | 90389.95 | 0 | -3463.21 | 0% | NO | -3463.21 | 0 | 90389.95 | 0 | 0 | 0 | 0 | 0 | 13% | 16.18% | 0% | -13% |  | 42.39 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23342 | Spirit 2023 - Channapa Laxmeshwar | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 237.5059 | 53.17% | 109.3% | 73.25% | 4036.8 | -3.73% | 158696.7 | 84385.85 | 74310.85 | 312.88 | 84385.85 | 94827 | 0 | 0 | 92257.7 | 105.63 | -5021.85 | -1605% | NO | 5419.3 | 36533 | 61813.5333 | 0 | 32496.24 | 0 | 4036.8 | 4036.8 | 7% | 3.27% | 0% | -7% |  | 0 | [5 empty] | 2850
1737 | 2024-05-08 23:31 | P23729 | Honda Tooling | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | FIX |  |  |  | 4.3615 | 77.81% | 36.7% | 0% | 38934 | 2.96% | 113610 | 88399.5 | 25210.5 | 5780.25 | 0 | 0 | 0 | 0 | 32445 | 116.24 | 55954.5 | 968% | YES | 55954.5 | 38934 | 0 | 0 | 0 | 38934 | 0 | 38934 | 10% | 12.96% | 12.96% | 2.96% |  | 42 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23438 | A220 Spirit Shorts DTC - Stephen Corry | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 4.207 | 92.59% | 72.57% | 45.48% | 0 | -7.18% | 95928.4 | 88823.7 | 7104.7 | 1688.78 | 0 | 0 | 0 | 0 | 64459.8 | 246.71 | 24363.9 | 1443% | YES | 24363.9 | 28872 | 40399.8 | 0 | 0 | 28872.36 | 0 | 0 | 23% | 15.82% | 16.95% | -6.05% |  | 49.87 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23744 | Model Factory | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 29.6788 | 33.03% | 103.2% | 26.38% | 0 | 8.94% | 262300 | 86634.75 | 175665.25 | 5918.88 | 0 | 0 | 0 | 0 | 89432 | 93.67 | 202.75 | 3.425% | NO | 202.75 | 79889 | 22857.8333 | 27429.6 | 26229.6 | 0 | 26229.6 | 0 | 28% | 36.94% | 36.94% | 8.94% |  | 50.87 | [5 empty] | 3000
1737 | 2024-05-08 23:31 | P23079 | Spirit Shorts Nomenclature | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -3.9799 | 103.9% | 85.07% | 74.36% | 0 | 15.13% | 88455 | 91904.4 | -3449.4 | 866.7 | 0 | 0 | 5136 | 3449.4 | 78185.2 | 249.23 | 13719.2 | 1583% | YES | 13719.2 | 11811 | 68342.7 | 0 | 0 | 11810.64 | 0 | 0 | 7% | 22.13% | 25.23% | 18.23% |  | 30.82 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23340 | Spirit 2023 - John Cole | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 39.3514 | 61.42% | 92.02% | 60.18% | 8831.16 | -0.01% | 150129.72 | 92210.04 | 57919.68 | 1471.86 | 0 | 0 | 0 | 0 | 84850.74 | 179.47 | 7359.3 | 500% | YES | 7359.3 | 35229 | 55493.24 | 0 | 21576.67 | 4821.34 | 8831.16 | 8831.16 | 7% | 6.99% | 6.99% | -0.01% |  | 39.78 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23375 | GKN Jaap Peters NL 2023 | Steven Lawton | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2024-03-01 | 1 |  |  | 93.37% | 105.3% | 97.18% | 0 | -15.93% | 97123.22 | 90686.41 | 6436.81 | 0 | 90686.41 | 90686.41 | 0 | 0 | 95456.72 | 40.01 | -920.31 | 0% | NO | -920.31 | 8793 | 88129.22 | 0 | 0 | 0 | 8793.29 | 0 | 20% | 4.07% | 0% | -20% |  | 0 | [5 empty] | 3850
1737 | 2024-05-08 23:31 | P23171 | Spirt Shorts Weights Eng | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 10.9035 | 69.18% | 141.4% | 122.7% | 0 | 13.12% | 103113.14 | 71329.32 | 31783.82 | 2915 | 71329.32 | 85975.13 | 0 | 0 | 100870.18 | 54.04 | -5610.86 | -192.5% | NO | 9034.95 | 16006 | 87531.8467 | 6733.3 | 9273.05 | 0 | 0 | 0 | 12% | 25.12% | 47.26% | 35.26% |  | 0 | [5 empty] | 23930
1737 | 2024-05-08 23:31 | P23336 | Spirit 2023 - Neil Rampling | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 28.66 | 71.24% | 92.8% | 50.18% | 21586.03 | -0.01% | 133901.52 | 95387.98 | 38513.54 | 1343.81 | 0 | 0 | 0 | 0 | 88522.6 | 228.7 | 6865.38 | 510.9% | YES | 6865.38 | 48792 | 47862.6 | 0 | 22565.28 | 4640.79 | 21586.03 | 21586.03 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23465 | A220 ToW Design Offload (Wing) | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 58.8363 | 39.43% | 94.38% | 56.65% | 0 | -5.46% | 249700 | 98450.7 | 151249.3 | 2570.68 | 0 | 0 | 0 | 0 | 92918.8 | 137.24 | 5531.9 | 215.2% | YES | 5531.9 | 44580 | 55768.8 | 14843.04 | 0 | 29737.44 | 0 | 0 | 20% | 14.54% | 12.48% | -7.52% |  | 42.8 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23583 | Castalla - Test Rig Design | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 98.73% | 68% | 61.73% | 0 | -27% | 100520 | 99240.5 | 1279.5 | -297 | 0 | 0 | 0 | 0 | 67482.1 | 185.93 | 31758.4 | -10693% | NO | 31758.4 | 7469 | 61257.9333 | 0 | 0 | 7469.4 | 0 | 0 | 41% | 14% | 14.71% | -26.29% |  | 42.78 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23345 | Spirit 2023- Jonathan Escosio | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 20.3274 | 66.27% | 81.48% | 50.9% | 15846.34 | -0.48% | 151941.24 | 100686.41 | 51254.83 | 2521.46 | 0 | 0 | 0 | 0 | 82035.91 | 221.13 | 18650.5 | 739.7% | YES | 18650.5 | 36942 | 51250.91 | 0 | 16361 | 4734.58 | 15846.34 | 15846.34 | 7% | 6.52% | 18.97% | 11.97% |  | 43.01 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23560 | NJEWCS TAF202302 SM | Natalie Sinclair | 0 | COB | CHELTON LIMITED | EES | Level 2 | FIX |  |  |  | 16.9152 | 52.84% | 79.06% | 39.53% | 0 | 9.85% | 191500 | 101191.86 | 90308.14 | 5338.86 | 0 | 0 | 0 | 0 | 80000 | 175.33 | 21191.86 | 396.9% | YES | 21191.86 | 48000 | 40000 | 0 | 48000 | 0 | 0 | 0 | 30% | 39.85% | 39.49% | 9.49% |  | 73.01 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23551 | Ian Berry 2023 H2 | Natalie Sinclair | 0 | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  | -18.0968 | 133.7% | 66.32% | 66.32% | 0 | 13.59% | 75810 | 101350.41 | -25540.41 | 1411.32 | 0 | 0 | 24259.2 | 25540.41 | 67217.49 | 99.88 | 34132.92 | 2419% | YES | 34132.92 | 0 | 67217.49 | 0 | 0 | 0 | 0 | 0 | 22% | 35.59% | 37.71% | 15.71% |  | 77.75 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23586 | Project Management Support | Dushan Fernando | 0 | BDX | MBDA UK LIMITED | MPE | Level NC | REIM |  |  |  | 15.4753 | 65.39% | 93.84% | 64.13% | 0 | -26.59% | 160000 | 104631.86 | 55368.14 | 3577.85 | 1668.6 | 1668.6 | 0 | 0 | 98183.86 | 98.79 | 6448 | 180.2% | YES | 6448 | 37296 | 67103.86 | 37296 | 0 | 0 | 0 | 0 | 49% | 22.41% | 21.41% | -27.59% |  | 80 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23353 | Spirit 2023 - MRB Man Serv (JC) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  | 50.6167 | 62.78% | 59.53% | 59.53% | 0 | 9.71% | 183600 | 115267.5 | 68332.5 | 1350 | 0 | 0 | 0 | 0 | 68615.25 | 237.64 | 46652.25 | 3456% | YES | 46652.25 | 0 | 68615.25 | 0 | 0 | 0 | 0 | 0 | 7% | 16.71% | 13.06% | 6.06% |  | 45 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P22918 | Spirit Shorts Graduates | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 15.5393 | 91.03% | 90.19% | 90.19% | 0 | 9.49% | 130000 | 118343.84 | 11656.16 | 750.11 | 0 | 0 | 19800 | 0 | 106734.95 | 73.55 | 11608.89 | 1548% | YES | 11608.89 | 0 | 106734.95 | 0 | 0 | 0 | 0 | 0 | 7% | 16.49% | 17.19% | 10.19% |  | 23.32 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P22736 | WoT Fixed Leading Edge - Industrial | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 106.7% | 93.42% | 91.32% | 3019.54 | 0.01% | 112196.27 | 119668.47 | -7472.2 | 0 | 0 | 0 | 0 | 7472.2 | 111796.68 | 12465.69 | 7871.79 | 0% | NO | 7871.79 | 3020 | 109280.0133 | 0 | 0 | 0 | 3019.54 | 3019.54 | 7% | 7.01% | 0% | -7% |  | 32.26 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23545 | Ultra CSS continuation 2023 H2 | Natalie Sinclair | 0 | ULT | ULTRA SONAR SYSTEMS LIMITED | EES | Level NC | REIM |  |  |  | -8.9605 | 159.6% | 78.79% | 62.22% | 0 | 2.18% | 76000 | 121263.2 | -45263.2 | 5051.4 | 0 | 0 | 49859.2 | 45263.2 | 95544.8 | 130.84 | 25718.4 | 509.1% | YES | 25718.4 | 24112 | 75451.4667 | 24112.32 | 0 | 0 | 0 | 0 | 23% | 25.18% | 25% | 2% |  | 80 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23753 | Tempest Composites Maturation | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 0.63654 | 97.05% | 57.24% | 25.05% | 0 | -10.93% | 127848.45 | 124073.64 | 3774.81 | 5930.22 | 0 | 0 | 0 | 0 | 71025.53 | 78.37 | 53048.11 | 894.5% | YES | 53048.11 | 47929 | 31084.6967 | 47928.88 | 0 | 0 | 0 | 0 | 32% | 21.07% | 21.07% | -10.93% |  | 64.54 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23588 | BAE Typhoon MRB MC Shop Concessions | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 20.2923 | 71.13% | 90.04% | 64.48% | 38190.65 | -3.62% | 175060.5 | 124523.47 | 50537.03 | 2490.45 | 0 | 0 | 0 | 0 | 112121.71 | 129.88 | 12401.76 | 498% | YES | 12401.76 | 38191 | 80295.8767 | 0 | 10272.55 | 13518.34 | 14399.76 | 38190.65 | 31% | 27.38% | 29.16% | -1.84% |  | 55.56 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23784 | Tempest Tooling Offload 2024 | Gary Kempster | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  | -16.8838 |  | 0% | 0% | 0 | -7.03% | 0 | 124608.92 | -124608.92 | 7380.37 | 0 | 0 | 159270 | 124608.92 | 0 | 121.75 | 124608.92 | 1688% | YES | 124608.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 17.97% | 17.97% | -7.03% |  | 54.95 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P22861 | WoT FLE Lifting & Handling Tools | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2023-06-14 | 1 |  |  | 65.17% | 101.6% | 101.6% | 0 | 12.01% | 173987.21 | 113381.75 | 60605.46 | 0 | 50078 | 58423.58 | 0 | 0 | 115203.5 | 12813.9 | 10678.25 | 0% | NO | 19023.83 | 0 | 115203.5 | 0 | 0 | 0 | 0 | 0 | 1% | 13.01% | 0% | -1% |  | 45 | [5 empty] | 12500
1737 | 2024-05-08 23:31 | P23352 | Spirit 2023 - Stress Approve Man Serv (CC) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  | 24.97 | 64.35% | 55.48% | 55.48% | 0 | 5.85% | 195840 | 126024 | 69816 | 2796 | 0 | 0 | 0 | 0 | 69912 | 224.9 | 56112 | 2007% | YES | 56112 | 0 | 69912 | 0 | 0 | 0 | 0 | 0 | 7% | 12.85% | 4.69% | -2.31% |  | 48 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23664 | Tempest Composites WP3 | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -1.9749 | 105.4% | 66.71% | 12.8% | 0 | -5.14% | 122455.49 | 129072.38 | -6616.89 | 3350.48 | 0 | 0 | 14830.4 | 6616.89 | 86110.38 | 293.93 | 42962 | 1282% | YES | 42962 | 83510 | 16518.7133 | 0 | 83510.02 | 0 | 0 | 0 | 37% | 31.86% | 33.18% | -3.82% |  | 60.87 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23282 | Tooling Support (MBDA) | Dushan Fernando | 0 | BDV | MBDA UK LIMITED | ME | Level NC | REIM |  |  |  | 33.6697 | 66.99% | 97.03% | 79.19% | 0 | -7.86% | 195672.4 | 131079.76 | 64592.64 | 1918.42 | 0 | 0 | 0 | 0 | 127186.8 | 107.06 | 3892.96 | 202.9% | YES | 3892.96 | 28059 | 103804.3 | 7411.63 | 0 | 20647.76 | 0 | 0 | 30% | 22.14% | 30.37% | 0.37% |  | 49.73 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23270 | Shorts Project X | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 6.0382 | 92.85% | 92.82% | 66.55% | 0 | 0.41% | 142248 | 132072.08 | 10175.92 | 1685.25 | 0 | 0 | 0 | 0 | 122595.46 | 184.47 | 9476.62 | 562.3% | YES | 9476.62 | 41647 | 87889.6267 | 7981.34 | 10030.61 | 23635.49 | 0 | 0 | 13% | 13.41% | 10.99% | -2.01% |  | 45.32 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P22883 | Spirit Shorts Evtol PMO C. Hatton | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 17.0928 | 71.77% | 81.7% | 81.7% | 0 | -10.95% | 185800 | 133342.15 | 52457.85 | 3069 | 0 | 0 | 0 | 0 | 108946.73 | 126.29 | 24395.42 | 794.9% | YES | 24395.42 | 0 | 108946.73 | 0 | 0 | 0 | 0 | 0 | 26% | 15.05% | 22.96% | -3.04% |  | 37.36 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23810 | Strategic Enablement | Owain Jones | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -843.2318 |  | 0% | 0% | 0 | -20.63% | 0 | 133694.4 | -133694.4 | 158.55 | 0 | 0 | 134000 | 133694.4 | 0 | 195.66 | 133694.4 | 84323% | YES | 133694.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | -2.63% | -2.63% | -20.63% |  | 42 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23822 | FCASW Requirements Management | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 21.9008 | 22.86% | 83.59% | 0% | 0 | -2.39% | 595703 | 136177.88 | 459525.12 | 20982.14 | 0 | 0 | 0 | 0 | 113825 | 91 | 22352.88 | 106.5% | NO | 22352.88 | 136590 | 0 | 136590 | 0 | 0 | 0 | 0 | 17% | 14.61% | 14.61% | -2.39% |  | 78.5 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23533 | External Stowage Design and Detail Support | Dushan Fernando | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 1 |  |  | 102.4% | 97.65% | 73.24% | 42000 | 3.33% | 140000 | 143368.75 | -3368.75 | 0 | 0 | 0 | 3369 | 3368.75 | 140000 | 41999.7 | -0.25 | 0% | NO | -0.25 | 42000 | 105000 | 0 | 0 | 42000 | 0 | 42000 | 27% | 30.33% | 0% | -27% |  | 60.04 | [5 empty] | -3369
1737 | 2024-05-08 23:31 | P23650 | MBDA Recruitment Management costs | Andrew Slaney | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM | 2024-02-01 | 0 |  |  |  | 0% | 0% | 0 | -20.2% | 0 | 240971.5 | -240971.5 | 0 | 0 | 0 | 266000 | 240971.5 | 0 | 169165.8 | 140971.5 | 0% | NO | 140971.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | -17.2% | -441% | -444% |  | 82.3 | [5 empty] | -100000
1737 | 2024-05-08 23:31 | P22954 | Technical Support Step 1 | Owain Jones | 0 | HUV | HUARUI SPIRIT AEROSPACE MANUFACT | ME | Level 2 | REIM |  |  |  |  | 94.81% | 58.01% | 58.01% | 0 | 0.31% | 155501.18 | 147431.58 | 8069.6 | 0 | 23043 | 23043 | 0 | 0 | 85525.49 | 61906.09 | 61906.09 | 0% | NO | 61906.09 | 0 | 85525.49 | 0 | 0 | 0 | 0 | 0 | 30% | 30.31% | 0% | -30% |  | 60.79 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23386 | Software Development - BMS | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 98.78% | 100% | 100% | 0 | 4.31% | 149650 | 147823.35 | 1826.65 | 0 | 0 | 0 | 0 | 0 | 147823.35 | 0 | 0 | 0% | NO | 0 | 0 | 147823.35 | 0 | 0 | 0 | 0 | 0 | 18% | 22.31% | 22.61% | 4.61% |  | 78.5 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23437 | Embedded Software Engineer | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 98.73% | 100% | 96.08% | 0 | -6.29% | 150150 | 148239.36 | 1910.64 | 0 | 737.86 | 737.86 | 0 | 0 | 148239.36 | 36.4 | 0 | 0% | NO | 0 | 6971 | 142430.1933 | 0 | 0 | 6970.8 | 0 | 0 | 22% | 15.71% | 16.24% | -5.76% |  | 78.5 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23550 | Tempest Composites | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -6.1907 | 102.5% | 97.57% | 97.57% | 0 | 5.11% | 149494.92 | 153217.46 | -3722.54 | 601.31 | 0 | 0 | 2396.12 | 3722.54 | 149494.92 | 35.88 | 3722.54 | 619.1% | YES | 3722.54 | 0 | 149494.92 | 0 | 0 | 0 | 0 | 0 | 26% | 31.11% | 33.8% | 7.8% |  | 61.6 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P22440 | Spirit Managed Service - F&DT and Static Approval | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 3 |  |  | 88.56% | 92.56% | 92.56% | 0 | 11.51% | 173500 | 153656.25 | 19843.75 | 0 | 52115 | 55720 | 0 | 0 | 142225.12 | 13717.36 | 11431.13 | 0% | NO | 15036.13 | 0 | 142225.12 | 0 | 0 | 0 | 0 | 0 | 0% | 11.51% | 0% | 0% |  | 44.73 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P22982 | Spirit 2022 - Hugh Sloan | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 255.5759 | 62.7% | 96.91% | 81.81% | 8217.17 | -0.66% | 247473 | 155171.78 | 92301.22 | 361.15 | 0 | 0 | 0 | 0 | 150381.98 | 197.52 | 4789.8 | 1326% | YES | 4789.8 | 28121 | 126947.8133 | 0 | 15604.11 | 4300.18 | 8217.17 | 8217.17 | 7% | 6.34% | 0.48% | -6.52% |  | 35.48 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23518 | Systems Engineering support to FCAS | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 9.5532 | 87.32% | 94.03% | 83.59% | 0 | -5.32% | 193736.8 | 169176.75 | 24560.05 | 2570.88 | 3927.4 | 3927.4 | 0 | 0 | 159084.68 | 78.47 | 10092.07 | 392.6% | YES | 10092.07 | 21195 | 141422.18 | 11351.1 | 0 | 9843.9 | 0 | 0 | 30% | 24.68% | 3.5% | -26.5% |  | 68.56 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23754 | Tempest Composites WP4 | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 8.939 | 55.19% | 0% | 0% | 0 | -1.34% | 310945.68 | 171625.32 | 139320.36 | 15585.66 | 1784.87 | 1784.87 | 0 | 0 | 0 | 114.67 | 171625.32 | 1101% | YES | 171625.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36% | 34.66% | 34.66% | -1.34% |  | 61.51 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23508 | Verification and Validation | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 80.77% | 100% | 97.06% | 0 | 10.77% | 212950 | 171993.5 | 40956.5 | 0 | 0 | 0 | 0 | 0 | 171993.53 | 32.47 | -0.03 | 0% | NO | -0.03 | 6076 | 166930.1967 | 0 | 0 | 6075.9 | 0 | 0 | 24% | 34.77% | 33.6% | 9.6% |  | 78.5 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23667 | Safety Systems Engineer | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 54.3833 | 44.39% | 95.39% | 77.58% | 0 | -10.67% | 398000 | 176660 | 221340 | 4070 | 0 | 0 | 0 | 0 | 168520 | 69.55 | 8140 | 200% | YES | 8140 | 37752 | 137060 | 18216 | 19536 | 0 | 0 | 0 | 47% | 36.33% | 29.32% | -17.68% |  | 110 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23464 | A220 Project X Design Offload | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 97.4 | 53.59% | 97.33% | 61.81% | 27862.8 | -9.39% | 332340 | 178097.3 | 154242.7 | 1583.6 | 0 | 0 | 0 | 0 | 173346.5 | 223.84 | 4750.8 | 300% | YES | 4750.8 | 75910 | 110088.1667 | 1900.32 | 18361.2 | 27785.76 | 27862.8 | 27862.8 | 26% | 16.61% | 14.68% | -11.32% |  | 42.88 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23421 | A220 DTC | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 9.5149 | 82.72% | 72.73% | 59.64% | 0 | -28.28% | 217089.12 | 179567.07 | 37522.05 | 3943.49 | 0 | 0 | 0 | 0 | 130597.8 | 121.72 | 48969.27 | 1242% | YES | 48969.27 | 28204 | 107094.4667 | 12403.44 | 0 | 15800.9 | 0 | 0 | 29% | 0.72% | 5.39% | -23.61% |  | 45.95 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23008 | Spirit Shorts Project Rachel | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 68.49% | 91.32% | 91.32% | 0 | -9.7% | 286960 | 196531.2 | 90428.8 | 0 | 0 | 0 | 0 | 0 | 179472.8 | 20470.08 | 17058.4 | 0% | NO | 17058.4 | 0 | 179472.8 | 0 | 0 | 0 | 0 | 0 | 15% | 5.3% | 0.31% | -14.69% |  | 46.04 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23019 | EXP034-B Actuator Development | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 103.1% | 89.91% | 89.91% | 0 | -16.68% | 215541.2 | 222215.54 | -6674.34 | 0 | 12297.9 | 12297.9 | 0 | 6674.34 | 199796.76 | 122.03 | 397.78 | 0% | NO | 397.78 | 0 | 199796.76 | 0 | 0 | 0 | 0 | 0 | 34% | 17.32% | 79.64% | 45.64% |  | 58.45 | [5 empty] | -22021
1737 | 2024-05-08 23:31 | P23741 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  | 30.9742 | 31.04% | 99.71% | 22.57% | 0 | 2.19% | 640812 | 198883.8 | 441928.2 | 14267.64 | 0 | 0 | 0 | 0 | 198299 | 91.19 | 4584.8 | 32.13% | NO | 4584.8 | 184097 | 44884.8333 | 68808 | 62626.8 | 0 | 52662 | 0 | 28% | 30.19% | 30.19% | 2.19% |  | 38.82 | [5 empty] | 4000
1737 | 2024-05-08 23:31 | P23505 | EXP-022 Meteor TBUS T&E support | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 7.8454 | 87.15% | 96.24% | 83.5% | 0 | -1.34% | 246744.4 | 215030.56 | 31713.84 | 4042.35 | 0 | 0 | 0 | 0 | 206945.88 | 67.82 | 8084.68 | 200% | YES | 8084.68 | 32878 | 179547.5467 | 13636.2 | 0 | 19241.59 | 0 | 0 | 20% | 18.66% | 15.67% | -4.33% |  | 89.83 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23739 | Lifing Services DACs | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  | 31.3228 | 32% | 105.1% | 26.52% | 0 | 4.62% | 656508 | 210103.7 | 446404.3 | 14251.73 | 0 | 0 | 0 | 0 | 220836 | 94.04 | -5732.3 | -40.22% | NO | -5732.3 | 198152 | 55709.3333 | 66850.8 | 65650.8 | 0 | 65650.8 | 0 | 28% | 32.62% | 32.62% | 4.62% |  | 37.77 | [5 empty] | 5000
1737 | 2024-05-08 23:31 | P23506 | ASTER Mid-Life Refurbishment Project Manager | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 20.9365 | 65.92% | 96.02% | 81.09% | 0 | 1.1% | 326900 | 215491.41 | 111408.59 | 5321.25 | 2806.41 | 2806.41 | 0 | 0 | 206911.41 | 69.18 | 8580 | 161.2% | YES | 8580 | 38610 | 174736.41 | 24552 | 14058 | 0 | 0 | 0 | 25% | 26.1% | 26.42% | 1.42% |  | 110 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23242 | Physical Architecture & System Engineering Support | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 32.0711 | 70.84% | 96.93% | 86.6% | 0 | 7.14% | 305459 | 216399.46 | 89059.54 | 2776.94 | 775.55 | 775.55 | 0 | 0 | 209745.3 | 70.55 | 6300.16 | 226.9% | YES | 6300.16 | 26800 | 187411.9667 | 12669.9 | 0 | 14130 | 0 | 0 | 15% | 22.14% | 7.22% | -7.78% |  | 78.21 | [5 empty] | -354
1737 | 2024-05-08 23:31 | P23373 | Raytheon Michael Bellini | Natalie Sinclair | 0 | RAS | RAYTHEON UNITED KINGDOM LIMITED | EES | Level NC | REIM |  |  |  | -1.596 | 102.1% | 87.6% | 78.18% | 24734.7 | -7.76% | 214367.4 | 218881.63 | -4514.23 | 2828.46 | 0 | 0 | 13558.28 | 4514.23 | 191739.73 | 100.39 | 27141.9 | 959.6% | YES | 27141.9 | 24735 | 171127.23 | 0 | 0 | 24734.7 | 0 | 24734.7 | 45% | 37.24% | 38.69% | -6.31% |  | 91.61 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23648 | EXP-032 Delivery of Datalink Eng support - FCAS AP | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 15.259 | 60.21% | 73.1% | 60.84% | 0 | 7.05% | 371000 | 223387.95 | 147612.05 | 9673.75 | 1032.95 | 1032.95 | 0 | 0 | 163302.95 | 71.63 | 60085 | 621.1% | YES | 60085 | 32868 | 135912.95 | 13332 | 19536 | 0 | 0 | 0 | 22% | 29.05% | 29.71% | 7.71% |  | 102.21 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23524 | Bombardier Regional Jets (BRJ) | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -9.3271 | 154% | 48.32% | 46.95% | 3694.07 | -3.85% | 146287.84 | 225239.76 | -78951.92 | 8464.77 | 0 | 0 | 113075 | 78951.92 | 108838.22 | 293.44 | 116401.54 | 1375% | YES | 116401.54 | 3694 | 105759.8867 | 0 | 0 | 0 | 3694.07 | 3694.07 | 18% | 14.15% | 17.31% | -0.69% |  | 43.75 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23472 | Tempest Wing Design | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 66.135 | 52.29% | 120.4% | 109.7% | 0 | -11.62% | 483869.78 | 253017.11 | 230852.67 | 3490.63 | 237137.5 | 356900 | 0 | 0 | 304757.78 | 0.9 | -26740.68 | -766.1% | NO | 93021.82 | 32717 | 277493.6133 | 0 | 32716.75 | 0 | 0 | 0 | 23% | 11.38% | 29.4% | 6.4% |  | 46.74 | [5 empty] | 25000
1737 | 2024-05-08 23:31 | P23007 | EXP-006A - Brimstone 3 | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 88.485 | 68.6% | 99.48% | 88.69% | 14977.8 | -2.61% | 406450 | 278815.66 | 127634.34 | 1442.44 | 0 | 0 | 0 | 0 | 277363.38 | 100.83 | 1422.28 | 98.6% | NO | 1422.28 | 36102 | 247278.38 | 9631.96 | 11492.4 | 14977.8 | 0 | 14977.8 | 25% | 22.39% | 29.94% | 4.94% |  | 69.99 | [5 empty] | -30
1737 | 2024-05-08 23:31 | P21463 | Safety & Monitoring Systems at DM Beith & Gosport | Harry James Kellett | 0 | BXW | MOD | EES | Level 2 | FIX |  |  |  | 29.7487 | 78.71% | 127% | 125.1% | 0 | -28.14% | 368916.31 | 290384.74 | 78531.57 | 2639.83 | 75403.45 | 77420.74 | 21721 | 0 | 368898.31 | 0 | -78513.57 | -2974% | NO | -76496.28 | 6883 | 363162.4767 | 6883.39 | 0 | 0 | 0 | 0 | 48% | 19.86% | 19.87% | -28.13% |  | 53.04 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23603 | Typhoon IMDLR | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 1.9596 | 95.85% | 40.97% | 0.0001163% | 143769.41 | 3.51% | 305067.09 | 292400.18 | 12666.91 | 6464.02 | 1500 | 1500 | 0 | 0 | 119807.84 | 612.75 | 172592.34 | 2670% | YES | 172592.34 | 143769 | 0.34 | 0 | 0 | 143769.41 | 0 | 143769.41 | 26% | 29.51% | 27.03% | 1.03% |  | 56.7 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23629 | F35 FTI | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level NC | REIM |  |  |  | -18.0261 |  | 78.59% | 78.59% | 0 | -1.27% | 0 | 300013.9 | -300013.9 | 16643.27 | 0 | 0 | 0 | 300013.9 | 235774.05 | 39.99 | 64239.85 | 386% | YES | 64239.85 | 0 | 235774.05 | 0 | 0 | 0 | 0 | 0 | 31% | 29.73% | 28.8% | -2.2% |  | 61.38 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23308 | NATO JEWCS | Natalie Sinclair | 0 | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  | 20.6505 | 84.87% | 94.83% | 90.36% | 0 | -3.92% | 356307 | 302394.55 | 53912.45 | 2610.71 | 613.89 | 613.89 | 0 | 0 | 286767.43 | 110.78 | 15627.12 | 598.6% | YES | 15627.12 | 16216 | 273254.0967 | 15829.13 | 386.92 | 0 | 0 | 0 | 24% | 20.08% | 11.86% | -12.14% |  | 75.81 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23743 | EHM Cloud Migration | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 33.6732 | 28.19% | 119.5% | 29.82% | 0 | 5.98% | 1016000 | 286431.13 | 729568.87 | 21666.16 | 0 | 0 | 0 | 0 | 342376 | 79.36 | -35944.88 | -165.9% | NO | -35944.88 | 308362 | 85407.6667 | 103612.8 | 102336 | 0 | 102412.8 | 0 | 28% | 33.98% | 33.98% | 5.98% |  | 55.07 | [5 empty] | 20000
1737 | 2024-05-08 23:31 | P23677 | ME Managed Service - Phase 1 | Paul Watson | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  | 9.8055 | 56.98% | 75.56% | 0% | 0 | -14.79% | 554400 | 315878.85 | 238521.15 | 24325.31 | 0 | 38000 | 0 | 0 | 238680 | 119.63 | 77198.85 | 317.4% | YES | 115198.85 | 286416 | 0 | 71536.5 | 214879.5 | 0 | 0 | 0 | 33% | 18.21% | 20.46% | -12.54% |  | 44.07 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P22953 | Spirit Shorts eVTOL | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-05-08 | 2 |  |  | 103.1% | 80.83% | 79.36% | 0 | -9.51% | 324272 | 334483.6 | -10211.6 | 0 | 66696.6 | 67387.9 | 0 | 10211.6 | 270366 | 70861.92 | 54117.6 | 0% | NO | 54808.9 | 5921 | 265431.8333 | 0 | 0 | 5920.8 | 0 | 0 | 17% | 7.49% | 100% | 83% |  | 46.19 | [5 empty] | -10000
1737 | 2024-05-08 23:31 | P22515 | Shorts A220 100/300 ALI Phase III | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 36.7959 | 83.25% | 98.43% | 89.19% | 0 | 0.62% | 400628.76 | 333510.05 | 67118.71 | 1824.08 | 3450.98 | 3450.98 | 0 | 0 | 328273.11 | 143.5 | 5236.94 | 287.1% | YES | 5236.94 | 36969 | 297465.61 | 0 | 18582.69 | 18386.68 | 0 | 0 | 10% | 10.62% | 6.9% | -3.1% |  | 40.53 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23699 | A220 Stress Checkers | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 83.82% | 0% | 0% | 0 | 4.01% | 408328.79 | 342248.61 | 66080.18 | 0 | 12000 | 12000 | 0 | 0 | 0 | 164.48 | 342248.61 | 0% | NO | 342248.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16% | 20.01% | 20.04% | 4.04% |  | 61.88 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P22842 | ME Support (Aim Altitude) | Trevor Knox | 0 | AVI | AIM ALTITUDE UK LIMITED | ME | Level 3 | FIX | 2023-06-14 | 4 |  |  | 99.31% | 100.5% | 86.63% | 57290.84 | 0.49% | 346293.67 | 343918.08 | 2375.59 | 0 | 2909.86 | 2909.86 | 0 | 0 | 345673.01 | 55184.93 | -1754.93 | 0% | NO | -1754.93 | 57291 | 297930.51 | 0 | 0 | 0 | 57290.84 | 57290.84 | 13% | 13.49% | 0% | -13% |  | 46.3 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23816 | Typhoon FTI Works - 2024 Fixed Price Element | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 2.4956 | 83.96% | 54.08% | 4.912e-05% | 0 | -1.41% | 404176.65 | 339328.23 | 64848.42 | 25984.78 | 0 | 0 | 0 | 0 | 183496 | 94.31 | 165832.23 | 638.2% | YES | 165832.23 | 220195 | 0.16667 | 220195.2 | 0 | 0 | 0 | 0 | 30% | 28.59% | 28.59% | -1.41% |  | 51.98 | [5 empty] | 10000
1737 | 2024-05-08 23:31 | P22391 | GE System Engineering support | Vinayakumar Sugur | 0 | GEE | EXPERIS LIMITED | EES | Level NC | REIM | 2024-04-08 | 0 |  |  | 82.01% | 100.7% | 100.7% | 0 | 0.13% | 434434.25 | 356260.63 | 78173.62 | 0 | 0 | 0 | 0 | 0 | 358805.6 | 0 | -2544.97 | 0% | NO | -2544.97 | 0 | 358805.6 | 0 | 0 | 0 | 0 | 0 | 6% | 6.13% | 6.09% | 0.09% |  | 57.33 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23617 | Tempest Composites WP2 | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -11.5872 | 148.4% | 27.89% | 15.94% | 29536.68 | 11.64% | 244405.26 | 362706.59 | -118301.33 | 10209.67 | 0 | 0 | 120669.84 | 118301.33 | 101150.9 | 319.44 | 261555.69 | 2562% | YES | 261555.69 | 51981 | 57833.4 | 0 | 22444.14 | 0 | 29536.68 | 29536.68 | 22% | 33.64% | 33.34% | 11.34% |  | 62.15 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23045 | Shotgun Adaptors - 10 Sets | Harry James Kellett | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | FIX | 2024-02-27 | 3 |  |  | 74.76% | 133.8% | 133.8% | 0 | 2.29% | 399276.11 | 298512.88 | 100763.23 | 0 | 214550.47 | 214550.47 | 0 | 0 | 399276.11 | 0 | -7763.23 | 0% | NO | -7763.23 | 0 | 399276.11 | 0 | 0 | 0 | 0 | 0 | 29% | 31.29% | 99.78% | 70.78% |  | 55.76 | [5 empty] | 93000
1737 | 2024-05-08 23:31 | P23432 | Spirit Belfast MRB On-Site Support (Mon & Clear) | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 65.77% | 128.6% | 103.8% | 0 | -11.53% | 449545 | 295665.27 | 153879.73 | 0 | 295665.27 | 451827.33 | 0 | 0 | 380234.75 | 120831.02 | 27430.52 | 0% | NO | 183592.58 | 87914 | 306973.0833 | 0 | 0 | 87914.4 | 0 | 0 | 39% | 27.47% | 0% | -39% |  | 0 | [5 empty] | 112000
1737 | 2024-05-08 23:31 | P23023 | Spirit Shorts R Foster/M Gourley | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 40.4002 | 70.54% | 104.9% | 92.03% | 0 | -1.1% | 590659.44 | 416673.6 | 173985.84 | 4306.56 | 237621.5 | 267726 | 0 | 0 | 437064.88 | 65.38 | 1974.72 | 45.85% | NO | 32079.22 | 64309 | 383474.0467 | 20217.14 | 24971.11 | 19120.72 | 0 | 0 | 9% | 7.9% | 11.47% | 2.47% |  | 29.67 | [5 empty] | 22366
1737 | 2024-05-08 23:31 | P23372 | BAE Carbon Tooling Off-load | Gary Kempster | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  |  | 100.5% | 95.27% | 95.27% | 0 | -1.13% | 454982.37 | 457433.31 | -2450.94 | 0 | 0 | 0 | 1285.68 | 2450.94 | 435785.94 | 25976.85 | 21647.37 | 0% | NO | 21647.37 | 0 | 435785.94 | 0 | 0 | 0 | 0 | 0 | 24% | 22.87% | 20.74% | -3.26% |  | 53.57 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P22906 | Spirit Shorts - MRB JD Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 4.6425 | 96.47% | 83.21% | 65.38% | 99451.32 | -7.9% | 481714 | 464695.18 | 17018.82 | 3665.88 | 0 | 0 | 0 | 0 | 386687.62 | 349.81 | 86007.56 | 2346% | YES | 86007.56 | 99451 | 303811.7867 | 0 | 0 | 0 | 99451.32 | 99451.32 | 13% | 5.1% | 2.47% | -10.53% |  | 36.95 | [5 empty] | 8000
1737 | 2024-05-08 23:31 | P22652 | L3 - Saftey Engineering | Sean Simmons | 0 | LHW | L3HARRIS MAPPS LIMITED | EES | Level NC | FIX |  |  |  |  | 95.63% | 95.66% | 86.69% | 0 | 5.66% | 523390 | 500497.5 | 22892.5 | 0 | 0 | 0 | 0 | 0 | 478783.75 | 79938 | 21713.75 | 0% | NO | 21713.75 | 53882 | 433882.0833 | 0 | 53881.5 | 0 | 0 | 0 | 21% | 26.66% | 25.88% | 4.88% |  | 83.05 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23554 | Dornier Seawings 328 2023 H2 Support | Steven Lawton | 0 | DAX | EXPLEO GERMANY GMBH (EC) | MPE | Level 2 | REIM |  |  |  | 0.73506 | 98.57% | 85.45% | 85.45% | 0 | 5.7% | 508481.81 | 501202.03 | 7279.78 | 9903.7 | 4046.44 | 4046.44 | 0 | 0 | 428252.8 | 58.47 | 72949.23 | 736.6% | YES | 72949.23 | 0 | 428252.8 | 0 | 0 | 0 | 0 | 0 | 21% | 26.7% | 22.95% | 1.95% |  | 65.94 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23531 | BAe Systems F35 MRB Support | Richard Brook | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | -56.0034 |  | 92.92% | 92.92% | 0 | 3.48% | 0 | 503175.12 | -503175.12 | 8984.73 | 287.44 | 287.44 | 0 | 503175.12 | 467545.66 | 23.61 | 35629.46 | 396.6% | YES | 35629.46 | 0 | 467545.66 | 0 | 0 | 0 | 0 | 0 | 25% | 28.48% | 31.76% | 6.76% |  | 60 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23281 | Systems Portfolio | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM | 2024-02-28 | 0 |  |  | 44.43% | 97.31% | 97.31% | 0 | -17.25% | 1177697.24 | 523236.96 | 654460.28 | 0 | 2133.28 | 2133.28 | 0 | 0 | 509179.87 | 15792.1 | 13160.09 | 0% | NO | 13160.09 | 0 | 509179.87 | 0 | 0 | 0 | 0 | 0 | 25% | 7.75% | 100% | 75% |  | 70.48 | [5 empty] | -897
1737 | 2024-05-08 23:31 | P23520 | FCAS AP Portfolio Systems | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 21.0156 | 66.44% | 95.11% | 76.79% | 0 | -6.58% | 810821 | 538740.93 | 272080.07 | 12946.6 | 423 | 423 | 0 | 0 | 512377.44 | 67.45 | 22080.49 | 170.6% | YES | 22080.49 | 118439 | 413678.2733 | 56206.8 | 0 | 62232.16 | 0 | 0 | 22% | 15.42% | 16.32% | -5.68% |  | 81.13 | [5 empty] | -4283
1737 | 2024-05-08 23:31 | P23140 | Spirit Shorts A220 MLG Stress Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  | 20.6271 | 69.29% | 106.1% | 64.86% | 0 | -13.91% | 735573.4 | 509692.55 | 225880.85 | 10950.67 | 20870.3 | 87811.88 | 0 | 0 | 540939.4 | 207.82 | -6246.85 | -57.05% | NO | 60694.73 | 252442 | 330571.0667 | 0 | 204098.4 | 48343.2 | 0 | 0 | 25% | 11.09% | -10.44% | -35.44% |  | 45.44 | [5 empty] | 25000
1737 | 2024-05-08 23:31 | P23001 | Spirit Shorts A220 Design | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -18.8804 | 112.3% | 76.26% | 67.01% | 0 | 11.48% | 486640 | 546438 | -59798 | 3167.2 | 0 | 0 | 65953.2 | 59798 | 416705.3 | 401.27 | 129732.7 | 4096% | YES | 129732.7 | 60669 | 366147.8 | 21930.72 | 9501.6 | 29236.68 | 0 | 0 | 9% | 20.48% | 11.54% | 2.54% |  | 43.57 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23473 | Tempest Vertical Tail | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 23.6218 | 67.65% | 96.97% | 86.17% | 0 | -7.08% | 846017.62 | 572341.48 | 273676.14 | 11585.75 | 105500 | 112425 | 12000 | 0 | 554989.62 | 54.65 | 22351.86 | 192.9% | YES | 29276.86 | 74168 | 493182.9533 | 0 | 74168.03 | 0 | 0 | 0 | 29% | 21.92% | 24.49% | -4.51% |  | 62.54 | [5 empty] | 5000
1737 | 2024-05-08 23:31 | P23219 | Tornado Air 800 Engineering Support | Richard Brook | 0 | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 3 | REIM |  |  |  |  | 98.48% | 95.49% | 95.49% | 0 | -1.52% | 615046 | 605713.28 | 9332.72 | -6324.63 | 459.21 | 459.21 | 0 | 0 | 578373.17 | 13.69 | 2433.11 | -38.47% | NO | 2433.11 | 0 | 578373.17 | 0 | 0 | 0 | 0 | 0 | 31% | 29.48% | 307.2% | 276.2% |  | 81.67 | [5 empty] | -24907
1737 | 2024-05-08 23:31 | P23694 | Systems Portfolio EXP-011a | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 1.9739 | 92.48% | 91.1% | 60.49% | 0 | 1.92% | 648492.8 | 599721.28 | 48771.52 | 24707.6 | 444.4 | 444.4 | 0 | 0 | 546332.19 | 71.4 | 53389.09 | 216.1% | YES | 53389.09 | 220264 | 362778.8567 | 142737.46 | 77526.61 | 0 | 0 | 0 | 21% | 22.92% | 20.1% | -0.9% |  | 88.55 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23685 | DAC LUC Support and Recompliance | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 35.7381 | 25.59% | 173.5% | 45.07% | 0 | 3.49% | 2180000 | 557836.26 | 1622163.74 | 45390.36 | 0 | 0 | 0 | 0 | 967868 | 70.1 | -361267.74 | -795.9% | NO | -361267.74 | 859729 | 251427.1667 | 297441.6 | 274286.4 | 0 | 288001.2 | 0 | 30% | 33.49% | 33.49% | 3.49% |  | 57.82 | [5 empty] | 48764
1737 | 2024-05-08 23:31 | P23323 | CNC-CMM Programming Support | Stephen Young | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  | -0.21227 | 100.4% | 92.66% | 82.65% | 40305.01 | -2.27% | 617809.74 | 620027.13 | -2217.39 | 10446 | 15941.56 | 15941.56 | 49744.45 | 2217.39 | 574493.52 | 77.38 | 45533.61 | 435.9% | YES | 45533.61 | 74458 | 512445.1867 | 0 | 74458.13 | 0 | 0 | 40305.01 | 32% | 29.73% | 36.62% | 4.62% |  | 57.51 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23366 | Business Analyst Support | Peter Williams | 0 | BDZ | MBDA UK LIMITED | DET | Level 3 | REIM |  |  |  | 60.9649 | 25.12% | 192.4% | 172.5% | 0 | 3.56% | 1302200 | 327055.9 | 975144.1 | 15995.17 | 273532.34 | 900687.4 | 0 | 0 | 629120 | 37.85 | -8929.1 | -55.82% | NO | 618225.96 | 77952 | 564160 | 77952 | 0 | 0 | 0 | 0 | 43% | 46.56% | 24.34% | -18.66% |  | 45.73 | [5 empty] | 293135
1737 | 2024-05-08 23:31 | P23605 | Typhoon Work Package 2 Continuation | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM |  |  |  |  | 119.5% | 83.59% | 29.9% | 401637.33 | 5.12% | 545536.01 | 651980.1 | -106444.09 | -410.47 | 5554 | 5554 | 81999.09 | 106444.09 | 544986.65 | 2099.34 | 106993.45 | -26066% | NO | 106993.45 | 420070 | 194928.3167 | 0 | 22887.68 | 397182.01 | 0 | 401637.33 | 23% | 28.12% | 28.67% | 5.67% |  | 55.83 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P22790 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | REIM | 2024-04-28 | 0 |  | -134.62 | 197.4% | 89.11% | 89.11% | 0 | 1.11% | 352240 | 695460.45 | -343220.45 | 2549.55 | 1611.52 | 1611.52 | 44500 | 343220.45 | 619743.88 | 396.6 | 44446.57 | 1743% | YES | 44446.57 | 0 | 619743.88 | 0 | 0 | 0 | 0 | 0 | 13% | 14.11% | -2.72% | -15.72% |  | 45.08 | [5 empty] | -31270
1737 | 2024-05-08 23:31 | P23426 | BAE Tempest WP 3 Harness Maturation | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 6.0889 | 87.8% | 87.81% | 76.24% | 0 | -6.27% | 884012.04 | 776150.92 | 107861.12 | 17714.41 | 213.34 | 213.34 | 0 | 0 | 681568.4 | 71.85 | 94582.52 | 533.9% | YES | 94582.52 | 107758 | 591770.0667 | 0 | 107757.52 | 0 | 0 | 0 | 33% | 26.73% | 26.9% | -6.1% |  | 51.84 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23602 | EXP-025 Portfolio Software Engineering Support | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 13.232 | 67% | 91.58% | 64.75% | 0 | -1.03% | 1327080 | 889099.01 | 437980.99 | 33100.16 | 3624.28 | 3868.41 | 0 | 0 | 814204.07 | 70.46 | 74894.94 | 226.3% | YES | 75139.07 | 286222 | 575685.7367 | 143172.62 | 143049.25 | 0 | 0 | 0 | 24% | 22.97% | 22.67% | -1.33% |  | 83.34 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23451 | BAE Tempest - DFM-ASO Planning | Stephen Young | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | 2.5706 | 95.03% | 72.88% | 65.32% | 39715.08 | -3.14% | 953905.42 | 906463.01 | 47442.41 | 18455.45 | 0 | 0 | 0 | 0 | 660614.46 | 110.45 | 244765.55 | 1326% | YES | 244765.55 | 82200 | 592114.46 | 42485.15 | 57003.88 | -44513.7 | 27224.9 | 39715.08 | 28% | 24.86% | 26.36% | -1.64% |  | 53.78 | [5 empty] | -1083
1737 | 2024-05-08 23:31 | P23105 | Raytheon Supply Engineering Support | Natalie Sinclair | 0 | RAY | RAYTHEON UNITED KINGDOM LIMITED | MPE | Level 3A | REIM | 2023-07-13 | 2 |  |  | 76.96% | 94.49% | 90.07% | 49156.8 | -2.02% | 1205008 | 927395.25 | 277612.75 | 0 | 0 | 0 | 0 | 0 | 876291.5 | 107644.5 | 48739.75 | 0% | NO | 48739.75 | 49157 | 835327.3333 | 0 | 0 | 0 | 49156.8 | 49156.8 | 26% | 23.98% | 100% | 74% |  | 48.97 | [5 empty] | -2364
1737 | 2024-05-08 23:31 | P23117 | BAE Typhoon Eng Support | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | 2024-03-12 | 11 |  |  | 105.2% | 95.01% | 90.49% | 54289.71 | -1.06% | 950771.99 | 1000558.49 | -49786.5 | -5566.92 | 19090.01 | 21165.02 | 69773.84 | 49786.5 | 950609.41 | 81713.4 | 22853.08 | -410.5% | NO | 24928.09 | 54290 | 905367.7433 | 0 | 0 | 54289.71 | 0 | 54289.71 | 30% | 28.94% | 12.07% | -17.93% |  | 52.3 | [5 empty] | -27096
1737 | 2024-05-08 23:31 | P22350 | EMP 2020-2021 | Natalie Sinclair | 0 | ARY | GUIDANT GLOBAL UK LIMITED | PCPR | Level NC | REIM |  |  |  | 2.4702 | 98.92% | 98.47% | 94.94% | 0 | -2.13% | 1017579.76 | 1006586.9 | 10992.86 | 4450.18 | 400 | 400 | 0 | 0 | 991148.66 | 62.16 | 15438.24 | 346.9% | YES | 15438.24 | 42626 | 955626.9933 | 11715.76 | 24861.97 | 6048.6 | 0 | 0 | 32% | 29.87% | 27.53% | -4.47% |  | 44.14 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P22671 | Spirit Shorts Pylon and Fairing Package | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX | 2023-05-03 | 0 |  |  | 105% | 95.26% | 95.26% | 0 | -7.21% | 1198494.77 | 1258071.09 | -59576.32 | 0 | 106494.89 | 106494.89 | 0 | 59576.32 | 1198494.77 | 2544.39 | 2120.32 | 0% | NO | 2120.32 | 0 | 1198494.77 | 0 | 0 | 0 | 0 | 0 | 20% | 12.79% | 0% | -20% |  | 45.4 | [5 empty] | -57456
1737 | 2024-05-08 23:31 | P23152 | Project Aragon - Design and Stress Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | -0.27472 | 100.3% | 76.13% | 54.55% | 0 | -9.55% | 1333452.21 | 1337037.65 | -3585.44 | 13051.27 | 0 | 0 | 0 | 3585.44 | 1017835.58 | 357.73 | 319202.07 | 2446% | YES | 319202.07 | 346248 | 729295.58 | 0 | 346247.55 | 0 | 0 | 0 | 39% | 29.45% | 29.23% | -9.77% |  | 51.97 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23292 | BAE Tempest WP 4 AV Trays | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 6.7403 | 89.96% | 98.88% | 76.47% | 155584.85 | 1.48% | 1498284.22 | 1347910.74 | 150373.48 | 22309.65 | 0 | 0 | 0 | 0 | 1332801.4 | 99.21 | 15109.34 | 67.73% | NO | 15109.34 | 362500 | 1030718.0667 | 0 | 245826.2 | 116674.18 | 0 | 155584.85 | 32% | 33.48% | 31.89% | -0.11% |  | 53.83 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23519 | Mechanical and Electrical Design Eng Support | Dushan Fernando | 0 | BAX | SAFRAN SEATS GB LIMITED | MPE | Level 2 | REIM |  |  |  | 11.3988 | 80.09% | 96.25% | 76.91% | 0 | -1.56% | 1807261.3 | 1447492.65 | 359768.65 | 31561.88 | 1004.45 | 1504.45 | 0 | 0 | 1393199.8 | 72.91 | 54292.85 | 172% | YES | 54792.85 | 335892 | 1113289.8 | 141083.4 | 194808.9 | 0 | 0 | 0 | 33% | 31.44% | 31.47% | -1.53% |  | 56.65 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23411 | Agile & Scrum Delivery Service | Peter Williams | 0 | BDZ | MBDA UK LIMITED | DET | Level 2 | REIM | 2023-08-14 | 0 |  |  | 36.3% | 170.5% | 170.5% | 0 | 13.08% | 2487000 | 902903.79 | 1584096.21 | 0 | 894178.59 | 894178.59 | 0 | 0 | 1539600 | 19368.95 | 16140.79 | 0% | NO | 16140.79 | 0 | 1539600 | 0 | 0 | 0 | 0 | 0 | 29% | 42.08% | 0% | -29% |  | 74.57 | [5 empty] | 652837
1737 | 2024-05-08 23:31 | P22278 | TAI Supply Engineers to Ankara | Natalie Sinclair | 0 | TAI | TUSAS-TURK HAVACILIK VE UZAY | MPE | Level 3A | REIM |  |  |  | 844.3201 | 19.69% | 460.9% | 460.9% | 0 | -15.7% | 2105282 | 414530.91 | 1690751.09 | 2002.5 | 49400.29 | 49400.29 | 0 | 0 | 1910696.33 | 106.78 | 14234.58 | 710.8% | YES | 14234.58 | 0 | 1910696.33 | 0 | 0 | 0 | 0 | 0 | 95% | 79.3% | 69.27% | -25.73% |  | 34.15 | [5 empty] | 1510400
1737 | 2024-05-08 23:31 | P23175 | BAe Aero Typhoon Package 2 | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM | 2024-03-12 | 2 |  |  | 103.8% | 96.32% | 96.32% | 0 | -1.63% | 1984265.09 | 2060011.83 | -75746.74 | 0 | 57677.87 | 86030.82 | 15444.64 | 75746.74 | 1984257.03 | 84731.75 | 70609.8 | 0% | NO | 98962.75 | 0 | 1984257.03 | 0 | 0 | 0 | 0 | 0 | 29% | 27.37% | 0% | -29% |  | 51.76 | [5 empty] | -5145
1737 | 2024-05-08 23:31 | P23006 | Spirit Shorts A350 Freighter Toulouse | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 6.6441 | 86.64% | 101.6% | 74.02% | 0 | 23.43% | 1925837.92 | 1668509.84 | 257328.08 | 38730.42 | 1086670.26 | 2010741.94 | 0 | 0 | 1695787.93 | 399.7 | 383995.91 | 991.5% | YES | 1308067.59 | 552824 | 1235101.2633 | 0 | 140525.66 | 412298.62 | 0 | 0 | 5% | 28.43% | 53.26% | 48.26% |  | 48.17 | [5 empty] | 411274
1737 | 2024-05-08 23:31 | P19020 | Spirit Concessions - 2018 | Carl Warren | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2024-01-23 | 1 |  |  | 86.3% | 111.8% | 111.2% | 12156.8 | 2.09% | 2015043.23 | 1739018.14 | 276025.09 | 0 | 44317.61 | 44317.61 | 0 | 0 | 1944710.76 | 248541.66 | 196987.38 | 0% | NO | 196987.38 | 12157 | 1934579.9267 | 0 | 0 | 0 | 12156.8 | 12156.8 | 25% | 27.09% | 9.32% | -15.68% |  | 40.87 | [5 empty] | 402680
1737 | 2024-05-08 23:31 | P23435 | Andy Baker Portfolio | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 37.0035 | 53.99% | 95.1% | 68.46% | 0 | -7.12% | 4023207.4 | 2172137.53 | 1851069.87 | 50024.25 | 2596.25 | 2596.25 | 0 | 0 | 2065770.21 | 96.16 | 106367.32 | 212.6% | YES | 106367.32 | 694595 | 1486941.0433 | 204990.14 | 0 | 489604.46 | 0 | 0 | 25% | 17.88% | 19.74% | -5.26% |  | 80.95 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23257 | BAE Tempest WP 5 Centre Fuselage | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 3.5594 | 97.32% | 97.74% | 90.24% | 110362.14 | -5.73% | 2265401.51 | 2204685.37 | 60716.14 | 17057.86 | 78100 | 78100 | 0 | 0 | 2154862.7 | 89.7 | 49822.67 | 292.1% | YES | 49822.67 | 198362 | 1989561.0333 | 0 | 87999.86 | 110362.14 | 0 | 110362.14 | 33% | 27.27% | 28.12% | -4.88% |  | 61.05 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23179 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX |  |  |  | -3.9615 | 100.6% | 94.33% | 86.24% | 0 | -9.27% | 2542643.04 | 2557270.9 | -14627.86 | 3692.48 | 156991.12 | 248243.92 | 0 | 14627.86 | 2412235.69 | 713.26 | 145035.21 | 3928% | YES | 236288.01 | 248280 | 2205335.69 | 0 | 0 | 248280.21 | 0 | 0 | 22% | 12.73% | 17.57% | -4.43% |  | 44.4 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P23207 | A350 Approvers - Design and Stress Support | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  | 6.311 | 87.78% | 93.56% | 72.18% | 63762.48 | -0.3% | 3097098 | 2718681.94 | 378416.06 | 59961.59 | 36201.43 | 36766.42 | 0 | 0 | 2543608.88 | 90.5 | 175073.06 | 292% | YES | 175638.05 | 697590 | 1962283.88 | 102151.98 | 342017.26 | 253420.79 | 0 | 63762.48 | 18% | 17.7% | 16.64% | -1.36% |  | 54.52 | [5 empty] | 0
1737 | 2024-05-08 23:31 | P19731 | Hapri HPC Rear Bearing Housing PDR & CDR | Steven Lawton | 0 | ATC | AECC Hunan Aviation Powerplant | MPE | Level 1 | FIX |  |  |  | -4.4096 | 100.3% | 99.67% | 87.21% | 447000 | -15.41% | 2980000 | 2989767.41 | -9767.41 | 2215.04 | 366282.13 | 500382.13 | 0 | 9767.41 | 2980000 | 741.36 | -215232.59 | -9717% | NO | -81132.59 | 447000 | 2607500 | 0 | 0 | 0 | 447000 | 447000 | 38% | 22.59% | 15.47% | -22.53% |  | 64.85 | [5 empty] | -225000
1737 | 2024-05-08 23:31 | P23487 | Tornado Air 800 Engineering Support | Richard Brook | 0 | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 2 | FIX |  |  |  | 8.64 | 83.95% | 90.04% | 78.18% | 47390.58 | 2.26% | 3925502.05 | 3295441.92 | 630060.13 | 72923.21 | 0 | 0 | 0 | 0 | 2967206.61 | 83.17 | 355235.31 | 487.1% | YES | 355235.31 | 468813 | 2576529.11 | 421421.93 | 0 | 8658.1 | 38732.48 | 47390.58 | 34% | 36.26% | 38.53% | 4.53% |  | 78.95 | [5 empty] | 27000
Extend Table

## AP5-2
WIP No | Date Created | Project ID | Project Description | Project Manager | Agency (1=yes, 0=no) | Department Id | Client | CBU | Complexity | Type | Stop Booking Hrs | Closing Project: Action(s) to close | RAG | Approx. PO Burndown (weeks) | Turnover vs Contract Value | Invoice To Date vs Turnover | Cash in vs Turnover | Open Amount Overdue | Actual PM% to Baseline PM% delta | Contract Value | Total Project Turnover | Contract Value - Total Turnover | Run Rate (based on total turnover) | Total BOI Spend to Date | Total Committed PO (supplier/best shore) | Current AA in PT3 | Exposure (turnover - contract value) | Invoiced To Date | DSO | Unbilled (WIP) | WIP / Run rate | WIP / Run rate >1.3 | WIP + Remaining Committed PO for BOI | Total Open Amount | Cash in (Invoiced - (Open amount -VAT)) | Debt <=30 Days | Debt 31 - 60 Days | Debt 61 - 90 Days | Debt >= 90 Days | Open Amount Overdue2 | Baseline Project Margin | Project To Date (PTD) PM | Year to Date (YTD) PM | YTD Delta Actual PM% to BPM% | Forecast PM at Completion (Manual input from PTT) | Average Sale Rate | CSat score for last quarter (Manual input from PTT) | Comments and Actions | Judged income adjustment at completion | Profit to take now | Provision required now | Fully Traded | Last Months Comments and Actions
1738 | 2024-05-15 23:33 | P23650 | MBDA Recruitment Management costs | Andrew Slaney | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM | 2024-02-01 | 1 |  |  |  | 0% | 0% | 0 | 33042515% | 0 | 240971.5 | -240971.5 | -35243 | 0 | 0 | 266000 | 240971.5 | 0 | 0 | -0.5 | 0.001419% | NO | -0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | 33042518% | 165.6% | 162.6% |  | 82.3 | [5 empty] | -240972
1738 | 2024-05-15 23:33 | P23552 | FCAS AP Product Technology Development | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -25% | 597871 | 0 | 597871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0% | -25% |  | 0 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23543 | EXP-024 FCAS AP Transformation & Change Enablers | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -26% | 385921 | 0 | 385921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26% | 0% | 0% | -26% |  | 0 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23637 | MBSE Proposal | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM | 2024-04-28 | 0 | [5 empty] | 0 | -35% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23784 | Tempest Tooling Offload 2024 | Gary Kempster | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM | 2024-05-09 | 48 | [5 empty] | 0 | -25% | 0 | 0 | 0 | -25540.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0% | -25% |  | 0 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23628 | Design Assurance | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | -7% | 0 | 0 | 0 | -977.31 | 0 | 0 | 4454.8 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 0% | 0.33% | -6.67% |  | 0 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23711 | DO NOT USE - RAISED IN ERROR | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23585 | Systems Design - Missile Systems, Meteor,Brimstone | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM | 2024-04-28 | 0 | [5 empty] | 0 | -35% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23717 | GKN Ted Tomblin 2024 | Matthew Tweed | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2024-04-28 | 0 | [5 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23902 | Typhoon Rear Fuselage | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX | [7 empty] | 0 | -30% | 0 | 0 | 0 | 0 | 0 | 0 | 45382.5 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 0% | 0% | -30% |  | 0 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23892 | Warrior Environmental Control Unit | Trevin Fernandopulle | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -32% | 3920 | 0 | 3920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32% | 0% | 0% | -32% |  | 0 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23899 | Turret Test Rig | Trevin Fernandopulle | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -16% | 24864 | 0 | 24864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16% | 0% | 0% | -16% |  | 0 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23730 | FLE Project | Siyun Fan | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -18.03% | 0 | 1120 | -1120 | 0 | 0 | 0 | 24000 | 1120 | 0 | 224 | 1120 | 0% | NO | 1120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | -18.03% | -18.03% | -18.03% |  | 35 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23463 | A220 Wing MaMo Design Checking | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-03-07 | 0 |  |  |  | 0% | 0% | 0 | 7.85% | 0 | 1628 | -1628 | 0 | 0 | 0 | 15000 | 1628 | 0 | 1953.6 | 1628 | 0% | NO | 1628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | 10.85% | 0% | -3% |  | 44 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23898 | EXP-041 ISV Engineering Support | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | -1 |  | 0% | 0% | 0 | -13.04% | 0 | 2315.75 | -2315.75 | 2315.75 | 0 | 0 | 12618 | 2315.75 | 0 | 6 | 2315.75 | 100% | NO | 2315.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21% | 7.96% | 7.96% | -13.04% |  | 78.5 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P21028 | Rebate Collection (BACC) | David Catchpole | 0 | TOO | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | [5 empty] | 0% | 0% | 0 | 0% | 0 | 2680 | -2680 | 0 | 2680 | 2680 | 0 | 2680 | 0 | 3216 | 2680 | 0% | NO | 2680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23886 | A220 F&DT Support | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -3 |  | 0% | 0% | 0 | -9.07% | 0 | 3380.2 | -3380.2 | 1126.73 | 0 | 0 | 12199.2 | 3380.2 | 0 | 14 | 3380.2 | 300% | YES | 3380.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 8.93% | 8.93% | -9.07% |  | 50.83 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23578 | ESN Work Package | Hannah Mead | 0 | COZ | CHELTON LIMITED | DET | Level 3 | FIX | 2024-01-01 | 0 |  |  | 86.17% | 116.1% | 116.1% | 0 | 35.86% | 4410 | 3800 | 610 | 0 | 0 | 0 | 0 | 0 | 4410 | 0 | -610 | 0% | NO | -610 | 0 | 4410 | 0 | 0 | 0 | 0 | 0 | 24% | 59.86% | 0% | -24% |  | 95 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23894 | EE Test and Integration Lead | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | -2 |  | 0% | 0% | 0 | 10.6% | 0 | 4248.02 | -4248.02 | 2124.01 | 0 | 0 | 15430 | 4248.02 | 0 | 14 | 4248.02 | 200% | YES | 4248.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23% | 33.6% | 33.6% | 10.6% |  | 63.88 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23880 | Warrior Crew Heater Design | Trevin Fernandopulle | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM |  |  |  | 0.41379 | 87.88% | 0% | 0% | 0 | 3.58% | 5544 | 4872 | 672 | 1624 | 0 | 0 | 0 | 0 | 0 | 28 | 4872 | 300% | YES | 4872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32% | 35.58% | 35.58% | 3.58% |  | 56 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23881 | Bulldog Fuel System Design | Trevin Fernandopulle | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM |  |  |  | 1.169 | 71.96% | 0% | 0% | 0 | 1.29% | 8288 | 5964 | 2324 | 1988 | 0 | 0 | 0 | 0 | 0 | 21 | 5964 | 300% | YES | 5964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13% | 14.29% | 14.29% | 1.29% |  | 56 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23002 | WoT MAJ Transit Flag Stress | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2024-04-03 | 1 |  |  | 62.41% | 160.2% | 160.2% | 0 | 38.54% | 4735 | 2955.29 | 1779.71 | 0 | 1492.79 | 2242.5 | 0 | 0 | 4735 | 91.03 | 1493.29 | 0% | NO | 2243 | 0 | 4735 | 0 | 0 | 0 | 0 | 0 | 10% | 48.54% | 0% | -10% |  | 45 | [5 empty] | 3273
1738 | 2024-05-15 23:33 | P23888 | HondaJet FWD Assy Jig Tool Design | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX |  |  |  | 11.5161 | 20.67% | 0% | 0% | 0 | 4.29% | 31500 | 6510 | 24990 | 2170 | 0 | 0 | 0 | 0 | 0 | 28 | 6510 | 300% | YES | 6510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 14.29% | 14.29% | 4.29% |  | 42 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23864 | REACH Coordinator | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 26.8122 | 12.98% | 0% | 0% | 0 | -10.24% | 52920 | 6870 | 46050 | 1717.5 | 0 | 0 | 0 | 0 | 0 | 56 | 6870 | 400% | YES | 6870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27% | 16.76% | 16.76% | -10.24% |  | 30 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23607 | SAFRAN - A330neo Turnover Frame | Gary Kempster | 0 | TOO | SAFRAN SEATS GB LIMITED | MPE | Level 3 | FIX |  |  |  |  | 95.69% | 104.5% | 104.5% | 0 | -19.52% | 8736 | 8359.05 | 376.95 | 0 | 0 | 0 | 0 | 0 | 8736 | 0.06 | 0.05 | 0% | NO | 0.05 | 0 | 8736 | 0 | 0 | 0 | 0 | 0 | 23% | 3.48% | 8.5% | -14.5% |  | 50.46 | [5 empty] | 377
1738 | 2024-05-15 23:33 | P23274 | ME Support (Aim Altitude - Cambridge) | Trevor Knox | 0 | AVI | AVIC CABIN SYSTEMS (UK) LIMITED | ME | Level 3 | FIX | 2023-08-18 | 0 |  |  | 51.88% | 56.3% | 56.3% | 0 | -0.17% | 17280 | 8964 | 8316 | 0 | 0 | 0 | 0 | 0 | 5046.3 | 4701.24 | 3917.7 | 0% | NO | 3917.7 | 0 | 5046.3 | 0 | 0 | 0 | 0 | 0 | 21% | 20.83% | 0% | -21% |  | 48 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23843 | EXP-035 FT15 Exemplar information set | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 95.5691 | 5.306% | 0% | 0% | 0 | -11.85% | 175985.16 | 9338.49 | 166646.67 | 1743.73 | 0 | 0 | 0 | 0 | 0 | 56 | 9338.49 | 535.5% | YES | 9338.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 8.15% | 8.15% | -11.85% |  | 71.35 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23283 | Spirit Tooling Audit | Charidimos Valadakis | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-05-03 | 0 |  |  | 97.22% | 48.57% | 48.57% | 0 | -7.99% | 9910.08 | 9634.8 | 275.28 | 0 | 0 | 0 | 0 | 0 | 4679.76 | 5946.05 | 4955.04 | 0% | NO | 4955.04 | 0 | 4679.76 | 0 | 0 | 0 | 0 | 0 | 7% | -0.99% | 0% | -7% |  | 34.41 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23127 | Loft Hall Design Support | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-04-19 | 0 |  |  | 101% | 99.06% | 99.06% | 0 | -9.55% | 9680 | 9772 | -92 | 0 | 0 | 0 | 0 | 92 | 9680 | 110.4 | 92 | 0% | NO | 92 | 0 | 9680 | 0 | 0 | 0 | 0 | 0 | 41% | 31.45% | 0% | -41% |  | 44 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23630 | 2Excel CFD Analysis Support | Dushan Fernando | 0 | BAX | STIRLING DYNAMICS LTD | MPE | Level NC | FIX |  |  |  |  | 61.2% | 100% | 100% | 0 | -1.87% | 16195.49 | 9911.34 | 6284.15 | 0 | 0 | 0 | 0 | 0 | 9911.63 | 0 | -0.29 | 0% | NO | -0.29 | 0 | 9911.63 | 0 | 0 | 0 | 0 | 0 | 26% | 24.13% | 0% | -26% |  | 64.78 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23873 | FCAS Systems Engineering Support | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 52.1496 | 7.124% | 0% | 0% | 0 | -9.72% | 156475 | 11147 | 145328 | 2786.75 | 0 | 0 | 0 | 0 | 0 | 28 | 11147 | 400% | YES | 11147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 8.28% | 8.28% | -9.72% |  | 78.5 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23313 | Laser Trim Fixtures | Gary Kempster | 0 | TOO | ALKEN ENGINEERING LIMITED | MPE | Level 3 | FIX | 2023-11-20 | 0 |  |  | 89.87% | 111.3% | 111.3% | 0 | 0.53% | 13770 | 12375 | 1395 | 0 | 0 | 0 | 0 | 0 | 13770 | 0 | -1395 | 0% | NO | -1395 | 0 | 13770 | 0 | 0 | 0 | 0 | 0 | 17% | 17.53% | 0% | -17% |  | 45 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23718 | Requalification of EJ200 GSS ESS EHM SW module | Vijayakumara Nanjundappa | 0 | ARZ | MTU AERO ENGINES AG | DET | Level 3 | FIX |  |  |  | 113.4762 | 13.14% | 185.3% | 185.3% | 0 | 16.21% | 74463 | 9781.57 | 64681.43 | 570 | 991.93 | 991.93 | 0 | 0 | 18125 | 0 | -5343.43 | -937.4% | NO | -5343.43 | 0 | 18125 | 0 | 0 | 0 | 0 | 0 | 28% | 44.21% | 44.21% | 16.21% |  | 80 | [5 empty] | 3000
1738 | 2024-05-15 23:33 | P22761 | Red Bull Chassis Spit | Trevor Knox | 0 | TOO | MANUFAX ENGINEERING LTD | MPE | Level 3 | FIX | 2022-11-15 | 0 |  |  | 72.18% | 96.98% | 96.98% | 0 | 7.92% | 12961.2 | 9355.5 | 3605.7 | 0 | 0 | 0 | 0 | 0 | 9072.84 | 4666.39 | 3888.66 | 0% | NO | 3888.66 | 0 | 9072.84 | 0 | 0 | 0 | 0 | 0 | 23% | 30.92% | 0% | -23% |  | 42.19 | [5 empty] | 3606
1738 | 2024-05-15 23:33 | P23350 | Spirit 2023 - Stress Approve Man Serv (DH) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 14.15% | 72.64% | 72.64% | 0 | -0.29% | 97920 | 13860 | 84060 | 0 | 0 | 0 | 0 | 0 | 10068 | 4550.4 | 3792 | 0% | NO | 3792 | 0 | 10068 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23344 | Spirit A320 Spoilers Support 2023 | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 38.75% | 100% | 100% | 0 | 5.82% | 35786.4 | 13867.23 | 21919.17 | 0 | 0 | 0 | 0 | 0 | 13867.23 | 0 | 0 | 0% | NO | 0 | 0 | 13867.23 | 0 | 0 | 0 | 0 | 0 | 7% | 12.82% | 0% | -7% |  | 34.41 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23337 | Spirit 2023 - Steve Grimley | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 25.28% | 100% | 100% | 0 | 0.01% | 56812.9 | 14362.47 | 42450.43 | 0 | 0 | 0 | 0 | 0 | 14362.47 | 0 | 0 | 0% | NO | 0 | 0 | 14362.47 | 0 | 0 | 0 | 0 | 0 | 7% | 7.01% | 0% | -7% |  | 30.11 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23597 | MRB Onsite support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-02-16 | 1 |  |  |  | 0% | 0% | 0 | -10.04% | 0 | 15100.57 | -15100.57 | 0 | 9448.07 | 17381.62 | 24200 | 15100.57 | 0 | 176.93 | 15100.57 | 0% | NO | 23034.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 7.96% | 8.95% | -9.05% |  | 42.5 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23869 | EXP-037 Land Ceptor Development Hardware Test Def | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 38.2422 | 9.469% | 57.43% | -0.000476% | 0 | 0.81% | 162694 | 15405.85 | 147288.15 | 3851.46 | 0 | 0 | 0 | 0 | 8848.26 | 49 | 6557.59 | 170.3% | YES | 6557.59 | 10618 | -0.073333 | 10617.91 | 0 | 0 | 0 | 0 | 26% | 26.81% | 26.81% | 0.81% |  | 89.83 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23343 | Spirit 2023 - John Agnew | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-08-09 | 0 |  |  | 24.64% | 100% | 100% | 0 | -0.02% | 65120.37 | 16047.15 | 49073.22 | -638.44 | 0 | 0 | 0 | 0 | 16047.15 | 0 | 0 | 0% | NO | 0 | 0 | 16047.15 | 0 | 0 | 0 | 0 | 0 | 7% | 6.98% | 6.98% | -0.02% |  | 34.51 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23635 | Engineering Services: FAI Support | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 49.9% | 100% | 0.0008972% | 0 | -3.4% | 37230 | 18576 | 18654 | 0 | 0 | 0 | 0 | 0 | 18576 | 1820 | 0 | 0% | NO | 0 | 22291 | 0.16667 | 0 | 7058.88 | 15232.32 | 0 | 0 | 8% | 4.6% | 5.04% | -2.96% |  | 38.7 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23842 | Tranche 1 Evolution Package Step 2 | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -6.5236 |  | 0% | 0% | 0 | -13.7% | 0 | 19600.64 | -19600.64 | 3004.57 | 1000 | 1000 | 67488.9 | 19600.64 | 0 | 56 | 19600.64 | 652.4% | YES | 19600.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31% | 17.3% | 17.3% | -13.7% |  | 56.09 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23839 | Stirling Dynamics - ST002-GFEM | Matthew Dodd | 0 | BAX | STIRLING DYNAMICS LTD | MPE | Level NC | FIX |  |  |  | -42.4787 |  | 0% | 0% | 0 | -4.87% | 0 | 20565.2 | -20565.2 | 484.13 | 1225.5 | 1225.5 | 19985.76 | 20565.2 | 0 | 96.85 | 20565.2 | 4248% | YES | 20565.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 2.13% | 2.13% | -4.87% |  | 43.75 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23355 | Spirit Tooling Support 2023 | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-23 | 0 |  |  | 22.93% | 89.02% | 89.02% | 0 | -0.82% | 91800 | 21053.34 | 70746.66 | 0 | 0 | 0 | 0 | 0 | 18742.5 | 2773.01 | 2310.84 | 0% | NO | 2310.84 | 0 | 18742.5 | 0 | 0 | 0 | 0 | 0 | 20% | 19.18% | 0% | -20% |  | 44.46 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23663 | Spirit Tooling Verification and Inspection | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 1 | FIX |  |  |  | 1.4194 | 95.09% | 77.93% | 0.001577% | 0 | -6.39% | 23123.52 | 21987.99 | 1135.53 | 800.03 | 0 | 0 | 0 | 0 | 17136.18 | 188.18 | 4851.81 | 606.5% | YES | 4851.81 | 20563 | 0.34667 | 0 | 12635.35 | 7928.06 | 0 | 0 | 11% | 4.61% | 4.82% | -6.18% |  | 34.41 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23874 | Environmental Engineering (Sea Venom/ANL) | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | -4 |  | 0% | 0% | 0 | 18.55% | 0 | 24021 | -24021 | 6005.25 | 0 | 0 | 27140.5 | 24021 | 0 | 35 | 24021 | 400% | YES | 24021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 18.55% | 18.55% | 18.55% |  | 78.5 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23351 | Spirit 2023 - Design Man Serv (KL) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 26.47% | 93.15% | 93.15% | 0 | 0.09% | 93840 | 24840 | 69000 | 0 | 0 | 0 | 0 | 0 | 23138 | 2042.4 | 1702 | 0% | NO | 1702 | 0 | 23138 | 0 | 0 | 0 | 0 | 0 | 26% | 26.09% | 0% | -26% |  | 46 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23356 | Spirit 2023 - Design Man Serv (AH) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX | 2023-08-09 | 1 |  |  |  | 76.66% | 0.001332% | 23018.4 | 0.48% | 0 | 25023.08 | -25023.08 | 0 | 0 | 0 | 25300 | 25023.08 | 19182 | 30027.7 | 5841.08 | 0% | NO | 5841.08 | 23018 | 0.33333 | 0 | 0 | 0 | 23018.4 | 23018.4 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P22884 | Spirit Shorts Config Eng | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 66.3% | 100.1% | 100.1% | 0 | 0.56% | 38976 | 25841.9 | 13134.1 | 0 | 0 | 0 | 0 | 0 | 25863.2 | 0 | -0.3 | 0% | NO | -0.3 | 0 | 25863.2 | 0 | 0 | 0 | 0 | 0 | 7% | 7.56% | 0% | -7% |  | 20.3 | [5 empty] | 21
1738 | 2024-05-15 23:33 | P23742 | Cyber Security Support | Hannah Mead | 0 | COZ | CHELTON LIMITED | DET | Level 3 | FIX |  |  |  | 0.93333 | 94.91% | 105.4% | 0% | 0 | -0.96% | 27500 | 26100 | 1400 | 1500 | 0 | 0 | 0 | 0 | 27500 | 121.8 | -1400 | -93.33% | NO | -1400 | 33000 | 0 | 33000 | 0 | 0 | 0 | 0 | 32% | 31.04% | 31.04% | -0.96% |  | 100 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23354 | Spirit 2023 - Design Man Serv (PC) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 27.97% | 99.36% | 99.36% | 0 | 0.48% | 93840 | 26248.98 | 67591.02 | 0 | 0 | 0 | 0 | 0 | 26082 | 200.38 | 166.98 | 0% | NO | 166.98 | 0 | 26082 | 0 | 0 | 0 | 0 | 0 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23891 | A220 FLE Support | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -2 |  | 0% | 0% | 0 | 6.1% | 0 | 28140.96 | -28140.96 | 14070.48 | 0 | 0 | 36633.6 | 28140.96 | 0 | 45 | 28140.96 | 200% | YES | 28140.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 13.1% | 13.1% | 6.1% |  | 49.72 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P22756 | A350 FLE Design Checker | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2022-03-23 | 1 |  |  | 68.39% | 119.7% | 119.7% | 0 | 16.46% | 34898.4 | 23867.15 | 11031.25 | 0 | 23867.15 | 24342.3 | 0 | 0 | 28571.1 | 0.06 | 0.05 | 0% | NO | 475.2 | 0 | 28571.1 | 0 | 0 | 0 | 0 | 0 | 0% | 16.46% | 0% | 0% |  | 0 | [5 empty] | 4704
1738 | 2024-05-15 23:33 | P23458 | Spirit Belfast Tooling Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-08-11 | 0 |  |  | 101.3% | 94.65% | 94.65% | 0 | 8.64% | 30384 | 30784.9 | -400.9 | 0 | 0 | 0 | 0 | 400.9 | 29139.1 | 1974.96 | 1645.8 | 0% | NO | 1645.8 | 0 | 29139.1 | 0 | 0 | 0 | 0 | 0 | 7% | 15.64% | 0% | -7% |  | 42.2 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23433 | Cavendish | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 7.7975 | 75.21% | 43.63% | 43.63% | 0 | -0.42% | 42240 | 31767.2 | 10472.8 | 1343.1 | 0 | 0 | 0 | 0 | 13859.2 | 91 | 17908 | 1333% | YES | 17908 | 0 | 13859.2 | 0 | 0 | 0 | 0 | 0 | 7% | 6.58% | 6.51% | -0.49% |  | 46.34 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23831 | Contract DM/00113 for maintenance, repair and post | Harry James Kellett | 0 | BXW | MOD | EES | Level 2 | FIX |  |  |  | 7.8354 | 69.71% | 17.46% | 0.0002059% | 0 | 17.27% | 46455.9 | 32384.91 | 14070.99 | 1795.82 | 0 | 0 | 0 | 0 | 5655.9 | 91 | 26729.01 | 1488% | YES | 26729.01 | 6787 | 0.066667 | 6787.08 | 0 | 0 | 0 | 0 | 34% | 51.27% | 51.27% | 17.27% |  | 80.26 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23365 | GKN 777x Lip Skin Fixture | Steven Lawton | 0 | TOO | GKN AEROSPACE SERVICES LTD | MPE | Level 3 | FIX | 2023-10-12 | 0 |  |  | 41.91% | 113.2% | 113.2% | 0 | -9.26% | 79161.46 | 33175.67 | 45985.79 | 0 | 5109.88 | 5109.88 | 0 | 0 | 37544.22 | 0 | -4368.55 | 0% | NO | -4368.55 | 0 | 37544.22 | 0 | 0 | 0 | 0 | 0 | 22% | 12.74% | 0% | -22% |  | 56 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23724 | GKN S McConnell 2024 | Matthew Tweed | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  | 9.3143 | 67.4% | 90.21% | -0.000814% | 0 | 0.86% | 49820 | 33578.71 | 16241.29 | 1743.7 | 0 | 0 | 0 | 0 | 30290.56 | 133.33 | 3288.15 | 188.6% | YES | 3288.15 | 36349 | -0.27333 | 8369.76 | 10761.12 | 8848.03 | 8369.76 | 0 | 19% | 19.86% | 19.86% | 0.86% |  | 49.6 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P22768 | MRB Onsite Support - Spirit Belfast | Trevor Knox | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2023-07-27 | 0 |  |  |  | 0% | 0% | 0 | -17.07% | 0 | 34614 | -34614 | 0 | 0 | 0 | 36800 | 34614 | 0 | 41536.8 | 34614 | 0% | NO | 34614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | -7.07% | 0% | -10% |  | 36 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23651 | PMO Spirit | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 7.1498 | 72.97% | 65.22% | -0.0004634% | 0 | -19.33% | 49284 | 35964 | 13320 | 1863 | 0 | 0 | 0 | 0 | 23454 | 234.3 | 12510 | 671.5% | YES | 12510 | 28145 | -0.16667 | 0 | 0 | 28144.8 | 0 | 0 | 43% | 23.67% | 23.12% | -19.88% |  | 36 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23821 | Supply of Safety Engineer | Dinna Elkhalifa | 0 | BXW | STIRLING DYNAMICS LTD | EES | Level NC | REIM |  |  |  | -3.8294 | 106.6% | 49% | -0.0006437% | 22765.86 | 45.1% | 34006.44 | 36247.77 | -2241.33 | 585.29 | 0 | 0 | 0 | 2241.33 | 17760.6 | 142.37 | 18487.17 | 3159% | YES | 18487.17 | 21313 | -0.23333 | 0 | 21312.72 | -15645.36 | 15645.36 | 22765.86 | 0% | 45.1% | 45.1% | 45.1% |  | 80.73 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23347 | WoT Fixed Leading Edge - Industrial 2023 | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | -10.6486 | 120.5% | 39.34% | 39.34% | 0 | -0.38% | 31034.12 | 37389.34 | -6355.22 | 596.81 | 0 | 0 | 10500 | 6355.22 | 14710.56 | 27214.54 | 22678.78 | 3800% | YES | 22678.78 | 0 | 14710.56 | 0 | 0 | 0 | 0 | 0 | 7% | 6.62% | 7.01% | 0.01% |  | 32.26 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23051 | Spirit Shorts A350 PAX Door | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3A | REIM |  |  |  |  | 205.9% | 105.4% | 105.4% | 0 | -0.63% | 18216 | 37513 | -19297 | 0 | 0 | 0 | 0 | 19297 | 39537 | 0 | 0 | 0% | NO | 0 | 0 | 39537 | 0 | 0 | 0 | 0 | 0 | 30% | 29.37% | 0% | -30% |  | 46 | [5 empty] | 2024
1738 | 2024-05-15 23:33 | P23338 | Spirit 2023 - Blair Hainey | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 12.0105 | 64.39% | 44.55% | 44.55% | 0 | 5.95% | 62893.71 | 40499.34 | 22394.37 | 1864.56 | 0 | 0 | 0 | 0 | 18042.36 | 250.52 | 22456.98 | 1204% | YES | 22456.98 | 0 | 18042.36 | 0 | 0 | 0 | 0 | 0 | 7% | 12.95% | 17.66% | 10.66% |  | 18.28 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23811 | Spirit T300 MRB Concessions | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -11.4176 |  | 0% | 0% | 0 | -7.17% | 0 | 41185.98 | -41185.98 | 3607.23 | 0 | 0 | 50000 | 41185.98 | 0 | 91 | 41185.98 | 1142% | YES | 41185.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21% | 13.83% | 13.83% | -7.17% |  | 47.22 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P22752 | Tooling WoT - 2021 (Spirit) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | REIM | 2023-05-03 | 0 |  |  | 101.1% | 74.02% | 74.02% | 0 | -8.5% | 41525.1 | 41982.28 | -457.18 | 0 | 0 | 0 | 0 | 457.18 | 31076.1 | 13087.42 | 10906.18 | 0% | NO | 10906.18 | 0 | 31076.1 | 0 | 0 | 0 | 0 | 0 | 0% | -8.5% | 0% | 0% |  | 39.09 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23823 | EXP-034 Spear 3 Test Equip Requirement Authority | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 11.4826 | 50.03% | 72.1% | 8.561% | 0 | -0.01% | 85825 | 42941.25 | 42883.75 | 3734.66 | 1000 | 1000 | 0 | 0 | 30961.13 | 83.21 | 11980.12 | 320.8% | YES | 11980.12 | 32742 | 3676.13 | 15494.7 | 17247.76 | 0 | 0 | 0 | 14% | 13.99% | 13.99% | -0.01% |  | 94.25 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23740 | Phase 2 - EJ200 ESS EHM Platform Migration | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 3 | FIX |  |  |  | 27.4327 | 19.58% | 218.9% | 72.97% | 0 | 20.17% | 175971 | 34452.5 | 141518.5 | 5158.75 | 0 | 0 | 0 | 0 | 75417 | 62.46 | -28964.5 | -561.5% | NO | -28964.5 | 60334 | 25138.6667 | 30166.8 | 30166.8 | 0 | 0 | 0 | 28% | 48.17% | 48.17% | 20.17% |  | 42.82 | [5 empty] | 12000
1738 | 2024-05-15 23:33 | P23339 | Spirit 2023 - Stewart Russell | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 64.51% | 100% | 100% | 0 | 0.62% | 72766.8 | 46941.72 | 25825.08 | 0 | 0 | 0 | 0 | 0 | 46941.74 | 0 | -0.02 | 0% | NO | -0.02 | 0 | 46941.74 | 0 | 0 | 0 | 0 | 0 | 7% | 7.62% | 0% | -7% |  | 35.67 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P22760 | SA Leading Edge Transport Media ('A' Frames) | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-11-15 | 1 |  |  | 85.99% | 110.7% | 116.3% | -3082.8 | 3.97% | 53480.8 | 45985.5 | 7495.3 | 0 | 42804 | 42804 | 0 | 0 | 50911.8 | 0 | -0.3 | 0% | NO | -0.3 | -3083 | 53480.9667 | 0 | 0 | 0 | -3082.8 | -3082.8 | 6% | 9.97% | 0% | -6% |  | 42 | [5 empty] | 4926
1738 | 2024-05-15 23:33 | P23598 | MRB Onsite support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 24.109 | 38.78% | 0% | 0% | 0 | -10.34% | 133056 | 51597.67 | 81458.33 | 3378.75 | 8736.42 | 14079.58 | 0 | 0 | 0 | 104.19 | 51597.67 | 1527% | YES | 56940.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 17.66% | 17.96% | -10.04% |  | 42.5 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23642 | MRB Belfast Support | Carl Warren | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -34.6888 |  | 0% | 0% | 0 | -44.28% | 0 | 52674.97 | -52674.97 | 1518.5 | 3566.12 | 3566.12 | 48125 | 52674.97 | 0 | 209.4 | 52674.97 | 3469% | YES | 52674.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22% | -22.28% | -24.62% | -46.62% |  | 38.52 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23760 | EXP-033 Systems Engineering Support | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 30.113 | 37.71% | 83.54% | 44.4% | 0 | -0.02% | 142300 | 53654.75 | 88645.25 | 2943.75 | 0 | 0 | 0 | 0 | 44823.5 | 75.26 | 8831.25 | 300% | YES | 8831.25 | 25199 | 23824.3333 | 12387.3 | 0 | 12811.2 | 0 | 0 | 29% | 28.98% | 28.98% | -0.02% |  | 78.5 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23349 | Spirit 2023 - Stress Approve Man Serv (SB) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 58.24% | 80.05% | 80.05% | 0 | -0.29% | 97920 | 57024 | 40896 | 0 | 0 | 0 | 0 | 0 | 45648 | 13651.2 | 11376 | 0% | NO | 11376 | 0 | 45648 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23322 | GKN T Tomblin 2023 | Steven Lawton | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2024-04-15 | 1 |  |  | 99.66% | 100% | 95.06% | 0 | -0.33% | 58952 | 58752 | 200 | 0 | 0 | 0 | 0 | 0 | 58752 | 50.74 | 0 | 0% | NO | 0 | 3485 | 55847.8333 | 0 | 0 | 3484.8 | 0 | 0 | 17% | 16.67% | 16.67% | -0.33% |  | 48 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23106 | ME Support to NPD - Bobby Haggart | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  |  | 95.79% | 97.03% | 97.03% | 0 | 0.3% | 65675 | 62912.11 | 2762.89 | 0 | 0 | 0 | 0 | 0 | 61042.75 | 2243.24 | 1869.36 | 0% | NO | 1869.36 | 0 | 61042.75 | 0 | 0 | 0 | 0 | 0 | 15% | 15.3% | 0% | -15% |  | 35.65 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P22967 | Spirit 2022 - Channapa Laxmeshwar | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2023-01-26 | 2 |  |  | 69.69% | 121.3% | 121.3% | 0 | 9.53% | 75159.1 | 52376.15 | 22782.95 | 0 | 52376.15 | 54898.1 | 0 | 0 | 63508.8 | 0.42 | 0.35 | 0% | NO | 2522.3 | 0 | 63508.8 | 0 | 0 | 0 | 0 | 0 | 8% | 17.53% | 0% | -8% |  | 0 | [5 empty] | 11133
1738 | 2024-05-15 23:33 | P23193 | Spirit Shorts Stephen Greer | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -8.3202 | 110.9% | 89.06% | 80.18% | 7268.72 | 8.74% | 61472 | 68168.98 | -6696.98 | 804.91 | 0 | 0 | 10878 | 6696.98 | 60712.78 | 144.76 | 7456.2 | 926.3% | YES | 7456.2 | 7269 | 54655.28 | 0 | 0 | 7268.72 | 0 | 7268.72 | 23% | 31.74% | 34.03% | 11.03% |  | 35.16 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23341 | Spirit 2023 - Tom McFarlane | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 37.5687 | 64.81% | 91.26% | 61.08% | 7110.19 | -0.01% | 108666.4 | 70427.8 | 38238.6 | 1017.83 | 0 | 0 | 0 | 0 | 64272.02 | 179.9 | 6155.78 | 604.8% | YES | 6155.78 | 25503 | 43019.52 | 0 | 16061.8 | 2331.04 | 7110.19 | 7110.19 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23877 | Strategic Enablement | Owain Jones | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -4 |  | 0% | 0% | 0 | -16.99% | 0 | 71017.3 | -71017.3 | 17754.33 | 4000 | 4000 | 67200 | 71017.3 | 0 | 102.18 | 71017.3 | 400% | YES | 71017.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 1.01% | 1.01% | -16.99% |  | 42 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23600 | MBDA EXP-EE-023 Bristone Certification | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 59.65% | 100% | 100% | 0 | 0.4% | 126600 | 75517 | 51083 | 0 | 0 | 0 | 0 | 0 | 75517 | 0 | 0 | 0% | NO | 0 | 0 | 75517 | 0 | 0 | 0 | 0 | 0 | 41% | 41.4% | 0% | -41% |  | 78.5 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23080 | Spirit Shorts DManagement Cairan Cullen | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 1143.1262 | 50.94% | 97.36% | 94.85% | 0 | -1.27% | 149600 | 76211.3 | 73388.7 | 64.2 | 0 | 0 | 0 | 0 | 74199.7 | 127.47 | 2011.6 | 3133% | YES | 2011.6 | 2298 | 72284.7 | 0 | 0 | 2298.36 | 0 | 0 | 24% | 22.73% | 13.03% | -10.97% |  | 44.39 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P22505 | Spirit MRB Engineering Support 2021 | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 1 |  |  | 91.17% | 100% | 95.78% | 4020.48 | 21.2% | 87110.4 | 79414.95 | 7695.45 | 0 | 0 | 0 | 0 | 0 | 79414.95 | 4020.48 | 0 | 0% | NO | 0 | 4020 | 76064.95 | 0 | 0 | 0 | 4020.48 | 4020.48 | 0% | 21.2% | 0% | 0% |  | 41.88 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P22885 | ME Support (Baxi) | Trevor Knox | 0 | HUV | BAXI HEATING UK LIMITED | ME | Level 3 | FIX | 2023-01-12 | 0 |  |  | 68.78% | 108.7% | 108.7% | 0 | 13.05% | 106632.96 | 73340.24 | 33292.72 | 0 | 0 | 0 | 0 | 0 | 79748.12 | 1531.35 | 1276.12 | 0% | NO | 1276.12 | 0 | 79748.12 | 0 | 0 | 0 | 0 | 0 | 15% | 28.05% | 0% | -15% |  | 44.37 | [5 empty] | 7684
1738 | 2024-05-15 23:33 | P23700 | IPDT Leads | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 13.1332 | 50.47% | 29.19% | -0.0004449% | 29918.54 | -1.7% | 169263.9 | 85419.89 | 83844.01 | 6384.15 | 0 | 0 | 0 | 0 | 24932.12 | 138.74 | 60487.77 | 947.5% | YES | 60487.77 | 29919 | -0.38 | 0 | 0 | 29918.54 | 0 | 29918.54 | 26% | 24.3% | 22.87% | -3.13% |  | 49.97 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P22965 | Spirit 2022 - Design Man Serv (AH) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 106.7% | 96.66% | 96.66% | 0 | 3.14% | 80079.56 | 85441.32 | -5361.76 | 0 | 0 | 0 | 0 | 5361.76 | 82588.96 | 3422.84 | 2852.36 | 0% | NO | 2852.36 | 0 | 82588.96 | 0 | 0 | 0 | 0 | 0 | 14% | 17.14% | 0% | -14% |  | 42.44 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23523 | Applique Armour Support | Dushan Fernando | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-18 | 1 |  |  | 72.43% | 138.1% | 98.47% | 40680 | 3.42% | 118200 | 85606.5 | 32593.5 | 0 | 0 | 0 | 0 | 0 | 118200 | 1567.8 | -32593.5 | 0% | NO | -32593.5 | 40680 | 84300 | 0 | 0 | 40680 | 0 | 40680 | 25% | 28.42% | 0% | -25% |  | 64.29 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P22964 | Spirit 2022 - MRB Man Serv (JC) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 100.6% | 97.95% | 97.95% | 0 | 1.91% | 85435.2 | 85960.26 | -525.06 | 0 | 0 | 0 | 0 | 525.06 | 84199.74 | 2112.62 | 1760.52 | 0% | NO | 1760.52 | 0 | 84199.74 | 0 | 0 | 0 | 0 | 0 | 16% | 17.91% | 0% | -16% |  | 42.69 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P22963 | Spirit 2022 - Design Man Serv (PC) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 108.6% | 104% | 104% | 0 | 3.18% | 80079.56 | 86926.74 | -6847.18 | 0 | 0 | 0 | 0 | 6847.18 | 90389.95 | 0 | -3463.21 | 0% | NO | -3463.21 | 0 | 90389.95 | 0 | 0 | 0 | 0 | 0 | 13% | 16.18% | 0% | -13% |  | 42.39 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23342 | Spirit 2023 - Channapa Laxmeshwar | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 53.17% | 109.3% | 77.24% | 0 | -3.73% | 158696.7 | 84385.85 | 74310.85 | 0 | 84385.85 | 94827 | 0 | 0 | 92257.7 | 91.65 | -5021.85 | 0% | NO | 5419.3 | 32496 | 65177.7 | 0 | 32496.24 | 0 | 0 | 0 | 7% | 3.27% | 0% | -7% |  | 0 | [5 empty] | 2850
1738 | 2024-05-15 23:33 | P23438 | A220 Spirit Shorts DTC - Stephen Corry | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 4.207 | 92.59% | 72.57% | 45.48% | 28872.36 | -7.18% | 95928.4 | 88823.7 | 7104.7 | 1688.78 | 0 | 0 | 0 | 0 | 64459.8 | 276.47 | 24363.9 | 1443% | YES | 24363.9 | 28872 | 40399.8 | 0 | 0 | 28872.36 | 0 | 28872.36 | 23% | 15.82% | 16.95% | -6.05% |  | 49.87 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23079 | Spirit Shorts Nomenclature | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -4.7783 | 104.3% | 84.72% | 74.05% | 5855.04 | 15.14% | 88455 | 92289.6 | -3834.6 | 802.5 | 0 | 0 | 5136 | 3834.6 | 78185.2 | 261.1 | 14104.4 | 1758% | YES | 14104.4 | 11811 | 68342.7 | 0 | 0 | 11810.64 | 0 | 5855.04 | 7% | 22.14% | 25.23% | 18.23% |  | 30.82 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23340 | Spirit 2023 - John Cole | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 38.3514 | 62.4% | 90.57% | 67.09% | 0 | -0.01% | 150129.72 | 93681.9 | 56447.82 | 1471.86 | 0 | 0 | 0 | 0 | 84850.74 | 150.69 | 8831.16 | 600% | YES | 8831.16 | 26398 | 62852.4067 | 0 | 21576.67 | 4821.34 | 0 | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 39.78 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23375 | GKN Jaap Peters NL 2023 | Steven Lawton | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2024-03-01 | 1 |  |  | 93.37% | 105.3% | 97.18% | 0 | -15.93% | 97123.22 | 90686.41 | 6436.81 | 0 | 90686.41 | 90686.41 | 0 | 0 | 95456.72 | 40.01 | -920.31 | 0% | NO | -920.31 | 8793 | 88129.22 | 0 | 0 | 0 | 8793.29 | 0 | 20% | 4.07% | 0% | -20% |  | 0 | [5 empty] | 3850
1738 | 2024-05-15 23:33 | P23171 | Spirt Shorts Weights Eng | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 69.18% | 141.4% | 122.7% | 0 | 13.12% | 103113.14 | 71329.32 | 31783.82 | 0 | 71329.32 | 85975.13 | 0 | 0 | 100870.18 | 54.04 | -5610.86 | 0% | NO | 9034.95 | 16006 | 87531.8467 | 6733.3 | 9273.05 | 0 | 0 | 0 | 12% | 25.12% | 47.26% | 35.26% |  | 0 | [5 empty] | 23930
1738 | 2024-05-15 23:33 | P23744 | Model Factory | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 28.8404 | 34.78% | 98.02% | 25.05% | 26229.6 | 10.2% | 262300 | 91236.75 | 171063.25 | 5931.38 | 0 | 0 | 0 | 0 | 89432 | 104.61 | 6804.75 | 114.7% | NO | 6804.75 | 79889 | 22857.8333 | 27429.6 | 26229.6 | 0 | 26229.6 | 26229.6 | 28% | 38.2% | 38.2% | 10.2% |  | 50.93 | [5 empty] | 5000
1738 | 2024-05-15 23:33 | P23336 | Spirit 2023 - Neil Rampling | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 27.5775 | 72.32% | 91.41% | 49.42% | 21586.03 | -0.01% | 133901.52 | 96842.66 | 37058.86 | 1343.81 | 0 | 0 | 0 | 0 | 88522.6 | 235.7 | 8320.06 | 619.1% | YES | 8320.06 | 48792 | 47862.6 | 0 | 22565.28 | 4640.79 | 21586.03 | 21586.03 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23729 | Honda Tooling | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | FIX |  |  |  | 2.2968 | 86.02% | 76.86% | 33.2% | 0 | 2.83% | 113610 | 97723.5 | 15886.5 | 6916.88 | 0 | 0 | 0 | 0 | 75106.5 | 80.86 | 22617 | 327% | YES | 22617 | 51194 | 32444.8333 | 51193.8 | 0 | 0 | 0 | 0 | 10% | 12.83% | 12.83% | 2.83% |  | 42 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23465 | A220 ToW Design Offload (Wing) | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 50.4506 | 40.06% | 92.89% | 55.75% | 14380.8 | -5.64% | 249700 | 100034.3 | 149665.7 | 2966.58 | 0 | 0 | 0 | 0 | 92918.8 | 148.62 | 7115.5 | 239.9% | YES | 7115.5 | 44580 | 55768.8 | 14843.04 | 0 | 29737.44 | 0 | 14380.8 | 20% | 14.36% | 12.13% | -7.87% |  | 42.8 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23583 | Castalla - Test Rig Design | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 100% | 67.12% | 60.93% | 0 | -26.99% | 100520 | 100538.5 | -18.5 | -379.5 | 0 | 0 | 0 | 18.5 | 67482.1 | 195.76 | 33056.4 | -8711% | NO | 33056.4 | 7469 | 61257.9333 | 0 | 0 | 7469.4 | 0 | 0 | 41% | 14.01% | 14.71% | -26.29% |  | 42.79 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23345 | Spirit 2023- Jonathan Escosio | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 22.922 | 67.31% | 80.21% | 57.19% | 7150.18 | -0.5% | 151941.24 | 102277.78 | 49663.46 | 2166.63 | 0 | 0 | 0 | 0 | 82035.91 | 195.83 | 20241.87 | 934.3% | YES | 20241.87 | 28246 | 58497.5767 | 0 | 16361 | 4734.58 | 7150.18 | 7150.18 | 7% | 6.5% | 18.32% | 11.32% |  | 43.01 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23551 | Ian Berry 2023 H2 | Natalie Sinclair | 0 | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  | -15.6849 | 135.2% | 65.57% | 65.57% | 0 | 13.61% | 75810 | 102515.63 | -26705.63 | 1702.63 | 0 | 0 | 24259.2 | 26705.63 | 67217.49 | 109.81 | 35298.14 | 2073% | YES | 35298.14 | 0 | 67217.49 | 0 | 0 | 0 | 0 | 0 | 22% | 35.61% | 37.71% | 15.71% |  | 77.78 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23560 | NJEWCS TAF202302 SM | Natalie Sinclair | 0 | COB | CHELTON LIMITED | EES | Level 2 | FIX |  |  |  | 14.9697 | 53.99% | 77.38% | 38.69% | 0 | 9.84% | 191500 | 103382.16 | 88117.84 | 5886.43 | 0 | 0 | 0 | 0 | 80000 | 184.79 | 23382.16 | 397.2% | YES | 23382.16 | 48000 | 40000 | 0 | 48000 | 0 | 0 | 0 | 30% | 39.84% | 39.49% | 9.49% |  | 73.01 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23586 | Project Management Support | Dushan Fernando | 0 | BDX | MBDA UK LIMITED | MPE | Level NC | REIM |  |  |  | 18.2293 | 66.87% | 91.77% | 62.72% | 0 | -26.6% | 160000 | 106991.86 | 53008.14 | 2907.85 | 1668.6 | 1668.6 | 0 | 0 | 98183.86 | 106.86 | 8808 | 302.9% | YES | 8808 | 37296 | 67103.86 | 37296 | 0 | 0 | 0 | 0 | 49% | 22.4% | 21.42% | -27.58% |  | 80 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23353 | Spirit 2023 - MRB Man Serv (JC) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  | 47.95 | 64.74% | 57.72% | 57.72% | 0 | 9.54% | 183600 | 118867.5 | 64732.5 | 1350 | 0 | 0 | 0 | 0 | 68615.25 | 232.54 | 50252.25 | 3722% | YES | 50252.25 | 0 | 68615.25 | 0 | 0 | 0 | 0 | 0 | 7% | 16.54% | 12.83% | 5.83% |  | 45 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P22918 | Spirit Shorts Graduates | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 11.9517 | 91.55% | 89.68% | 89.68% | 0 | 9.5% | 130000 | 119018.64 | 10981.36 | 918.81 | 0 | 0 | 19800 | 0 | 106734.95 | 79.02 | 12283.69 | 1337% | YES | 12283.69 | 0 | 106734.95 | 0 | 0 | 0 | 0 | 0 | 7% | 16.5% | 17.2% | 10.2% |  | 23.33 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P22736 | WoT Fixed Leading Edge - Industrial | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 106.7% | 93.42% | 91.32% | 3019.54 | 0.01% | 112196.27 | 119668.47 | -7472.2 | 0 | 0 | 0 | 0 | 7472.2 | 111796.68 | 12465.69 | 7871.79 | 0% | NO | 7871.79 | 3020 | 109280.0133 | 0 | 0 | 0 | 3019.54 | 3019.54 | 7% | 7.01% | 0% | -7% |  | 32.26 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23545 | Ultra CSS continuation 2023 H2 | Natalie Sinclair | 0 | ULT | ULTRA SONAR SYSTEMS LIMITED | EES | Level NC | REIM |  |  |  | -8.2803 | 163.8% | 76.76% | 60.62% | 0 | 2.18% | 76000 | 124474.4 | -48474.4 | 5854.2 | 0 | 0 | 49859.2 | 48474.4 | 95544.8 | 138.95 | 28929.6 | 494.2% | YES | 28929.6 | 24112 | 75451.4667 | 24112.32 | 0 | 0 | 0 | 0 | 23% | 25.18% | 25% | 2% |  | 80 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P22861 | WoT FLE Lifting & Handling Tools | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2023-06-14 | 1 |  |  | 65.17% | 101.6% | 101.6% | 0 | 12.01% | 173987.21 | 113381.75 | 60605.46 | 0 | 50078 | 58423.58 | 0 | 0 | 115203.5 | 12813.9 | 10678.25 | 0% | NO | 19023.83 | 0 | 115203.5 | 0 | 0 | 0 | 0 | 0 | 1% | 13.01% | 0% | -1% |  | 45 | [5 empty] | 12500
1738 | 2024-05-15 23:33 | P23753 | Tempest Composites Maturation | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 0.36893 | 98.74% | 84.15% | 24.62% | 0 | -10.72% | 127848.45 | 126243.1 | 1605.35 | 4351.37 | 0 | 0 | 0 | 0 | 106238.78 | 81 | 20004.32 | 459.7% | YES | 20004.32 | 90185 | 31084.6133 | 90184.78 | 0 | 0 | 0 | 0 | 32% | 21.28% | 21.28% | -10.72% |  | 64.54 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23352 | Spirit 2023 - Stress Approve Man Serv (CC) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  | 23.284 | 65.33% | 54.64% | 54.64% | 0 | 5.73% | 195840 | 127944 | 67896 | 2916 | 0 | 0 | 0 | 0 | 69912 | 232.6 | 58032 | 1990% | YES | 58032 | 0 | 69912 | 0 | 0 | 0 | 0 | 0 | 7% | 12.73% | 4.69% | -2.31% |  | 48 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23664 | Tempest Composites WP3 | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -2.8046 | 105.9% | 66.43% | 12.74% | 0 | -5.15% | 122455.49 | 129622.84 | -7167.35 | 2555.56 | 0 | 0 | 14830.4 | 7167.35 | 86110.38 | 330.97 | 43512.46 | 1703% | YES | 43512.46 | 83510 | 16518.7133 | 0 | 83510.02 | 0 | 0 | 0 | 37% | 31.85% | 33.16% | -3.84% |  | 60.88 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23588 | BAE Typhoon MRB MC Shop Concessions | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 13.4048 | 74.49% | 85.98% | 61.58% | 38190.65 | -4.2% | 175060.5 | 130398.35 | 44662.15 | 3331.8 | 0 | 0 | 0 | 0 | 112121.71 | 148.87 | 18276.64 | 548.6% | YES | 18276.64 | 38191 | 80295.8767 | 0 | 10272.55 | 13518.34 | 14399.76 | 38190.65 | 31% | 26.8% | 27.44% | -3.56% |  | 55.8 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23282 | Tooling Support (MBDA) | Dushan Fernando | 0 | BDV | MBDA UK LIMITED | ME | Level NC | REIM |  |  |  | 34.5032 | 67.77% | 95.92% | 78.28% | 0 | -7.76% | 195672.4 | 132602.02 | 63070.38 | 1827.96 | 0 | 0 | 0 | 0 | 127186.8 | 115.15 | 5415.22 | 296.2% | YES | 5415.22 | 28059 | 103804.3 | 7411.63 | 0 | 20647.76 | 0 | 0 | 30% | 22.24% | 30.37% | 0.37% |  | 49.73 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23810 | Strategic Enablement | Owain Jones | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -127328 |  | 0% | 0% | 0 | -20.63% | 0 | 133694.4 | -133694.4 | 1.05 | 0 | 0 | 134000 | 133694.4 | 0 | 277.6 | 133694.4 | 12732800% | YES | 133694.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | -2.63% | -2.63% | -20.63% |  | 42 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23270 | Shorts Project X | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 4.8218 | 94.17% | 91.52% | 65.61% | 15962.69 | 0.38% | 142248 | 133959.56 | 8288.44 | 1718.96 | 0 | 0 | 0 | 0 | 122595.46 | 190.39 | 11364.1 | 661.1% | YES | 11364.1 | 41647 | 87889.6267 | 7981.34 | 10030.61 | 23635.49 | 0 | 15962.69 | 13% | 13.38% | 10.99% | -2.01% |  | 45.31 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P22883 | Spirit Shorts Evtol PMO C. Hatton | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 15.1068 | 72.45% | 80.93% | 80.93% | 0 | -10.87% | 185800 | 134618.15 | 51181.85 | 3388 | 0 | 0 | 0 | 0 | 108946.73 | 135.61 | 25671.42 | 757.7% | YES | 25671.42 | 0 | 108946.73 | 0 | 0 | 0 | 0 | 0 | 26% | 15.13% | 22.96% | -3.04% |  | 37.41 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23533 | External Stowage Design and Detail Support | Dushan Fernando | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 1 |  |  | 102.4% | 97.65% | 73.24% | 42000 | 3.33% | 140000 | 143368.75 | -3368.75 | 0 | 0 | 0 | 3369 | 3368.75 | 140000 | 41999.7 | -0.25 | 0% | NO | -0.25 | 42000 | 105000 | 0 | 0 | 42000 | 0 | 42000 | 27% | 30.33% | 0% | -27% |  | 60.04 | [5 empty] | -3369
1738 | 2024-05-15 23:33 | P23822 | FCASW Requirements Management | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 29.2528 | 24.42% | 78.24% | 0% | 0 | -2.37% | 595703 | 145480.13 | 450222.87 | 15390.75 | 0 | 0 | 0 | 0 | 113825 | 96.88 | 31655.13 | 205.7% | YES | 31655.13 | 136590 | 0 | 136590 | 0 | 0 | 0 | 0 | 17% | 14.63% | 14.63% | -2.37% |  | 78.5 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P22954 | Technical Support Step 1 | Owain Jones | 0 | HUV | HUARUI SPIRIT AEROSPACE MANUFACT | ME | Level 2 | REIM |  |  |  |  | 94.81% | 58.01% | 58.01% | 0 | 0.31% | 155501.18 | 147431.58 | 8069.6 | 0 | 23043 | 23043 | 0 | 0 | 85525.49 | 61906.09 | 61906.09 | 0% | NO | 61906.09 | 0 | 85525.49 | 0 | 0 | 0 | 0 | 0 | 30% | 30.31% | 0% | -30% |  | 60.79 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23386 | Software Development - BMS | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 98.78% | 100% | 100% | 0 | 4.31% | 149650 | 147823.35 | 1826.65 | 0 | 0 | 0 | 0 | 0 | 147823.35 | 0 | 0 | 0% | NO | 0 | 0 | 147823.35 | 0 | 0 | 0 | 0 | 0 | 18% | 22.31% | 22.61% | 4.61% |  | 78.5 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23437 | Embedded Software Engineer | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 98.73% | 100% | 96.08% | 0 | -6.29% | 150150 | 148239.36 | 1910.64 | 0 | 737.86 | 737.86 | 0 | 0 | 148239.36 | 45.5 | 0 | 0% | NO | 0 | 6971 | 142430.1933 | 0 | 0 | 6970.8 | 0 | 0 | 22% | 15.71% | 16.24% | -5.76% |  | 78.5 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23550 | Tempest Composites | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  |  | 102.5% | 97.57% | 97.57% | 0 | 5.11% | 149494.92 | 153217.46 | -3722.54 | 0 | 0 | 0 | 2396.12 | 3722.54 | 149494.92 | 51.51 | 3722.54 | 0% | NO | 3722.54 | 0 | 149494.92 | 0 | 0 | 0 | 0 | 0 | 26% | 31.11% | 33.8% | 7.8% |  | 61.6 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P22440 | Spirit Managed Service - F&DT and Static Approval | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 3 |  |  | 88.56% | 92.56% | 92.56% | 0 | 11.51% | 173500 | 153656.25 | 19843.75 | 0 | 52115 | 55720 | 0 | 0 | 142225.12 | 13717.36 | 11431.13 | 0% | NO | 15036.13 | 0 | 142225.12 | 0 | 0 | 0 | 0 | 0 | 0% | 11.51% | 0% | 0% |  | 44.73 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P22982 | Spirit 2022 - Hugh Sloan | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 240.8939 | 63.12% | 96.27% | 81.27% | 8217.17 | -0.69% | 247473 | 156200.7 | 91272.3 | 378.89 | 0 | 0 | 0 | 0 | 150381.98 | 203.88 | 5818.72 | 1536% | YES | 5818.72 | 28121 | 126947.8133 | 0 | 15604.11 | 4300.18 | 8217.17 | 8217.17 | 7% | 6.31% | 0.53% | -6.47% |  | 35.48 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23518 | Systems Engineering support to FCAS | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 9.1247 | 88.54% | 92.74% | 82.45% | 0 | -5.61% | 193736.8 | 171531.75 | 22205.05 | 2433.5 | 3927.4 | 3927.4 | 0 | 0 | 159084.68 | 86.61 | 12447.07 | 511.5% | YES | 12447.07 | 21195 | 141422.18 | 11351.1 | 0 | 9843.9 | 0 | 0 | 30% | 24.39% | 3.5% | -26.5% |  | 68.69 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23508 | Verification and Validation | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 80.77% | 100% | 97.06% | 0 | 10.77% | 212950 | 171993.5 | 40956.5 | 0 | 0 | 0 | 0 | 0 | 171993.53 | 37.75 | -0.03 | 0% | NO | -0.03 | 6076 | 166930.1967 | 0 | 0 | 6075.9 | 0 | 0 | 24% | 34.77% | 33.6% | 9.6% |  | 78.5 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23464 | A220 Project X Design Offload | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 80.5476 | 53.97% | 96.65% | 61.38% | 55648.56 | -9.48% | 332340 | 179359.9 | 152980.1 | 1899.25 | 0 | 0 | 0 | 0 | 173346.5 | 244.86 | 6013.4 | 316.6% | YES | 6013.4 | 75910 | 110088.1667 | 1900.32 | 18361.2 | 27785.76 | 27862.8 | 55648.56 | 26% | 16.52% | 14.38% | -11.62% |  | 42.88 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23667 | Safety Systems Engineer | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 55.3897 | 45.27% | 93.53% | 76.07% | 0 | -10.81% | 398000 | 180180 | 217820 | 3932.5 | 0 | 0 | 0 | 0 | 168520 | 76.55 | 11660 | 296.5% | YES | 11660 | 37752 | 137060 | 18216 | 19536 | 0 | 0 | 0 | 47% | 36.19% | 29.32% | -17.68% |  | 110 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23421 | A220 DTC | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 14.2744 | 83.38% | 72.15% | 59.17% | 15800.9 | -28.15% | 217089.12 | 181005.15 | 36083.97 | 2527.88 | 0 | 0 | 0 | 0 | 130597.8 | 129.17 | 50407.35 | 1994% | YES | 50407.35 | 28204 | 107094.4667 | 12403.44 | 0 | 15800.9 | 0 | 15800.9 | 29% | 0.85% | 5.61% | -23.39% |  | 45.94 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23754 | Tempest Composites WP4 | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 8.8215 | 60.31% | 0% | 0% | 0 | -1.29% | 310945.68 | 187525.07 | 123420.61 | 13990.96 | 1784.87 | 1784.87 | 0 | 0 | 0 | 115.83 | 187525.07 | 1340% | YES | 187525.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36% | 34.71% | 34.71% | -1.29% |  | 61.54 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23008 | Spirit Shorts Project Rachel | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 68.49% | 91.32% | 91.32% | 0 | -9.7% | 286960 | 196531.2 | 90428.8 | 0 | 0 | 0 | 0 | 0 | 179472.8 | 20470.08 | 17058.4 | 0% | NO | 17058.4 | 0 | 179472.8 | 0 | 0 | 0 | 0 | 0 | 15% | 5.3% | 0.31% | -14.69% |  | 46.04 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23019 | EXP034-B Actuator Development | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 103.1% | 89.91% | 89.91% | 0 | -16.68% | 215541.2 | 222215.54 | -6674.34 | 0 | 12297.9 | 12297.9 | 0 | 6674.34 | 199796.76 | 122.03 | 397.78 | 0% | NO | 397.78 | 0 | 199796.76 | 0 | 0 | 0 | 0 | 0 | 34% | 17.32% | 79.64% | 45.64% |  | 58.45 | [5 empty] | -22021
1738 | 2024-05-15 23:33 | P23741 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  | 30.8975 | 32.82% | 94.29% | 21.34% | 52662 | 2.78% | 640812 | 210318 | 430494 | 13932.95 | 0 | 0 | 0 | 0 | 198299 | 98.34 | 18019 | 129.3% | NO | 18019 | 184097 | 44884.8333 | 68808 | 62626.8 | 0 | 52662 | 52662 | 28% | 30.78% | 30.78% | 2.78% |  | 38.82 | [5 empty] | 6000
1738 | 2024-05-15 23:33 | P23242 | Physical Architecture & System Engineering Support | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 30.99 | 71.63% | 95.86% | 85.66% | 0 | 6.99% | 305459 | 218793.71 | 86665.29 | 2796.56 | 775.55 | 775.55 | 0 | 0 | 209745.3 | 77.52 | 8694.41 | 310.9% | YES | 8694.41 | 26800 | 187411.9667 | 12669.9 | 0 | 14130 | 0 | 0 | 15% | 21.99% | 7.26% | -7.74% |  | 78.22 | [5 empty] | -354
1738 | 2024-05-15 23:33 | P23506 | ASTER Mid-Life Refurbishment Project Manager | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 25.1975 | 66.97% | 94.51% | 79.81% | 0 | 0.98% | 326900 | 218935.37 | 107964.63 | 4284.74 | 3830.37 | 3830.37 | 0 | 0 | 206911.41 | 77.49 | 12023.96 | 280.6% | YES | 12023.96 | 38610 | 174736.41 | 24552 | 14058 | 0 | 0 | 0 | 25% | 25.98% | 26.07% | 1.07% |  | 110 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23505 | EXP-022 Meteor TBUS T&E support | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 6.8454 | 88.79% | 94.46% | 81.96% | 0 | -1.4% | 246744.4 | 219072.91 | 27671.49 | 4042.35 | 0 | 0 | 0 | 0 | 206945.88 | 75.55 | 12127.03 | 300% | YES | 12127.03 | 32878 | 179547.5467 | 13636.2 | 0 | 19241.59 | 0 | 0 | 20% | 18.6% | 15.67% | -4.33% |  | 89.83 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23373 | Raytheon Michael Bellini | Natalie Sinclair | 0 | RAS | RAYTHEON UNITED KINGDOM LIMITED | EES | Level NC | REIM |  |  |  | -2.7817 | 103.7% | 94.67% | 76.96% | 24734.7 | -7.73% | 214367.4 | 222362.81 | -7995.41 | 2874.27 | 0 | 0 | 13558.28 | 7995.41 | 210519.78 | 109.33 | 11843.03 | 412% | YES | 11843.03 | 47271 | 171127.28 | 22536.06 | 0 | 24734.7 | 0 | 24734.7 | 45% | 37.27% | 38.7% | -6.3% |  | 91.61 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23524 | Bombardier Regional Jets (BRJ) | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -8.9198 | 155.9% | 47.73% | 46.38% | 3694.07 | -3.78% | 146287.84 | 228043.16 | -81755.32 | 9165.62 | 0 | 0 | 113075 | 81755.32 | 108838.22 | 302.95 | 119204.94 | 1301% | YES | 119204.94 | 3694 | 105759.8867 | 0 | 0 | 0 | 3694.07 | 3694.07 | 18% | 14.22% | 17.4% | -0.6% |  | 43.74 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23739 | Lifing Services DACs | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  | 30.9587 | 33.45% | 100.6% | 25.37% | 65650.8 | 6.56% | 656508 | 219626.6 | 436881.4 | 14111.75 | 0 | 0 | 0 | 0 | 220836 | 106.91 | 10790.6 | 76.47% | NO | 10790.6 | 198152 | 55709.3333 | 66850.8 | 65650.8 | 0 | 65650.8 | 65650.8 | 28% | 34.56% | 34.56% | 6.56% |  | 37.73 | [5 empty] | 12000
1738 | 2024-05-15 23:33 | P23648 | EXP-032 Delivery of Datalink Eng support - FCAS AP | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 13.314 | 63.81% | 68.98% | 57.41% | 0 | 7.13% | 371000 | 236745.45 | 134254.55 | 10083.75 | 1032.95 | 1032.95 | 0 | 0 | 163302.95 | 78.68 | 73442.5 | 728.3% | YES | 73442.5 | 32868 | 135912.95 | 13332 | 19536 | 0 | 0 | 0 | 22% | 29.13% | 29.76% | 7.76% |  | 102.22 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23472 | Tempest Wing Design | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 68.2354 | 52.67% | 127.4% | 108.9% | 0 | -11.69% | 483869.78 | 254854.61 | 229015.17 | 3356.25 | 238975 | 356900 | 0 | 0 | 324639.1 | 4.08 | -44784.5 | -1334% | NO | 73140.5 | 56574 | 277494.1 | 23857.58 | 32716.75 | 0 | 0 | 0 | 23% | 11.31% | 28.89% | 5.89% |  | 46.74 | [5 empty] | 25000
1738 | 2024-05-15 23:33 | P23007 | EXP-006A - Brimstone 3 | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 84.2061 | 69.1% | 98.76% | 92.49% | 0 | -2.56% | 406450 | 280856.66 | 125593.34 | 1491.5 | 0 | 0 | 0 | 0 | 277363.38 | 70.13 | 3463.28 | 232.2% | YES | 3463.28 | 21124 | 259760.0467 | 9631.96 | 11492.4 | 0 | 0 | 0 | 25% | 22.44% | 29.94% | 4.94% |  | 70.04 | [5 empty] | -30
1738 | 2024-05-15 23:33 | P23603 | Typhoon IMDLR | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 2.5727 | 96.06% | 40.88% | 40.88% | 0 | 3.45% | 305067.09 | 293060.17 | 12006.92 | 4667.12 | 1500 | 1500 | 0 | 0 | 119807.84 | 406.39 | 173252.33 | 3712% | YES | 173252.33 | 0 | 119807.84 | 0 | 0 | 0 | 0 | 0 | 26% | 29.45% | 26.86% | 0.86% |  | 56.7 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23308 | NATO JEWCS | Natalie Sinclair | 0 | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  | 19.8223 | 85.53% | 94.1% | 89.67% | 0 | -3.99% | 356307 | 304744.66 | 51562.34 | 2601.23 | 613.89 | 613.89 | 0 | 0 | 286767.43 | 122.04 | 17977.23 | 691.1% | YES | 17977.23 | 16216 | 273254.0967 | 15829.13 | 386.92 | 0 | 0 | 0 | 24% | 20.01% | 11.87% | -12.13% |  | 75.81 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23629 | F35 FTI | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level NC | REIM |  |  |  | -18.0585 |  | 79.6% | 76.07% | 0 | -1.39% | 0 | 309930.88 | -309930.88 | 17162.61 | 0 | 0 | 0 | 309930.88 | 246695.06 | 45.76 | 63235.82 | 368.5% | YES | 63235.82 | 13105 | 235774.2267 | 13105.21 | 0 | 0 | 0 | 0 | 31% | 29.61% | 28.66% | -2.34% |  | 61.38 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P22953 | Spirit Shorts eVTOL | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-05-08 | 2 |  |  | 103.1% | 80.83% | 79.36% | 5920.8 | -9.51% | 324272 | 334483.6 | -10211.6 | 0 | 66696.6 | 67387.9 | 0 | 10211.6 | 270366 | 70861.92 | 54117.6 | 0% | NO | 54808.9 | 5921 | 265431.8333 | 0 | 0 | 5920.8 | 0 | 5920.8 | 17% | 7.49% | 100% | 83% |  | 46.19 | [5 empty] | -10000
1738 | 2024-05-15 23:33 | P21463 | Safety & Monitoring Systems at DM Beith & Gosport | Harry James Kellett | 0 | BXW | MOD | EES | Level 2 | FIX |  |  |  | 4.2464 | 87.54% | 114.2% | 111.3% | 0 | -23.69% | 378612.83 | 331451.16 | 47161.67 | 11106.34 | 75403.45 | 79611.43 | 45616.14 | 0 | 378594.83 | 0 | -47143.67 | -424.5% | NO | -42935.69 | 11636 | 368898.1633 | 11635.81 | 0 | 0 | 0 | 0 | 48% | 24.31% | 39.03% | -8.97% |  | 56.15 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23743 | EHM Cloud Migration | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 31.3384 | 29.46% | 114.4% | 28.53% | 102412.8 | 8.85% | 1016000 | 299322.13 | 716677.87 | 22868.97 | 0 | 0 | 0 | 0 | 342376 | 90.81 | -8053.88 | -35.22% | NO | -8053.88 | 308362 | 85407.6667 | 103612.8 | 102336 | 0 | 102412.8 | 102412.8 | 28% | 36.85% | 36.85% | 8.85% |  | 55.2 | [5 empty] | 35000
1738 | 2024-05-15 23:33 | P22515 | Shorts A220 100/300 ALI Phase III | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 41.1343 | 83.51% | 98.12% | 88.91% | 18386.68 | 0.61% | 400628.76 | 334555.49 | 66073.27 | 1606.28 | 3450.98 | 3450.98 | 0 | 0 | 328273.11 | 156.38 | 6282.38 | 391.1% | YES | 6282.38 | 36969 | 297465.61 | 0 | 18582.69 | 18386.68 | 0 | 18386.68 | 10% | 10.61% | 6.85% | -3.15% |  | 40.54 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23677 | ME Managed Service - Phase 1 | Paul Watson | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  | 8.6602 | 61.26% | 70.27% | 0% | 0 | -14.51% | 554400 | 339641.35 | 214758.65 | 24798.44 | 0 | 38000 | 0 | 0 | 238680 | 122.72 | 100961.35 | 407.1% | YES | 138961.35 | 286416 | 0 | 71536.5 | 214879.5 | 0 | 0 | 0 | 33% | 18.49% | 20.6% | -12.4% |  | 44.11 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P22842 | ME Support (Aim Altitude) | Trevor Knox | 0 | AVI | AIM ALTITUDE UK LIMITED | ME | Level 3 | FIX | 2023-06-14 | 4 |  |  | 99.31% | 100.5% | 86.63% | 57290.84 | 0.49% | 346293.67 | 343918.08 | 2375.59 | 0 | 2909.86 | 2909.86 | 0 | 0 | 345673.01 | 55184.93 | -1754.93 | 0% | NO | -1754.93 | 57291 | 297930.51 | 0 | 0 | 0 | 57290.84 | 57290.84 | 13% | 13.49% | 0% | -13% |  | 46.3 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P22391 | GE System Engineering support | Vinayakumar Sugur | 0 | GEE | EXPERIS LIMITED | EES | Level NC | REIM | 2024-04-08 | 0 |  |  | 82.01% | 100.7% | 100.7% | 0 | 0.13% | 434434.25 | 356260.63 | 78173.62 | 0 | 0 | 0 | 0 | 0 | 358805.6 | 0 | -2544.97 | 0% | NO | -2544.97 | 0 | 358805.6 | 0 | 0 | 0 | 0 | 0 | 6% | 6.13% | 6.09% | 0.09% |  | 57.33 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23816 | Typhoon FTI Works - 2024 Fixed Price Element | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 2.6131 | 86% | 52.79% | 4.795e-05% | 0 | -1.44% | 404176.65 | 347574.62 | 56602.03 | 21660.77 | 0 | 0 | 0 | 0 | 183496 | 101.63 | 174078.62 | 803.7% | YES | 174078.62 | 220195 | 0.16667 | 220195.2 | 0 | 0 | 0 | 0 | 30% | 28.56% | 28.56% | -1.44% |  | 52.01 | [5 empty] | 10000
1738 | 2024-05-15 23:33 | P23617 | Tempest Composites WP2 | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -15.6135 | 148.5% | 27.87% | 15.93% | 29536.68 | 11.64% | 244405.26 | 362998.01 | -118592.75 | 7595.52 | 0 | 0 | 120669.84 | 118592.75 | 101150.9 | 369.76 | 261847.11 | 3447% | YES | 261847.11 | 51981 | 57833.4 | 0 | 22444.14 | 0 | 29536.68 | 29536.68 | 22% | 33.64% | 33.33% | 11.33% |  | 62.15 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23432 | Spirit Belfast MRB On-Site Support (Mon & Clear) | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 65.77% | 128.6% | 103.8% | 69935.4 | -11.53% | 449545 | 295665.27 | 153879.73 | 0 | 295665.27 | 451827.33 | 0 | 0 | 380234.75 | 120831.02 | 27430.52 | 0% | NO | 183592.58 | 87914 | 306973.0833 | 0 | 0 | 87914.4 | 0 | 69935.4 | 39% | 27.47% | 0% | -39% |  | 0 | [5 empty] | 112000
1738 | 2024-05-15 23:33 | P23045 | Shotgun Adaptors - 10 Sets | Harry James Kellett | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | FIX | 2024-02-27 | 4 |  | 15.0752 | 78.52% | 127.4% | 127.4% | 0 | 2.52% | 399276.11 | 313507.44 | 85768.67 | 5689.39 | 214550.47 | 214550.47 | 0 | 0 | 399276.11 | 320.77 | 14994.33 | 263.5% | YES | 14994.33 | 0 | 399276.11 | 0 | 0 | 0 | 0 | 0 | 31% | 33.52% | 94.3% | 63.3% |  | 58.38 | [5 empty] | 100763
1738 | 2024-05-15 23:33 | P23699 | A220 Stress Checkers | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -0.96203 | 105.1% | 0% | 0% | 0 | 7.46% | 408328.79 | 429254.36 | -20925.57 | 21751.44 | 12000 | 12000 | 185592 | 20925.57 | 0 | 155.15 | 429254.36 | 1973% | YES | 429254.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13% | 20.46% | 20.54% | 7.54% |  | 61.88 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23023 | Spirit Shorts R Foster/M Gourley | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 77.3915 | 70.86% | 104.4% | 91.62% | 0 | -1.1% | 590659.44 | 418544.65 | 172114.79 | 2223.95 | 237621.5 | 267726 | 0 | 0 | 437064.88 | 68.05 | 3845.77 | 172.9% | YES | 33950.27 | 64309 | 383474.0467 | 20217.14 | 24971.11 | 19120.72 | 0 | 0 | 9% | 7.9% | 11.41% | 2.41% |  | 29.68 | [5 empty] | 22366
1738 | 2024-05-15 23:33 | P22906 | Spirit Shorts - MRB JD Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 5.955 | 96.69% | 83.02% | 65.23% | 99451.32 | -7.9% | 481714 | 465773.18 | 15940.82 | 2676.88 | 0 | 0 | 0 | 0 | 386687.62 | 374.43 | 87085.56 | 3253% | YES | 87085.56 | 99451 | 303811.7867 | 0 | 0 | 0 | 99451.32 | 99451.32 | 13% | 5.1% | 2.55% | -10.45% |  | 36.95 | [5 empty] | 8000
1738 | 2024-05-15 23:33 | P22652 | L3 - Saftey Engineering | Sean Simmons | 0 | LHW | L3HARRIS MAPPS LIMITED | EES | Level NC | FIX |  |  |  |  | 95.63% | 95.66% | 86.69% | 0 | 5.66% | 523390 | 500497.5 | 22892.5 | 0 | 0 | 0 | 0 | 0 | 478783.75 | 79938 | 21713.75 | 0% | NO | 21713.75 | 53882 | 433882.0833 | 0 | 53881.5 | 0 | 0 | 0 | 21% | 26.66% | 25.88% | 4.88% |  | 83.05 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23531 | BAe Systems F35 MRB Support | Richard Brook | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | -64.206 |  | 95.51% | 92% | 0 | 3.52% | 0 | 508206.17 | -508206.17 | 7915.24 | 287.44 | 287.44 | 0 | 508206.17 | 485408.08 | 28.54 | 22798.09 | 288% | YES | 22798.09 | 21435 | 467545.58 | 21434.91 | 0 | 0 | 0 | 0 | 25% | 28.52% | 31.79% | 6.79% |  | 60.02 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23554 | Dornier Seawings 328 2023 H2 Support | Natalie Sinclair | 0 | DAX | EXPLEO GERMANY GMBH (EC) | MPE | Level 2 | REIM |  |  |  | -0.23455 | 100.5% | 83.82% | 83.82% | 0 | 5.56% | 508481.81 | 510900.32 | -2418.51 | 10311.33 | 4046.44 | 4046.44 | 32100 | 2418.51 | 428252.8 | 66.25 | 82647.52 | 801.5% | YES | 82647.52 | 0 | 428252.8 | 0 | 0 | 0 | 0 | 0 | 21% | 26.56% | 22.72% | 1.72% |  | 65.81 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23281 | Systems Portfolio | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM | 2024-02-28 | 0 |  |  | 44.43% | 97.31% | 97.31% | 0 | -17.25% | 1177697.24 | 523236.96 | 654460.28 | 0 | 2133.28 | 2133.28 | 0 | 0 | 509179.87 | 15792.1 | 13160.09 | 0% | NO | 13160.09 | 0 | 509179.87 | 0 | 0 | 0 | 0 | 0 | 25% | 7.75% | 100% | 75% |  | 70.48 | [5 empty] | -897
1738 | 2024-05-15 23:33 | P23520 | FCAS AP Portfolio Systems | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 23.543 | 67.14% | 94.12% | 75.99% | 0 | -6.58% | 810821 | 544412.55 | 266408.45 | 11315.81 | 423 | 423 | 0 | 0 | 512377.44 | 73.55 | 27752.11 | 245.3% | YES | 27752.11 | 118439 | 413678.2733 | 56206.8 | 0 | 62232.16 | 0 | 0 | 22% | 15.42% | 16.3% | -5.7% |  | 81.1 | [5 empty] | -4283
1738 | 2024-05-15 23:33 | P23001 | Spirit Shorts A220 Design | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -20.4357 | 112.9% | 75.88% | 66.67% | 29236.68 | 11.43% | 486640 | 549177.2 | -62537.2 | 3060.2 | 0 | 0 | 65953.2 | 62537.2 | 416705.3 | 433.35 | 132471.9 | 4329% | YES | 132471.9 | 60669 | 366147.8 | 21930.72 | 9501.6 | 29236.68 | 0 | 29236.68 | 9% | 20.43% | 11.52% | 2.52% |  | 43.56 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23140 | Spirit Shorts A220 MLG Stress Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  | 12.4637 | 72.75% | 101.1% | 61.77% | 0 | -14.59% | 735573.4 | 535147.07 | 200426.33 | 16080.85 | 20870.3 | 87811.88 | 0 | 0 | 540939.4 | 188.87 | 19207.67 | 119.4% | NO | 86149.25 | 252442 | 330571.0667 | 0 | 204098.4 | 48343.2 | 0 | 0 | 25% | 10.41% | -9.26% | -34.26% |  | 45.12 | [5 empty] | 25000
1738 | 2024-05-15 23:33 | P23219 | Tornado Air 800 Engineering Support | Richard Brook | 0 | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 3 | REIM |  |  |  |  | 98.48% | 95.49% | 95.49% | 0 | -1.52% | 615046 | 605713.28 | 9332.72 | -7373.61 | 459.21 | 459.21 | 0 | 0 | 578373.17 | 13.69 | 2433.11 | -33% | NO | 2433.11 | 0 | 578373.17 | 0 | 0 | 0 | 0 | 0 | 31% | 29.48% | 307.2% | 276.2% |  | 81.67 | [5 empty] | -24907
1738 | 2024-05-15 23:33 | P23473 | Tempest Vertical Tail | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 26.954 | 68.64% | 102.1% | 84.93% | 0 | -7.09% | 846017.62 | 580682.7 | 265334.92 | 9843.99 | 106750 | 112425 | 0 | 0 | 592767.31 | 61.79 | -7084.61 | -71.97% | NO | -1409.61 | 119501 | 493183.1433 | 45333.23 | 74168.03 | 0 | 0 | 0 | 29% | 21.91% | 24.37% | -4.63% |  | 62.58 | [5 empty] | 5000
1738 | 2024-05-15 23:33 | P23372 | BAE Carbon Tooling Off-load | Gary Kempster | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | 2.5864 | 87.38% | 98.77% | 73.98% | 0 | -3.18% | 674141.57 | 589043.26 | 85098.31 | 32902.49 | 0 | 0 | 0 | 0 | 581806.73 | 148.08 | 7236.53 | 21.99% | NO | 7236.53 | 175225 | 435785.8967 | 175224.95 | 0 | 0 | 0 | 0 | 25% | 21.82% | 18.29% | -6.71% |  | 53.91 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23366 | Business Analyst Support | Peter Williams | 0 | BDZ | MBDA UK LIMITED | DET | Level 3 | REIM |  |  |  | 74.0192 | 25.27% | 191.2% | 171.5% | 0 | 3.41% | 1302200 | 329029.4 | 973170.6 | 13147.54 | 273532.34 | 900687.4 | 0 | 0 | 629120 | 38.62 | -6955.6 | -52.9% | NO | 620199.46 | 77952 | 564160 | 77952 | 0 | 0 | 0 | 0 | 43% | 46.41% | 24.16% | -18.84% |  | 45.64 | [5 empty] | 293135
1738 | 2024-05-15 23:33 | P23323 | CNC-CMM Programming Support | Stephen Young | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  | -1.0373 | 101.7% | 91.47% | 81.59% | 40305.01 | -2.23% | 617809.74 | 628058.91 | -10249.17 | 9880.84 | 15941.56 | 15941.56 | 49744.45 | 10249.17 | 574493.52 | 84.5 | 53565.39 | 542.1% | YES | 53565.39 | 74458 | 512445.1867 | 0 | 74458.13 | 0 | 0 | 40305.01 | 32% | 29.77% | 36.48% | 4.48% |  | 57.55 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23694 | Systems Portfolio EXP-011a | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 0.79293 | 96.96% | 86.89% | 57.7% | 0 | 1.94% | 648492.8 | 628758.28 | 19734.52 | 24888.13 | 444.4 | 444.4 | 0 | 0 | 546332.19 | 78.16 | 82426.09 | 331.2% | YES | 82426.09 | 220264 | 362778.8567 | 142737.46 | 77526.61 | 0 | 0 | 0 | 21% | 22.94% | 20.33% | -0.67% |  | 88.61 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23605 | Typhoon Work Package 2 Continuation | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM |  |  |  |  | 119.5% | 83.59% | 81.23% | 0 | 5.12% | 545536.01 | 651980.1 | -106444.09 | -587.74 | 5554 | 5554 | 81999.09 | 106444.09 | 544986.65 | 811.27 | 106993.45 | -18204% | NO | 106993.45 | 18432 | 529626.65 | 0 | 18432.36 | 0 | 0 | 0 | 23% | 28.12% | 28.67% | 5.67% |  | 55.83 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P22790 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | REIM | 2024-04-28 | 0 |  | -134.62 | 197.4% | 89.11% | 89.11% | 0 | 1.11% | 352240 | 695460.45 | -343220.45 | 2549.55 | 1611.52 | 1611.52 | 44500 | 343220.45 | 619743.88 | 396.6 | 44446.57 | 1743% | YES | 44446.57 | 0 | 619743.88 | 0 | 0 | 0 | 0 | 0 | 13% | 14.11% | -2.72% | -15.72% |  | 45.08 | [5 empty] | -31270
1738 | 2024-05-15 23:33 | P23685 | DAC LUC Support and Recompliance | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 28.0435 | 27.13% | 163.6% | 42.5% | 288001.2 | 9.46% | 2180000 | 591526.51 | 1588473.49 | 56643.29 | 0 | 0 | 0 | 0 | 967868 | 87.12 | -262577.49 | -463.6% | NO | -262577.49 | 859729 | 251427.1667 | 297441.6 | 274286.4 | 0 | 288001.2 | 288001.2 | 30% | 39.46% | 39.46% | 9.46% |  | 57.65 | [5 empty] | 113764
1738 | 2024-05-15 23:33 | P23426 | BAE Tempest WP 3 Harness Maturation | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 4.8556 | 89.8% | 94.2% | 74.55% | 0 | -6.27% | 884012.04 | 793820.66 | 90191.38 | 18574.55 | 213.34 | 213.34 | 0 | 0 | 747777.74 | 78.24 | 46042.92 | 247.9% | YES | 46042.92 | 187209 | 591770.24 | 79451.21 | 107757.52 | 0 | 0 | 0 | 33% | 26.73% | 26.88% | -6.12% |  | 51.92 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23602 | EXP-025 Portfolio Software Engineering Support | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 11.9352 | 69.25% | 88.6% | 62.65% | 0 | -1.09% | 1327080 | 918948.09 | 408131.91 | 34195.59 | 3624.28 | 3868.41 | 0 | 0 | 814204.07 | 76.84 | 104744.02 | 306.3% | YES | 104988.15 | 286222 | 575685.7367 | 143172.62 | 143049.25 | 0 | 0 | 0 | 24% | 22.91% | 22.59% | -1.41% |  | 83.42 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23451 | BAE Tempest - DFM-ASO Planning | Stephen Young | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | 1.7751 | 96.67% | 71.64% | 64.21% | 39715.08 | -3.12% | 953905.42 | 922141.68 | 31763.74 | 17893.84 | 0 | 0 | 0 | 0 | 660614.46 | 118.95 | 260444.22 | 1455% | YES | 260444.22 | 82200 | 592114.46 | 42485.15 | 57003.88 | -44513.7 | 27224.9 | 39715.08 | 28% | 24.88% | 26.35% | -1.65% |  | 53.8 | [5 empty] | -1083
1738 | 2024-05-15 23:33 | P23105 | Raytheon Supply Engineering Support | Natalie Sinclair | 0 | RAY | RAYTHEON UNITED KINGDOM LIMITED | MPE | Level 3A | REIM | 2023-07-13 | 2 |  |  | 76.96% | 94.49% | 90.07% | 49156.8 | -2.02% | 1205008 | 927395.25 | 277612.75 | 0 | 0 | 0 | 0 | 0 | 876291.5 | 107644.5 | 48739.75 | 0% | NO | 48739.75 | 49157 | 835327.3333 | 0 | 0 | 0 | 49156.8 | 49156.8 | 26% | 23.98% | 100% | 74% |  | 48.97 | [5 empty] | -2364
1738 | 2024-05-15 23:33 | P23117 | BAE Typhoon Eng Support | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | 2024-03-12 | 9 |  |  | 105.2% | 95.01% | 95.01% | 0 | -1.06% | 950771.99 | 1000558.49 | -49786.5 | -5566.92 | 19090.01 | 21165.02 | 69773.84 | 49786.5 | 950609.41 | 27423.69 | 22853.08 | -410.5% | NO | 24928.09 | 0 | 950609.41 | 0 | 0 | 0 | 0 | 0 | 30% | 28.94% | 12.07% | -17.93% |  | 52.3 | [5 empty] | -27096
1738 | 2024-05-15 23:33 | P22350 | EMP 2020-2021 | Natalie Sinclair | 0 | ARY | GUIDANT GLOBAL UK LIMITED | PCPR | Level NC | REIM |  |  |  | 2.1539 | 99.18% | 98.64% | 95.18% | 0 | -2.12% | 1017579.76 | 1009266.09 | 8313.67 | 3859.85 | 400 | 400 | 0 | 0 | 995530.73 | 62.56 | 13735.36 | 355.9% | YES | 13735.36 | 41836 | 960667.3967 | 16974.24 | 24861.97 | 0 | 0 | 0 | 32% | 29.88% | 27.61% | -4.39% |  | 44.14 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P22671 | Spirit Shorts Pylon and Fairing Package | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX | 2023-05-03 | 0 |  |  | 105% | 95.26% | 95.26% | 0 | -7.21% | 1198494.77 | 1258071.09 | -59576.32 | 0 | 106494.89 | 106494.89 | 0 | 59576.32 | 1198494.77 | 2544.39 | 2120.32 | 0% | NO | 2120.32 | 0 | 1198494.77 | 0 | 0 | 0 | 0 | 0 | 20% | 12.79% | 0% | -20% |  | 45.4 | [5 empty] | -57456
1738 | 2024-05-15 23:33 | P23152 | Project Aragon - Design and Stress Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | -1.1283 | 101% | 75.55% | 54.13% | 0 | -9.54% | 1333452.21 | 1347284.46 | -13832.25 | 12259.12 | 0 | 0 | 0 | 13832.25 | 1017835.58 | 365.56 | 329448.88 | 2687% | YES | 329448.88 | 346248 | 729295.58 | 0 | 346247.55 | 0 | 0 | 0 | 39% | 29.46% | 29.26% | -9.74% |  | 51.98 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23292 | BAE Tempest WP 4 AV Trays | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 6.3001 | 91.18% | 96.48% | 75.45% | 155584.85 | 1.45% | 1498284.22 | 1366070.34 | 132213.88 | 20985.87 | 0 | 0 | 0 | 0 | 1317945.86 | 107.31 | 48124.48 | 229.3% | YES | 48124.48 | 344674 | 1030717.5267 | -17826.65 | 245826.2 | 116674.18 | 0 | 155584.85 | 32% | 33.45% | 31.88% | -0.12% |  | 53.88 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23519 | Mechanical and Electrical Design Eng Support | Dushan Fernando | 0 | BAX | SAFRAN SEATS GB LIMITED | MPE | Level 2 | REIM |  |  |  | 11.5271 | 81.31% | 94.81% | 75.76% | 0 | -1.59% | 1807261.3 | 1469469.7 | 337791.6 | 29304.08 | 1004.45 | 1504.45 | 0 | 0 | 1393199.8 | 80.21 | 76269.9 | 260.3% | YES | 76769.9 | 335892 | 1113289.8 | 141083.4 | 194808.9 | 0 | 0 | 0 | 33% | 31.41% | 31.41% | -1.59% |  | 56.66 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23411 | Agile & Scrum Delivery Service | Peter Williams | 0 | BDZ | MBDA UK LIMITED | DET | Level 2 | REIM | 2023-08-14 | 0 |  |  | 36.3% | 170.5% | 170.5% | 0 | 13.08% | 2487000 | 902903.79 | 1584096.21 | 0 | 894178.59 | 894178.59 | 0 | 0 | 1539600 | 19368.95 | 16140.79 | 0% | NO | 16140.79 | 0 | 1539600 | 0 | 0 | 0 | 0 | 0 | 29% | 42.08% | 0% | -29% |  | 74.57 | [5 empty] | 652837
1738 | 2024-05-15 23:33 | P22278 | TAI Supply Engineers to Ankara | Natalie Sinclair | 0 | TAI | TUSAS-TURK HAVACILIK VE UZAY | MPE | Level 3A | REIM |  |  |  | 1448.0224 | 19.78% | 458.7% | 458.7% | 0 | -15.77% | 2105282 | 416525.91 | 1688756.09 | 1166.25 | 49400.29 | 49400.29 | 0 | 0 | 1910696.33 | 113.47 | 16229.58 | 1392% | YES | 16229.58 | 0 | 1910696.33 | 0 | 0 | 0 | 0 | 0 | 95% | 79.23% | 67.16% | -27.84% |  | 34.12 | [5 empty] | 1510400
1738 | 2024-05-15 23:33 | P23175 | BAe Aero Typhoon Package 2 | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM | 2024-03-12 | 2 |  |  | 103.8% | 96.32% | 96.32% | 0 | -1.63% | 1984265.09 | 2060011.83 | -75746.74 | 0 | 57677.87 | 86030.82 | 15444.64 | 75746.74 | 1984257.03 | 84731.75 | 70609.8 | 0% | NO | 98962.75 | 0 | 1984257.03 | 0 | 0 | 0 | 0 | 0 | 29% | 27.37% | 0% | -29% |  | 51.76 | [5 empty] | -5145
1738 | 2024-05-15 23:33 | P23006 | Spirit Shorts A350 Freighter Toulouse | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 42.2253 | 87.46% | 106.1% | 73.33% | 33464.4 | 22.31% | 1925837.92 | 1684266.24 | 241571.68 | 5721.02 | 1086670.26 | 2010741.94 | 0 | 0 | 1787659.45 | 393.63 | 273880.79 | 4787% | YES | 1197952.47 | 663070 | 1235101.1167 | 110245.82 | 140525.66 | 412298.62 | 0 | 33464.4 | 5% | 27.31% | 47.96% | 42.96% |  | 48.22 | [5 empty] | 377274
1738 | 2024-05-15 23:33 | P19020 | Spirit Concessions - 2018 | Carl Warren | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2024-01-23 | 1 |  |  | 86.3% | 111.8% | 111.2% | 12156.8 | 2.09% | 2015043.23 | 1739018.14 | 276025.09 | 0 | 44317.61 | 44317.61 | 0 | 0 | 1944710.76 | 248541.66 | 196987.38 | 0% | NO | 196987.38 | 12157 | 1934579.9267 | 0 | 0 | 0 | 12156.8 | 12156.8 | 25% | 27.09% | 9.32% | -15.68% |  | 40.87 | [5 empty] | 402680
1738 | 2024-05-15 23:33 | P23435 | Andy Baker Portfolio | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 36.0598 | 55.08% | 91.79% | 67.1% | 0 | -7.13% | 4023207.4 | 2215947.09 | 1807260.31 | 50118.43 | 2596.25 | 2596.25 | 0 | 0 | 2033949.78 | 103.79 | 181997.31 | 363.1% | YES | 181997.31 | 656410 | 1486941.4467 | 166805.62 | 0 | 489604.46 | 0 | 0 | 25% | 17.87% | 19.64% | -5.36% |  | 81.04 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23257 | BAE Tempest WP 5 Centre Fuselage | Lauren Victoria Savage | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 2.9326 | 98.06% | 99.54% | 93.7% | 0 | -5.7% | 2265401.51 | 2221538.57 | 43862.94 | 14956.78 | 78100 | 78100 | 0 | 0 | 2211380.12 | 59.16 | 10158.45 | 67.92% | NO | 10158.45 | 155821 | 2081529.2867 | 67820.9 | 87999.86 | 0 | 0 | 0 | 33% | 27.3% | 28.26% | -4.74% |  | 61.05 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23179 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX |  |  |  | -3.9673 | 100.7% | 94.23% | 86.15% | 85390.96 | -9.26% | 2542643.04 | 2559881.86 | -17238.82 | 4345.22 | 156991.12 | 248243.92 | 0 | 17238.82 | 2412235.69 | 789.42 | 147646.17 | 3398% | YES | 238898.97 | 248280 | 2205335.69 | 0 | 0 | 248280.21 | 0 | 85390.96 | 22% | 12.74% | 17.67% | -4.33% |  | 44.4 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P19731 | Hapri HPC Rear Bearing Housing PDR & CDR | Steven Lawton | 0 | ATC | AECC Hunan Aviation Powerplant | MPE | Level 1 | FIX | 2024-05-13 | 4 |  | -5.7488 | 100.3% | 99.67% | 87.21% | 447000 | -15.41% | 2980000 | 2989767.41 | -9767.41 | 1699.04 | 366282.13 | 500382.13 | 0 | 9767.41 | 2980000 | 859.77 | -215232.59 | -12668% | NO | -81132.59 | 447000 | 2607500 | 0 | 0 | 0 | 447000 | 447000 | 38% | 22.59% | 15.47% | -22.53% |  | 64.85 | [5 empty] | -225000
1738 | 2024-05-15 23:33 | P23207 | A350 Approvers - Design and Stress Support | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  | 5.9789 | 88.45% | 95.64% | 72.67% | 0 | -4.27% | 3135290 | 2773209.85 | 362080.15 | 60559.24 | 36201.43 | 36766.42 | 0 | 0 | 2652260.57 | 91 | 120949.28 | 199.7% | YES | 121514.27 | 764210 | 2015418.9033 | 232534.01 | 342017.26 | 189658.31 | 0 | 0 | 22% | 17.73% | 16.77% | -5.23% |  | 54.54 | [5 empty] | 0
1738 | 2024-05-15 23:33 | P23487 | Tornado Air 800 Engineering Support | Richard Brook | 0 | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 2 | FIX |  |  |  | 11.6911 | 77.9% | 88.86% | 77.16% | 47390.58 | -2.84% | 4286367.76 | 3339045.68 | 947322.08 | 81029.33 | 0 | 0 | 0 | 0 | 2967206.61 | 95.27 | 443839.07 | 547.8% | YES | 443839.07 | 468813 | 2576529.11 | 421421.93 | 0 | 8658.1 | 38732.48 | 47390.58 | 40% | 37.16% | 40.88% | 0.88% |  | 78.97 | [5 empty] | 72000
Extend Table

## AP5-3
WIP No | Date Created | Project ID | Project Description | Project Manager | Agency (1=yes, 0=no) | Department Id | Client | CBU | Complexity | Type | Stop Booking Hrs | Closing Project: Action(s) to close | RAG | Approx. PO Burndown (weeks) | Turnover vs Contract Value | Invoice To Date vs Turnover | Cash in vs Turnover | Open Amount Overdue | Actual PM% to Baseline PM% delta | Contract Value | Total Project Turnover | Contract Value - Total Turnover | Run Rate (based on total turnover) | Total BOI Spend to Date | Total Committed PO (supplier/best shore) | Current AA in PT3 | Exposure (turnover - contract value) | Invoiced To Date | DSO | Unbilled (WIP) | WIP / Run rate | WIP / Run rate >1.3 | WIP + Remaining Committed PO for BOI | Total Open Amount | Cash in (Invoiced - (Open amount -VAT)) | Debt <=30 Days | Debt 31 - 60 Days | Debt 61 - 90 Days | Debt >= 90 Days | Open Amount Overdue2 | Baseline Project Margin | Project To Date (PTD) PM | Year to Date (YTD) PM | YTD Delta Actual PM% to BPM% | Forecast PM at Completion (Manual input from PTT) | Average Sale Rate | CSat score for last quarter (Manual input from PTT) | Comments and Actions | Judged income adjustment at completion | Profit to take now | Provision required now | Fully Traded | Last Months Comments and Actions
1739 | 2024-05-22 23:35 | P23650 | MBDA Recruitment Management costs | Andrew Slaney | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM | 2024-02-01 | 1 |  |  |  | 0% | 0% | 0 | 33042515% | 0 | 240971.5 | -240971.5 | -35243 | 0 | 0 | 266000 | 240971.5 | 0 | 0 | -0.5 | 0.001419% | NO | -0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | 33042518% | 165.6% | 162.6% |  | 82.3 | [5 empty] | -240972
1739 | 2024-05-22 23:35 | P23637 | MBSE Proposal | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM | 2024-04-28 | 0 | [5 empty] | 0 | -35% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23552 | FCAS AP Product Technology Development | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -25% | 597871 | 0 | 597871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0% | -25% |  | 0 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23543 | EXP-024 FCAS AP Transformation & Change Enablers | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -26% | 385921 | 0 | 385921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26% | 0% | 0% | -26% |  | 0 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23784 | Tempest Tooling Offload 2024 | Gary Kempster | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM | 2024-05-09 | 48 | [5 empty] | 0 | -25% | 0 | 0 | 0 | -26713.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0% | -25% |  | 0 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23628 | Design Assurance | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | -7% | 0 | 0 | 0 | -977.31 | 0 | 0 | 4454.8 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 0% | 0.33% | -6.67% |  | 0 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23711 | DO NOT USE - RAISED IN ERROR | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23585 | Systems Design - Missile Systems, Meteor,Brimstone | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM | 2024-04-28 | 0 | [5 empty] | 0 | -35% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35% | 0% | 0% | -35% |  | 0 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23717 | GKN Ted Tomblin 2024 | Matthew Tweed | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2024-04-28 | 0 | [5 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23899 | Turret Test Rig | Trevin Fernandopulle | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -16% | 24864 | 0 | 24864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16% | 0% | 0% | -16% |  | 0 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23730 | FLE Project | Siyun Fan | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -18.03% | 0 | 1120 | -1120 | 0 | 0 | 0 | 24000 | 1120 | 0 | 1344 | 1120 | 0% | NO | 1120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | -18.03% | -18.03% | -18.03% |  | 35 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23892 | Warrior Environmental Control Unit | Trevin Fernandopulle | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM |  |  |  | 4.7778 | 38.57% | 0% | 0% | 0 | 3.58% | 3920 | 1512 | 2408 | 504 | 0 | 0 | 0 | 0 | 0 | 14 | 1512 | 300% | YES | 1512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32% | 35.58% | 35.58% | 3.58% |  | 56 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23463 | A220 Wing MaMo Design Checking | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-03-07 | 0 |  |  |  | 0% | 0% | 0 | 7.85% | 0 | 1628 | -1628 | 0 | 0 | 0 | 15000 | 1628 | 0 | 1953.6 | 1628 | 0% | NO | 1628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | 10.85% | 0% | -3% |  | 44 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P21028 | Rebate Collection (BACC) | David Catchpole | 0 | TOO | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | [5 empty] | 0% | 0% | 0 | 0% | 0 | 2680 | -2680 | 0 | 2680 | 2680 | 0 | 2680 | 0 | 3216 | 2680 | 0% | NO | 2680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23886 | A220 F&DT Support | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -4 |  | 0% | 0% | 0 | -9.07% | 0 | 3380.2 | -3380.2 | 845.05 | 0 | 0 | 12199.2 | 3380.2 | 0 | 21 | 3380.2 | 400% | YES | 3380.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 8.93% | 8.93% | -9.07% |  | 50.83 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23578 | ESN Work Package | Hannah Mead | 0 | COZ | CHELTON LIMITED | DET | Level 3 | FIX | 2024-01-01 | 0 |  |  | 86.17% | 116.1% | 116.1% | 0 | 35.86% | 4410 | 3800 | 610 | 0 | 0 | 0 | 0 | 0 | 4410 | 0 | -610 | 0% | NO | -610 | 0 | 4410 | 0 | 0 | 0 | 0 | 0 | 24% | 59.86% | 0% | -24% |  | 95 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23880 | Warrior Crew Heater Design | Trevin Fernandopulle | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM |  |  |  | 0.4 | 90.91% | 0% | 0% | 0 | 3.58% | 5544 | 5040 | 504 | 1260 | 0 | 0 | 0 | 0 | 0 | 35 | 5040 | 400% | YES | 5040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32% | 35.58% | 35.58% | 3.58% |  | 56 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23898 | EXP-041 ISV Engineering Support | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | -2 |  | 0% | 0% | 0 | -13.04% | 0 | 5220.25 | -5220.25 | 2610.13 | 0 | 0 | 12618 | 5220.25 | 0 | 13 | 5220.25 | 200% | YES | 5220.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21% | 7.96% | 7.96% | -13.04% |  | 78.5 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23002 | WoT MAJ Transit Flag Stress | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2024-04-03 | 1 |  |  | 62.41% | 160.2% | 160.2% | 0 | 38.54% | 4735 | 2955.29 | 1779.71 | 0 | 1492.79 | 2242.5 | 0 | 0 | 4735 | 91.03 | 1493.29 | 0% | NO | 2243 | 0 | 4735 | 0 | 0 | 0 | 0 | 0 | 10% | 48.54% | 0% | -10% |  | 45 | [5 empty] | 3273
1739 | 2024-05-22 23:35 | P23894 | EE Test and Integration Lead | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | -3 |  | 0% | 0% | 0 | 10.6% | 0 | 6611.58 | -6611.58 | 2203.86 | 0 | 0 | 15430 | 6611.58 | 0 | 21 | 6611.58 | 300% | YES | 6611.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23% | 33.6% | 33.6% | 10.6% |  | 63.88 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23881 | Bulldog Fuel System Design | Trevin Fernandopulle | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM |  |  |  | 0.5364 | 88.18% | 0% | 0% | 0 | 1.29% | 8288 | 7308 | 980 | 1827 | 0 | 0 | 0 | 0 | 0 | 28 | 7308 | 400% | YES | 7308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13% | 14.29% | 14.29% | 1.29% |  | 56 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23864 | REACH Coordinator | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 43.1079 | 15.08% | 0% | 0% | 0 | -10.24% | 52920 | 7980 | 44940 | 1042.5 | 0 | 0 | 0 | 0 | 0 | 63 | 7980 | 765.5% | YES | 7980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27% | 16.76% | 16.76% | -10.24% |  | 30 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23888 | HondaJet FWD Assy Jig Tool Design | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX |  |  |  | 11.544 | 25.73% | 0% | 0% | 0 | 4.29% | 31500 | 8106 | 23394 | 2026.5 | 0 | 0 | 0 | 0 | 0 | 35 | 8106 | 400% | YES | 8106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 14.29% | 14.29% | 4.29% |  | 42 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23607 | SAFRAN - A330neo Turnover Frame | Gary Kempster | 0 | TOO | SAFRAN SEATS GB LIMITED | MPE | Level 3 | FIX |  |  |  |  | 95.69% | 104.5% | 104.5% | 0 | -19.52% | 8736 | 8359.05 | 376.95 | 0 | 0 | 0 | 0 | 0 | 8736 | 0.06 | 0.05 | 0% | NO | 0.05 | 0 | 8736 | 0 | 0 | 0 | 0 | 0 | 23% | 3.48% | 8.5% | -14.5% |  | 50.46 | [5 empty] | 377
1739 | 2024-05-22 23:35 | P23274 | ME Support (Aim Altitude - Cambridge) | Trevor Knox | 0 | AVI | AVIC CABIN SYSTEMS (UK) LIMITED | ME | Level 3 | FIX | 2023-08-18 | 0 |  |  | 51.88% | 56.3% | 56.3% | 0 | -0.17% | 17280 | 8964 | 8316 | 0 | 0 | 0 | 0 | 0 | 5046.3 | 4701.24 | 3917.7 | 0% | NO | 3917.7 | 0 | 5046.3 | 0 | 0 | 0 | 0 | 0 | 21% | 20.83% | 0% | -21% |  | 48 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23283 | Spirit Tooling Audit | Charidimos Valadakis | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-05-03 | 0 |  |  | 97.22% | 48.57% | 48.57% | 0 | -7.99% | 9910.08 | 9634.8 | 275.28 | 0 | 0 | 0 | 0 | 0 | 4679.76 | 5946.05 | 4955.04 | 0% | NO | 4955.04 | 0 | 4679.76 | 0 | 0 | 0 | 0 | 0 | 7% | -0.99% | 0% | -7% |  | 34.41 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23127 | Loft Hall Design Support | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-04-19 | 0 |  |  | 101% | 99.06% | 99.06% | 0 | -9.55% | 9680 | 9772 | -92 | 0 | 0 | 0 | 0 | 92 | 9680 | 110.4 | 92 | 0% | NO | 92 | 0 | 9680 | 0 | 0 | 0 | 0 | 0 | 41% | 31.45% | 0% | -41% |  | 44 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23630 | 2Excel CFD Analysis Support | Dushan Fernando | 0 | BAX | STIRLING DYNAMICS LTD | MPE | Level NC | FIX |  |  |  |  | 61.2% | 100% | 100% | 0 | -1.87% | 16195.49 | 9911.34 | 6284.15 | 0 | 0 | 0 | 0 | 0 | 9911.63 | 0 | -0.29 | 0% | NO | -0.29 | 0 | 9911.63 | 0 | 0 | 0 | 0 | 0 | 26% | 24.13% | 0% | -26% |  | 64.78 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23313 | Laser Trim Fixtures | Gary Kempster | 0 | TOO | ALKEN ENGINEERING LIMITED | MPE | Level 3 | FIX | 2023-11-20 | 0 |  |  | 89.87% | 111.3% | 111.3% | 0 | 0.53% | 13770 | 12375 | 1395 | 0 | 0 | 0 | 0 | 0 | 13770 | 0 | -1395 | 0% | NO | -1395 | 0 | 13770 | 0 | 0 | 0 | 0 | 0 | 17% | 17.53% | 0% | -17% |  | 45 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23902 | Typhoon Rear Fuselage | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -2 |  | 0% | 0% | 0 | -0.85% | 0 | 12619.27 | -12619.27 | 6309.64 | 0 | 0 | 45382.5 | 12619.27 | 0 | 13 | 12619.27 | 200% | YES | 12619.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 29.15% | 29.15% | -0.85% |  | 52.15 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23843 | EXP-035 FT15 Exemplar information set | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 62.4252 | 7.284% | 0% | 0% | 0 | -11.17% | 175985.16 | 12818.7 | 163166.46 | 2613.79 | 0 | 0 | 0 | 0 | 0 | 63 | 12818.7 | 490.4% | YES | 12818.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 8.83% | 8.83% | -11.17% |  | 71.87 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23718 | Requalification of EJ200 GSS ESS EHM SW module | Vijayakumara Nanjundappa | 0 | ARZ | MTU AERO ENGINES AG | DET | Level 3 | FIX |  |  |  | 121.7385 | 13.35% | 182.3% | 182.3% | 0 | 16.06% | 74463 | 9941.57 | 64521.43 | 530 | 991.93 | 991.93 | 0 | 0 | 18125 | 0 | -5183.43 | -978% | NO | -5183.43 | 0 | 18125 | 0 | 0 | 0 | 0 | 0 | 28% | 44.06% | 44.06% | 16.06% |  | 80 | [5 empty] | 3000
1739 | 2024-05-22 23:35 | P22761 | Red Bull Chassis Spit | Trevor Knox | 0 | TOO | MANUFAX ENGINEERING LTD | MPE | Level 3 | FIX | 2022-11-15 | 0 |  |  | 72.18% | 96.98% | 96.98% | 0 | 7.92% | 12961.2 | 9355.5 | 3605.7 | 0 | 0 | 0 | 0 | 0 | 9072.84 | 4666.39 | 3888.66 | 0% | NO | 3888.66 | 0 | 9072.84 | 0 | 0 | 0 | 0 | 0 | 23% | 30.92% | 0% | -23% |  | 42.19 | [5 empty] | 3606
1739 | 2024-05-22 23:35 | P23350 | Spirit 2023 - Stress Approve Man Serv (DH) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 14.15% | 72.64% | 72.64% | 0 | -0.29% | 97920 | 13860 | 84060 | 0 | 0 | 0 | 0 | 0 | 10068 | 4550.4 | 3792 | 0% | NO | 3792 | 0 | 10068 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23344 | Spirit A320 Spoilers Support 2023 | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 38.75% | 100% | 100% | 0 | 5.82% | 35786.4 | 13867.23 | 21919.17 | 0 | 0 | 0 | 0 | 0 | 13867.23 | 0 | 0 | 0% | NO | 0 | 0 | 13867.23 | 0 | 0 | 0 | 0 | 0 | 7% | 12.82% | 0% | -7% |  | 34.41 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23873 | FCAS Systems Engineering Support | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 51.1074 | 8.98% | 0% | 0% | 0 | -9.72% | 156475 | 14051.5 | 142423.5 | 2786.75 | 0 | 0 | 0 | 0 | 0 | 35 | 14051.5 | 504.2% | YES | 14051.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 8.28% | 8.28% | -9.72% |  | 78.5 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23337 | Spirit 2023 - Steve Grimley | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 25.28% | 100% | 100% | 0 | 0.01% | 56812.9 | 14362.47 | 42450.43 | 0 | 0 | 0 | 0 | 0 | 14362.47 | 0 | 0 | 0% | NO | 0 | 0 | 14362.47 | 0 | 0 | 0 | 0 | 0 | 7% | 7.01% | 0% | -7% |  | 30.11 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23597 | MRB Onsite support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-02-16 | 1 |  |  |  | 0% | 0% | 0 | -10.04% | 0 | 15100.57 | -15100.57 | 0 | 9448.07 | 17381.62 | 24200 | 15100.57 | 0 | 18120.68 | 15100.57 | 0% | NO | 23034.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 7.96% | 8.95% | -9.05% |  | 42.5 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23869 | EXP-037 Land Ceptor Development Hardware Test Def | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 36.8142 | 9.801% | 55.49% | -0.0004599% | 0 | 0.81% | 162694 | 15944.83 | 146749.17 | 3986.21 | 0 | 0 | 0 | 0 | 8848.26 | 56 | 7096.57 | 178% | YES | 7096.57 | 10618 | -0.073333 | 10617.91 | 0 | 0 | 0 | 0 | 26% | 26.81% | 26.81% | 0.81% |  | 89.83 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23343 | Spirit 2023 - John Agnew | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-08-09 | 0 |  |  | 24.64% | 100% | 100% | 0 | -0.02% | 65120.37 | 16047.15 | 49073.22 | -638.44 | 0 | 0 | 0 | 0 | 16047.15 | 0 | 0 | 0% | NO | 0 | 0 | 16047.15 | 0 | 0 | 0 | 0 | 0 | 7% | 6.98% | 6.98% | -0.02% |  | 34.51 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23635 | Engineering Services: FAI Support | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 49.9% | 100% | 0.0008972% | 0 | -3.4% | 37230 | 18576 | 18654 | 0 | 0 | 0 | 0 | 0 | 18576 | 22291.2 | 0 | 0% | NO | 0 | 22291 | 0.16667 | 0 | 7058.88 | 15232.32 | 0 | 0 | 8% | 4.6% | 5.04% | -2.96% |  | 38.7 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23355 | Spirit Tooling Support 2023 | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-23 | 0 |  |  | 22.93% | 89.02% | 89.02% | 0 | -0.82% | 91800 | 21053.34 | 70746.66 | 0 | 0 | 0 | 0 | 0 | 18742.5 | 2773.01 | 2310.84 | 0% | NO | 2310.84 | 0 | 18742.5 | 0 | 0 | 0 | 0 | 0 | 20% | 19.18% | 0% | -20% |  | 44.46 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23839 | Stirling Dynamics - ST002-GFEM | Matthew Dodd | 0 | BAX | STIRLING DYNAMICS LTD | MPE | Level NC | FIX |  |  |  | 4.3336 | 89.35% | 0% | 0% | 0 | -4.93% | 24057.34 | 21496.26 | 2561.08 | 590.98 | 2126.93 | 2126.93 | 0 | 0 | 0 | 106.39 | 21496.26 | 3637% | YES | 21496.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 2.07% | 2.07% | -4.93% |  | 43.77 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23663 | Spirit Tooling Verification and Inspection | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  | 0.3871 | 98.66% | 75.11% | 0.00152% | 0 | -6.39% | 23123.52 | 22813.83 | 309.69 | 800.03 | 0 | 0 | 0 | 0 | 17136.18 | 195.25 | 5677.65 | 709.7% | YES | 5677.65 | 20563 | 0.34667 | 0 | 12635.35 | 7928.06 | 0 | 0 | 11% | 4.61% | 4.82% | -6.18% |  | 34.41 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23351 | Spirit 2023 - Design Man Serv (KL) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 26.47% | 93.15% | 93.15% | 0 | 0.09% | 93840 | 24840 | 69000 | 0 | 0 | 0 | 0 | 0 | 23138 | 2042.4 | 1702 | 0% | NO | 1702 | 0 | 23138 | 0 | 0 | 0 | 0 | 0 | 26% | 26.09% | 0% | -26% |  | 46 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23356 | Spirit 2023 - Design Man Serv (AH) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX | 2023-08-09 | 1 |  |  |  | 76.66% | 0.001332% | 23018.4 | 0.48% | 0 | 25023.08 | -25023.08 | 0 | 0 | 0 | 25300 | 25023.08 | 19182 | 30027.7 | 5841.08 | 0% | NO | 5841.08 | 23018 | 0.33333 | 0 | 0 | 0 | 23018.4 | 23018.4 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P22884 | Spirit Shorts Config Eng | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 66.3% | 100.1% | 100.1% | 0 | 0.56% | 38976 | 25841.9 | 13134.1 | 0 | 0 | 0 | 0 | 0 | 25863.2 | 0 | -0.3 | 0% | NO | -0.3 | 0 | 25863.2 | 0 | 0 | 0 | 0 | 0 | 7% | 7.56% | 0% | -7% |  | 20.3 | [5 empty] | 21
1739 | 2024-05-22 23:35 | P23742 | Cyber Security Support | Hannah Mead | 0 | COZ | CHELTON LIMITED | DET | Level 3 | FIX |  |  |  | 1.2444 | 94.91% | 105.4% | 0% | 0 | -0.96% | 27500 | 26100 | 1400 | 1125 | 0 | 0 | 0 | 0 | 27500 | 131.95 | -1400 | -124.4% | NO | -1400 | 33000 | 0 | 33000 | 0 | 0 | 0 | 0 | 32% | 31.04% | 31.04% | -0.96% |  | 100 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23354 | Spirit 2023 - Design Man Serv (PC) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 27.97% | 99.36% | 99.36% | 0 | 0.48% | 93840 | 26248.98 | 67591.02 | 0 | 0 | 0 | 0 | 0 | 26082 | 200.38 | 166.98 | 0% | NO | 166.98 | 0 | 26082 | 0 | 0 | 0 | 0 | 0 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P22756 | A350 FLE Design Checker | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2022-03-23 | 1 |  |  | 68.39% | 119.7% | 119.7% | 0 | 16.46% | 34898.4 | 23867.15 | 11031.25 | 0 | 23867.15 | 24342.3 | 0 | 0 | 28571.1 | 0.06 | 0.05 | 0% | NO | 475.2 | 0 | 28571.1 | 0 | 0 | 0 | 0 | 0 | 0% | 16.46% | 0% | 0% |  | 0 | [5 empty] | 4704
1739 | 2024-05-22 23:35 | P23842 | Tranche 1 Evolution Package Step 2 | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 17.2868 | 25.96% | 0% | 0% | 0 | -10.18% | 112526.3 | 29207.1 | 83319.2 | 4819.83 | 1000 | 1000 | 0 | 0 | 0 | 63 | 29207.1 | 606% | YES | 29207.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31% | 20.82% | 20.82% | -10.18% |  | 56.14 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23458 | Spirit Belfast Tooling Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-08-11 | 0 |  |  | 101.3% | 94.65% | 94.65% | 0 | 8.64% | 30384 | 30784.9 | -400.9 | 0 | 0 | 0 | 0 | 400.9 | 29139.1 | 1974.96 | 1645.8 | 0% | NO | 1645.8 | 0 | 29139.1 | 0 | 0 | 0 | 0 | 0 | 7% | 15.64% | 0% | -7% |  | 42.2 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23874 | Environmental Engineering (Sea Venom/ANL) | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | -5.5225 |  | 0% | 0% | 0 | -1.02% | 0 | 32459.75 | -32459.75 | 5877.69 | 0 | 0 | 49199 | 32459.75 | 0 | 42 | 32459.75 | 552.3% | YES | 32459.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 18.98% | 18.98% | -1.02% |  | 78.5 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23365 | GKN 777x Lip Skin Fixture | Steven Lawton | 0 | TOO | GKN AEROSPACE SERVICES LTD | MPE | Level 3 | FIX | 2023-10-12 | 0 |  |  | 41.91% | 113.2% | 113.2% | 0 | -9.26% | 79161.46 | 33175.67 | 45985.79 | 0 | 5109.88 | 5109.88 | 0 | 0 | 37544.22 | 0 | -4368.55 | 0% | NO | -4368.55 | 0 | 37544.22 | 0 | 0 | 0 | 0 | 0 | 22% | 12.74% | 0% | -22% |  | 56 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23891 | A220 FLE Support | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -3 |  | 0% | 0% | 0 | 6.61% | 0 | 34297.44 | -34297.44 | 11432.48 | 0 | 0 | 36633.6 | 34297.44 | 0 | 52 | 34297.44 | 300% | YES | 34297.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 13.61% | 13.61% | 6.61% |  | 49.92 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23433 | Cavendish | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 4.7994 | 81.85% | 40.09% | 40.09% | 0 | -0.43% | 42240 | 34574.4 | 7665.6 | 1597.2 | 0 | 0 | 0 | 0 | 13859.2 | 91 | 20715.2 | 1297% | YES | 20715.2 | 0 | 13859.2 | 0 | 0 | 0 | 0 | 0 | 7% | 6.57% | 6.51% | -0.49% |  | 46.5 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23831 | Contract DM/00113 for maintenance, repair and post | Harry James Kellett | 0 | BXW | MOD | EES | Level 2 | FIX |  |  |  | 7.0811 | 74.46% | 16.35% | 16.35% | 0 | 17.11% | 46455.9 | 34592.06 | 11863.84 | 1675.43 | 0 | 0 | 0 | 0 | 5655.9 | 76.92 | 28936.16 | 1727% | YES | 28936.16 | 0 | 5655.9 | 0 | 0 | 0 | 0 | 0 | 34% | 51.11% | 51.11% | 17.11% |  | 80.26 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P22768 | MRB Onsite Support - Spirit Belfast | Trevor Knox | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2023-07-27 | 0 |  |  |  | 0% | 0% | 0 | -17.07% | 0 | 34614 | -34614 | 0 | 0 | 0 | 36800 | 34614 | 0 | 41536.8 | 34614 | 0% | NO | 34614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | -7.07% | 0% | -10% |  | 36 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23724 | GKN S McConnell 2024 | Matthew Tweed | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  | 8.2571 | 71.1% | 85.51% | -0.0007716% | 0 | 0.9% | 49820 | 35422.05 | 14397.95 | 1743.7 | 0 | 0 | 0 | 0 | 30290.56 | 140.65 | 5131.49 | 294.3% | YES | 5131.49 | 36349 | -0.27333 | 8369.76 | 10761.12 | 8848.03 | 8369.76 | 0 | 19% | 19.9% | 19.9% | 0.9% |  | 49.61 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23821 | Supply of Safety Engineer | Dinna Elkhalifa | 0 | BXW | STIRLING DYNAMICS LTD | EES | Level NC | REIM |  |  |  | -1.8664 | 106.6% | 49% | 49% | 0 | 45.1% | 34006.44 | 36247.77 | -2241.33 | 1200.86 | 0 | 0 | 0 | 2241.33 | 17760.6 | 78.64 | 18487.17 | 1539% | YES | 18487.17 | 0 | 17760.6 | 0 | 0 | 0 | 0 | 0 | 0% | 45.1% | 45.1% | 45.1% |  | 80.73 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23651 | PMO Spirit | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 7.8698 | 75.71% | 62.86% | -0.0004467% | 0 | -19.36% | 49284 | 37314 | 11970 | 1521 | 0 | 0 | 0 | 0 | 23454 | 221.67 | 13860 | 911.2% | YES | 13860 | 28145 | -0.16667 | 0 | 0 | 28144.8 | 0 | 0 | 43% | 23.64% | 23.11% | -19.89% |  | 36 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23338 | Spirit 2023 - Blair Hainey | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 28.0819 | 59.39% | 96.81% | 48.3% | 0 | -2.93% | 62893.71 | 37355.16 | 25538.55 | 909.43 | 0 | 0 | 0 | 0 | 36165.24 | 243.79 | 1189.92 | 130.8% | YES | 1189.92 | 21747 | 18042.74 | 21747.46 | 0 | 0 | 0 | 0 | 7% | 4.07% | -5.75% | -12.75% |  | 16.58 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23347 | WoT Fixed Leading Edge - Industrial 2023 | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | -10.6486 | 120.5% | 82.92% | 39.34% | 0 | -0.38% | 31034.12 | 37389.34 | -6355.22 | 596.81 | 0 | 0 | 10500 | 6355.22 | 31001.86 | 27214.54 | 6387.48 | 1070% | YES | 6387.48 | 19550 | 14710.1933 | 19549.56 | 0 | 0 | 0 | 0 | 7% | 6.62% | 7.01% | 0.01% |  | 32.26 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23051 | Spirit Shorts A350 PAX Door | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3A | REIM |  |  |  |  | 205.9% | 105.4% | 105.4% | 0 | -0.63% | 18216 | 37513 | -19297 | 0 | 0 | 0 | 0 | 19297 | 39537 | 0 | 0 | 0% | NO | 0 | 0 | 39537 | 0 | 0 | 0 | 0 | 0 | 30% | 29.37% | 0% | -30% |  | 46 | [5 empty] | 2024
1739 | 2024-05-22 23:35 | P22752 | Tooling WoT - 2021 (Spirit) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | REIM | 2023-05-03 | 0 |  |  | 101.1% | 74.02% | 74.02% | 0 | -8.5% | 41525.1 | 41982.28 | -457.18 | 0 | 0 | 0 | 0 | 457.18 | 31076.1 | 13087.42 | 10906.18 | 0% | NO | 10906.18 | 0 | 31076.1 | 0 | 0 | 0 | 0 | 0 | 0% | -8.5% | 0% | 0% |  | 39.09 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23811 | Spirit T300 MRB Concessions | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -12.0335 |  | 0% | 0% | 0 | -7.19% | 0 | 44450.98 | -44450.98 | 3693.95 | 0 | 0 | 50000 | 44450.98 | 0 | 97.14 | 44450.98 | 1203% | YES | 44450.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21% | 13.81% | 13.81% | -7.19% |  | 47.19 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23823 | EXP-034 Spear 3 Test Equip Requirement Authority | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 10.4227 | 54.65% | 66.02% | 7.838% | 0 | 0.02% | 85825 | 46899.75 | 38925.25 | 3734.66 | 1000 | 1000 | 0 | 0 | 30961.13 | 83.87 | 15938.62 | 426.8% | YES | 15938.62 | 32742 | 3676.13 | 15494.7 | 17247.76 | 0 | 0 | 0 | 14% | 14.02% | 14.02% | 0.02% |  | 94.25 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23339 | Spirit 2023 - Stewart Russell | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 64.51% | 100% | 100% | 0 | 0.62% | 72766.8 | 46941.72 | 25825.08 | 0 | 0 | 0 | 0 | 0 | 46941.74 | 0 | -0.02 | 0% | NO | -0.02 | 0 | 46941.74 | 0 | 0 | 0 | 0 | 0 | 7% | 7.62% | 0% | -7% |  | 35.67 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23740 | Phase 2 - EJ200 ESS EHM Platform Migration | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 3 | FIX |  |  |  | 26.0608 | 21.82% | 196.4% | 65.46% | 0 | 18.9% | 175971 | 38402.5 | 137568.5 | 5278.75 | 0 | 0 | 0 | 0 | 75417 | 65.68 | -25014.5 | -473.9% | NO | -25014.5 | 60334 | 25138.6667 | 30166.8 | 30166.8 | 0 | 0 | 0 | 28% | 46.9% | 46.9% | 18.9% |  | 42.88 | [5 empty] | 12000
1739 | 2024-05-22 23:35 | P22760 | SA Leading Edge Transport Media ('A' Frames) | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-11-15 | 1 |  |  | 85.99% | 110.7% | 116.3% | -3082.8 | 3.97% | 53480.8 | 45985.5 | 7495.3 | 0 | 42804 | 42804 | 0 | 0 | 50911.8 | 0 | -0.3 | 0% | NO | -0.3 | -3083 | 53480.9667 | 0 | 0 | 0 | -3082.8 | -3082.8 | 6% | 9.97% | 0% | -6% |  | 42 | [5 empty] | 4926
1739 | 2024-05-22 23:35 | P23642 | MRB Belfast Support | Paul Watson | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -33.493 |  | 0% | 0% | 0 | -44.18% | 0 | 52921.25 | -52921.25 | 1580.07 | 3566.12 | 3566.12 | 48125 | 52921.25 | 0 | 234.79 | 52921.25 | 3349% | YES | 52921.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22% | -22.18% | -24.45% | -46.45% |  | 38.52 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23598 | MRB Onsite support | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 20.7624 | 41.14% | 0% | 0% | 0 | -10.14% | 133056 | 54742.67 | 78313.33 | 3771.88 | 8736.42 | 14079.58 | 0 | 0 | 0 | 133.88 | 54742.67 | 1451% | YES | 60085.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 17.86% | 18.15% | -9.85% |  | 42.5 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23760 | EXP-033 Systems Engineering Support | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 29.113 | 39.77% | 79.2% | 42.09% | 0 | -0.02% | 142300 | 56598.5 | 85701.5 | 2943.75 | 0 | 0 | 0 | 0 | 44823.5 | 83.5 | 11775 | 400% | YES | 11775 | 25199 | 23824.3333 | 12387.3 | 0 | 12811.2 | 0 | 0 | 29% | 28.98% | 28.98% | -0.02% |  | 78.5 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23349 | Spirit 2023 - Stress Approve Man Serv (SB) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 58.24% | 80.05% | 80.05% | 0 | -0.29% | 97920 | 57024 | 40896 | 0 | 0 | 0 | 0 | 0 | 45648 | 13651.2 | 11376 | 0% | NO | 11376 | 0 | 45648 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23322 | GKN T Tomblin 2023 | Steven Lawton | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2024-04-15 | 0 |  |  | 99.66% | 100% | 100% | 0 | -0.33% | 58952 | 58752 | 200 | 0 | 0 | 0 | 0 | 0 | 58752 | 0 | 0 | 0% | NO | 0 | 0 | 58752 | 0 | 0 | 0 | 0 | 0 | 17% | 16.67% | 16.67% | -0.33% |  | 48 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23106 | ME Support to NPD - Bobby Haggart | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  |  | 95.79% | 97.03% | 97.03% | 0 | 0.3% | 65675 | 62912.11 | 2762.89 | 0 | 0 | 0 | 0 | 0 | 61042.75 | 2243.24 | 1869.36 | 0% | NO | 1869.36 | 0 | 61042.75 | 0 | 0 | 0 | 0 | 0 | 15% | 15.3% | 0% | -15% |  | 35.65 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P22967 | Spirit 2022 - Channapa Laxmeshwar | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2023-01-26 | 2 |  |  | 69.69% | 121.3% | 121.3% | 0 | 9.53% | 75159.1 | 52376.15 | 22782.95 | 0 | 52376.15 | 54898.1 | 0 | 0 | 63508.8 | 0.42 | 0.35 | 0% | NO | 2522.3 | 0 | 63508.8 | 0 | 0 | 0 | 0 | 0 | 8% | 17.53% | 0% | -8% |  | 0 | [5 empty] | 11133
1739 | 2024-05-22 23:35 | P23193 | Spirit Shorts Stephen Greer | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -9.2552 | 112.3% | 87.98% | 87.98% | 0 | 8.77% | 61472 | 69005.72 | -7533.72 | 814 | 0 | 0 | 10878 | 7533.72 | 60712.78 | 88.08 | 8292.94 | 1019% | YES | 8292.94 | 0 | 60712.78 | 0 | 0 | 0 | 0 | 0 | 23% | 31.77% | 34.03% | 11.03% |  | 35.18 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23877 | Strategic Enablement | Owain Jones | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -10.1686 |  | 0% | 0% | 0 | -16.99% | 0 | 71017.3 | -71017.3 | 6983.95 | 4000 | 4000 | 67200 | 71017.3 | 0 | 107.46 | 71017.3 | 1017% | YES | 71017.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 1.01% | 1.01% | -16.99% |  | 42 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23341 | Spirit 2023 - Tom McFarlane | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 36.645 | 65.68% | 96.93% | 60.28% | 7110.19 | -0.01% | 108666.4 | 71368.02 | 37298.38 | 1017.83 | 0 | 0 | 0 | 0 | 69177.13 | 186.31 | 2190.89 | 215.3% | YES | 2190.89 | 31389 | 43019.63 | 5886.13 | 16061.8 | 2331.04 | 7110.19 | 7110.19 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23600 | MBDA EXP-EE-023 Bristone Certification | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 59.65% | 100% | 100% | 0 | 0.4% | 126600 | 75517 | 51083 | 0 | 0 | 0 | 0 | 0 | 75517 | 0 | 0 | 0% | NO | 0 | 0 | 75517 | 0 | 0 | 0 | 0 | 0 | 41% | 41.4% | 0% | -41% |  | 78.5 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23080 | Spirit Shorts DManagement Cairan Cullen | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 881.98 | 51.11% | 97.05% | 94.54% | 2298.36 | -1.3% | 149600 | 76457.4 | 73142.6 | 82.93 | 0 | 0 | 0 | 0 | 74199.7 | 142.53 | 2257.7 | 2722% | YES | 2257.7 | 2298 | 72284.7 | 0 | 0 | 2298.36 | 0 | 2298.36 | 24% | 22.7% | 13.03% | -10.97% |  | 44.38 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P22505 | Spirit MRB Engineering Support 2021 | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 1 |  |  | 91.17% | 100% | 95.78% | 4020.48 | 21.2% | 87110.4 | 79414.95 | 7695.45 | 0 | 0 | 0 | 0 | 0 | 79414.95 | 4020.48 | 0 | 0% | NO | 0 | 4020 | 76064.95 | 0 | 0 | 0 | 4020.48 | 4020.48 | 0% | 21.2% | 0% | 0% |  | 41.88 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P22885 | ME Support (Baxi) | Trevor Knox | 0 | HUV | BAXI HEATING UK LIMITED | ME | Level 3 | FIX | 2023-01-12 | 0 |  |  | 68.78% | 108.7% | 108.7% | 0 | 13.05% | 106632.96 | 73340.24 | 33292.72 | 0 | 0 | 0 | 0 | 0 | 79748.12 | 1531.35 | 1276.12 | 0% | NO | 1276.12 | 0 | 79748.12 | 0 | 0 | 0 | 0 | 0 | 15% | 28.05% | 0% | -15% |  | 44.37 | [5 empty] | 7684
1739 | 2024-05-22 23:35 | P22965 | Spirit 2022 - Design Man Serv (AH) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 106.7% | 96.66% | 96.66% | 0 | 3.14% | 80079.56 | 85441.32 | -5361.76 | 0 | 0 | 0 | 0 | 5361.76 | 82588.96 | 3422.84 | 2852.36 | 0% | NO | 2852.36 | 0 | 82588.96 | 0 | 0 | 0 | 0 | 0 | 14% | 17.14% | 0% | -14% |  | 42.44 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23523 | Applique Armour Support | Dushan Fernando | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-18 | 1 |  |  | 72.43% | 138.1% | 98.47% | 40680 | 3.42% | 118200 | 85606.5 | 32593.5 | 0 | 0 | 0 | 0 | 0 | 118200 | 1567.8 | -32593.5 | 0% | NO | -32593.5 | 40680 | 84300 | 0 | 0 | 40680 | 0 | 40680 | 25% | 28.42% | 0% | -25% |  | 64.29 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P22964 | Spirit 2022 - MRB Man Serv (JC) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 100.6% | 97.95% | 97.95% | 0 | 1.91% | 85435.2 | 85960.26 | -525.06 | 0 | 0 | 0 | 0 | 525.06 | 84199.74 | 2112.62 | 1760.52 | 0% | NO | 1760.52 | 0 | 84199.74 | 0 | 0 | 0 | 0 | 0 | 16% | 17.91% | 0% | -16% |  | 42.69 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P22963 | Spirit 2022 - Design Man Serv (PC) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 108.6% | 104% | 104% | 0 | 3.18% | 80079.56 | 86926.74 | -6847.18 | 0 | 0 | 0 | 0 | 6847.18 | 90389.95 | 0 | -3463.21 | 0% | NO | -3463.21 | 0 | 90389.95 | 0 | 0 | 0 | 0 | 0 | 13% | 16.18% | 0% | -13% |  | 42.39 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23342 | Spirit 2023 - Channapa Laxmeshwar | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 53.17% | 119.3% | 77.24% | 0 | -3.73% | 158696.7 | 84385.85 | 74310.85 | 0 | 84385.85 | 108671.94 | 0 | 0 | 100667.7 | 91.65 | -13431.85 | 0% | NO | 10854.24 | 42588 | 65177.7 | 10092 | 32496.24 | 0 | 0 | 0 | 7% | 3.27% | 0% | -7% |  | 0 | [5 empty] | 2850
1739 | 2024-05-22 23:35 | P23700 | IPDT Leads | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 13.0747 | 53.66% | 27.45% | 27.45% | 0 | -1.7% | 169263.9 | 90823.04 | 78440.86 | 5999.42 | 0 | 0 | 0 | 0 | 24932.12 | 103.2 | 65890.92 | 1098% | YES | 65890.92 | 0 | 24932.12 | 0 | 0 | 0 | 0 | 0 | 26% | 24.3% | 22.96% | -3.04% |  | 49.95 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23079 | Spirit Shorts Nomenclature | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -5.3638 | 105.1% | 84.13% | 78.79% | 0 | 15.16% | 88455 | 92931.6 | -4476.6 | 834.6 | 0 | 0 | 5136 | 4476.6 | 78185.2 | 214.9 | 14746.4 | 1767% | YES | 14746.4 | 5956 | 73221.8667 | 0 | 0 | 5955.6 | 0 | 0 | 7% | 22.16% | 25.23% | 18.23% |  | 30.83 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23438 | A220 Spirit Shorts DTC - Stephen Corry | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 0.56515 | 98.21% | 68.42% | 68.42% | 0 | -7.1% | 95928.4 | 94212.6 | 1715.8 | 3036 | 0 | 0 | 0 | 0 | 64459.8 | 139.53 | 29752.8 | 980% | YES | 29752.8 | 0 | 64459.8 | 0 | 0 | 0 | 0 | 0 | 23% | 15.9% | 17.03% | -5.97% |  | 49.91 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23375 | GKN Jaap Peters NL 2023 | Steven Lawton | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2024-03-01 | 1 |  |  | 93.37% | 105.3% | 97.18% | 0 | -15.93% | 97123.22 | 90686.41 | 6436.81 | 0 | 90686.41 | 90686.41 | 0 | 0 | 95456.72 | 7688.92 | -920.31 | 0% | NO | -920.31 | 8793 | 88129.22 | 0 | 0 | 0 | 8793.29 | 0 | 20% | 4.07% | 0% | -20% |  | 0 | [5 empty] | 3850
1739 | 2024-05-22 23:35 | P23340 | Spirit 2023 - John Cole | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 37.3514 | 63.38% | 96.91% | 66.05% | 0 | -0.01% | 150129.72 | 95153.76 | 54975.96 | 1471.86 | 0 | 0 | 0 | 0 | 92210.04 | 157.89 | 2943.72 | 200% | YES | 2943.72 | 35229 | 62852.54 | 8831.16 | 21576.67 | 4821.34 | 0 | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 39.78 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23171 | Spirt Shorts Weights Eng | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 69.18% | 141.4% | 122.7% | 0 | 13.12% | 103113.14 | 71329.32 | 31783.82 | 0 | 71329.32 | 85975.13 | 0 | 0 | 100870.18 | 9273.32 | -5610.86 | 0% | NO | 9034.95 | 16006 | 87531.8467 | 6733.3 | 9273.05 | 0 | 0 | 0 | 12% | 25.12% | 47.26% | 35.26% |  | 0 | [5 empty] | 23930
1739 | 2024-05-22 23:35 | P23336 | Spirit 2023 - Neil Rampling | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 26.495 | 73.41% | 97.04% | 48.69% | 21586.03 | -0.01% | 133901.52 | 98297.34 | 35604.18 | 1343.81 | 0 | 0 | 0 | 0 | 95387.98 | 243.15 | 2909.36 | 216.5% | YES | 2909.36 | 57031 | 47862.1467 | 8238.46 | 22565.28 | 4640.79 | 21586.03 | 21586.03 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23583 | Castalla - Test Rig Design | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 100% | 92.54% | 60.93% | 0 | -26.99% | 100520 | 100538.5 | -18.5 | -786.5 | 0 | 0 | 0 | 18.5 | 93036.5 | 214.92 | 7502 | -953.8% | NO | 7502 | 38135 | 61257.3333 | 30665.28 | 0 | 7469.4 | 0 | 0 | 41% | 14.01% | 14.71% | -26.29% |  | 42.79 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23744 | Model Factory | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 27.8673 | 36.98% | 92.19% | 46.09% | 0 | 10.07% | 262300 | 97008.75 | 165291.25 | 5931.38 | 0 | 0 | 0 | 0 | 89432 | 81.51 | 12576.75 | 212% | YES | 12576.75 | 53659 | 44716.1667 | 27429.6 | 26229.6 | 0 | 0 | 0 | 28% | 38.07% | 38.07% | 10.07% |  | 50.99 | [5 empty] | 5000
1739 | 2024-05-22 23:35 | P23551 | Ian Berry 2023 H2 | Natalie Sinclair | 0 | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  | -15.6849 | 135.2% | 65.57% | 65.57% | 0 | 13.61% | 75810 | 102515.63 | -26705.63 | 1702.63 | 0 | 0 | 24259.2 | 26705.63 | 67217.49 | 122.42 | 35298.14 | 2073% | YES | 35298.14 | 0 | 67217.49 | 0 | 0 | 0 | 0 | 0 | 22% | 35.61% | 37.71% | 15.71% |  | 77.78 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23345 | Spirit 2023- Jonathan Escosio | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 22.1875 | 68.36% | 92.44% | 56.32% | 7150.18 | -0.52% | 151941.24 | 103869.15 | 48072.09 | 2166.63 | 0 | 0 | 0 | 0 | 96014.16 | 202.95 | 7854.99 | 362.5% | YES | 7854.99 | 45020 | 58497.4933 | 16773.9 | 16361 | 4734.58 | 7150.18 | 7150.18 | 7% | 6.48% | 17.74% | 10.74% |  | 43.01 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23465 | A220 ToW Design Offload (Wing) | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 40.671 | 41.96% | 88.68% | 64.66% | 0 | -5.91% | 249700 | 104785.1 | 144914.9 | 3563.1 | 0 | 0 | 0 | 0 | 92918.8 | 118 | 11866.3 | 333% | YES | 11866.3 | 30200 | 67752.1333 | 14843.04 | 0 | 15356.64 | 0 | 0 | 20% | 14.09% | 11.77% | -8.23% |  | 42.8 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23560 | NJEWCS TAF202302 SM | Natalie Sinclair | 0 | COB | CHELTON LIMITED | EES | Level 2 | FIX |  |  |  | 12.9936 | 55.42% | 75.39% | 75.39% | 0 | 9.83% | 191500 | 106120.04 | 85379.96 | 6570.9 | 0 | 0 | 0 | 0 | 80000 | 76.15 | 26120.04 | 397.5% | YES | 26120.04 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 30% | 39.83% | 39.49% | 9.49% |  | 73.01 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23729 | Honda Tooling | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | FIX |  |  |  | 0.71802 | 94.92% | 69.65% | 30.09% | 0 | 2.77% | 113610 | 107835 | 5775 | 8043 | 0 | 0 | 0 | 0 | 75106.5 | 87.06 | 32728.5 | 406.9% | YES | 32728.5 | 51194 | 32444.8333 | 51193.8 | 0 | 0 | 0 | 0 | 10% | 12.77% | 12.77% | 2.77% |  | 42 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23586 | Project Management Support | Dushan Fernando | 0 | BDX | MBDA UK LIMITED | MPE | Level NC | REIM |  |  |  | 17.2114 | 68.72% | 89.3% | 61.03% | 0 | -26.62% | 160000 | 109951.86 | 50048.14 | 2907.85 | 1668.6 | 1668.6 | 0 | 0 | 98183.86 | 114.79 | 11768 | 404.7% | YES | 11768 | 37296 | 67103.86 | 37296 | 0 | 0 | 0 | 0 | 49% | 22.38% | 21.44% | -27.56% |  | 80 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P22736 | WoT Fixed Leading Edge - Industrial | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 106.7% | 93.42% | 91.32% | 3019.54 | 0.01% | 112196.27 | 119668.47 | -7472.2 | 0 | 0 | 0 | 0 | 7472.2 | 111796.68 | 12465.69 | 7871.79 | 0% | NO | 7871.79 | 3020 | 109280.0133 | 0 | 0 | 0 | 3019.54 | 3019.54 | 7% | 7.01% | 0% | -7% |  | 32.26 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P22918 | Spirit Shorts Graduates | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 10.424 | 92.29% | 88.96% | 88.96% | 0 | 9.51% | 130000 | 119982.64 | 10017.36 | 960.99 | 0 | 0 | 19800 | 0 | 106734.95 | 87.91 | 13247.69 | 1379% | YES | 13247.69 | 0 | 106734.95 | 0 | 0 | 0 | 0 | 0 | 7% | 16.51% | 17.21% | 10.21% |  | 23.33 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23353 | Spirit 2023 - MRB Man Serv (JC) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  | 46.6167 | 65.72% | 56.86% | 56.86% | 0 | 9.46% | 183600 | 120667.5 | 62932.5 | 1350 | 0 | 0 | 0 | 0 | 68615.25 | 239.23 | 52052.25 | 3856% | YES | 52052.25 | 0 | 68615.25 | 0 | 0 | 0 | 0 | 0 | 7% | 16.46% | 12.73% | 5.73% |  | 45 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23545 | Ultra CSS continuation 2023 H2 | Natalie Sinclair | 0 | ULT | ULTRA SONAR SYSTEMS LIMITED | EES | Level NC | REIM |  |  |  | -15.5098 | 164.2% | 76.55% | 60.45% | 0 | 2.18% | 76000 | 124821.6 | -48821.6 | 3147.8 | 0 | 0 | 49859.2 | 48821.6 | 95544.8 | 151.77 | 29276.8 | 930.1% | YES | 29276.8 | 24112 | 75451.4667 | 24112.32 | 0 | 0 | 0 | 0 | 23% | 25.18% | 25% | 2% |  | 80 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P22861 | WoT FLE Lifting & Handling Tools | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2023-06-14 | 1 |  |  | 65.17% | 101.6% | 101.6% | 0 | 12.01% | 173987.21 | 113381.75 | 60605.46 | 0 | 50078 | 58423.58 | 0 | 0 | 115203.5 | 12813.9 | 10678.25 | 0% | NO | 19023.83 | 0 | 115203.5 | 0 | 0 | 0 | 0 | 0 | 1% | 13.01% | 0% | -1% |  | 45 | [5 empty] | 12500
1739 | 2024-05-22 23:35 | P23664 | Tempest Composites WP3 | Phillip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -2.9105 | 105.9% | 66.38% | 12.73% | 0 | -5.14% | 122455.49 | 129719.98 | -7264.49 | 2495.93 | 0 | 0 | 14830.4 | 7264.49 | 86110.38 | 369.46 | 43609.6 | 1747% | YES | 43609.6 | 83510 | 16518.7133 | 0 | 83510.02 | 0 | 0 | 0 | 37% | 31.86% | 33.17% | -3.83% |  | 60.89 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23588 | BAE Typhoon MRB MC Shop Concessions | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 12.1221 | 76.12% | 84.14% | 60.26% | 38190.65 | -4.15% | 175060.5 | 133254.29 | 41806.21 | 3448.77 | 0 | 0 | 0 | 0 | 112121.71 | 155.59 | 21132.58 | 612.8% | YES | 21132.58 | 38191 | 80295.8767 | 0 | 10272.55 | 13518.34 | 14399.76 | 38190.65 | 31% | 26.85% | 27.51% | -3.49% |  | 55.81 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23810 | Strategic Enablement | Owain Jones | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -20.63% | 0 | 133694.4 | -133694.4 | 0 | 0 | 0 | 134000 | 133694.4 | 0 | 455.1 | 133694.4 | 0% | NO | 133694.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | -2.63% | -2.63% | -20.63% |  | 42 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23282 | Tooling Support (MBDA) | Dushan Fernando | 0 | BDV | MBDA UK LIMITED | ME | Level NC | REIM |  |  |  | 33.4521 | 68.75% | 94.55% | 77.16% | 0 | -7.65% | 195672.4 | 134523.55 | 61148.85 | 1827.95 | 0 | 0 | 0 | 0 | 127186.8 | 123.03 | 7336.75 | 401.4% | YES | 7336.75 | 28059 | 103804.3 | 7411.63 | 0 | 20647.76 | 0 | 0 | 30% | 22.35% | 30.37% | 0.37% |  | 49.73 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P22883 | Spirit Shorts Evtol PMO C. Hatton | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 17.1694 | 72.45% | 80.93% | 80.93% | 0 | -10.87% | 185800 | 134618.15 | 51181.85 | 2981 | 0 | 0 | 0 | 0 | 108946.73 | 149.77 | 25671.42 | 861.2% | YES | 25671.42 | 0 | 108946.73 | 0 | 0 | 0 | 0 | 0 | 26% | 15.13% | 22.96% | -3.04% |  | 37.41 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23270 | Shorts Project X | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 3.6059 | 95.5% | 90.25% | 74.49% | 0 | 0.35% | 142248 | 135847.04 | 6400.96 | 1775.13 | 0 | 0 | 0 | 0 | 122595.46 | 142.34 | 13251.58 | 746.5% | YES | 13251.58 | 25685 | 101191.2933 | 7981.34 | 10030.61 | 7672.8 | 0 | 0 | 13% | 13.35% | 10.99% | -2.01% |  | 45.3 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23753 | Tempest Composites Maturation | Phillip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | -2.3224 | 109.3% | 76.01% | 22.24% | 0 | -6.58% | 127848.45 | 139777.94 | -11929.49 | 5136.61 | 0 | 0 | 49419.2 | 11929.49 | 106238.78 | 86.52 | 33539.16 | 652.9% | YES | 33539.16 | 90185 | 31084.6133 | 90184.78 | 0 | 0 | 0 | 0 | 29% | 22.42% | 22.42% | -6.58% |  | 64.56 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23533 | External Stowage Design and Detail Support | Dushan Fernando | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 1 |  |  | 102.4% | 97.65% | 73.24% | 42000 | 3.33% | 140000 | 143368.75 | -3368.75 | 0 | 0 | 0 | 3369 | 3368.75 | 140000 | 41999.7 | -0.25 | 0% | NO | -0.25 | 42000 | 105000 | 0 | 0 | 42000 | 0 | 42000 | 27% | 30.33% | 0% | -27% |  | 60.04 | [5 empty] | -3369
1739 | 2024-05-22 23:35 | P23352 | Spirit 2023 - Stress Approve Man Serv (CC) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  | 10.3692 | 72.81% | 49.03% | 49.03% | 0 | 4.91% | 195840 | 142584 | 53256 | 5136 | 0 | 0 | 0 | 0 | 69912 | 186.69 | 72672 | 1415% | YES | 72672 | 0 | 69912 | 0 | 0 | 0 | 0 | 0 | 7% | 11.91% | 4.69% | -2.31% |  | 48 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P22954 | Technical Support Step 1 | Owain Jones | 0 | HUV | HUARUI SPIRIT AEROSPACE MANUFACT | ME | Level 2 | REIM |  |  |  |  | 94.81% | 58.01% | 58.01% | 0 | 0.31% | 155501.18 | 147431.58 | 8069.6 | 0 | 23043 | 23043 | 0 | 0 | 85525.49 | 61906.09 | 61906.09 | 0% | NO | 61906.09 | 0 | 85525.49 | 0 | 0 | 0 | 0 | 0 | 30% | 30.31% | 0% | -30% |  | 60.79 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23386 | Software Development - BMS | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 98.78% | 100% | 100% | 0 | 4.31% | 149650 | 147823.35 | 1826.65 | 0 | 0 | 0 | 0 | 0 | 147823.35 | 0 | 0 | 0% | NO | 0 | 0 | 147823.35 | 0 | 0 | 0 | 0 | 0 | 18% | 22.31% | 22.61% | 4.61% |  | 78.5 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23437 | Embedded Software Engineer | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 98.73% | 100% | 96.08% | 0 | -6.29% | 150150 | 148239.36 | 1910.64 | 0 | 737.86 | 737.86 | 0 | 0 | 148239.36 | 60.67 | 0 | 0% | NO | 0 | 6971 | 142430.1933 | 0 | 0 | 6970.8 | 0 | 0 | 22% | 15.71% | 16.24% | -5.76% |  | 78.5 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23550 | Tempest Composites | Phillip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  |  | 102.5% | 97.57% | 97.57% | 0 | 5.11% | 149494.92 | 153217.46 | -3722.54 | 0 | 0 | 0 | 4209.4 | 3722.54 | 149494.92 | 97.83 | 3722.54 | 0% | NO | 3722.54 | 0 | 149494.92 | 0 | 0 | 0 | 0 | 0 | 26% | 31.11% | 33.8% | 7.8% |  | 61.6 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P22440 | Spirit Managed Service - F&DT and Static Approval | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 3 |  |  | 88.56% | 92.56% | 92.56% | 0 | 11.51% | 173500 | 153656.25 | 19843.75 | 0 | 52115 | 55720 | 0 | 0 | 142225.12 | 13717.36 | 11431.13 | 0% | NO | 15036.13 | 0 | 142225.12 | 0 | 0 | 0 | 0 | 0 | 0% | 11.51% | 0% | 0% |  | 44.73 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P22982 | Spirit 2022 - Hugh Sloan | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 192.3898 | 63.65% | 98.51% | 80.59% | 8217.17 | -0.73% | 247473 | 157513.46 | 89959.54 | 467.59 | 0 | 0 | 0 | 0 | 155171.78 | 205.77 | 2341.68 | 500.8% | YES | 2341.68 | 33869 | 126947.6133 | 5747.76 | 15604.11 | 4300.18 | 8217.17 | 8217.17 | 7% | 6.27% | 0.59% | -6.41% |  | 35.48 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23822 | FCASW Requirements Management | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 28.5733 | 26.5% | 72.11% | 0% | 0 | -2.33% | 595703 | 157843.88 | 437859.12 | 15324.05 | 0 | 0 | 0 | 0 | 113825 | 102.21 | 44018.88 | 287.3% | YES | 44018.88 | 136590 | 0 | 136590 | 0 | 0 | 0 | 0 | 17% | 14.67% | 14.67% | -2.33% |  | 78.5 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23508 | Verification and Validation | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 80.77% | 100% | 97.06% | 0 | 10.77% | 212950 | 171993.5 | 40956.5 | 0 | 0 | 0 | 0 | 0 | 171993.53 | 65.58 | -0.03 | 0% | NO | -0.03 | 6076 | 166930.1967 | 0 | 0 | 6075.9 | 0 | 0 | 24% | 34.77% | 33.6% | 9.6% |  | 78.5 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23518 | Systems Engineering support to FCAS | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 6.9749 | 90.04% | 91.2% | 81.07% | 0 | -5.95% | 193736.8 | 174436.25 | 19300.55 | 2767.13 | 3927.4 | 3927.4 | 0 | 0 | 159084.68 | 94.97 | 15351.57 | 554.8% | YES | 15351.57 | 21195 | 141422.18 | 11351.1 | 0 | 9843.9 | 0 | 0 | 30% | 24.05% | 3.5% | -26.5% |  | 68.84 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23464 | A220 Project X Design Offload | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 71.2241 | 54.25% | 96.14% | 73.9% | 27862.8 | -9.55% | 332340 | 180301.5 | 152038.5 | 2134.65 | 0 | 0 | 0 | 0 | 173346.5 | 179.63 | 6955 | 325.8% | YES | 6955 | 48124 | 133243.1667 | 1900.32 | 18361.2 | 0 | 27862.8 | 27862.8 | 26% | 16.45% | 14.16% | -11.84% |  | 42.88 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23667 | Safety Systems Engineer | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 54.3547 | 46.29% | 91.46% | 74.39% | 0 | -10.96% | 398000 | 184250 | 213750 | 3932.5 | 0 | 0 | 0 | 0 | 168520 | 83.77 | 15730 | 400% | YES | 15730 | 37752 | 137060 | 18216 | 19536 | 0 | 0 | 0 | 47% | 36.04% | 29.32% | -17.68% |  | 110 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23421 | A220 DTC | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 10.4325 | 85.8% | 70.11% | 64.57% | 0 | -28.21% | 217089.12 | 186263.13 | 30825.99 | 2954.81 | 0 | 0 | 0 | 0 | 130597.8 | 111.78 | 55665.33 | 1884% | YES | 55665.33 | 12403 | 120261.9667 | 12403.44 | 0 | 0 | 0 | 0 | 29% | 0.79% | 5.14% | -23.86% |  | 45.91 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23008 | Spirit Shorts Project Rachel | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 68.49% | 91.32% | 91.32% | 0 | -9.7% | 286960 | 196531.2 | 90428.8 | 0 | 0 | 0 | 0 | 0 | 179472.8 | 20470.08 | 17058.4 | 0% | NO | 17058.4 | 0 | 179472.8 | 0 | 0 | 0 | 0 | 0 | 15% | 5.3% | 0.31% | -14.69% |  | 46.04 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23019 | EXP034-B Actuator Development | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 103.1% | 89.91% | 89.91% | 0 | -16.68% | 215541.2 | 222215.54 | -6674.34 | 0 | 12297.9 | 12297.9 | 0 | 6674.34 | 199796.76 | 477.34 | 397.78 | 0% | NO | 397.78 | 0 | 199796.76 | 0 | 0 | 0 | 0 | 0 | 34% | 17.32% | 79.64% | 45.64% |  | 58.45 | [5 empty] | -22021
1739 | 2024-05-22 23:35 | P23754 | Tempest Composites WP4 | Phillip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 6.2718 | 66.31% | 0% | 0% | 0 | -2.65% | 310945.68 | 206183.68 | 104762 | 16703.56 | 1784.87 | 1784.87 | 0 | 0 | 0 | 117.31 | 206183.68 | 1234% | YES | 206183.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36% | 33.35% | 33.35% | -2.65% |  | 60.28 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23242 | Physical Architecture & System Engineering Support | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 29.9514 | 72.58% | 94.61% | 84.53% | 0 | 6.8% | 305459 | 221698.21 | 83760.79 | 2796.56 | 775.55 | 775.55 | 0 | 0 | 209745.3 | 84.77 | 11598.91 | 414.8% | YES | 11598.91 | 26800 | 187411.9667 | 12669.9 | 0 | 14130 | 0 | 0 | 15% | 21.8% | 7.3% | -7.7% |  | 78.22 | [5 empty] | -354
1739 | 2024-05-22 23:35 | P23506 | ASTER Mid-Life Refurbishment Project Manager | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 27.2085 | 68% | 93.08% | 78.61% | 0 | 0.99% | 326900 | 222290.37 | 104609.63 | 3844.74 | 3830.37 | 3830.37 | 0 | 0 | 206911.41 | 83.74 | 15378.96 | 400% | YES | 15378.96 | 38610 | 174736.41 | 24552 | 14058 | 0 | 0 | 0 | 25% | 25.99% | 26.1% | 1.1% |  | 110 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23505 | EXP-022 Meteor TBUS T&E support | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 5.8454 | 90.42% | 92.75% | 80.47% | 0 | -1.45% | 246744.4 | 223115.26 | 23629.14 | 4042.35 | 0 | 0 | 0 | 0 | 206945.88 | 83.27 | 16169.38 | 400% | YES | 16169.38 | 32878 | 179547.5467 | 13636.2 | 0 | 19241.59 | 0 | 0 | 20% | 18.55% | 15.67% | -4.33% |  | 89.83 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23373 | Raytheon Michael Bellini | Natalie Sinclair | 0 | RAS | RAYTHEON UNITED KINGDOM LIMITED | EES | Level NC | REIM |  |  |  | -4.1336 | 105.7% | 92.95% | 75.56% | 24734.7 | -7.7% | 214367.4 | 226485.26 | -12117.86 | 2931.52 | 0 | 0 | 13558.28 | 12117.86 | 210519.78 | 118.13 | 15965.48 | 544.6% | YES | 15965.48 | 47271 | 171127.28 | 22536.06 | 0 | 24734.7 | 0 | 24734.7 | 45% | 37.3% | 38.71% | -6.29% |  | 91.61 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23741 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  | 29.8682 | 35.06% | 88.27% | 39.51% | 0 | 2.68% | 640812 | 224659.2 | 416152.8 | 13932.95 | 0 | 0 | 0 | 0 | 198299 | 79.92 | 32360.2 | 232.3% | YES | 32360.2 | 131435 | 88769.8333 | 68808 | 62626.8 | 0 | 0 | 0 | 28% | 30.68% | 30.68% | 2.68% |  | 38.81 | [5 empty] | 6000
1739 | 2024-05-22 23:35 | P23524 | Bombardier Regional Jets (BRJ) | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -27.8829 | 158% | 47.08% | 45.75% | 3694.07 | -3.72% | 146287.84 | 231167.56 | -84879.72 | 3044.15 | 0 | 0 | 113075 | 84879.72 | 108838.22 | 310.69 | 122329.34 | 4019% | YES | 122329.34 | 3694 | 105759.8867 | 0 | 0 | 0 | 3694.07 | 3694.07 | 18% | 14.28% | 17.48% | -0.52% |  | 43.73 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23739 | Lifing Services DACs | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  | 29.5361 | 35.59% | 94.52% | 47.26% | 0 | 6.36% | 656508 | 233645.9 | 422862.1 | 14316.81 | 0 | 0 | 0 | 0 | 220836 | 81.47 | 24809.9 | 173.3% | YES | 24809.9 | 132502 | 110417.6667 | 66850.8 | 65650.8 | 0 | 0 | 0 | 28% | 34.36% | 34.36% | 6.36% |  | 37.74 | [5 empty] | 12000
1739 | 2024-05-22 23:35 | P23648 | EXP-032 Delivery of Datalink Eng support - FCAS AP | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 11.0747 | 66.93% | 65.76% | 54.73% | 0 | 7.34% | 371000 | 248320.45 | 122679.55 | 11077.5 | 1032.95 | 1032.95 | 0 | 0 | 163302.95 | 84.98 | 85017.5 | 767.5% | YES | 85017.5 | 32868 | 135912.95 | 13332 | 19536 | 0 | 0 | 0 | 22% | 29.34% | 30% | 8% |  | 102.1 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23472 | Tempest Wing Design | Phillip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 105.4456 | 52.67% | 127.4% | 108.9% | 0 | -11.69% | 483869.78 | 254854.61 | 229015.17 | 2171.88 | 238975 | 356900 | 0 | 0 | 324639.1 | 5.81 | -44784.5 | -2062% | NO | 73140.5 | 56574 | 277494.1 | 23857.58 | 32716.75 | 0 | 0 | 0 | 23% | 11.31% | 28.89% | 5.89% |  | 46.74 | [5 empty] | 25000
1739 | 2024-05-22 23:35 | P23007 | EXP-006A - Brimstone 3 | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 79.2613 | 69.77% | 97.81% | 91.61% | 0 | -2.49% | 406450 | 283564.91 | 122885.09 | 1550.38 | 0 | 0 | 0 | 0 | 277363.38 | 80.29 | 6171.53 | 398.1% | YES | 6171.53 | 21124 | 259760.0467 | 9631.96 | 11492.4 | 0 | 0 | 0 | 25% | 22.51% | 29.94% | 4.94% |  | 70.12 | [5 empty] | -30
1739 | 2024-05-22 23:35 | P23603 | Typhoon IMDLR | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | -0.17626 | 100.4% | 39.12% | 39.12% | 0 | 3.49% | 305067.09 | 306272.29 | -1205.2 | 6837.77 | 1500 | 1500 | 0 | 1205.2 | 119807.84 | 359.65 | 186464.45 | 2727% | YES | 186464.45 | 0 | 119807.84 | 0 | 0 | 0 | 0 | 0 | 26% | 29.49% | 27.28% | 1.28% |  | 56.89 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23308 | NATO JEWCS | Natalie Sinclair | 0 | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  | 18.744 | 86.32% | 93.24% | 88.95% | 0 | -4.06% | 356307 | 307549.63 | 48757.37 | 2601.23 | 613.89 | 613.89 | 0 | 0 | 286767.43 | 129.05 | 20782.2 | 798.9% | YES | 20782.2 | 15829 | 273576.5967 | 15829.13 | 0 | 0 | 0 | 0 | 24% | 19.94% | 11.87% | -12.13% |  | 75.81 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23629 | F35 FTI | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level NC | REIM |  |  |  | -18.2449 |  | 77.31% | 77.31% | 0 | -1.53% | 0 | 319114.3 | -319114.3 | 17490.61 | 0 | 0 | 0 | 319114.3 | 246695.06 | 44.42 | 72419.24 | 414% | YES | 72419.24 | 0 | 246695.06 | 0 | 0 | 0 | 0 | 0 | 31% | 29.47% | 28.48% | -2.52% |  | 61.41 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P22953 | Spirit Shorts eVTOL | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-05-08 | 1 |  |  | 103.1% | 80.83% | 80.83% | 0 | -9.51% | 324272 | 334483.6 | -10211.6 | 0 | 66696.6 | 67387.9 | 0 | 10211.6 | 270366 | 64941.12 | 54117.6 | 0% | NO | 54808.9 | 0 | 270366 | 0 | 0 | 0 | 0 | 0 | 17% | 7.49% | 100% | 83% |  | 46.19 | [5 empty] | -10000
1739 | 2024-05-22 23:35 | P21463 | Safety & Monitoring Systems at DM Beith & Gosport | Harry James Kellett | 0 | BXW | MOD | EES | Level 2 | FIX |  |  |  | 3.8561 | 88.13% | 113.5% | 113.5% | 0 | -23.46% | 378612.83 | 333658.28 | 44954.55 | 11658.12 | 75403.45 | 79611.43 | 45616.14 | 0 | 378594.83 | 0 | -44936.55 | -385.5% | NO | -40728.57 | 0 | 378594.83 | 0 | 0 | 0 | 0 | 0 | 48% | 24.54% | 39.6% | -8.4% |  | 56.29 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P22515 | Shorts A220 100/300 ALI Phase III | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 43.2917 | 83.94% | 97.62% | 93.02% | 0 | 0.58% | 400628.76 | 336276.11 | 64352.65 | 1486.49 | 3450.98 | 3450.98 | 0 | 0 | 328273.11 | 98.34 | 8003 | 538.4% | YES | 8003 | 18583 | 312787.2767 | 0 | 18582.69 | 0 | 0 | 0 | 10% | 10.58% | 6.74% | -3.26% |  | 40.56 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P22842 | ME Support (Aim Altitude) | Trevor Knox | 0 | AVI | AIM ALTITUDE UK LIMITED | ME | Level 3 | FIX | 2023-06-14 | 4 |  |  | 99.31% | 100.5% | 86.63% | 57290.84 | 0.49% | 346293.67 | 343918.08 | 2375.59 | 0 | 2909.86 | 2909.86 | 0 | 0 | 345673.01 | 55184.93 | -1754.93 | 0% | NO | -1754.93 | 57291 | 297930.51 | 0 | 0 | 0 | 57290.84 | 57290.84 | 13% | 13.49% | 0% | -13% |  | 46.3 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23743 | EHM Cloud Migration | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 32.6115 | 31% | 108.7% | 54.21% | 0 | 8.61% | 1016000 | 314988.13 | 701011.87 | 21495.85 | 0 | 0 | 0 | 0 | 342376 | 66.44 | 7612.13 | 35.41% | NO | 7612.13 | 205949 | 170751.8333 | 103612.8 | 102336 | 0 | 0 | 0 | 28% | 36.61% | 36.61% | 8.61% |  | 55.38 | [5 empty] | 35000
1739 | 2024-05-22 23:35 | P23816 | Typhoon FTI Works - 2024 Fixed Price Element | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 5.2585 | 85.36% | 53.19% | 4.831e-05% | 0 | -1.59% | 404176.65 | 344987.09 | 59189.56 | 11256.06 | 0 | 0 | 0 | 0 | 183496 | 110.37 | 171491.09 | 1524% | YES | 171491.09 | 220195 | 0.16667 | 220195.2 | 0 | 0 | 0 | 0 | 30% | 28.41% | 28.41% | -1.59% |  | 51.73 | [5 empty] | 10000
1739 | 2024-05-22 23:35 | P22391 | GE System Engineering support | Vinayakumar Sugur | 0 | GEE | EXPERIS LIMITED | EES | Level NC | REIM | 2024-04-08 | 0 |  |  | 82.01% | 100.7% | 100.7% | 0 | 0.13% | 434434.25 | 356260.63 | 78173.62 | 0 | 0 | 0 | 0 | 0 | 358805.6 | 0 | -2544.97 | 0% | NO | -2544.97 | 0 | 358805.6 | 0 | 0 | 0 | 0 | 0 | 6% | 6.13% | 6.09% | 0.09% |  | 57.33 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23617 | Tempest Composites WP2 | Phillip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -28.2023 | 148.5% | 27.87% | 15.93% | 29536.68 | 11.64% | 244405.26 | 362998.01 | -118592.75 | 4205.08 | 0 | 0 | 120669.84 | 118592.75 | 101150.9 | 409.47 | 261847.11 | 6227% | YES | 261847.11 | 51981 | 57833.4 | 0 | 22444.14 | 0 | 29536.68 | 29536.68 | 22% | 33.64% | 33.33% | 11.33% |  | 62.15 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23677 | ME Managed Service - Phase 1 | Paul Watson | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  | 7.0583 | 66.68% | 64.57% | 0% | 0 | -14.18% | 554400 | 369663.85 | 184736.15 | 26172.81 | 0 | 38000 | 0 | 0 | 238680 | 126.09 | 130983.85 | 500.5% | YES | 168983.85 | 286416 | 0 | 71536.5 | 214879.5 | 0 | 0 | 0 | 33% | 18.82% | 20.78% | -12.22% |  | 44.15 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23432 | Spirit Belfast MRB On-Site Support (Mon & Clear) | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 65.77% | 128.6% | 128.6% | 0 | -11.53% | 449545 | 295665.27 | 153879.73 | 0 | 295665.27 | 451827.33 | 0 | 0 | 380234.75 | 32916.62 | 27430.52 | 0% | NO | 183592.58 | 0 | 380234.75 | 0 | 0 | 0 | 0 | 0 | 39% | 27.47% | 0% | -39% |  | 0 | [5 empty] | 112000
1739 | 2024-05-22 23:35 | P23045 | Shotgun Adaptors - 10 Sets | Harry James Kellett | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | FIX | 2024-02-27 | 4 |  | 14.3628 | 78.74% | 127% | 127% | 0 | 2.55% | 399276.11 | 314390.3 | 84885.81 | 5910.11 | 214550.47 | 214550.47 | 0 | 0 | 399276.11 | 349.55 | 15877.19 | 268.6% | YES | 15877.19 | 0 | 399276.11 | 0 | 0 | 0 | 0 | 0 | 31% | 33.55% | 93.96% | 62.96% |  | 58.52 | [5 empty] | 100763
1739 | 2024-05-22 23:35 | P23023 | Spirit Shorts R Foster/M Gourley | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 75.9136 | 71.28% | 103.8% | 91.09% | 19120.72 | -1.1% | 590659.44 | 420994.14 | 169665.3 | 2234.98 | 237621.5 | 267726 | 0 | 0 | 437064.88 | 130.65 | 6295.26 | 281.7% | YES | 36399.76 | 64309 | 383474.0467 | 20217.14 | 24971.11 | 19120.72 | 0 | 19120.72 | 9% | 7.9% | 11.33% | 2.33% |  | 29.69 | [5 empty] | 22366
1739 | 2024-05-22 23:35 | P22906 | Spirit Shorts - MRB JD Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 7.234 | 96.98% | 82.77% | 65.03% | 99451.32 | -7.89% | 481714 | 467159.18 | 14554.82 | 2012 | 0 | 0 | 0 | 0 | 386687.62 | 405.46 | 88471.56 | 4397% | YES | 88471.56 | 99451 | 303811.7867 | 0 | 0 | 0 | 99451.32 | 99451.32 | 13% | 5.11% | 2.64% | -10.36% |  | 36.96 | [5 empty] | 8000
1739 | 2024-05-22 23:35 | P23699 | A220 Stress Checkers | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -2.2132 | 120% | 0% | 0% | 0 | 7.01% | 408328.79 | 490178.94 | -81850.15 | 36982.58 | 12000 | 12000 | 185592 | 81850.15 | 0 | 157.93 | 490178.94 | 1325% | YES | 490178.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13% | 20.01% | 20.03% | 7.03% |  | 61.88 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P22652 | L3 - Saftey Engineering | Sean Simmons | 0 | LHW | L3HARRIS MAPPS LIMITED | EES | Level NC | FIX |  |  |  |  | 95.63% | 95.66% | 95.66% | 0 | 5.66% | 523390 | 500497.5 | 22892.5 | 0 | 0 | 0 | 0 | 0 | 478783.75 | 26056.5 | 21713.75 | 0% | NO | 21713.75 | 0 | 478783.75 | 0 | 0 | 0 | 0 | 0 | 21% | 26.66% | 25.88% | 4.88% |  | 83.05 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23531 | BAe Systems F35 MRB Support | Richard Brook | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | -69.2156 |  | 94.25% | 94.25% | 0 | 3.58% | 0 | 515038.13 | -515038.13 | 7441.07 | 287.44 | 287.44 | 0 | 515038.13 | 485408.08 | 21.63 | 29630.05 | 398.2% | YES | 29630.05 | 0 | 485408.08 | 0 | 0 | 0 | 0 | 0 | 25% | 28.58% | 31.83% | 6.83% |  | 60.03 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23554 | Dornier Seawings 328 2023 H2 Support | Natalie Sinclair | 0 | DAX | EXPLEO GERMANY GMBH (EC) | MPE | Level 2 | REIM |  |  |  | -1.2504 | 102.7% | 82% | 82% | 0 | 5.43% | 508481.81 | 522269.99 | -13788.18 | 11026.66 | 4046.44 | 4046.44 | 32100 | 13788.18 | 428252.8 | 75.25 | 94017.19 | 852.6% | YES | 94017.19 | 0 | 428252.8 | 0 | 0 | 0 | 0 | 0 | 21% | 26.43% | 22.59% | 1.59% |  | 65.67 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23281 | Systems Portfolio | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM | 2024-02-28 | 0 |  |  | 44.43% | 97.31% | 97.31% | 0 | -17.25% | 1177697.24 | 523236.96 | 654460.28 | 0 | 2133.28 | 2133.28 | 0 | 0 | 509179.87 | 15792.1 | 13160.09 | 0% | NO | 13160.09 | 0 | 509179.87 | 0 | 0 | 0 | 0 | 0 | 25% | 7.75% | 100% | 75% |  | 70.48 | [5 empty] | -897
1739 | 2024-05-22 23:35 | P23520 | FCAS AP Portfolio Systems | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 27.3402 | 67.89% | 93.08% | 75.15% | 0 | -6.58% | 810821 | 550457.05 | 260363.95 | 9523.13 | 423 | 423 | 0 | 0 | 512377.44 | 80.41 | 33796.61 | 354.9% | YES | 33796.61 | 118439 | 413678.2733 | 56206.8 | 0 | 62232.16 | 0 | 0 | 22% | 15.42% | 16.28% | -5.72% |  | 81.07 | [5 empty] | -4283
1739 | 2024-05-22 23:35 | P23001 | Spirit Shorts A220 Design | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -21.4706 | 113.5% | 75.44% | 70.7% | 0 | 11.38% | 486640 | 552344.4 | -65704.4 | 3060.2 | 0 | 0 | 65953.2 | 65704.4 | 416705.3 | 383.17 | 135639.1 | 4432% | YES | 135639.1 | 31432 | 390511.9667 | 21930.72 | 9501.6 | 0 | 0 | 0 | 9% | 20.38% | 11.51% | 2.51% |  | 43.56 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23140 | Spirit Shorts A220 MLG Stress Support | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  | 10.3685 | 74.76% | 98.36% | 60.11% | 48343.2 | -7.28% | 735573.4 | 549934.76 | 185638.64 | 17904.07 | 20870.3 | 87811.88 | 111743 | 0 | 540939.4 | 183.86 | 33995.36 | 189.9% | YES | 100936.94 | 252442 | 330571.0667 | 0 | 204098.4 | 48343.2 | 0 | 48343.2 | 17% | 9.72% | -9.91% | -26.91% |  | 44.82 | [5 empty] | 25000
1739 | 2024-05-22 23:35 | P23219 | Tornado Air 800 Engineering Support | Richard Brook | 0 | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 3 | REIM |  |  |  |  | 98.56% | 95.41% | 95.41% | 0 | -1.52% | 615046 | 606185.54 | 8860.46 | -5312.39 | 459.21 | 459.21 | 0 | 0 | 578373.17 | 18.98 | 2905.37 | -54.69% | NO | 2905.37 | 0 | 578373.17 | 0 | 0 | 0 | 0 | 0 | 31% | 29.48% | 329.3% | 298.3% |  | 81.66 | [5 empty] | -24907
1739 | 2024-05-22 23:35 | P23473 | Tempest Vertical Tail | Phillip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 28.1973 | 69.54% | 100.8% | 83.83% | 0 | -7.04% | 846017.62 | 588292 | 257725.62 | 9140.07 | 106750 | 112425 | 0 | 0 | 592767.31 | 68.66 | 524.69 | 5.741% | NO | 6199.69 | 119501 | 493183.1433 | 45333.23 | 74168.03 | 0 | 0 | 0 | 29% | 21.96% | 24.42% | -4.58% |  | 62.61 | [5 empty] | 5000
1739 | 2024-05-22 23:35 | P23372 | BAE Carbon Tooling Off-load | Gary Kempster | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | 2.2083 | 88.57% | 97.45% | 72.99% | 0 | -3.2% | 674141.57 | 597057.08 | 77084.49 | 34905.94 | 0 | 0 | 0 | 0 | 581806.73 | 152.84 | 15250.35 | 43.69% | NO | 15250.35 | 175225 | 435785.8967 | 175224.95 | 0 | 0 | 0 | 0 | 25% | 21.8% | 18.39% | -6.61% |  | 53.96 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23366 | Business Analyst Support | Peter Williams | 0 | BDZ | MBDA UK LIMITED | DET | Level 3 | REIM |  |  |  | 86.3778 | 25.76% | 187.6% | 168.2% | 0 | 3.12% | 1302200 | 335406.91 | 966793.09 | 11192.61 | 273532.34 | 900687.4 | 0 | 0 | 629120 | 41.14 | -578.09 | -5.165% | NO | 626576.97 | 77952 | 564160 | 77952 | 0 | 0 | 0 | 0 | 43% | 46.12% | 23.99% | -19.01% |  | 46.66 | [5 empty] | 293135
1739 | 2024-05-22 23:35 | P23323 | CNC-CMM Programming Support | Stephen Young | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  | -1.8197 | 102.6% | 90.66% | 80.87% | 40305.01 | -2.13% | 617809.74 | 633651.6 | -15841.86 | 8705.91 | 15941.56 | 17789.56 | 99488.9 | 15841.86 | 574493.52 | 92.35 | 59158.08 | 679.5% | YES | 61006.08 | 74458 | 512445.1867 | 0 | 74458.13 | 0 | 0 | 40305.01 | 32% | 29.87% | 36.6% | 4.6% |  | 57.59 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23605 | Typhoon Work Package 2 Continuation | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM |  |  |  |  | 119% | 83.94% | 81.57% | 0 | 5.11% | 545536.01 | 649260.18 | -103724.17 | -1246.63 | 5554 | 5554 | 81999.09 | 103724.17 | 544986.65 | 1675.54 | 104273.53 | -8364% | NO | 104273.53 | 18432 | 529626.65 | 0 | 18432.36 | 0 | 0 | 0 | 23% | 28.11% | 28.63% | 5.63% |  | 55.8 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23694 | Systems Portfolio EXP-011a | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | -0.39233 | 101.7% | 82.85% | 55.01% | 0 | 1.88% | 648492.8 | 659457.28 | -10964.48 | 27947.22 | 444.4 | 444.4 | 0 | 10964.48 | 546332.19 | 85.52 | 113125.09 | 404.8% | YES | 113125.09 | 220264 | 362778.8567 | 142737.46 | 77526.61 | 0 | 0 | 0 | 21% | 22.88% | 20.43% | -0.57% |  | 88.53 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P22790 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | REIM | 2024-04-28 | 0 |  | -134.62 | 197.4% | 89.11% | 89.11% | 0 | 1.11% | 352240 | 695460.45 | -343220.45 | 2549.55 | 1611.52 | 1611.52 | 44500 | 343220.45 | 619743.88 | 396.6 | 44446.57 | 1743% | YES | 44446.57 | 0 | 619743.88 | 0 | 0 | 0 | 0 | 0 | 13% | 14.11% | -2.72% | -15.72% |  | 45.08 | [5 empty] | -31270
1739 | 2024-05-22 23:35 | P23685 | DAC LUC Support and Recompliance | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 26.5503 | 29.24% | 151.8% | 77.1% | 0 | 8.91% | 2180000 | 637404.82 | 1542595.18 | 58100.81 | 0 | 0 | 0 | 0 | 967868 | 48.15 | -216699.18 | -373% | NO | -216699.18 | 571728 | 491428 | 297441.6 | 274286.4 | 0 | 0 | 0 | 30% | 38.91% | 38.91% | 8.91% |  | 57.53 | [5 empty] | 113764
1739 | 2024-05-22 23:35 | P23426 | BAE Tempest WP 3 Harness Maturation | Phillip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 2.9018 | 92.96% | 91% | 72.01% | 0 | -6.23% | 884012.04 | 821764.66 | 62247.38 | 21451.49 | 213.34 | 213.34 | 0 | 0 | 747777.74 | 85.89 | 73986.92 | 344.9% | YES | 73986.92 | 187209 | 591770.24 | 79451.21 | 107757.52 | 0 | 0 | 0 | 33% | 26.77% | 26.97% | -6.03% |  | 52.18 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23105 | Raytheon Supply Engineering Support | Natalie Sinclair | 0 | RAY | RAYTHEON UNITED KINGDOM LIMITED | MPE | Level 3A | REIM | 2023-07-13 | 2 |  |  | 76.96% | 94.49% | 90.07% | 49156.8 | -2.02% | 1205008 | 927395.25 | 277612.75 | 0 | 0 | 0 | 0 | 0 | 876291.5 | 107644.5 | 48739.75 | 0% | NO | 48739.75 | 49157 | 835327.3333 | 0 | 0 | 0 | 49156.8 | 49156.8 | 26% | 23.98% | 100% | 74% |  | 48.97 | [5 empty] | -2364
1739 | 2024-05-22 23:35 | P23451 | BAE Tempest - DFM-ASO Planning | Stephen Young | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | 11.3116 | 82.03% | 70.29% | 63% | 39715.08 | -3.09% | 1145785.42 | 939844.44 | 205940.98 | 18206.1 | 0 | 0 | 0 | 0 | 660614.46 | 127.58 | 278146.98 | 1528% | YES | 278146.98 | 82200 | 592114.46 | 42485.15 | 57003.88 | -44513.7 | 27224.9 | 39715.08 | 28% | 24.91% | 26.35% | -1.65% |  | 53.83 | [5 empty] | -1083
1739 | 2024-05-22 23:35 | P23602 | EXP-025 Portfolio Software Engineering Support | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 11.4525 | 71.58% | 85.72% | 60.61% | 0 | -1.15% | 1327080 | 949892.03 | 377187.97 | 32934.95 | 4034.26 | 4034.26 | 0 | 0 | 814204.07 | 84.05 | 135687.96 | 412% | YES | 135687.96 | 286222 | 575685.7367 | 143172.62 | 143049.25 | 0 | 0 | 0 | 24% | 22.85% | 22.51% | -1.49% |  | 83.43 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23117 | BAE Typhoon Eng Support | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | 2024-03-12 | 9 |  |  | 105.2% | 95.01% | 95.01% | 0 | -1.06% | 950771.99 | 1000558.49 | -49786.5 | -5566.92 | 19090.01 | 21165.02 | 69773.84 | 49786.5 | 950609.41 | 27423.69 | 22853.08 | -410.5% | NO | 24928.09 | 0 | 950609.41 | 0 | 0 | 0 | 0 | 0 | 30% | 28.94% | 12.07% | -17.93% |  | 52.3 | [5 empty] | -27096
1739 | 2024-05-22 23:35 | P22350 | EMP 2020-2021 | Natalie Sinclair | 0 | ARY | GUIDANT GLOBAL UK LIMITED | PCPR | Level NC | REIM |  |  |  | 0.77924 | 99.68% | 99.04% | 94.71% | 0 | -2.11% | 1017579.76 | 1014306.6 | 3273.16 | 4200.43 | 400 | 400 | 0 | 0 | 1004590.04 | 70.64 | 9716.56 | 231.3% | YES | 9716.56 | 52707 | 960667.54 | 27845.4 | 24861.97 | 0 | 0 | 0 | 32% | 29.89% | 27.79% | -4.21% |  | 44.15 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P22671 | Spirit Shorts Pylon and Fairing Package | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX | 2023-05-03 | 0 |  |  | 105% | 95.26% | 95.26% | 0 | -7.21% | 1198494.77 | 1258071.09 | -59576.32 | 0 | 106494.89 | 106494.89 | 0 | 59576.32 | 1198494.77 | 2544.39 | 2120.32 | 0% | NO | 2120.32 | 0 | 1198494.77 | 0 | 0 | 0 | 0 | 0 | 20% | 12.79% | 0% | -20% |  | 45.4 | [5 empty] | -57456
1739 | 2024-05-22 23:35 | P23152 | Project Aragon - Design and Stress Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | -2.1053 | 101.9% | 74.9% | 53.67% | 0 | -9.55% | 1333452.21 | 1358835.71 | -25383.5 | 12057.01 | 0 | 0 | 0 | 25383.5 | 1017835.58 | 375.01 | 341000.13 | 2828% | YES | 341000.13 | 346248 | 729295.58 | 0 | 346247.55 | 0 | 0 | 0 | 39% | 29.45% | 29.27% | -9.73% |  | 51.99 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23292 | BAE Tempest WP 4 AV Trays | Phillip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 5.3425 | 92.65% | 94.94% | 74.25% | 155584.85 | 1.4% | 1498284.22 | 1388196.45 | 110087.77 | 20606.1 | 0 | 0 | 0 | 0 | 1317945.86 | 114.69 | 70250.59 | 340.9% | YES | 70250.59 | 344674 | 1030717.5267 | -17826.65 | 245826.2 | 116674.18 | 0 | 155584.85 | 32% | 33.4% | 31.79% | -0.21% |  | 53.89 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23519 | Mechanical and Electrical Design Eng Support | Dushan Fernando | 0 | BAX | SAFRAN SEATS GB LIMITED | MPE | Level 2 | REIM |  |  |  | 10.4412 | 83.08% | 92.79% | 74.15% | 0 | -1.56% | 1807261.3 | 1501394.35 | 305866.95 | 29294.36 | 1004.45 | 1504.45 | 0 | 0 | 1393199.8 | 88.12 | 108194.55 | 369.3% | YES | 108694.55 | 335892 | 1113289.8 | 141083.4 | 194808.9 | 0 | 0 | 0 | 33% | 31.44% | 31.47% | -1.53% |  | 56.65 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23411 | Agile & Scrum Delivery Service | Peter Williams | 0 | BDZ | MBDA UK LIMITED | DET | Level 2 | REIM | 2023-08-14 | 0 |  |  | 36.3% | 170.5% | 170.5% | 0 | 13.08% | 2487000 | 902903.79 | 1584096.21 | 0 | 894178.59 | 894178.59 | 0 | 0 | 1539600 | 19368.95 | 16140.79 | 0% | NO | 16140.79 | 0 | 1539600 | 0 | 0 | 0 | 0 | 0 | 29% | 42.08% | 0% | -29% |  | 74.57 | [5 empty] | 652837
1739 | 2024-05-22 23:35 | P22278 | TAI Supply Engineers to Ankara | Natalie Sinclair | 0 | TAI | TUSAS-TURK HAVACILIK VE UZAY | MPE | Level 3A | REIM |  |  |  | 1601.5621 | 19.84% | 457.5% | 457.5% | 0 | -15.81% | 2105282 | 417635.91 | 1687646.09 | 1053.75 | 49400.29 | 49400.29 | 0 | 0 | 1910696.33 | 122.46 | 17339.58 | 1646% | YES | 17339.58 | 0 | 1910696.33 | 0 | 0 | 0 | 0 | 0 | 95% | 79.19% | 66.05% | -28.95% |  | 34.11 | [5 empty] | 1510400
1739 | 2024-05-22 23:35 | P23175 | BAe Aero Typhoon Package 2 | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM | 2024-03-12 | 2 |  |  | 103.8% | 96.32% | 96.32% | 0 | -1.63% | 1984265.09 | 2060011.83 | -75746.74 | 0 | 57677.87 | 86030.82 | 15444.64 | 75746.74 | 1984257.03 | 84731.75 | 70609.8 | 0% | NO | 98962.75 | 0 | 1984257.03 | 0 | 0 | 0 | 0 | 0 | 29% | 27.37% | 0% | -29% |  | 51.76 | [5 empty] | -5145
1739 | 2024-05-22 23:35 | P23006 | Spirit Shorts A350 Freighter Toulouse | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 45.9561 | 88.07% | 105.4% | 74.47% | 0 | 22.36% | 1925837.92 | 1696071.44 | 229766.48 | 4999.7 | 1086670.26 | 2010741.94 | 0 | 0 | 1787659.45 | 392.85 | 285685.99 | 5714% | YES | 1209757.67 | 629606 | 1262987.7833 | 110245.82 | 140525.66 | 378834.22 | 0 | 0 | 5% | 27.36% | 47.53% | 42.53% |  | 48.25 | [5 empty] | 377274
1739 | 2024-05-22 23:35 | P19020 | Spirit Concessions - 2018 | Carl Warren | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2024-01-23 | 1 |  |  | 86.3% | 111.8% | 111.2% | 12156.8 | 2.09% | 2015043.23 | 1739018.14 | 276025.09 | 0 | 44317.61 | 44317.61 | 0 | 0 | 1944710.76 | 248541.66 | 196987.38 | 0% | NO | 196987.38 | 12157 | 1934579.9267 | 0 | 0 | 0 | 12156.8 | 12156.8 | 25% | 27.09% | 9.32% | -15.68% |  | 40.87 | [5 empty] | 402680
1739 | 2024-05-22 23:35 | P23257 | BAE Tempest WP 5 Centre Fuselage | Phillip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 1.465 | 98.94% | 98.66% | 92.87% | 0 | -5.71% | 2265401.51 | 2241368.27 | 24033.24 | 16404.88 | 78100 | 78100 | 0 | 0 | 2211380.12 | 66.38 | 29988.15 | 182.8% | YES | 29988.15 | 155821 | 2081529.2867 | 67820.9 | 87999.86 | 0 | 0 | 0 | 33% | 27.29% | 28.15% | -4.85% |  | 61.05 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23435 | Andy Baker Portfolio | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 35.6355 | 56.26% | 89.77% | 65.69% | 0 | -7.29% | 4023207.4 | 2263533.02 | 1759674.38 | 49379.81 | 2596.25 | 2596.25 | 0 | 0 | 2031957.41 | 110.52 | 231575.61 | 469% | YES | 231575.61 | 654019 | 1486941.5767 | 164414.78 | 0 | 489604.46 | 0 | 0 | 25% | 17.71% | 19.18% | -5.82% |  | 81 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23179 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX |  |  |  | -4.6193 | 101% | 93.93% | 88.64% | 0 | -9.23% | 2542643.04 | 2568168.38 | -25525.34 | 5525.85 | 156991.12 | 248243.92 | 0 | 25525.34 | 2412235.69 | 647.3 | 155932.69 | 2822% | YES | 247185.49 | 162889 | 2276494.8567 | 0 | 0 | 162889.25 | 0 | 0 | 22% | 12.77% | 18.03% | -3.97% |  | 44.4 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P19731 | Hapri HPC Rear Bearing Housing PDR & CDR | Steven Lawton | 0 | ATC | AECC Hunan Aviation Powerplant | MPE | Level 1 | FIX | 2024-05-13 | 4 |  | -21.3706 | 100.3% | 99.67% | 87.21% | 447000 | -15.41% | 2980000 | 2989767.41 | -9767.41 | 457.05 | 366282.13 | 500382.13 | 0 | 9767.41 | 2980000 | 1164.26 | -215232.59 | -47092% | NO | -81132.59 | 447000 | 2607500 | 0 | 0 | 0 | 447000 | 447000 | 38% | 22.59% | 15.47% | -22.53% |  | 64.85 | [5 empty] | -225000
1739 | 2024-05-22 23:35 | P23207 | A350 Approvers - Design and Stress Support | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  | 4.8063 | 90.56% | 93.42% | 70.99% | 100132.13 | -4.3% | 3135290 | 2839197.65 | 296092.35 | 61605.31 | 38692.54 | 38754.28 | 0 | 0 | 2652260.57 | 98.29 | 186937.08 | 303.4% | YES | 186998.82 | 764210 | 2015418.9033 | 232534.01 | 342017.26 | 189658.31 | 0 | 100132.13 | 22% | 17.7% | 16.74% | -5.26% |  | 54.54 | [5 empty] | 0
1739 | 2024-05-22 23:35 | P23487 | Tornado Air 800 Engineering Support | Richard Brook | 0 | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 2 | FIX |  |  |  | 11.5589 | 79.25% | 87.35% | 75.85% | 47390.58 | -2.83% | 4286367.76 | 3396759.86 | 889607.9 | 76963.03 | 500 | 500 | 0 | 0 | 2967206.61 | 102.53 | 501553.25 | 651.7% | YES | 501553.25 | 468813 | 2576529.11 | 421421.93 | 0 | 8658.1 | 38732.48 | 47390.58 | 40% | 37.17% | 40.75% | 0.75% |  | 78.99 | [5 empty] | 72000
Extend Table

## AP5-4
WIP No | Date Created | Project ID | Project Description | Project Manager | Agency (1=yes, 0=no) | Department Id | Client | CBU | Complexity | Type | Stop Booking Hrs | Closing Project: Action(s) to close | RAG | Approx. PO Burndown (weeks) | Turnover vs Contract Value | Invoice To Date vs Turnover | Cash in vs Turnover | Open Amount Overdue | Actual PM% to Baseline PM% delta | Contract Value | Total Project Turnover | Contract Value - Total Turnover | Run Rate (based on total turnover) | Total BOI Spend to Date | Total Committed PO (supplier/best shore) | Current AA in PT3 | Exposure (turnover - contract value) | Invoiced To Date | DSO | Unbilled (WIP) | WIP / Run rate | WIP / Run rate >1.3 | WIP + Remaining Committed PO for BOI | Total Open Amount | Cash in (Invoiced - (Open amount -VAT)) | Debt - <=30 Days since invoice | Debt - 31 - 60 Days since invoice | Debt - 61 - 90 Days since invoice | Debt - >= 90 Days since invoice | Open Amount Overdue2 | Baseline Project Margin | Project To Date (PTD) PM | Year to Date (YTD) PM | YTD Delta Actual PM% to BPM% | Forecast PM at Completion (Manual input from PTT) | Average Sale Rate | CSat score for last quarter (Manual input from PTT) | Comments and Actions | Judged income adjustment at completion | Profit to take now | Provision required now | Fully Traded | Last Months Comments and Actions
1740 | 2024-05-29 23:36 | P23650 | MBDA Recruitment Management costs | Andrew Slaney | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM | 2024-02-01 | 1 |  |  |  | 0% | 0% | 0 | 33042515% | 0 | 240971.5 | -240971.5 | -35243 | 0 | 0 | 266000 | 240971.5 | 0 | 0 | -0.5 | 0.001419% | NO | -0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | 33042518% | 165.6% | 162.6% |  | 82.3 | [5 empty] | -240972
1740 | 2024-05-29 23:36 | P23552 | FCAS AP Product Technology Development | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -25% | 597871 | 0 | 597871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0% | -25% |  | 0 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23543 | EXP-024 FCAS AP Transformation & Change Enablers | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -26% | 385921 | 0 | 385921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26% | 0% | 0% | -26% |  | 0 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23784 | Tempest Tooling Offload 2024 | Gary Kempster | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM | 2024-05-09 | 48 | [5 empty] | 0 | -25% | 0 | 0 | 0 | -29244.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0% | -25% |  | 0 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23711 | DO NOT USE - RAISED IN ERROR | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23628 | Design Assurance | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | -7% | 0 | 0 | 0 | -977.31 | 0 | 0 | 4454.8 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 0% | 0.33% | -6.67% |  | 0 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23909 | A220-300 Wing L5v01M09 Loads Increase | Siyun Fan | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 9920 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23730 | FLE Project | Siyun Fan | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -18.03% | 0 | 1120 | -1120 | 0 | 0 | 0 | 24000 | 1120 | 0 | 1344 | 1120 | 0% | NO | 1120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | -18.03% | -18.03% | -18.03% |  | 35 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23892 | Warrior Environmental Control Unit | Trevin Fernandopulle | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM |  |  |  | 6.3704 | 38.57% | 0% | 0% | 0 | 3.58% | 3920 | 1512 | 2408 | 378 | 0 | 0 | 0 | 0 | 0 | 21 | 1512 | 400% | YES | 1512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32% | 35.58% | 35.58% | 3.58% |  | 56 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23463 | A220 Wing MaMo Design Checking | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-03-07 | 0 |  |  |  | 0% | 0% | 0 | 7.85% | 0 | 1628 | -1628 | 0 | 0 | 0 | 15000 | 1628 | 0 | 1953.6 | 1628 | 0% | NO | 1628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | 10.85% | 0% | -3% |  | 44 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23899 | Turret Test Rig | Trevin Fernandopulle | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM |  |  |  | 32.9998 | 8.333% | 0% | 0% | 0 | 0.52% | 24864 | 2072 | 22792 | 690.67 | 0 | 0 | 0 | 0 | 0 | 7 | 2072 | 300% | YES | 2072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16% | 16.52% | 16.52% | 0.52% |  | 56 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P21028 | Rebate Collection (BACC) | David Catchpole | 0 | TOO | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | [5 empty] | 0% | 0% | 0 | 0% | 0 | 2680 | -2680 | 0 | 2680 | 2680 | 0 | 2680 | 0 | 3216 | 2680 | 0% | NO | 2680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23886 | A220 F&DT Support | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -4 |  | 0% | 0% | 0 | -9.07% | 0 | 3380.2 | -3380.2 | 845.05 | 0 | 0 | 12199.2 | 3380.2 | 0 | 28 | 3380.2 | 400% | YES | 3380.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 8.93% | 8.93% | -9.07% |  | 50.83 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23578 | ESN Work Package | Hannah Mead | 0 | COZ | CHELTON LIMITED | DET | Level 3 | FIX | 2024-01-01 | 0 |  |  | 86.17% | 116.1% | 116.1% | 0 | 35.86% | 4410 | 3800 | 610 | 0 | 0 | 0 | 0 | 0 | 4410 | 0 | -610 | 0% | NO | -610 | 0 | 4410 | 0 | 0 | 0 | 0 | 0 | 24% | 59.86% | 0% | -24% |  | 95 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23880 | Warrior Crew Heater Design | Trevin Fernandopulle | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM |  |  |  | 0.93506 | 90.91% | 0% | 0% | 0 | 3.58% | 5544 | 5040 | 504 | 539 | 0 | 0 | 0 | 0 | 0 | 42 | 5040 | 935.1% | YES | 5040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32% | 35.58% | 35.58% | 3.58% |  | 56 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23002 | WoT MAJ Transit Flag Stress | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2024-04-03 | 1 |  |  | 62.41% | 160.2% | 160.2% | 0 | 38.54% | 4735 | 2955.29 | 1779.71 | 0 | 1492.79 | 2242.5 | 0 | 0 | 4735 | 91.03 | 1493.29 | 0% | NO | 2243 | 0 | 4735 | 0 | 0 | 0 | 0 | 0 | 10% | 48.54% | 0% | -10% |  | 45 | [5 empty] | 3273
1740 | 2024-05-29 23:36 | P23881 | Bulldog Fuel System Design | Trevin Fernandopulle | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM |  |  |  | 0.74866 | 88.18% | 0% | 0% | 0 | 1.29% | 8288 | 7308 | 980 | 1309 | 0 | 0 | 0 | 0 | 0 | 35 | 7308 | 558.3% | YES | 7308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13% | 14.29% | 14.29% | 1.29% |  | 56 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23898 | EXP-041 ISV Engineering Support | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 134.9184 | 2.175% | 100% | 0.001913% | 0 | -13.04% | 400584 | 8713.5 | 391870.5 | 2904.5 | 0 | 0 | 0 | 0 | 8713.5 | 20 | 0 | 0% | NO | 0 | 10456 | 0.16667 | 10456.2 | 0 | 0 | 0 | 0 | 21% | 7.96% | 7.96% | -13.04% |  | 78.5 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23607 | SAFRAN - A330neo Turnover Frame | Gary Kempster | 0 | TOO | SAFRAN SEATS GB LIMITED | MPE | Level 3 | FIX |  |  |  |  | 95.69% | 104.5% | 104.5% | 0 | -19.52% | 8736 | 8359.05 | 376.95 | 0 | 0 | 0 | 0 | 0 | 8736 | 0.06 | 0.05 | 0% | NO | 0.05 | 0 | 8736 | 0 | 0 | 0 | 0 | 0 | 23% | 3.48% | 8.5% | -14.5% |  | 50.46 | [5 empty] | 377
1740 | 2024-05-29 23:36 | P23864 | REACH Coordinator | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 43.7612 | 16.89% | 0% | 0% | 0 | -10.24% | 52920 | 8940 | 43980 | 1005 | 0 | 0 | 0 | 0 | 0 | 70 | 8940 | 889.6% | YES | 8940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27% | 16.76% | 16.76% | -10.24% |  | 30 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23274 | ME Support (Aim Altitude - Cambridge) | Trevor Knox | 0 | AVI | AVIC CABIN SYSTEMS (UK) LIMITED | ME | Level 3 | FIX | 2023-08-18 | 0 |  |  | 51.88% | 56.3% | 56.3% | 0 | -0.17% | 17280 | 8964 | 8316 | 0 | 0 | 0 | 0 | 0 | 5046.3 | 4701.24 | 3917.7 | 0% | NO | 3917.7 | 0 | 5046.3 | 0 | 0 | 0 | 0 | 0 | 21% | 20.83% | 0% | -21% |  | 48 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23894 | EE Test and Integration Lead | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | -4 |  | 0% | 0% | 0 | 9.56% | 0 | 9260.23 | -9260.23 | 2315.06 | 0 | 0 | 15430 | 9260.23 | 0 | 28 | 9260.23 | 400% | YES | 9260.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23% | 32.56% | 32.56% | 9.56% |  | 63.88 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23283 | Spirit Tooling Audit | Charidimos Valadakis | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-05-03 | 0 |  |  | 97.22% | 48.57% | 48.57% | 0 | -7.99% | 9910.08 | 9634.8 | 275.28 | 0 | 0 | 0 | 0 | 0 | 4679.76 | 5946.05 | 4955.04 | 0% | NO | 4955.04 | 0 | 4679.76 | 0 | 0 | 0 | 0 | 0 | 7% | -0.99% | 0% | -7% |  | 34.41 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23127 | Loft Hall Design Support | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-04-19 | 0 |  |  | 101% | 99.06% | 99.06% | 0 | -9.55% | 9680 | 9772 | -92 | 0 | 0 | 0 | 0 | 92 | 9680 | 110.4 | 92 | 0% | NO | 92 | 0 | 9680 | 0 | 0 | 0 | 0 | 0 | 41% | 31.45% | 0% | -41% |  | 44 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23630 | 2Excel CFD Analysis Support | Dushan Fernando | 0 | BAX | STIRLING DYNAMICS LTD | MPE | Level NC | FIX |  |  |  |  | 61.2% | 100% | 100% | 0 | -1.87% | 16195.49 | 9911.34 | 6284.15 | 0 | 0 | 0 | 0 | 0 | 9911.63 | 0 | -0.29 | 0% | NO | -0.29 | 0 | 9911.63 | 0 | 0 | 0 | 0 | 0 | 26% | 24.13% | 0% | -26% |  | 64.78 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23888 | HondaJet FWD Assy Jig Tool Design | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | FIX |  |  |  | 7.1524 | 35.87% | 0% | 0% | 0 | 4.18% | 31500 | 11298 | 20202 | 2824.5 | 0 | 0 | 0 | 0 | 0 | 42 | 11298 | 400% | YES | 11298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 14.18% | 14.18% | 4.18% |  | 42 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23313 | Laser Trim Fixtures | Gary Kempster | 0 | TOO | ALKEN ENGINEERING LIMITED | MPE | Level 3 | FIX | 2023-11-20 | 0 |  |  | 89.87% | 111.3% | 111.3% | 0 | 0.53% | 13770 | 12375 | 1395 | 0 | 0 | 0 | 0 | 0 | 13770 | 0 | -1395 | 0% | NO | -1395 | 0 | 13770 | 0 | 0 | 0 | 0 | 0 | 17% | 17.53% | 0% | -17% |  | 45 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23718 | Requalification of EJ200 GSS ESS EHM SW module | Vijayakumara Nanjundappa | 0 | ARZ | MTU AERO ENGINES AG | DET | Level 3 | FIX |  |  |  | 137.2796 | 13.35% | 182.3% | 182.3% | 0 | 16.06% | 74463 | 9941.57 | 64521.43 | 470 | 991.93 | 991.93 | 0 | 0 | 18125 | 0 | -5183.43 | -1103% | NO | -5183.43 | 0 | 18125 | 0 | 0 | 0 | 0 | 0 | 28% | 44.06% | 44.06% | 16.06% |  | 80 | [5 empty] | 3000
1740 | 2024-05-29 23:36 | P22761 | Red Bull Chassis Spit | Trevor Knox | 0 | TOO | MANUFAX ENGINEERING LTD | MPE | Level 3 | FIX | 2022-11-15 | 0 |  |  | 72.18% | 96.98% | 96.98% | 0 | 7.92% | 12961.2 | 9355.5 | 3605.7 | 0 | 0 | 0 | 0 | 0 | 9072.84 | 4666.39 | 3888.66 | 0% | NO | 3888.66 | 0 | 9072.84 | 0 | 0 | 0 | 0 | 0 | 23% | 30.92% | 0% | -23% |  | 42.19 | [5 empty] | 3606
1740 | 2024-05-29 23:36 | P23350 | Spirit 2023 - Stress Approve Man Serv (DH) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 14.15% | 72.64% | 72.64% | 0 | -0.29% | 97920 | 13860 | 84060 | 0 | 0 | 0 | 0 | 0 | 10068 | 4550.4 | 3792 | 0% | NO | 3792 | 0 | 10068 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23344 | Spirit A320 Spoilers Support 2023 | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 38.75% | 100% | 100% | 0 | 5.82% | 35786.4 | 13867.23 | 21919.17 | 0 | 0 | 0 | 0 | 0 | 13867.23 | 0 | 0 | 0% | NO | 0 | 0 | 13867.23 | 0 | 0 | 0 | 0 | 0 | 7% | 12.82% | 0% | -7% |  | 34.41 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23337 | Spirit 2023 - Steve Grimley | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 25.28% | 100% | 100% | 0 | 0.01% | 56812.9 | 14362.47 | 42450.43 | 0 | 0 | 0 | 0 | 0 | 14362.47 | 0 | 0 | 0% | NO | 0 | 0 | 14362.47 | 0 | 0 | 0 | 0 | 0 | 7% | 7.01% | 0% | -7% |  | 30.11 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23597 | MRB Onsite support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-02-16 | 1 |  |  |  | 0% | 0% | 0 | -10.04% | 0 | 15100.57 | -15100.57 | 0 | 9448.07 | 17381.62 | 24200 | 15100.57 | 0 | 18120.68 | 15100.57 | 0% | NO | 23034.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 7.96% | 8.95% | -9.05% |  | 42.5 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23869 | EXP-037 Land Ceptor Development Hardware Test Def | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 155.5832 | 9.801% | 0% | 0% | 0 | 0.81% | 162694 | 15944.83 | 146749.17 | 943.22 | 0 | 0 | 0 | 0 | 0 | 63 | 15944.83 | 1690% | YES | 15944.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26% | 26.81% | 26.81% | 0.81% |  | 89.83 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23343 | Spirit 2023 - John Agnew | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-08-09 | 0 |  |  | 24.64% | 100% | 100% | 0 | -0.02% | 65120.37 | 16047.15 | 49073.22 | -638.44 | 0 | 0 | 0 | 0 | 16047.15 | 0 | 0 | 0% | NO | 0 | 0 | 16047.15 | 0 | 0 | 0 | 0 | 0 | 7% | 6.98% | 6.98% | -0.02% |  | 34.51 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23843 | EXP-035 FT15 Exemplar information set | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 45.3222 | 9.461% | 84.46% | -0.0004204% | 0 | -10.77% | 175985.16 | 16649.85 | 159335.31 | 3515.61 | 0 | 0 | 0 | 0 | 14062.43 | 70 | 2587.42 | 73.6% | NO | 2587.42 | 16875 | -0.07 | 16874.92 | 0 | 0 | 0 | 0 | 20% | 9.23% | 9.23% | -10.77% |  | 72.2 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23873 | FCAS Systems Engineering Support | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 51.2319 | 10.69% | 100% | -0.001994% | 0 | -9.72% | 156475 | 16720.5 | 139754.5 | 2727.88 | 0 | 0 | 0 | 0 | 16720.5 | 42 | 0 | 0% | NO | 0 | 20065 | -0.33333 | 20064.6 | 0 | 0 | 0 | 0 | 18% | 8.28% | 8.28% | -9.72% |  | 78.5 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23635 | Engineering Services: FAI Support | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 49.9% | 100% | 0.0008972% | 0 | -3.4% | 37230 | 18576 | 18654 | 0 | 0 | 0 | 0 | 0 | 18576 | 22291.2 | 0 | 0% | NO | 0 | 22291 | 0.16667 | 0 | 7058.88 | 15232.32 | 0 | 0 | 8% | 4.6% | 5.04% | -2.96% |  | 38.7 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23902 | Typhoon Rear Fuselage | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -3 |  | 0% | 0% | 0 | -0.02% | 0 | 18739.09 | -18739.09 | 6246.36 | 0 | 0 | 45382.5 | 18739.09 | 0 | 20 | 18739.09 | 300% | YES | 18739.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 29.98% | 29.98% | -0.02% |  | 55.69 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23355 | Spirit Tooling Support 2023 | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-23 | 0 |  |  | 22.93% | 89.02% | 89.02% | 0 | -0.82% | 91800 | 21053.34 | 70746.66 | 0 | 0 | 0 | 0 | 0 | 18742.5 | 2773.01 | 2310.84 | 0% | NO | 2310.84 | 0 | 18742.5 | 0 | 0 | 0 | 0 | 0 | 20% | 19.18% | 0% | -20% |  | 44.46 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23839 | Stirling Dynamics - ST002-GFEM | Matthew Dodd | 0 | BAX | STIRLING DYNAMICS LTD | MPE | Level 3 | REIM |  |  |  | 10.3445 | 89.35% | 132.1% | 0.001814% | 0 | -3.93% | 24057.34 | 21496.26 | 2561.08 | 247.58 | 2126.93 | 2126.93 | 0 | 0 | 28392.89 | 127.86 | -6896.64 | -2786% | NO | -6896.64 | 34071 | 0.39 | 34071.47 | 0 | 0 | 0 | 0 | 6% | 2.07% | 2.07% | -3.93% |  | 43.77 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23663 | Spirit Tooling Verification and Inspection | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  | 0.52174 | 98.66% | 92.76% | -0.001534% | 0 | -6.39% | 23123.52 | 22813.83 | 309.69 | 593.57 | 0 | 0 | 0 | 0 | 21162.15 | 211.69 | 1651.68 | 278.3% | YES | 1651.68 | 25395 | -0.35 | 4831.16 | 12635.35 | 7928.06 | 0 | 0 | 11% | 4.61% | 4.82% | -6.18% |  | 34.41 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23351 | Spirit 2023 - Design Man Serv (KL) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 26.47% | 93.15% | 93.15% | 0 | 0.09% | 93840 | 24840 | 69000 | 0 | 0 | 0 | 0 | 0 | 23138 | 2042.4 | 1702 | 0% | NO | 1702 | 0 | 23138 | 0 | 0 | 0 | 0 | 0 | 26% | 26.09% | 0% | -26% |  | 46 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23356 | Spirit 2023 - Design Man Serv (AH) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX | 2023-08-09 | 1 |  |  |  | 76.66% | 0.001332% | 23018.4 | 0.48% | 0 | 25023.08 | -25023.08 | 0 | 0 | 0 | 25300 | 25023.08 | 19182 | 30027.7 | 5841.08 | 0% | NO | 5841.08 | 23018 | 0.33333 | 0 | 0 | 0 | 23018.4 | 23018.4 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P22884 | Spirit Shorts Config Eng | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 66.3% | 100.1% | 100.1% | 0 | 0.56% | 38976 | 25841.9 | 13134.1 | 0 | 0 | 0 | 0 | 0 | 25863.2 | 0 | -0.3 | 0% | NO | -0.3 | 0 | 25863.2 | 0 | 0 | 0 | 0 | 0 | 7% | 7.56% | 0% | -7% |  | 20.3 | [5 empty] | 21
1740 | 2024-05-29 23:36 | P23742 | Cyber Security Support | Hannah Mead | 0 | COZ | CHELTON LIMITED | DET | Level 3 | FIX |  |  |  | 1.8667 | 94.91% | 105.4% | 0% | 0 | -0.96% | 27500 | 26100 | 1400 | 750 | 0 | 0 | 0 | 0 | 27500 | 143.95 | -1400 | -186.7% | NO | -1400 | 33000 | 0 | 33000 | 0 | 0 | 0 | 0 | 32% | 31.04% | 31.04% | -0.96% |  | 100 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23354 | Spirit 2023 - Design Man Serv (PC) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 27.97% | 99.36% | 99.36% | 0 | 0.48% | 93840 | 26248.98 | 67591.02 | 0 | 0 | 0 | 0 | 0 | 26082 | 200.38 | 166.98 | 0% | NO | 166.98 | 0 | 26082 | 0 | 0 | 0 | 0 | 0 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P22756 | A350 FLE Design Checker | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2022-03-23 | 1 |  |  | 68.39% | 119.7% | 119.7% | 0 | 16.46% | 34898.4 | 23867.15 | 11031.25 | 0 | 23867.15 | 24342.3 | 0 | 0 | 28571.1 | 0.06 | 0.05 | 0% | NO | 475.2 | 0 | 28571.1 | 0 | 0 | 0 | 0 | 0 | 0% | 16.46% | 0% | 0% |  | 0 | [5 empty] | 4704
1740 | 2024-05-29 23:36 | P23458 | Spirit Belfast Tooling Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-08-11 | 0 |  |  | 101.3% | 94.65% | 94.65% | 0 | 8.64% | 30384 | 30784.9 | -400.9 | 0 | 0 | 0 | 0 | 400.9 | 29139.1 | 1974.96 | 1645.8 | 0% | NO | 1645.8 | 0 | 29139.1 | 0 | 0 | 0 | 0 | 0 | 7% | 15.64% | 0% | -7% |  | 42.2 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23365 | GKN 777x Lip Skin Fixture | Steven Lawton | 0 | TOO | GKN AEROSPACE SERVICES LTD | MPE | Level 3 | FIX | 2023-10-12 | 0 |  |  | 41.91% | 113.2% | 113.2% | 0 | -9.26% | 79161.46 | 33175.67 | 45985.79 | 0 | 5109.88 | 5109.88 | 0 | 0 | 37544.22 | 0 | -4368.55 | 0% | NO | -4368.55 | 0 | 37544.22 | 0 | 0 | 0 | 0 | 0 | 22% | 12.74% | 0% | -22% |  | 56 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23891 | A220 FLE Support | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -4 |  | 0% | 0% | 0 | 6.61% | 0 | 34297.44 | -34297.44 | 8574.36 | 0 | 0 | 46656.96 | 34297.44 | 0 | 59 | 34297.44 | 400% | YES | 34297.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 13.61% | 13.61% | 6.61% |  | 49.92 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P22768 | MRB Onsite Support - Spirit Belfast | Trevor Knox | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2023-07-27 | 0 |  |  |  | 0% | 0% | 0 | -17.07% | 0 | 34614 | -34614 | 0 | 0 | 0 | 36800 | 34614 | 0 | 41536.8 | 34614 | 0% | NO | 34614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | -7.07% | 0% | -10% |  | 36 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23842 | Tranche 1 Evolution Package Step 2 | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 12.4971 | 30.93% | 0% | 0% | 0 | -10.64% | 112526.3 | 34804.58 | 77721.72 | 6219.2 | 1000 | 1000 | 0 | 0 | 0 | 70 | 34804.58 | 559.6% | YES | 34804.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31% | 20.36% | 20.36% | -10.64% |  | 56.45 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23831 | Contract DM/00113 for maintenance, repair and post | Harry James Kellett | 0 | BXW | MOD | EES | Level 2 | FIX |  |  |  | 8.9238 | 75.81% | 16.06% | 16.06% | 0 | 16.55% | 46455.9 | 35215.97 | 11239.93 | 1259.55 | 343 | 343 | 0 | 0 | 5655.9 | 90.88 | 29560.07 | 2347% | YES | 29560.07 | 0 | 5655.9 | 0 | 0 | 0 | 0 | 0 | 34% | 50.55% | 50.55% | 16.55% |  | 80.26 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23821 | Supply of Safety Engineer | Dinna Elkhalifa | 0 | BXW | STIRLING DYNAMICS LTD | EES | Level NC | REIM |  |  |  |  | 106.6% | 49% | 49% | 0 | 45.1% | 34006.44 | 36247.77 | -2241.33 | 0 | 0 | 0 | 0 | 2241.33 | 17760.6 | 91.4 | 18487.17 | 0% | NO | 18487.17 | 0 | 17760.6 | 0 | 0 | 0 | 0 | 0 | 0% | 45.1% | 45.1% | 45.1% |  | 80.73 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23433 | Cavendish | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 3.6782 | 86.09% | 38.11% | 38.11% | 0 | -0.43% | 42240 | 36365.2 | 5874.8 | 1597.2 | 0 | 0 | 0 | 0 | 13859.2 | 91 | 22506 | 1409% | YES | 22506 | 0 | 13859.2 | 0 | 0 | 0 | 0 | 0 | 7% | 6.57% | 6.51% | -0.49% |  | 46.59 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23724 | GKN S McConnell 2024 | Matthew Tweed | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  | 7.2 | 74.8% | 100% | 0.000966% | 0 | 0.93% | 49820 | 37265.39 | 12554.61 | 1743.7 | 0 | 0 | 0 | 0 | 37265.36 | 147.97 | 0.03 | 0.00172% | NO | 0.03 | 44718 | 0.36 | 16739.52 | 10761.12 | 8848.03 | 8369.76 | 0 | 19% | 19.93% | 19.93% | 0.93% |  | 49.62 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23347 | WoT Fixed Leading Edge - Industrial 2023 | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | -10.6486 | 120.5% | 82.92% | 39.34% | 0 | -0.38% | 31034.12 | 37389.34 | -6355.22 | 596.81 | 0 | 0 | 10500 | 6355.22 | 31001.86 | 27214.54 | 6387.48 | 1070% | YES | 6387.48 | 19550 | 14710.1933 | 19549.56 | 0 | 0 | 0 | 0 | 7% | 6.62% | 7.01% | 0.01% |  | 32.26 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23338 | Spirit 2023 - Blair Hainey | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 28.0555 | 60.34% | 95.3% | 47.54% | 0 | -2.96% | 62893.71 | 37950.12 | 24943.59 | 889.08 | 0 | 0 | 0 | 0 | 36165.24 | 249.98 | 1784.88 | 200.8% | YES | 1784.88 | 21747 | 18042.74 | 21747.46 | 0 | 0 | 0 | 0 | 7% | 4.04% | -5.4% | -12.4% |  | 16.58 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23874 | Environmental Engineering (Sea Venom/ANL) | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | -6.5291 |  | 0% | 0% | 0 | -0.97% | 0 | 38504.25 | -38504.25 | 5897.31 | 0 | 0 | 49199 | 38504.25 | 0 | 49 | 38504.25 | 652.9% | YES | 38504.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 19.03% | 19.03% | -0.97% |  | 78.5 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23651 | PMO Spirit | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 8.9886 | 78.41% | 60.69% | -0.0004313% | 28144.8 | -19.38% | 49284 | 38646 | 10638 | 1183.5 | 0 | 0 | 0 | 0 | 23454 | 231.49 | 15192 | 1284% | YES | 15192 | 28145 | -0.16667 | 0 | 0 | 28144.8 | 0 | 28144.8 | 43% | 23.62% | 23.1% | -19.9% |  | 36 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23051 | Spirit Shorts A350 PAX Door | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3A | REIM |  |  |  |  | 205.9% | 105.4% | 105.4% | 0 | -0.63% | 18216 | 37513 | -19297 | 0 | 0 | 0 | 0 | 19297 | 39537 | 0 | 0 | 0% | NO | 0 | 0 | 39537 | 0 | 0 | 0 | 0 | 0 | 30% | 29.37% | 0% | -30% |  | 46 | [5 empty] | 2024
1740 | 2024-05-29 23:36 | P22752 | Tooling WoT - 2021 (Spirit) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | REIM | 2023-05-03 | 0 |  |  | 101.1% | 74.02% | 74.02% | 0 | -8.5% | 41525.1 | 41982.28 | -457.18 | 0 | 0 | 0 | 0 | 457.18 | 31076.1 | 13087.42 | 10906.18 | 0% | NO | 10906.18 | 0 | 31076.1 | 0 | 0 | 0 | 0 | 0 | 0% | -8.5% | 0% | 0% |  | 39.09 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23339 | Spirit 2023 - Stewart Russell | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 64.51% | 100% | 100% | 0 | 0.62% | 72766.8 | 46941.72 | 25825.08 | 0 | 0 | 0 | 0 | 0 | 46941.74 | 0 | -0.02 | 0% | NO | -0.02 | 0 | 46941.74 | 0 | 0 | 0 | 0 | 0 | 7% | 7.62% | 0% | -7% |  | 35.67 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23811 | Spirit T300 MRB Concessions | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -12.617 |  | 0% | 0% | 0 | -7.25% | 0 | 48339.23 | -48339.23 | 3831.27 | 0 | 0 | 50000 | 48339.23 | 0 | 103.76 | 48339.23 | 1262% | YES | 48339.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21% | 13.75% | 13.75% | -7.25% |  | 47.51 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23823 | EXP-034 Spear 3 Test Equip Requirement Authority | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 9.3628 | 59.26% | 98.03% | 7.227% | 17247.76 | 0.04% | 85825 | 50858.25 | 34966.75 | 3734.66 | 1000 | 1000 | 0 | 0 | 49858.26 | 91 | 999.99 | 26.78% | NO | 999.99 | 55419 | 3675.76 | 38171.26 | 17247.76 | 0 | 0 | 17247.76 | 14% | 14.04% | 14.04% | 0.04% |  | 94.25 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P22760 | SA Leading Edge Transport Media ('A' Frames) | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-11-15 | 1 |  |  | 85.99% | 110.7% | 116.3% | -3082.8 | 3.97% | 53480.8 | 45985.5 | 7495.3 | 0 | 42804 | 42804 | 0 | 0 | 50911.8 | 0 | -0.3 | 0% | NO | -0.3 | -3083 | 53480.9667 | 0 | 0 | 0 | -3082.8 | -3082.8 | 6% | 9.97% | 0% | -6% |  | 42 | [5 empty] | 4926
1740 | 2024-05-29 23:36 | P23740 | Phase 2 - EJ200 ESS EHM Platform Migration | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 3 | FIX |  |  |  | 26.0639 | 23.3% | 184% | 61.33% | 0 | 18.19% | 175971 | 40992.5 | 134978.5 | 5178.75 | 0 | 0 | 0 | 0 | 75417 | 71.73 | -22424.5 | -433% | NO | -22424.5 | 60334 | 25138.6667 | 30166.8 | 30166.8 | 0 | 0 | 0 | 28% | 46.19% | 46.19% | 18.19% |  | 42.28 | [5 empty] | 12000
1740 | 2024-05-29 23:36 | P23642 | MRB Belfast Support | Paul Watson | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -95.276 |  | 0% | 0% | 0 | -44.11% | 0 | 53073.47 | -53073.47 | 557.05 | 3718.34 | 3718.34 | 48125 | 53073.47 | 0 | 258.95 | 53073.47 | 9528% | YES | 53073.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22% | -22.11% | -24.34% | -46.34% |  | 38.52 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23349 | Spirit 2023 - Stress Approve Man Serv (SB) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 58.24% | 80.05% | 80.05% | 0 | -0.29% | 97920 | 57024 | 40896 | 0 | 0 | 0 | 0 | 0 | 45648 | 13651.2 | 11376 | 0% | NO | 11376 | 0 | 45648 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23598 | MRB Onsite support | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 25.1767 | 43.51% | 0% | 0% | 0 | -9.95% | 133056 | 57887.67 | 75168.33 | 2985.63 | 8736.42 | 14079.58 | 0 | 0 | 0 | 141.57 | 57887.67 | 1939% | YES | 63230.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 18.05% | 18.33% | -9.67% |  | 42.5 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23760 | EXP-033 Systems Engineering Support | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 28.113 | 41.84% | 100% | 57.94% | 0 | -0.02% | 142300 | 59542.25 | 82757.75 | 2943.75 | 0 | 0 | 0 | 0 | 59542.25 | 63.8 | 0 | 0% | NO | 0 | 30050 | 34500.5833 | 30049.8 | 0 | 0 | 0 | 0 | 29% | 28.98% | 28.98% | -0.02% |  | 78.5 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23106 | ME Support to NPD - Bobby Haggart | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  |  | 95.79% | 97.03% | 97.03% | 0 | 0.3% | 65675 | 62912.11 | 2762.89 | 0 | 0 | 0 | 0 | 0 | 61042.75 | 2243.24 | 1869.36 | 0% | NO | 1869.36 | 0 | 61042.75 | 0 | 0 | 0 | 0 | 0 | 15% | 15.3% | 0% | -15% |  | 35.65 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P22967 | Spirit 2022 - Channapa Laxmeshwar | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2023-01-26 | 2 |  |  | 69.69% | 121.3% | 121.3% | 0 | 9.53% | 75159.1 | 52376.15 | 22782.95 | 0 | 52376.15 | 54898.1 | 0 | 0 | 63508.8 | 0.42 | 0.35 | 0% | NO | 2522.3 | 0 | 63508.8 | 0 | 0 | 0 | 0 | 0 | 8% | 17.53% | 0% | -8% |  | 0 | [5 empty] | 11133
1740 | 2024-05-29 23:36 | P23193 | Spirit Shorts Stephen Greer | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -10.1937 | 113.5% | 87.02% | 87.02% | 0 | 8.8% | 61472 | 69769.7 | -8297.7 | 814 | 0 | 0 | 10878 | 8297.7 | 60712.78 | 96.82 | 9056.92 | 1113% | YES | 9056.92 | 0 | 60712.78 | 0 | 0 | 0 | 0 | 0 | 23% | 31.8% | 34.03% | 11.03% |  | 35.19 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23877 | Strategic Enablement | Owain Jones | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -16.99% | 0 | 71017.3 | -71017.3 | 0 | 4000 | 4000 | 67200 | 71017.3 | 0 | 113.32 | 71017.3 | 0% | NO | 71017.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 1.01% | 1.01% | -16.99% |  | 42 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23341 | Spirit 2023 - Tom McFarlane | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 34.3833 | 66.67% | 95.48% | 59.38% | 7110.19 | -0.01% | 108666.4 | 72450.16 | 36216.24 | 1053.31 | 0 | 0 | 0 | 0 | 69177.13 | 191.95 | 3273.03 | 310.7% | YES | 3273.03 | 31389 | 43019.63 | 5886.13 | 16061.8 | 2331.04 | 7110.19 | 7110.19 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23600 | MBDA EXP-EE-023 Bristone Certification | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 59.65% | 100% | 100% | 0 | 0.4% | 126600 | 75517 | 51083 | 0 | 0 | 0 | 0 | 0 | 75517 | 0 | 0 | 0% | NO | 0 | 0 | 75517 | 0 | 0 | 0 | 0 | 0 | 41% | 41.4% | 0% | -41% |  | 78.5 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23080 | Spirit Shorts DManagement Cairan Cullen | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 828.0449 | 51.14% | 96.99% | 96.99% | 0 | -1.3% | 149600 | 76500.2 | 73099.8 | 88.28 | 0 | 0 | 0 | 0 | 74199.7 | 91 | 2300.5 | 2606% | YES | 2300.5 | 0 | 74199.7 | 0 | 0 | 0 | 0 | 0 | 24% | 22.7% | 13.03% | -10.97% |  | 44.38 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P22505 | Spirit MRB Engineering Support 2021 | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 1 |  |  | 91.17% | 100% | 95.78% | 4020.48 | 21.2% | 87110.4 | 79414.95 | 7695.45 | 0 | 0 | 0 | 0 | 0 | 79414.95 | 4020.48 | 0 | 0% | NO | 0 | 4020 | 76064.95 | 0 | 0 | 0 | 4020.48 | 4020.48 | 0% | 21.2% | 0% | 0% |  | 41.88 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P22885 | ME Support (Baxi) | Trevor Knox | 0 | HUV | BAXI HEATING UK LIMITED | ME | Level 3 | FIX | 2023-01-12 | 0 |  |  | 68.78% | 108.7% | 108.7% | 0 | 13.05% | 106632.96 | 73340.24 | 33292.72 | 0 | 0 | 0 | 0 | 0 | 79748.12 | 1531.35 | 1276.12 | 0% | NO | 1276.12 | 0 | 79748.12 | 0 | 0 | 0 | 0 | 0 | 15% | 28.05% | 0% | -15% |  | 44.37 | [5 empty] | 7684
1740 | 2024-05-29 23:36 | P22965 | Spirit 2022 - Design Man Serv (AH) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 106.7% | 96.66% | 96.66% | 0 | 3.14% | 80079.56 | 85441.32 | -5361.76 | 0 | 0 | 0 | 0 | 5361.76 | 82588.96 | 3422.84 | 2852.36 | 0% | NO | 2852.36 | 0 | 82588.96 | 0 | 0 | 0 | 0 | 0 | 14% | 17.14% | 0% | -14% |  | 42.44 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23523 | Applique Armour Support | Dushan Fernando | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-18 | 1 |  |  | 72.43% | 138.1% | 98.47% | 40680 | 3.42% | 118200 | 85606.5 | 32593.5 | 0 | 0 | 0 | 0 | 0 | 118200 | 1567.8 | -32593.5 | 0% | NO | -32593.5 | 40680 | 84300 | 0 | 0 | 40680 | 0 | 40680 | 25% | 28.42% | 0% | -25% |  | 64.29 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P22964 | Spirit 2022 - MRB Man Serv (JC) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 100.6% | 97.95% | 97.95% | 0 | 1.91% | 85435.2 | 85960.26 | -525.06 | 0 | 0 | 0 | 0 | 525.06 | 84199.74 | 2112.62 | 1760.52 | 0% | NO | 1760.52 | 0 | 84199.74 | 0 | 0 | 0 | 0 | 0 | 16% | 17.91% | 0% | -16% |  | 42.69 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P22963 | Spirit 2022 - Design Man Serv (PC) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 108.6% | 104% | 104% | 0 | 3.18% | 80079.56 | 86926.74 | -6847.18 | 0 | 0 | 0 | 0 | 6847.18 | 90389.95 | 0 | -3463.21 | 0% | NO | -3463.21 | 0 | 90389.95 | 0 | 0 | 0 | 0 | 0 | 13% | 16.18% | 0% | -13% |  | 42.39 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23079 | Spirit Shorts Nomenclature | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -8.3925 | 105.8% | 83.55% | 78.25% | 5955.6 | 15.18% | 88455 | 93573.6 | -5118.6 | 609.9 | 0 | 0 | 5136 | 5118.6 | 78185.2 | 221.9 | 15388.4 | 2523% | YES | 15388.4 | 5956 | 73221.8667 | 0 | 0 | 5955.6 | 0 | 5955.6 | 7% | 22.18% | 25.23% | 18.23% |  | 30.84 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23438 | A220 Spirit Shorts DTC - Stephen Corry | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 1.2736 | 98.21% | 68.42% | 68.42% | 0 | -7.1% | 95928.4 | 94212.6 | 1715.8 | 1347.23 | 0 | 0 | 0 | 0 | 64459.8 | 154.87 | 29752.8 | 2208% | YES | 29752.8 | 0 | 64459.8 | 0 | 0 | 0 | 0 | 0 | 23% | 15.9% | 17.03% | -5.97% |  | 49.91 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23375 | GKN Jaap Peters NL 2023 | Steven Lawton | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2024-03-01 | 1 |  |  | 93.37% | 105.3% | 97.18% | 0 | -15.93% | 97123.22 | 90686.41 | 6436.81 | 0 | 90686.41 | 90686.41 | 0 | 0 | 95456.72 | 7688.92 | -920.31 | 0% | NO | -920.31 | 8793 | 88129.22 | 0 | 0 | 0 | 8793.29 | 0 | 20% | 4.07% | 0% | -20% |  | 0 | [5 empty] | 3850
1740 | 2024-05-29 23:36 | P23171 | Spirt Shorts Weights Eng | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 69.18% | 141.4% | 122.7% | 0 | 13.12% | 103113.14 | 71329.32 | 31783.82 | 0 | 71329.32 | 85975.13 | 0 | 0 | 100870.18 | 9273.32 | -5610.86 | 0% | NO | 9034.95 | 16006 | 87531.8467 | 6733.3 | 9273.05 | 0 | 0 | 0 | 12% | 25.12% | 47.26% | 35.26% |  | 0 | [5 empty] | 23930
1740 | 2024-05-29 23:36 | P23700 | IPDT Leads | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 12.7523 | 57.01% | 25.84% | 25.84% | 0 | -1.7% | 169263.9 | 96502.01 | 72761.89 | 5705.78 | 0 | 0 | 0 | 0 | 24932.12 | 106.71 | 71569.89 | 1254% | YES | 71569.89 | 0 | 24932.12 | 0 | 0 | 0 | 0 | 0 | 26% | 24.3% | 23.06% | -2.94% |  | 49.93 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23340 | Spirit 2023 - John Cole | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 36.3514 | 64.36% | 95.43% | 65.05% | 0 | -0.01% | 150129.72 | 96625.62 | 53504.1 | 1471.86 | 0 | 0 | 0 | 0 | 92210.04 | 162.31 | 4415.58 | 300% | YES | 4415.58 | 35229 | 62852.54 | 8831.16 | 21576.67 | 4821.34 | 0 | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 39.78 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23336 | Spirit 2023 - Neil Rampling | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 24.3396 | 74.36% | 95.8% | 48.07% | 21586.03 | -0.01% | 133901.52 | 99574.62 | 34326.9 | 1410.33 | 0 | 0 | 0 | 0 | 95387.98 | 252.15 | 4186.64 | 296.9% | YES | 4186.64 | 57031 | 47862.1467 | 8238.46 | 22565.28 | 4640.79 | 21586.03 | 21586.03 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23583 | Castalla - Test Rig Design | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -0.028266 | 100% | 92.54% | 60.93% | 7469.4 | -26.99% | 100520 | 100538.5 | -18.5 | 654.5 | 0 | 0 | 0 | 18.5 | 93036.5 | 238.24 | 7502 | 1146% | YES | 7502 | 38135 | 61257.3333 | 30665.28 | 0 | 7469.4 | 0 | 7469.4 | 41% | 14.01% | 14.71% | -26.29% |  | 42.79 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23342 | Spirit 2023 - Channapa Laxmeshwar | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 17.4694 | 61.9% | 102.5% | 66.35% | 0 | -4.18% | 158696.7 | 98230.79 | 60465.91 | 3461.24 | 98230.79 | 108671.94 | 0 | 0 | 100667.7 | 91.4 | 413.09 | 11.93% | NO | 10854.24 | 42588 | 65177.7 | 10092 | 32496.24 | 0 | 0 | 0 | 7% | 2.82% | 0% | -7% |  | 0 | [5 empty] | 2850
1740 | 2024-05-29 23:36 | P23551 | Ian Berry 2023 H2 | Natalie Sinclair | 0 | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  | -91.6743 | 135.2% | 65.57% | 65.57% | 0 | 13.61% | 75810 | 102515.63 | -26705.63 | 291.31 | 0 | 0 | 24259.2 | 26705.63 | 67217.49 | 138.31 | 35298.14 | 12117% | YES | 35298.14 | 0 | 67217.49 | 0 | 0 | 0 | 0 | 0 | 22% | 35.61% | 37.71% | 15.71% |  | 77.78 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23345 | Spirit 2023- Jonathan Escosio | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 21.453 | 69.41% | 91.04% | 55.47% | 7150.18 | -0.54% | 151941.24 | 105460.52 | 46480.72 | 2166.63 | 0 | 0 | 0 | 0 | 96014.16 | 210.07 | 9446.36 | 436% | YES | 9446.36 | 45020 | 58497.4933 | 16773.9 | 16361 | 4734.58 | 7150.18 | 7150.18 | 7% | 6.46% | 17.2% | 10.2% |  | 43.01 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23465 | A220 ToW Design Offload (Wing) | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 51.7199 | 42.6% | 87.36% | 63.7% | 15356.64 | -6.07% | 249700 | 106368.7 | 143331.3 | 2771.3 | 0 | 0 | 0 | 0 | 92918.8 | 130.27 | 13449.9 | 485.3% | YES | 13449.9 | 30200 | 67752.1333 | 14843.04 | 0 | 15356.64 | 0 | 15356.64 | 20% | 13.93% | 11.49% | -8.51% |  | 42.8 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23744 | Model Factory | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 26.6777 | 39.18% | 87.01% | 43.51% | 0 | 9.95% | 262300 | 102780.75 | 159519.25 | 5979.5 | 0 | 0 | 0 | 0 | 89432 | 89.54 | 18348.75 | 306.9% | YES | 18348.75 | 53659 | 44716.1667 | 27429.6 | 26229.6 | 0 | 0 | 0 | 28% | 37.95% | 37.95% | 9.95% |  | 51.05 | [5 empty] | 5000
1740 | 2024-05-29 23:36 | P23560 | NJEWCS TAF202302 SM | Natalie Sinclair | 0 | COB | CHELTON LIMITED | EES | Level 2 | FIX |  |  |  | 11.3905 | 56.84% | 73.49% | 73.49% | 0 | 9.82% | 191500 | 108857.91 | 82642.09 | 7255.37 | 0 | 0 | 0 | 0 | 80000 | 84.14 | 28857.91 | 397.7% | YES | 28857.91 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 30% | 39.82% | 39.49% | 9.49% |  | 73.01 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23729 | Honda Tooling | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | FIX |  |  |  | 0.088254 | 99.37% | 66.53% | 28.74% | 0 | 2.67% | 113610 | 112896 | 714 | 8090.25 | 0 | 0 | 21000 | 0 | 75106.5 | 91.01 | 37789.5 | 467.1% | YES | 37789.5 | 51194 | 32444.8333 | 51193.8 | 0 | 0 | 0 | 0 | 10% | 12.67% | 12.67% | 2.67% |  | 42 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23586 | Project Management Support | Dushan Fernando | 0 | BDX | MBDA UK LIMITED | MPE | Level NC | REIM |  |  |  | 13.3902 | 71.93% | 97.65% | 58.31% | 0 | -27.07% | 160000 | 115088.17 | 44911.83 | 3354.08 | 1972 | 1972 | 0 | 0 | 112383.86 | 118.84 | 2704.31 | 80.63% | NO | 2704.31 | 54336 | 67103.86 | 54336 | 0 | 0 | 0 | 0 | 49% | 21.93% | 20.63% | -28.37% |  | 80 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P22736 | WoT Fixed Leading Edge - Industrial | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 106.7% | 93.42% | 91.32% | 3019.54 | 0.01% | 112196.27 | 119668.47 | -7472.2 | 0 | 0 | 0 | 0 | 7472.2 | 111796.68 | 12465.69 | 7871.79 | 0% | NO | 7871.79 | 3020 | 109280.0133 | 0 | 0 | 0 | 3019.54 | 3019.54 | 7% | 7.01% | 0% | -7% |  | 32.26 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P22918 | Spirit Shorts Graduates | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 11.8041 | 92.92% | 88.36% | 88.36% | 0 | 9.52% | 130000 | 120789.99 | 9210.01 | 780.24 | 0 | 0 | 19800 | 0 | 106734.95 | 99.66 | 14055.04 | 1801% | YES | 14055.04 | 0 | 106734.95 | 0 | 0 | 0 | 0 | 0 | 7% | 16.52% | 17.23% | 10.23% |  | 23.34 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23353 | Spirit 2023 - MRB Man Serv (JC) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  | 27.7595 | 67.47% | 55.39% | 55.39% | 0 | 9.32% | 183600 | 123873.75 | 59726.25 | 2151.56 | 0 | 0 | 0 | 0 | 68615.25 | 237.12 | 55258.5 | 2568% | YES | 55258.5 | 0 | 68615.25 | 0 | 0 | 0 | 0 | 0 | 7% | 16.32% | 12.58% | 5.58% |  | 45 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P22861 | WoT FLE Lifting & Handling Tools | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2023-06-14 | 1 |  |  | 65.17% | 101.6% | 101.6% | 0 | 12.01% | 173987.21 | 113381.75 | 60605.46 | 0 | 50078 | 58423.58 | 0 | 0 | 115203.5 | 12813.9 | 10678.25 | 0% | NO | 19023.83 | 0 | 115203.5 | 0 | 0 | 0 | 0 | 0 | 1% | 13.01% | 0% | -1% |  | 45 | [5 empty] | 12500
1740 | 2024-05-29 23:36 | P23545 | Ultra CSS continuation 2023 H2 | Natalie Sinclair | 0 | ULT | ULTRA SONAR SYSTEMS LIMITED | EES | Level NC | REIM |  |  |  | -13.8807 | 167% | 75.29% | 59.46% | 0 | 2.18% | 76000 | 126897.6 | -50897.6 | 3666.8 | 0 | 0 | 49859.2 | 50897.6 | 95544.8 | 162.13 | 31352.8 | 855% | YES | 31352.8 | 24112 | 75451.4667 | 24112.32 | 0 | 0 | 0 | 0 | 23% | 25.18% | 25% | 2% |  | 80 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23664 | Tempest Composites WP3 | Phillip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -17.7703 | 105.9% | 66.38% | 12.73% | 0 | -5.14% | 122455.49 | 129719.98 | -7264.49 | 408.8 | 0 | 0 | 14830.4 | 7264.49 | 86110.38 | 419.66 | 43609.6 | 10668% | YES | 43609.6 | 83510 | 16518.7133 | 0 | 83510.02 | 0 | 0 | 0 | 37% | 31.86% | 33.17% | -3.83% |  | 60.89 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23810 | Strategic Enablement | Owain Jones | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -20.63% | 0 | 133694.4 | -133694.4 | 0 | 0 | 0 | 134000 | 133694.4 | 0 | 1057.19 | 133694.4 | 0% | NO | 133694.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | -2.63% | -2.63% | -20.63% |  | 42 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P22883 | Spirit Shorts Evtol PMO C. Hatton | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 70.4984 | 72.45% | 89.77% | 80.93% | 0 | -10.87% | 185800 | 134618.15 | 51181.85 | 726 | 0 | 0 | 0 | 0 | 120848.73 | 167.22 | 13769.42 | 1897% | YES | 13769.42 | 14282 | 108947.0633 | 14282.4 | 0 | 0 | 0 | 0 | 26% | 15.13% | 22.96% | -3.04% |  | 37.41 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23588 | BAE Typhoon MRB MC Shop Concessions | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 11.2682 | 77.56% | 82.58% | 73.74% | 14399.76 | -4.1% | 175060.5 | 135773.25 | 39287.25 | 3486.55 | 0 | 0 | 0 | 0 | 112121.71 | 104.9 | 23651.54 | 678.4% | YES | 23651.54 | 14400 | 100121.71 | 0 | 0 | 0 | 14399.76 | 14399.76 | 31% | 26.9% | 27.61% | -3.39% |  | 55.79 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23282 | Tooling Support (MBDA) | Dushan Fernando | 0 | BDV | MBDA UK LIMITED | ME | Level NC | REIM |  |  |  | 32.3941 | 69.74% | 93.21% | 88.68% | 0 | -7.53% | 195672.4 | 136457.56 | 59214.84 | 1827.95 | 0 | 0 | 0 | 0 | 127186.8 | 61.83 | 9270.76 | 507.2% | YES | 9270.76 | 7412 | 121010.1333 | 7411.63 | 0 | 0 | 0 | 0 | 30% | 22.47% | 30.37% | 0.37% |  | 49.73 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23270 | Shorts Project X | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 3.1198 | 96.35% | 89.45% | 73.83% | 7672.8 | 0.33% | 142248 | 137060.42 | 5187.58 | 1662.78 | 0 | 0 | 0 | 0 | 122595.46 | 150.69 | 14464.96 | 869.9% | YES | 14464.96 | 25685 | 101191.2933 | 7981.34 | 10030.61 | 7672.8 | 0 | 7672.8 | 13% | 13.33% | 10.99% | -2.01% |  | 45.3 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23533 | External Stowage Design and Detail Support | Dushan Fernando | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 1 |  |  | 102.4% | 97.65% | 73.24% | 42000 | 3.33% | 140000 | 143368.75 | -3368.75 | 0 | 0 | 0 | 3369 | 3368.75 | 140000 | 41999.7 | -0.25 | 0% | NO | -0.25 | 42000 | 105000 | 0 | 0 | 42000 | 0 | 42000 | 27% | 30.33% | 0% | -27% |  | 60.04 | [5 empty] | -3369
1740 | 2024-05-29 23:36 | P23352 | Spirit 2023 - Stress Approve Man Serv (CC) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  | 7.8497 | 75.04% | 47.57% | 47.57% | 0 | 4.69% | 195840 | 146952 | 48888 | 6228 | 0 | 0 | 0 | 0 | 69912 | 185.11 | 77040 | 1237% | YES | 77040 | 0 | 69912 | 0 | 0 | 0 | 0 | 0 | 7% | 11.69% | 4.69% | -2.31% |  | 48 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P22954 | Technical Support Step 1 | Owain Jones | 0 | HUV | HUARUI SPIRIT AEROSPACE MANUFACT | ME | Level 2 | REIM |  |  |  |  | 94.81% | 58.01% | 58.01% | 0 | 0.31% | 155501.18 | 147431.58 | 8069.6 | 0 | 23043 | 23043 | 0 | 0 | 85525.49 | 61906.09 | 61906.09 | 0% | NO | 61906.09 | 0 | 85525.49 | 0 | 0 | 0 | 0 | 0 | 30% | 30.31% | 0% | -30% |  | 60.79 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23386 | Software Development - BMS | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 98.78% | 100% | 100% | 0 | 4.31% | 149650 | 147823.35 | 1826.65 | 0 | 0 | 0 | 0 | 0 | 147823.35 | 0 | 0 | 0% | NO | 0 | 0 | 147823.35 | 0 | 0 | 0 | 0 | 0 | 18% | 22.31% | 22.61% | 4.61% |  | 78.5 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23437 | Embedded Software Engineer | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 98.73% | 100% | 96.08% | 6970.8 | -6.29% | 150150 | 148239.36 | 1910.64 | 0 | 737.86 | 737.86 | 0 | 0 | 148239.36 | 91 | 0 | 0% | NO | 0 | 6971 | 142430.1933 | 0 | 0 | 6970.8 | 0 | 6970.8 | 22% | 15.71% | 16.24% | -5.76% |  | 78.5 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P22440 | Spirit Managed Service - F&DT and Static Approval | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 3 |  |  | 88.56% | 92.56% | 92.56% | 0 | 11.51% | 173500 | 153656.25 | 19843.75 | 0 | 52115 | 55720 | 0 | 0 | 142225.12 | 13717.36 | 11431.13 | 0% | NO | 15036.13 | 0 | 142225.12 | 0 | 0 | 0 | 0 | 0 | 0% | 11.51% | 0% | 0% |  | 44.73 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23550 | Tempest Composites | Phillip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -18.3705 | 103.2% | 96.92% | 96.92% | 0 | 5.1% | 149494.92 | 154253.62 | -4758.7 | 259.04 | 0 | 0 | 4209.4 | 4758.7 | 149494.92 | 96.26 | 4758.7 | 1837% | YES | 4758.7 | 0 | 149494.92 | 0 | 0 | 0 | 0 | 0 | 26% | 31.1% | 33.66% | 7.66% |  | 61.62 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23753 | Tempest Composites Maturation | Phillip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | -2.5543 | 122.2% | 68.01% | 45.47% | 0 | -5.64% | 127848.45 | 156199.08 | -28350.63 | 11099.37 | 0 | 0 | 49419.2 | 28350.63 | 106238.78 | 61.95 | 49960.3 | 450.1% | YES | 49960.3 | 42256 | 71025.4467 | 42255.9 | 0 | 0 | 0 | 0 | 29% | 23.36% | 23.36% | -5.64% |  | 64.24 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P22982 | Spirit 2022 - Hugh Sloan | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 183.2374 | 64.06% | 97.87% | 80.07% | 8217.17 | -0.76% | 247473 | 158542.38 | 88930.62 | 485.33 | 0 | 0 | 0 | 0 | 155171.78 | 211.58 | 3370.6 | 694.5% | YES | 3370.6 | 33869 | 126947.6133 | 5747.76 | 15604.11 | 4300.18 | 8217.17 | 8217.17 | 7% | 6.24% | 0.63% | -6.37% |  | 35.48 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23822 | FCASW Requirements Management | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 35.3859 | 28.65% | 100% | -4.882e-05% | 0 | -2.35% | 595703 | 170698.25 | 425004.75 | 12010.57 | 0 | 0 | 0 | 0 | 170698.25 | 107.6 | 0 | 0% | NO | 0 | 204838 | -0.083333 | 204837.9 | 0 | 0 | 0 | 0 | 17% | 14.65% | 14.65% | -2.35% |  | 78.5 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23508 | Verification and Validation | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 80.77% | 100% | 97.06% | 6075.9 | 10.77% | 212950 | 171993.5 | 40956.5 | 0 | 0 | 0 | 0 | 0 | 171993.53 | 91 | -0.03 | 0% | NO | -0.03 | 6076 | 166930.1967 | 0 | 0 | 6075.9 | 0 | 6075.9 | 24% | 34.77% | 33.6% | 9.6% |  | 78.5 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23518 | Systems Engineering support to FCAS | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 5.8554 | 91.58% | 89.67% | 79.71% | 9843.9 | -6.3% | 193736.8 | 177419.25 | 16317.55 | 2786.75 | 3927.4 | 3927.4 | 0 | 0 | 159084.68 | 103.29 | 18334.57 | 657.9% | YES | 18334.57 | 21195 | 141422.18 | 11351.1 | 0 | 9843.9 | 0 | 9843.9 | 30% | 23.7% | 3.5% | -26.5% |  | 68.98 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23464 | A220 Project X Design Offload | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 70.4822 | 54.73% | 95.31% | 73.26% | 27862.8 | -9.66% | 332340 | 181885.1 | 150454.9 | 2134.65 | 0 | 0 | 0 | 0 | 173346.5 | 198.89 | 8538.6 | 400% | YES | 8538.6 | 48124 | 133243.1667 | 1900.32 | 18361.2 | 0 | 27862.8 | 27862.8 | 26% | 16.34% | 13.82% | -12.18% |  | 42.87 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23421 | A220 DTC | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 11.6401 | 86.57% | 69.49% | 63.99% | 0 | -28.07% | 217089.12 | 187925.91 | 29163.21 | 2505.41 | 0 | 0 | 0 | 0 | 130597.8 | 119.08 | 57328.11 | 2288% | YES | 57328.11 | 12403 | 120261.9667 | 12403.44 | 0 | 0 | 0 | 0 | 29% | 0.93% | 5.38% | -23.62% |  | 45.91 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23667 | Safety Systems Engineer | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 53.3198 | 47.32% | 100% | 72.78% | 19536 | -11.11% | 398000 | 188320 | 209680 | 3932.5 | 0 | 0 | 0 | 0 | 188320 | 91 | 0 | 0% | NO | 0 | 61512 | 137060 | 41976 | 19536 | 0 | 0 | 19536 | 47% | 35.89% | 29.32% | -17.68% |  | 110 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23008 | Spirit Shorts Project Rachel | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 68.49% | 91.32% | 91.32% | 0 | -9.7% | 286960 | 196531.2 | 90428.8 | 0 | 0 | 0 | 0 | 0 | 179472.8 | 20470.08 | 17058.4 | 0% | NO | 17058.4 | 0 | 179472.8 | 0 | 0 | 0 | 0 | 0 | 15% | 5.3% | 0.31% | -14.69% |  | 46.04 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23019 | EXP034-B Actuator Development | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 103.1% | 89.91% | 89.91% | 0 | -16.68% | 215541.2 | 222215.54 | -6674.34 | 0 | 12297.9 | 12297.9 | 0 | 6674.34 | 199796.76 | 477.34 | 397.78 | 0% | NO | 397.78 | 0 | 199796.76 | 0 | 0 | 0 | 0 | 0 | 34% | 17.32% | 79.64% | 45.64% |  | 58.45 | [5 empty] | -22021
1740 | 2024-05-29 23:36 | P23506 | ASTER Mid-Life Refurbishment Project Manager | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 32.8058 | 68.45% | 99.54% | 78.09% | 0 | 0.99% | 326900 | 223775.37 | 103124.63 | 3143.49 | 3830.37 | 3830.37 | 0 | 0 | 222751.41 | 91 | 1023.96 | 32.57% | NO | 1023.96 | 57618 | 174736.41 | 43560 | 14058 | 0 | 0 | 0 | 25% | 25.99% | 26.1% | 1.1% |  | 110 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23754 | Tempest Composites WP4 | Phillip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 5.4002 | 72.08% | 0% | 0% | 0 | -2.59% | 310945.68 | 224136.23 | 86809.45 | 16075.28 | 1784.87 | 1784.87 | 0 | 0 | 0 | 118.63 | 224136.23 | 1394% | YES | 224136.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36% | 33.41% | 33.41% | -2.59% |  | 60.32 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23242 | Physical Architecture & System Engineering Support | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 28.6834 | 73.56% | 99.66% | 83.41% | 14130 | 6.62% | 305459 | 224681.21 | 80777.79 | 2816.19 | 775.55 | 775.55 | 0 | 0 | 223914.55 | 92.03 | 412.66 | 14.65% | NO | 412.66 | 43803 | 187412.05 | 29673 | 0 | 14130 | 0 | 14130 | 15% | 21.62% | 7.33% | -7.67% |  | 78.23 | [5 empty] | -354
1740 | 2024-05-29 23:36 | P23373 | Raytheon Michael Bellini | Natalie Sinclair | 0 | RAS | RAYTHEON UNITED KINGDOM LIMITED | EES | Level NC | REIM |  |  |  | -4.1333 | 105.7% | 92.94% | 75.55% | 24734.7 | -7.71% | 214367.4 | 226519.02 | -12151.62 | 2939.96 | 0 | 0 | 13558.28 | 12151.62 | 210519.78 | 130.74 | 15999.24 | 544.2% | YES | 15999.24 | 47271 | 171127.28 | 22536.06 | 0 | 24734.7 | 0 | 24734.7 | 45% | 37.29% | 38.69% | -6.31% |  | 91.61 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23505 | EXP-022 Meteor TBUS T&E support | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 4.8454 | 92.06% | 100% | 79.04% | 19241.59 | -1.5% | 246744.4 | 227157.61 | 19586.79 | 4042.35 | 0 | 0 | 0 | 0 | 227157.63 | 91 | -0.02 | -0.0004948% | NO | -0.02 | 57132 | 179547.63 | 37890.3 | 0 | 19241.59 | 0 | 19241.59 | 20% | 18.5% | 15.67% | -4.33% |  | 89.83 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23524 | Bombardier Regional Jets (BRJ) | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -28.9093 | 160.2% | 46.45% | 45.14% | 3694.07 | -3.65% | 146287.84 | 234291.96 | -88004.12 | 3044.15 | 0 | 0 | 113075 | 88004.12 | 108838.22 | 318.43 | 125453.74 | 4121% | YES | 125453.74 | 3694 | 105759.8867 | 0 | 0 | 0 | 3694.07 | 3694.07 | 18% | 14.35% | 17.56% | -0.44% |  | 43.71 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23741 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  | 29.3452 | 37.13% | 83.34% | 37.31% | 0 | 2.58% | 640812 | 237951 | 402861 | 13728.35 | 0 | 0 | 0 | 0 | 198299 | 86.27 | 45652 | 332.5% | YES | 45652 | 131435 | 88769.8333 | 68808 | 62626.8 | 0 | 0 | 0 | 28% | 30.58% | 30.58% | 2.58% |  | 38.78 | [5 empty] | 6000
1740 | 2024-05-29 23:36 | P23648 | EXP-032 Delivery of Datalink Eng support - FCAS AP | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 10.3951 | 69.83% | 70.75% | 52.47% | 19536 | 7.46% | 371000 | 259054.2 | 111945.8 | 10769.06 | 1032.95 | 1032.95 | 0 | 0 | 183267.95 | 91 | 75786.25 | 703.7% | YES | 75786.25 | 56826 | 135912.95 | 37290 | 19536 | 0 | 0 | 19536 | 22% | 29.46% | 30.11% | 8.11% |  | 102.04 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23739 | Lifing Services DACs | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  | 28.0765 | 37.72% | 89.17% | 44.58% | 0 | 6.18% | 656508 | 247665.2 | 408842.8 | 14561.73 | 0 | 0 | 0 | 0 | 220836 | 89.07 | 38829.2 | 266.7% | YES | 38829.2 | 132502 | 110417.6667 | 66850.8 | 65650.8 | 0 | 0 | 0 | 28% | 34.18% | 34.18% | 6.18% |  | 37.75 | [5 empty] | 12000
1740 | 2024-05-29 23:36 | P23472 | Tempest Wing Design | Phillip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 224.1116 | 52.67% | 127.4% | 119.6% | 0 | -11.69% | 483869.78 | 254854.61 | 229015.17 | 1021.88 | 238975 | 356900 | 0 | 0 | 324639.1 | 0 | -44784.5 | -4383% | NO | 73140.5 | 23858 | 304757.4333 | 23857.58 | 0 | 0 | 0 | 0 | 23% | 11.31% | 28.89% | 5.89% |  | 46.74 | [5 empty] | 25000
1740 | 2024-05-29 23:36 | P23007 | EXP-006A - Brimstone 3 | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 55.7959 | 70.5% | 100% | 90.65% | 0 | -2.41% | 406450 | 286547.91 | 119902.09 | 2148.94 | 0 | 0 | 0 | 0 | 286547.91 | 90.9 | -30.01 | -1.397% | NO | -30.01 | 32146 | 259759.5767 | 20653.4 | 11492.4 | 0 | 0 | 0 | 25% | 22.59% | 29.94% | 4.94% |  | 70.19 | [5 empty] | -30
1740 | 2024-05-29 23:36 | P23308 | NATO JEWCS | Natalie Sinclair | 0 | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  | 17.8439 | 87% | 92.51% | 88.26% | 0 | -4.12% | 356307 | 309975.55 | 46331.45 | 2596.49 | 613.89 | 613.89 | 0 | 0 | 286767.43 | 136.01 | 23208.12 | 893.8% | YES | 23208.12 | 15829 | 273576.5967 | 15829.13 | 0 | 0 | 0 | 0 | 24% | 19.88% | 11.88% | -12.12% |  | 75.81 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P22953 | Spirit Shorts eVTOL | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-05-08 | 1 |  |  | 103.1% | 80.83% | 80.83% | 0 | -9.51% | 324272 | 334483.6 | -10211.6 | 0 | 66696.6 | 67387.9 | 0 | 10211.6 | 270366 | 64941.12 | 54117.6 | 0% | NO | 54808.9 | 0 | 270366 | 0 | 0 | 0 | 0 | 0 | 17% | 7.49% | 100% | 83% |  | 46.19 | [5 empty] | -10000
1740 | 2024-05-29 23:36 | P23629 | F35 FTI | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level NC | REIM |  |  |  | -16.8886 |  | 84.88% | 74.45% | 0 | -1.66% | 0 | 331355.91 | -331355.91 | 19620.09 | 0 | 0 | 0 | 331355.91 | 281269.67 | 50.7 | 50086.24 | 255.3% | YES | 50086.24 | 41490 | 246694.67 | 41489.5 | 0 | 0 | 0 | 0 | 31% | 29.34% | 28.35% | -2.65% |  | 61.4 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P21463 | Safety & Monitoring Systems at DM Beith & Gosport | Harry James Kellett | 0 | BXW | MOD | EES | Level 2 | FIX |  |  |  | 4.0651 | 88.19% | 113.4% | 113.4% | 0 | -23.48% | 378612.83 | 333886.3 | 44726.53 | 11002.63 | 75631.47 | 79790.28 | 45616.14 | 0 | 378594.83 | 0 | -44708.53 | -406.3% | NO | -40549.72 | 0 | 378594.83 | 0 | 0 | 0 | 0 | 0 | 48% | 24.52% | 39.48% | -8.52% |  | 56.29 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23816 | Typhoon FTI Works - 2024 Fixed Price Element | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  |  | 80.3% | 89.17% | 4.314e-05% | 0 | -1.64% | 404176.65 | 324547.09 | 79629.56 | -1266.67 | 0 | 0 | 0 | 0 | 289390.14 | 120.73 | 45156.95 | -3565% | NO | 45156.95 | 347268 | 0.14 | 347268.17 | 0 | 0 | 0 | 0 | 30% | 28.36% | 28.36% | -1.64% |  | 50.93 | [5 empty] | 10000
1740 | 2024-05-29 23:36 | P22515 | Shorts A220 100/300 ALI Phase III | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 40.0928 | 84.36% | 97.13% | 92.55% | 0 | 0.55% | 400628.76 | 337974.95 | 62653.81 | 1562.72 | 3450.98 | 3450.98 | 0 | 0 | 328273.11 | 108.05 | 9701.84 | 620.8% | YES | 9701.84 | 18583 | 312787.2767 | 0 | 18582.69 | 0 | 0 | 0 | 10% | 10.55% | 6.64% | -3.36% |  | 40.57 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P22842 | ME Support (Aim Altitude) | Trevor Knox | 0 | AVI | AIM ALTITUDE UK LIMITED | ME | Level 3 | FIX | 2023-06-14 | 4 |  |  | 99.31% | 100.5% | 86.63% | 57290.84 | 0.49% | 346293.67 | 343918.08 | 2375.59 | 0 | 2909.86 | 2909.86 | 0 | 0 | 345673.01 | 55184.93 | -1754.93 | 0% | NO | -1754.93 | 57291 | 297930.51 | 0 | 0 | 0 | 57290.84 | 57290.84 | 13% | 13.49% | 0% | -13% |  | 46.3 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P22391 | GE System Engineering support | Vinayakumar Sugur | 0 | GEE | EXPERIS LIMITED | EES | Level NC | REIM | 2024-04-08 | 0 |  |  | 82.01% | 100.7% | 100.7% | 0 | 0.13% | 434434.25 | 356260.63 | 78173.62 | 0 | 0 | 0 | 0 | 0 | 358805.6 | 0 | -2544.97 | 0% | NO | -2544.97 | 0 | 358805.6 | 0 | 0 | 0 | 0 | 0 | 6% | 6.13% | 6.09% | 0.09% |  | 57.33 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23743 | EHM Cloud Migration | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 33.3616 | 32.71% | 103% | 51.38% | 0 | 8.38% | 1016000 | 332304.13 | 683695.87 | 20493.5 | 0 | 0 | 0 | 0 | 342376 | 73.5 | 24928.13 | 121.6% | NO | 24928.13 | 205949 | 170751.8333 | 103612.8 | 102336 | 0 | 0 | 0 | 28% | 36.38% | 36.38% | 8.38% |  | 55.53 | [5 empty] | 35000
1740 | 2024-05-29 23:36 | P23617 | Tempest Composites WP2 | Phillip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -34.0523 | 154.7% | 26.75% | 15.29% | 29536.68 | 11.57% | 244405.26 | 378159.1 | -133753.84 | 3927.89 | 0 | 0 | 153486.97 | 133753.84 | 101150.9 | 409.92 | 277008.2 | 7052% | YES | 277008.2 | 51981 | 57833.4 | 0 | 22444.14 | 0 | 29536.68 | 29536.68 | 22% | 33.57% | 33.19% | 11.19% |  | 62.15 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23677 | ME Managed Service - Phase 1 | Paul Watson | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  | 25.9731 | 35.65% | 59.99% | 0% | 0 | -10.92% | 1116000 | 397876.35 | 718123.65 | 27648.75 | 0 | 38000 | 0 | 0 | 238680 | 129.36 | 159196.35 | 575.8% | YES | 197196.35 | 286416 | 0 | 71536.5 | 214879.5 | 0 | 0 | 0 | 30% | 19.08% | 20.91% | -9.09% |  | 44.17 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23603 | Typhoon IMDLR | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | -4.0243 | 131.3% | 76.18% | 29.92% | 0 | 1.12% | 305067.09 | 400446.79 | -95379.7 | 23701.1 | 1500 | 1500 | 152797.11 | 95379.7 | 305064.02 | 256.84 | 95382.77 | 402.4% | YES | 95382.77 | 222307 | 119808.1867 | 222307.42 | 0 | 0 | 0 | 0 | 28% | 29.12% | 27.57% | -0.43% |  | 56.21 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23432 | Spirit Belfast MRB On-Site Support (Mon & Clear) | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 65.77% | 128.6% | 128.6% | 0 | -11.53% | 449545 | 295665.27 | 153879.73 | 0 | 295665.27 | 451827.33 | 0 | 0 | 380234.75 | 32916.62 | 27430.52 | 0% | NO | 183592.58 | 0 | 380234.75 | 0 | 0 | 0 | 0 | 0 | 39% | 27.47% | 0% | -39% |  | 0 | [5 empty] | 112000
1740 | 2024-05-29 23:36 | P23045 | Shotgun Adaptors - 10 Sets | Harry James Kellett | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | FIX | 2024-02-27 | 4 |  | 14.3628 | 78.74% | 127% | 127% | 0 | 2.55% | 399276.11 | 314390.3 | 84885.81 | 5910.11 | 214550.47 | 214550.47 | 0 | 0 | 399276.11 | 349.55 | 15877.19 | 268.6% | YES | 15877.19 | 0 | 399276.11 | 0 | 0 | 0 | 0 | 0 | 31% | 33.55% | 93.96% | 62.96% |  | 58.52 | [5 empty] | 100763
1740 | 2024-05-29 23:36 | P23023 | Spirit Shorts R Foster/M Gourley | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 79.3253 | 71.59% | 103.4% | 94.45% | 0 | -1.11% | 590659.44 | 422861.91 | 167797.53 | 2115.31 | 237621.5 | 267726 | 0 | 0 | 437064.88 | 101.41 | 8163.03 | 385.9% | YES | 38267.53 | 45188 | 399408.2133 | 20217.14 | 24971.11 | 0 | 0 | 0 | 9% | 7.89% | 11.25% | 2.25% |  | 29.7 | [5 empty] | 22366
1740 | 2024-05-29 23:36 | P22906 | Spirit Shorts - MRB JD Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 3.4935 | 98.08% | 81.84% | 64.3% | 99451.32 | -7.95% | 481714 | 472478.18 | 9235.82 | 2643.75 | 0 | 0 | 0 | 0 | 386687.62 | 402.91 | 93790.56 | 3548% | YES | 93790.56 | 99451 | 303811.7867 | 0 | 0 | 0 | 99451.32 | 99451.32 | 13% | 5.05% | 2.42% | -10.58% |  | 36.97 | [5 empty] | 8000
1740 | 2024-05-29 23:36 | P22652 | L3 - Saftey Engineering | Sean Simmons | 0 | LHW | L3HARRIS MAPPS LIMITED | EES | Level NC | FIX |  |  |  |  | 95.63% | 95.66% | 95.66% | 0 | 5.66% | 523390 | 500497.5 | 22892.5 | 0 | 0 | 0 | 0 | 0 | 478783.75 | 26056.5 | 21713.75 | 0% | NO | 21713.75 | 0 | 478783.75 | 0 | 0 | 0 | 0 | 0 | 21% | 26.66% | 25.88% | 4.88% |  | 83.05 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23699 | A220 Stress Checkers | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -2.5044 | 127.1% | 0% | 0% | 0 | 7.04% | 408328.79 | 518977.89 | -110649.1 | 44182.32 | 12000 | 12000 | 185592 | 110649.1 | 0 | 164.94 | 518977.89 | 1175% | YES | 518977.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13% | 20.04% | 20.07% | 7.07% |  | 61.88 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23281 | Systems Portfolio | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM | 2024-02-28 | 0 |  |  | 44.43% | 97.31% | 97.31% | 0 | -17.25% | 1177697.24 | 523236.96 | 654460.28 | 0 | 2133.28 | 2133.28 | 0 | 0 | 509179.87 | 15792.1 | 13160.09 | 0% | NO | 13160.09 | 0 | 509179.87 | 0 | 0 | 0 | 0 | 0 | 25% | 7.75% | 100% | 75% |  | 70.48 | [5 empty] | -897
1740 | 2024-05-29 23:36 | P23531 | BAe Systems F35 MRB Support | Richard Brook | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | -69.5736 |  | 96.56% | 92.49% | 0 | 3.64% | 0 | 524819.26 | -524819.26 | 7543.37 | 287.44 | 287.44 | 0 | 524819.26 | 506774.08 | 29.37 | 18045.18 | 239.2% | YES | 18045.18 | 25639 | 485408.2467 | 25639.2 | 0 | 0 | 0 | 0 | 25% | 28.64% | 31.83% | 6.83% |  | 60.08 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23554 | Dornier Seawings 328 2023 H2 Support | Natalie Sinclair | 0 | DAX | EXPLEO GERMANY GMBH (EC) | MPE | Level 2 | REIM |  |  |  | -2.1218 | 104.7% | 80.43% | 80.43% | 0 | 5.33% | 508481.81 | 532455.55 | -23973.74 | 11298.52 | 4046.44 | 4046.44 | 32100 | 23973.74 | 428252.8 | 81.48 | 104202.75 | 922.3% | YES | 104202.75 | 0 | 428252.8 | 0 | 0 | 0 | 0 | 0 | 21% | 26.33% | 22.51% | 1.51% |  | 65.57 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23001 | Spirit Shorts A220 Design | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -22.5056 | 114.2% | 75.01% | 70.3% | 0 | 11.33% | 486640 | 555511.6 | -68871.6 | 3060.2 | 0 | 0 | 65953.2 | 68871.6 | 416705.3 | 390.67 | 138806.3 | 4536% | YES | 138806.3 | 31432 | 390511.9667 | 21930.72 | 9501.6 | 0 | 0 | 0 | 9% | 20.33% | 11.49% | 2.49% |  | 43.56 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23520 | FCAS AP Portfolio Systems | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 27.2395 | 69.32% | 100% | 73.6% | 62232.16 | -6.53% | 810821 | 562034.55 | 248786.45 | 9133.31 | 423 | 423 | 0 | 0 | 562047.44 | 88.3 | -4295.89 | -47.04% | NO | -4295.89 | 178043 | 413678.2733 | 115810.8 | 0 | 62232.16 | 0 | 62232.16 | 22% | 15.47% | 16.35% | -5.65% |  | 81.14 | [5 empty] | -4283
1740 | 2024-05-29 23:36 | P23219 | Tornado Air 800 Engineering Support | Richard Brook | 0 | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 3 | REIM |  |  |  |  | 98.61% | 95.36% | 95.36% | 0 | -1.51% | 615046 | 606500.38 | 8545.62 | -5666.58 | 459.21 | 459.21 | 0 | 0 | 578373.17 | 20.57 | 3220.21 | -56.83% | NO | 3220.21 | 0 | 578373.17 | 0 | 0 | 0 | 0 | 0 | 31% | 29.49% | 346.1% | 315.1% |  | 81.66 | [5 empty] | -24907
1740 | 2024-05-29 23:36 | P23140 | Spirit Shorts A220 MLG Stress Support | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  | 10.3977 | 76.75% | 95.82% | 65.69% | 0 | -7.52% | 735573.4 | 564542.26 | 171031.14 | 16448.96 | 20870.3 | 87811.88 | 111743 | 0 | 540939.4 | 151.83 | 48602.86 | 295.5% | YES | 115544.44 | 204098 | 370857.7333 | 0 | 204098.4 | 0 | 0 | 0 | 17% | 9.48% | -9.07% | -26.07% |  | 44.75 | [5 empty] | 25000
1740 | 2024-05-29 23:36 | P23473 | Tempest Vertical Tail | Phillip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 27.8873 | 70.6% | 99.25% | 92.92% | 0 | -7.06% | 846017.62 | 597246.55 | 248771.07 | 8920.58 | 108500 | 129075 | 0 | 0 | 592767.31 | 32.78 | 9479.24 | 106.3% | NO | 30054.24 | 45333 | 554989.81 | 45333.23 | 0 | 0 | 0 | 0 | 29% | 21.94% | 24.27% | -4.73% |  | 62.64 | [5 empty] | 5000
1740 | 2024-05-29 23:36 | P23372 | BAE Carbon Tooling Off-load | Gary Kempster | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | 1.8832 | 89.71% | 96.2% | 72.06% | 0 | -3.23% | 674141.57 | 604774.74 | 69366.83 | 36835.36 | 0 | 0 | 0 | 0 | 581806.73 | 160.85 | 22968.01 | 62.35% | NO | 22968.01 | 175225 | 435785.8967 | 175224.95 | 0 | 0 | 0 | 0 | 25% | 21.77% | 18.45% | -6.55% |  | 53.99 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23366 | Business Analyst Support | Peter Williams | 0 | BDZ | MBDA UK LIMITED | DET | Level 3 | REIM |  |  |  | 83.0726 | 26.21% | 184.4% | 165.3% | 0 | 2.61% | 1302200 | 341249.51 | 960950.49 | 11567.6 | 273532.34 | 900687.4 | 0 | 0 | 629120 | 43.1 | 5264.51 | 45.51% | NO | 632419.57 | 77952 | 564160 | 77952 | 0 | 0 | 0 | 0 | 43% | 45.61% | 23.27% | -19.73% |  | 46.73 | [5 empty] | 293135
1740 | 2024-05-29 23:36 | P23605 | Typhoon Work Package 2 Continuation | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM |  |  |  |  | 101.5% | 85.64% | 85.64% | 0 | 4.83% | 627011.01 | 636344.13 | -9333.12 | -4475.64 | 5554 | 5554 | 0 | 9333.12 | 544986.65 | 3094.41 | 91357.48 | -2041% | NO | 91357.48 | 0 | 544986.65 | 0 | 0 | 0 | 0 | 0 | 23% | 27.83% | 27.5% | 4.5% |  | 55.62 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23323 | CNC-CMM Programming Support | Stephen Young | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  | -3.1631 | 104.2% | 89.28% | 89.28% | 0 | -2.01% | 617809.74 | 643497.2 | -25687.46 | 8120.86 | 15941.56 | 17789.56 | 99488.9 | 25687.46 | 574493.52 | 52.71 | 69003.68 | 849.7% | YES | 70851.68 | 0 | 574493.52 | 0 | 0 | 0 | 0 | 0 | 32% | 29.99% | 36.67% | 4.67% |  | 57.61 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P22790 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | REIM | 2024-04-28 | 0 |  |  | 197.4% | 89.11% | 89.11% | 0 | 1.11% | 352240 | 695460.45 | -343220.45 | 0 | 1611.52 | 1611.52 | 44500 | 343220.45 | 619743.88 | 396.6 | 44446.57 | 0% | NO | 44446.57 | 0 | 619743.88 | 0 | 0 | 0 | 0 | 0 | 13% | 14.11% | -2.72% | -15.72% |  | 45.08 | [5 empty] | -31270
1740 | 2024-05-29 23:36 | P23694 | Systems Portfolio EXP-011a | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | -1.2455 | 105.2% | 80.12% | 53.2% | 0 | 1.87% | 648492.8 | 681914.26 | -33421.46 | 26833.56 | 809.51 | 809.51 | 0 | 33421.46 | 546332.19 | 91.3 | 135582.07 | 505.3% | YES | 135582.07 | 220264 | 362778.8567 | 142737.46 | 77526.61 | 0 | 0 | 0 | 21% | 22.87% | 20.52% | -0.48% |  | 88.61 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23685 | DAC LUC Support and Recompliance | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 25.5902 | 31.34% | 141.7% | 71.93% | 0 | 8.34% | 2180000 | 683230.43 | 1496769.57 | 58489.95 | 0 | 0 | 0 | 0 | 967868 | 55.64 | -170873.57 | -292.1% | NO | -170873.57 | 571728 | 491428 | 297441.6 | 274286.4 | 0 | 0 | 0 | 30% | 38.34% | 38.34% | 8.34% |  | 57.57 | [5 empty] | 113764
1740 | 2024-05-29 23:36 | P23426 | BAE Tempest WP 3 Harness Maturation | Phillip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 1.9328 | 95.52% | 88.56% | 70.08% | 0 | -6.22% | 884012.04 | 844366.58 | 39645.46 | 20512.46 | 213.34 | 213.34 | 0 | 0 | 747777.74 | 93.31 | 96588.84 | 470.9% | YES | 96588.84 | 187209 | 591770.24 | 79451.21 | 107757.52 | 0 | 0 | 0 | 33% | 26.78% | 26.97% | -6.03% |  | 52.29 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23105 | Raytheon Supply Engineering Support | Natalie Sinclair | 0 | RAY | RAYTHEON UNITED KINGDOM LIMITED | MPE | Level 3A | REIM | 2023-07-13 | 2 |  |  | 76.96% | 94.49% | 90.07% | 49156.8 | -2.02% | 1205008 | 927395.25 | 277612.75 | 0 | 0 | 0 | 0 | 0 | 876291.5 | 107644.5 | 48739.75 | 0% | NO | 48739.75 | 49157 | 835327.3333 | 0 | 0 | 0 | 49156.8 | 49156.8 | 26% | 23.98% | 100% | 74% |  | 48.97 | [5 empty] | -2364
1740 | 2024-05-29 23:36 | P23117 | BAE Typhoon Eng Support | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | 2024-03-12 | 3 |  |  | 103.2% | 96.92% | 96.92% | 0 | -1.09% | 950771.99 | 980837.59 | -30065.6 | -4930.23 | 19213.34 | 20141.26 | 4921.28 | 30065.6 | 950609.41 | 2311.1 | 3132.18 | -63.53% | NO | 4060.1 | 0 | 950609.41 | 0 | 0 | 0 | 0 | 0 | 30% | 28.91% | 20.68% | -9.32% |  | 52.29 | [5 empty] | -27096
1740 | 2024-05-29 23:36 | P23451 | BAE Tempest - DFM-ASO Planning | Stephen Young | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | 10.9161 | 83.44% | 85.27% | 61.93% | 39715.08 | -3.06% | 1145785.42 | 956050.02 | 189735.4 | 17381.22 | 0 | 0 | 0 | 0 | 815259.15 | 137.32 | 139707.87 | 803.8% | YES | 139707.87 | 267774 | 592114.15 | 228058.79 | 57003.88 | -44513.7 | 27224.9 | 39715.08 | 28% | 24.94% | 26.36% | -1.64% |  | 53.83 | [5 empty] | -1083
1740 | 2024-05-29 23:36 | P23602 | EXP-025 Portfolio Software Engineering Support | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 10.651 | 74.1% | 82.8% | 58.54% | 143049.25 | -1.15% | 1327080 | 983393.87 | 343686.13 | 32267.84 | 4348.66 | 929790.21 | 0 | 0 | 814204.07 | 90.99 | 169189.8 | 524.3% | YES | 1094631.35 | 286222 | 575685.7367 | 143172.62 | 143049.25 | 0 | 0 | 143049.25 | 24% | 22.85% | 22.53% | -1.47% |  | 83.44 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P22350 | EMP 2020-2021 | Natalie Sinclair | 0 | ARY | GUIDANT GLOBAL UK LIMITED | PCPR | Level NC | REIM |  |  |  | -0.25894 | 100.1% | 98.62% | 94.47% | 0 | -2.1% | 1017579.76 | 1018665.96 | -1086.2 | 4194.75 | 400 | 400 | 0 | 1086.2 | 1004590.04 | 76.79 | 14075.92 | 335.6% | YES | 14075.92 | 50691 | 962347.54 | 27845.4 | 22845.77 | 0 | 0 | 0 | 32% | 29.9% | 27.95% | -4.05% |  | 44.15 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P22671 | Spirit Shorts Pylon and Fairing Package | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX | 2023-05-03 | 0 |  |  | 105% | 95.26% | 95.26% | 0 | -7.21% | 1198494.77 | 1258071.09 | -59576.32 | 0 | 106494.89 | 106494.89 | 0 | 59576.32 | 1198494.77 | 2544.39 | 2120.32 | 0% | NO | 2120.32 | 0 | 1198494.77 | 0 | 0 | 0 | 0 | 0 | 20% | 12.79% | 0% | -20% |  | 45.4 | [5 empty] | -57456
1740 | 2024-05-29 23:36 | P23152 | Project Aragon - Design and Stress Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | -3.1634 | 102.8% | 77.34% | 53.22% | 0 | -9.54% | 1333452.21 | 1370272.26 | -36820.05 | 11639.27 | 0 | 0 | 0 | 36820.05 | 1059816.5 | 386.66 | 310455.76 | 2667% | YES | 310455.76 | 396625 | 729295.6667 | 50377.1 | 346247.55 | 0 | 0 | 0 | 39% | 29.46% | 29.3% | -9.7% |  | 52 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23292 | BAE Tempest WP 4 AV Trays | Phillip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 3.955 | 94.24% | 93.34% | 87.5% | 116674.18 | 1.35% | 1498284.22 | 1412004.04 | 86280.18 | 21815.58 | 0 | 0 | 0 | 0 | 1317945.86 | 56.01 | 94058.18 | 431.2% | YES | 94058.18 | 98848 | 1235572.5267 | -17826.65 | 0 | 116674.18 | 0 | 116674.18 | 32% | 33.35% | 31.71% | -0.29% |  | 53.95 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23519 | Mechanical and Electrical Design Eng Support | Dushan Fernando | 0 | BAX | SAFRAN SEATS GB LIMITED | MPE | Level 2 | REIM |  |  |  | 9.1634 | 84.99% | 90.7% | 72.48% | 0 | -1.58% | 1807261.3 | 1536003.65 | 271257.65 | 29602.38 | 1004.45 | 1504.45 | 0 | 0 | 1393199.8 | 95.98 | 142803.85 | 482.4% | YES | 143303.85 | 335892 | 1113289.8 | 141083.4 | 194808.9 | 0 | 0 | 0 | 33% | 31.42% | 31.41% | -1.59% |  | 56.66 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23411 | Agile & Scrum Delivery Service | Peter Williams | 0 | BDZ | MBDA UK LIMITED | DET | Level 2 | REIM | 2023-08-14 | 0 |  |  | 36.3% | 170.5% | 170.5% | 0 | 13.08% | 2487000 | 902903.79 | 1584096.21 | 0 | 894178.59 | 894178.59 | 0 | 0 | 1539600 | 19368.95 | 16140.79 | 0% | NO | 16140.79 | 0 | 1539600 | 0 | 0 | 0 | 0 | 0 | 29% | 42.08% | 0% | -29% |  | 74.57 | [5 empty] | 652837
1740 | 2024-05-29 23:36 | P22278 | TAI Supply Engineers to Ankara | Natalie Sinclair | 0 | TAI | TUSAS-TURK HAVACILIK VE UZAY | MPE | Level 3A | REIM |  |  |  | 1266.8816 | 19.89% | 456.3% | 456.3% | 0 | -15.84% | 2105282 | 418745.91 | 1686536.09 | 1331.25 | 49400.29 | 49400.29 | 0 | 0 | 1910696.33 | 128.06 | 18449.58 | 1386% | YES | 18449.58 | 0 | 1910696.33 | 0 | 0 | 0 | 0 | 0 | 95% | 79.16% | 64.99% | -30.01% |  | 34.1 | [5 empty] | 1510400
1740 | 2024-05-29 23:36 | P23175 | BAe Aero Typhoon Package 2 | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM | 2024-03-12 | 2 |  |  | 103.8% | 96.32% | 96.32% | 0 | -1.63% | 1984265.09 | 2060011.83 | -75746.74 | 0 | 57677.87 | 86030.82 | 15444.64 | 75746.74 | 1984257.03 | 84731.75 | 70609.8 | 0% | NO | 98962.75 | 0 | 1984257.03 | 0 | 0 | 0 | 0 | 0 | 29% | 27.37% | 0% | -29% |  | 51.76 | [5 empty] | -5145
1740 | 2024-05-29 23:36 | P23006 | Spirit Shorts A350 Freighter Toulouse | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 41.2229 | 88.87% | 104.5% | 73.8% | 378834.22 | 22.43% | 1925837.92 | 1711469.24 | 214368.68 | 5200.23 | 1086670.26 | 2010741.94 | 0 | 0 | 1787659.45 | 402.47 | 301083.79 | 5790% | YES | 1225155.47 | 629606 | 1262987.7833 | 110245.82 | 140525.66 | 378834.22 | 0 | 378834.22 | 5% | 27.43% | 47.12% | 42.12% |  | 48.28 | [5 empty] | 377274
1740 | 2024-05-29 23:36 | P19020 | Spirit Concessions - 2018 | Carl Warren | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2024-01-23 | 0 |  |  | 86.3% | 111.8% | 111.8% | 0 | 2.09% | 2015043.23 | 1739018.14 | 276025.09 | 0 | 44317.61 | 44317.61 | 0 | 0 | 1944710.76 | 236384.86 | 196987.38 | 0% | NO | 196987.38 | 0 | 1944710.76 | 0 | 0 | 0 | 0 | 0 | 25% | 27.09% | 9.32% | -15.68% |  | 40.87 | [5 empty] | 402680
1740 | 2024-05-29 23:36 | P23257 | BAE Tempest WP 5 Centre Fuselage | Phillip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 0.6248 | 99.56% | 98.05% | 95.54% | 0 | -5.72% | 2265401.51 | 2255408.57 | 9992.94 | 15993.87 | 78100 | 78100 | 0 | 0 | 2211380.12 | 42.78 | 44028.45 | 275.3% | YES | 44028.45 | 67821 | 2154862.62 | 67820.9 | 0 | 0 | 0 | 0 | 33% | 27.28% | 28.05% | -4.95% |  | 61.07 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23435 | Andy Baker Portfolio | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 35.1023 | 57.53% | 87.79% | 64.25% | 489604.46 | -7.21% | 4023207.4 | 2314478.41 | 1708728.99 | 48678.49 | 2596.25 | 2596.25 | 0 | 0 | 2031957.41 | 119 | 282521 | 580.4% | YES | 282521 | 654019 | 1486941.5767 | 164414.78 | 0 | 489604.46 | 0 | 489604.46 | 25% | 17.79% | 19.28% | -5.72% |  | 81.17 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23179 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX |  |  |  | -6.0875 | 101.2% | 93.72% | 88.45% | 162889.25 | -9.22% | 2542643.04 | 2573752.42 | -31109.38 | 5110.38 | 156991.12 | 248243.92 | 0 | 31109.38 | 2412235.69 | 663.07 | 161516.73 | 3161% | YES | 252769.53 | 162889 | 2276494.8567 | 0 | 0 | 162889.25 | 0 | 162889.25 | 22% | 12.78% | 18.09% | -3.91% |  | 44.4 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P19731 | Hapri HPC Rear Bearing Housing PDR & CDR | Steven Lawton | 0 | ATC | AECC Hunan Aviation Powerplant | MPE | Level 1 | FIX | 2024-05-13 | 3 |  | -419.2815 | 100.3% | 99.67% | 99.67% | 0 | -15.41% | 2980000 | 2989861.5 | -9861.5 | 23.52 | 366376.22 | 500476.22 | 0 | 9861.5 | 2980000 | 0 | -215138.5 | -914705% | NO | -81038.5 | 0 | 2980000 | 0 | 0 | 0 | 0 | 0 | 38% | 22.59% | 15.42% | -22.58% |  | 64.85 | [5 empty] | -225000
1740 | 2024-05-29 23:36 | P23207 | A350 Approvers - Design and Stress Support | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  | 3.8035 | 92.58% | 91.37% | 72.3% | 89526.18 | -4.32% | 3135290 | 2902799.55 | 232490.45 | 61125.74 | 40525.59 | 40525.59 | 0 | 0 | 2652260.57 | 95.11 | 250538.98 | 409.9% | YES | 250538.98 | 664077 | 2098863.07 | 232534.01 | 342017.26 | 89526.18 | 0 | 89526.18 | 22% | 17.68% | 16.76% | -5.24% |  | 54.54 | [5 empty] | 0
1740 | 2024-05-29 23:36 | P23487 | Tornado Air 800 Engineering Support | Richard Brook | 0 | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 2 | FIX |  |  |  | 11.0243 | 80.71% | 88.85% | 74.48% | 47390.58 | -2.82% | 4286367.76 | 3459542.78 | 826824.98 | 75000.2 | 500 | 500 | 0 | 0 | 3073852.1 | 109.36 | 457690.68 | 610.3% | YES | 457690.68 | 596787 | 2576529.6 | 549396.51 | 0 | 8658.1 | 38732.48 | 47390.58 | 40% | 37.18% | 40.59% | 0.59% |  | 79.01 | [5 empty] | 72000
Extend Table

## AP6-1
WIP No | Date Created | Project ID | Project Description | Project Manager | Agency (1=yes, 0=no) | Department Id | Client | CBU | Complexity | Type | Stop Booking Hrs | Closing Project: Action(s) to close | RAG | Approx. PO Burndown (weeks) | Turnover vs Contract Value | Invoice To Date vs Turnover | Cash in vs Turnover | Open Amount Overdue | Actual PM% to Baseline PM% delta | Contract Value | Total Project Turnover | Contract Value - Total Turnover | Run Rate (based on total turnover) | Total BOI Spend to Date | Total Committed PO (supplier/best shore) | Current AA in PT3 | Exposure (turnover - contract value) | Invoiced To Date | DSO | Unbilled (WIP) | WIP / Run rate | WIP / Run rate >1.3 | WIP + Remaining Committed PO for BOI | Total Open Amount | Cash in (Invoiced - (Open amount -VAT)) | Debt - <=30 Days since invoice | Debt - 31 - 60 Days since invoice | Debt - 61 - 90 Days since invoice | Debt - >= 90 Days since invoice | Open Amount Overdue2 | Baseline Project Margin | Project To Date (PTD) PM | Year to Date (YTD) PM | YTD Delta Actual PM% to BPM% | Forecast PM at Completion (Manual input from PTT) | Average Sale Rate | CSat score for last quarter (Manual input from PTT) | Comments and Actions | Judged income adjustment at completion | Profit to take now | Provision required now | Fully Traded | Last Months Comments and Actions
1741 | 2024-06-05 23:29 | P23650 | MBDA Recruitment Management costs | Andrew Slaney | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM | 2024-02-01 | 0 |  |  |  | 0% | 0% | 0 | 33042515% | 0 | 240971.5 | -240971.5 | -35243 | 0 | 0 | 266000 | 240971.5 | 0 | 0 | -0.5 | 0.001419% | NO | -0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | 33042518% | 165.6% | 162.6% |  | 82.3 | [5 empty] | -240972
1741 | 2024-06-05 23:29 | P23552 | FCAS AP Product Technology Development | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -25% | 597871 | 0 | 597871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0% | -25% |  | 0 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23912 | EXP-042 Software Engineering Support to Elec Eng | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 0% |  |  | 0 | -22% | 620890 | 0 | 620890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22% | 0% | 0% | -22% |  | 0 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23543 | EXP-024 FCAS AP Transformation & Change Enablers | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -26% | 385921 | 0 | 385921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26% | 0% | 0% | -26% |  | 0 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23784 | Tempest Tooling Offload 2024 | Gary Kempster | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM | 2024-05-09 | 0 | [5 empty] | 0 | -25% | 0 | 0 | 0 | -31152.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0% | -25% |  | 0 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23628 | Design Assurance | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | -7% | 0 | 0 | 0 | 0 | 0 | 0 | 4454.8 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 0% | 0.33% | -6.67% |  | 0 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23711 | DO NOT USE - RAISED IN ERROR | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23915 | A220 FLE Design | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 18707.94 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23730 | FLE Project | Siyun Fan | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -18.03% | 0 | 1120 | -1120 | 0 | 0 | 0 | 24000 | 1120 | 0 | 1344 | 1120 | 0% | NO | 1120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | -18.03% | -18.03% | -18.03% |  | 35 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23463 | A220 Wing MaMo Design Checking | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-03-07 | 0 |  |  |  | 0% | 0% | 0 | 7.85% | 0 | 1628 | -1628 | 0 | 0 | 0 | 15000 | 1628 | 0 | 1953.6 | 1628 | 0% | NO | 1628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | 10.85% | 0% | -3% |  | 44 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23892 | Warrior Environmental Control Unit | Trevin Fernandopulle | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM |  |  |  | 2.747 | 59.29% | 0% | 0% | 0 | 3.58% | 3920 | 2324 | 1596 | 581 | 0 | 0 | 0 | 0 | 0 | 28 | 2324 | 400% | YES | 2324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32% | 35.58% | 35.58% | 3.58% |  | 56 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P21028 | Rebate Collection (BACC) | David Catchpole | 0 | TOO | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | [5 empty] | 0% | 0% | 0 | 0% | 0 | 2680 | -2680 | 0 | 2680 | 2680 | 0 | 2680 | 0 | 3216 | 2680 | 0% | NO | 2680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23886 | A220 F&DT Support | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -4 |  | 0% | 0% | 0 | -9.07% | 0 | 3380.2 | -3380.2 | 845.05 | 0 | 0 | 12199.2 | 3380.2 | 0 | 35 | 3380.2 | 400% | YES | 3380.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 8.93% | 8.93% | -9.07% |  | 50.83 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23578 | ESN Work Package | Hannah Mead | 0 | COZ | CHELTON LIMITED | DET | Level 3 | FIX | 2024-01-01 | 0 |  |  | 86.17% | 116.1% | 116.1% | 0 | 35.86% | 4410 | 3800 | 610 | 0 | 0 | 0 | 0 | 0 | 4410 | 0 | -610 | 0% | NO | -610 | 0 | 4410 | 0 | 0 | 0 | 0 | 0 | 24% | 59.86% | 0% | -24% |  | 95 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23899 | Turret Test Rig | Trevin Fernandopulle | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM |  |  |  | 22.1176 | 15.32% | 0% | 0% | 0 | 0.52% | 24864 | 3808 | 21056 | 952 | 0 | 0 | 0 | 0 | 0 | 14 | 3808 | 400% | YES | 3808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16% | 16.52% | 16.52% | 0.52% |  | 56 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23909 | A220-300 Wing L5v01M09 Loads Increase | Siyun Fan | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -2 |  | 0% | 0% | 0 | -19.08% | 0 | 3948.16 | -3948.16 | 1974.08 | 0 | 0 | 9920 | 3948.16 | 0 | 19 | 3948.16 | 200% | YES | 3948.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | -19.08% | -19.08% | -19.08% |  | 39.68 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23880 | Warrior Crew Heater Design | Trevin Fernandopulle | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM |  |  |  | 2.25 | 90.91% | 0% | 0% | 0 | 3.58% | 5544 | 5040 | 504 | 224 | 0 | 0 | 0 | 0 | 0 | 49 | 5040 | 2250% | YES | 5040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32% | 35.58% | 35.58% | 3.58% |  | 56 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23002 | WoT MAJ Transit Flag Stress | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2024-04-03 | 1 |  |  | 62.41% | 160.2% | 160.2% | 0 | 38.54% | 4735 | 2955.29 | 1779.71 | 0 | 1492.79 | 2242.5 | 0 | 0 | 4735 | 91.03 | 1493.29 | 0% | NO | 2243 | 0 | 4735 | 0 | 0 | 0 | 0 | 0 | 10% | 48.54% | 0% | -10% |  | 45 | [5 empty] | 3273
1741 | 2024-06-05 23:29 | P23881 | Bulldog Fuel System Design | Trevin Fernandopulle | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM |  |  |  | 1.3084 | 88.18% | 0% | 0% | 0 | 1.29% | 8288 | 7308 | 980 | 749 | 0 | 0 | 0 | 0 | 0 | 42 | 7308 | 975.7% | YES | 7308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13% | 14.29% | 14.29% | 1.29% |  | 56 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23607 | SAFRAN - A330neo Turnover Frame | Gary Kempster | 0 | TOO | SAFRAN SEATS GB LIMITED | MPE | Level 3 | FIX |  |  |  |  | 95.69% | 104.5% | 104.5% | 0 | -19.52% | 8736 | 8359.05 | 376.95 | 0 | 0 | 0 | 0 | 0 | 8736 | 0.06 | 0.05 | 0% | NO | 0.05 | 0 | 8736 | 0 | 0 | 0 | 0 | 0 | 23% | 3.48% | 8.5% | -14.5% |  | 50.46 | [5 empty] | 377
1741 | 2024-06-05 23:29 | P23274 | ME Support (Aim Altitude - Cambridge) | Trevor Knox | 0 | AVI | AVIC CABIN SYSTEMS (UK) LIMITED | ME | Level 3 | FIX | 2023-08-18 | 0 |  |  | 51.88% | 56.3% | 56.3% | 0 | -0.17% | 17280 | 8964 | 8316 | 0 | 0 | 0 | 0 | 0 | 5046.3 | 4701.24 | 3917.7 | 0% | NO | 3917.7 | 0 | 5046.3 | 0 | 0 | 0 | 0 | 0 | 21% | 20.83% | 0% | -21% |  | 48 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23283 | Spirit Tooling Audit | Charidimos Valadakis | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-05-03 | 0 |  |  | 97.22% | 48.57% | 48.57% | 0 | -7.99% | 9910.08 | 9634.8 | 275.28 | 0 | 0 | 0 | 0 | 0 | 4679.76 | 5946.05 | 4955.04 | 0% | NO | 4955.04 | 0 | 4679.76 | 0 | 0 | 0 | 0 | 0 | 7% | -0.99% | 0% | -7% |  | 34.41 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23127 | Loft Hall Design Support | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-04-19 | 0 |  |  | 101% | 99.06% | 99.06% | 0 | -9.55% | 9680 | 9772 | -92 | 0 | 0 | 0 | 0 | 92 | 9680 | 110.4 | 92 | 0% | NO | 92 | 0 | 9680 | 0 | 0 | 0 | 0 | 0 | 41% | 31.45% | 0% | -41% |  | 44 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23630 | 2Excel CFD Analysis Support | Dushan Fernando | 0 | BAX | STIRLING DYNAMICS LTD | MPE | Level NC | FIX |  |  |  |  | 61.2% | 100% | 100% | 0 | -1.87% | 16195.49 | 9911.34 | 6284.15 | 0 | 0 | 0 | 0 | 0 | 9911.63 | 0 | -0.29 | 0% | NO | -0.29 | 0 | 9911.63 | 0 | 0 | 0 | 0 | 0 | 26% | 24.13% | 0% | -26% |  | 64.78 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23864 | REACH Coordinator | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 42.1845 | 18.99% | 97.16% | 0% | 0 | -10.24% | 52920 | 10050 | 42870 | 1016.25 | 0 | 0 | 0 | 0 | 9765 | 77 | 285 | 28.04% | NO | 285 | 11718 | 0 | 0 | 11718 | 0 | 0 | 0 | 27% | 16.76% | 16.76% | -10.24% |  | 30 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23894 | EE Test and Integration Lead | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | -5.0767 |  | 0% | 0% | 0 | 9.74% | 0 | 11144.69 | -11144.69 | 2195.28 | 0 | 0 | 15430 | 11144.69 | 0 | 35 | 11144.69 | 507.7% | YES | 11144.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23% | 32.74% | 32.74% | 9.74% |  | 63.88 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23898 | EXP-041 ISV Engineering Support | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 137.2591 | 2.832% | 76.82% | 0.001469% | 0 | -13.04% | 400584 | 11343.25 | 389240.75 | 2835.81 | 0 | 0 | 0 | 0 | 8713.5 | 27 | 2629.75 | 92.73% | NO | 2629.75 | 10456 | 0.16667 | 0 | 10456.2 | 0 | 0 | 0 | 21% | 7.96% | 7.96% | -13.04% |  | 78.5 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23313 | Laser Trim Fixtures | Gary Kempster | 0 | TOO | ALKEN ENGINEERING LIMITED | MPE | Level 3 | FIX | 2023-11-20 | 0 |  |  | 89.87% | 111.3% | 111.3% | 0 | 0.53% | 13770 | 12375 | 1395 | 0 | 0 | 0 | 0 | 0 | 13770 | 0 | -1395 | 0% | NO | -1395 | 0 | 13770 | 0 | 0 | 0 | 0 | 0 | 17% | 17.53% | 0% | -17% |  | 45 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P22761 | Red Bull Chassis Spit | Trevor Knox | 0 | TOO | MANUFAX ENGINEERING LTD | MPE | Level 3 | FIX | 2022-11-15 | 0 |  |  | 72.18% | 96.98% | 96.98% | 0 | 7.92% | 12961.2 | 9355.5 | 3605.7 | 0 | 0 | 0 | 0 | 0 | 9072.84 | 4666.39 | 3888.66 | 0% | NO | 3888.66 | 0 | 9072.84 | 0 | 0 | 0 | 0 | 0 | 23% | 30.92% | 0% | -23% |  | 42.19 | [5 empty] | 3606
1741 | 2024-06-05 23:29 | P23718 | Requalification of EJ200 GSS ESS EHM SW module | Vijayakumara Nanjundappa | 0 | ARZ | MTU AERO ENGINES AG | DET | Level 3 | FIX |  |  |  | 173.9498 | 13.57% | 402.4% | 216.6% | 0 | 15.91% | 74463 | 10101.57 | 64361.43 | 370 | 991.93 | 991.93 | 0 | 0 | 40648 | 0 | -27546.43 | -7445% | NO | -27546.43 | 22523 | 21878.8333 | 0 | 22523 | 0 | 0 | 0 | 28% | 43.91% | 43.91% | 15.91% |  | 80 | [5 empty] | 3000
1741 | 2024-06-05 23:29 | P23888 | HondaJet FWD Assy Jig Tool Design | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | FIX |  |  |  | 7.1749 | 42.9% | 0% | 0% | 0 | 4.13% | 31500 | 13513.5 | 17986.5 | 2506.88 | 0 | 0 | 0 | 0 | 0 | 49 | 13513.5 | 539.1% | YES | 13513.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 14.13% | 14.13% | 4.13% |  | 42 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23350 | Spirit 2023 - Stress Approve Man Serv (DH) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 14.15% | 72.64% | 72.64% | 0 | -0.29% | 97920 | 13860 | 84060 | 0 | 0 | 0 | 0 | 0 | 10068 | 4550.4 | 3792 | 0% | NO | 3792 | 0 | 10068 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23344 | Spirit A320 Spoilers Support 2023 | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 38.75% | 100% | 100% | 0 | 5.82% | 35786.4 | 13867.23 | 21919.17 | 0 | 0 | 0 | 0 | 0 | 13867.23 | 0 | 0 | 0% | NO | 0 | 0 | 13867.23 | 0 | 0 | 0 | 0 | 0 | 7% | 12.82% | 0% | -7% |  | 34.41 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23337 | Spirit 2023 - Steve Grimley | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 25.28% | 100% | 100% | 0 | 0.01% | 56812.9 | 14362.47 | 42450.43 | 0 | 0 | 0 | 0 | 0 | 14362.47 | 0 | 0 | 0% | NO | 0 | 0 | 14362.47 | 0 | 0 | 0 | 0 | 0 | 7% | 7.01% | 0% | -7% |  | 30.11 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23597 | MRB Onsite support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-02-16 | 1 |  |  |  | 0% | 0% | 0 | -10.04% | 0 | 15100.57 | -15100.57 | 0 | 9448.07 | 17381.62 | 24200 | 15100.57 | 0 | 18120.68 | 15100.57 | 0% | NO | 23034.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 7.96% | 8.95% | -9.05% |  | 42.5 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23869 | EXP-037 Land Ceptor Development Hardware Test Def | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 155.5832 | 9.801% | 0% | 0% | 0 | 0.81% | 162694 | 15944.83 | 146749.17 | 943.22 | 0 | 0 | 0 | 0 | 0 | 70 | 15944.83 | 1690% | YES | 15944.83 | 0 | 0 | 0 | -10617.91 | 10617.91 | 0 | 0 | 26% | 26.81% | 26.81% | 0.81% |  | 89.83 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23343 | Spirit 2023 - John Agnew | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-08-09 | 0 |  |  | 24.64% | 100% | 100% | 0 | -0.02% | 65120.37 | 16047.15 | 49073.22 | 0 | 0 | 0 | 0 | 0 | 16047.15 | 0 | 0 | 0% | NO | 0 | 0 | 16047.15 | 0 | 0 | 0 | 0 | 0 | 7% | 6.98% | 6.98% | -0.02% |  | 34.51 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23843 | EXP-035 FT15 Exemplar information set | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 52.5134 | 10.48% | 76.23% | -0.0003795% | 0 | -11.18% | 175985.16 | 18447.6 | 157537.56 | 2999.95 | 0 | 0 | 0 | 0 | 14062.43 | 77 | 4385.17 | 146.2% | YES | 4385.17 | 16875 | -0.07 | 0 | 16874.92 | 0 | 0 | 0 | 20% | 8.82% | 8.82% | -11.18% |  | 72.89 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23635 | Engineering Services: FAI Support | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 49.9% | 100% | 0.0008972% | 0 | -3.4% | 37230 | 18576 | 18654 | 0 | 0 | 0 | 0 | 0 | 18576 | 22291.2 | 0 | 0% | NO | 0 | 22291 | 0.16667 | 0 | 0 | 7058.88 | 15232.32 | 0 | 8% | 4.6% | 5.04% | -2.96% |  | 38.7 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23873 | FCAS Systems Engineering Support | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 53.2566 | 12.17% | 87.84% | -0.001751% | 0 | -9.72% | 156475 | 19036.25 | 137438.75 | 2580.69 | 0 | 0 | 0 | 0 | 16720.5 | 49 | 2315.75 | 89.73% | NO | 2315.75 | 20065 | -0.33333 | 0 | 20064.6 | 0 | 0 | 0 | 18% | 8.28% | 8.28% | -9.72% |  | 78.5 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23355 | Spirit Tooling Support 2023 | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-23 | 0 |  |  | 22.93% | 89.02% | 89.02% | 0 | -0.82% | 91800 | 21053.34 | 70746.66 | 0 | 0 | 0 | 0 | 0 | 18742.5 | 2773.01 | 2310.84 | 0% | NO | 2310.84 | 0 | 18742.5 | 0 | 0 | 0 | 0 | 0 | 20% | 19.18% | 0% | -20% |  | 44.46 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23839 | Stirling Dynamics - ST002-GFEM | Matthew Dodd | 0 | BAX | STIRLING DYNAMICS LTD | MPE | Level 3 | REIM |  |  |  | 10.3445 | 89.35% | 92.63% | 0.0009304% | 0 | -3.93% | 24057.34 | 21496.26 | 2561.08 | 247.58 | 2126.93 | 2126.93 | 0 | 0 | 19912.7 | 187.85 | 1583.56 | 639.6% | YES | 1583.56 | 23895 | 0.2 | 0 | 23895.24 | 0 | 0 | 0 | 6% | 2.07% | 2.07% | -3.93% |  | 43.77 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23902 | Typhoon Rear Fuselage | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -4 |  | 0% | 0% | 0 | 0.21% | 0 | 21782.81 | -21782.81 | 5445.7 | 0 | 0 | 45382.5 | 21782.81 | 0 | 27 | 21782.81 | 400% | YES | 21782.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 30.21% | 30.21% | 0.21% |  | 56.8 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23663 | Spirit Tooling Verification and Inspection | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  | 0.75 | 98.66% | 92.76% | -0.001534% | 0 | -6.39% | 23123.52 | 22813.83 | 309.69 | 412.92 | 0 | 0 | 0 | 0 | 21162.15 | 231.16 | 1651.68 | 400% | YES | 1651.68 | 25395 | -0.35 | 0 | 4831.16 | 12635.35 | 7928.06 | 0 | 11% | 4.61% | 4.82% | -6.18% |  | 34.41 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23351 | Spirit 2023 - Design Man Serv (KL) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 26.47% | 93.15% | 93.15% | 0 | 0.09% | 93840 | 24840 | 69000 | 0 | 0 | 0 | 0 | 0 | 23138 | 2042.4 | 1702 | 0% | NO | 1702 | 0 | 23138 | 0 | 0 | 0 | 0 | 0 | 26% | 26.09% | 0% | -26% |  | 46 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23356 | Spirit 2023 - Design Man Serv (AH) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX | 2023-08-09 | 1 |  |  |  | 76.66% | 0.001332% | 23018.4 | 0.48% | 0 | 25023.08 | -25023.08 | 0 | 0 | 0 | 25300 | 25023.08 | 19182 | 30027.7 | 5841.08 | 0% | NO | 5841.08 | 23018 | 0.33333 | 0 | 0 | 0 | 23018.4 | 23018.4 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P22884 | Spirit Shorts Config Eng | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 66.3% | 100.1% | 100.1% | 0 | 0.56% | 38976 | 25841.9 | 13134.1 | 0 | 0 | 0 | 0 | 0 | 25863.2 | 0 | -0.3 | 0% | NO | -0.3 | 0 | 25863.2 | 0 | 0 | 0 | 0 | 0 | 7% | 7.56% | 0% | -7% |  | 20.3 | [5 empty] | 21
1741 | 2024-06-05 23:29 | P23742 | Cyber Security Support | Hannah Mead | 0 | COZ | CHELTON LIMITED | DET | Level 3 | FIX | 2024-06-05 | 1 |  | 3.7333 | 94.91% | 105.4% | 0% | 0 | -0.96% | 27500 | 26100 | 1400 | 375 | 0 | 0 | 0 | 0 | 27500 | 158.34 | -1400 | -373.3% | NO | -1400 | 33000 | 0 | 0 | 33000 | 0 | 0 | 0 | 32% | 31.04% | 31.04% | -0.96% |  | 100 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23354 | Spirit 2023 - Design Man Serv (PC) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 27.97% | 99.36% | 99.36% | 0 | 0.48% | 93840 | 26248.98 | 67591.02 | 0 | 0 | 0 | 0 | 0 | 26082 | 200.38 | 166.98 | 0% | NO | 166.98 | 0 | 26082 | 0 | 0 | 0 | 0 | 0 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P22756 | A350 FLE Design Checker | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2022-03-23 | 1 |  |  | 68.39% | 119.7% | 119.7% | 0 | 16.46% | 34898.4 | 23867.15 | 11031.25 | 0 | 23867.15 | 24342.3 | 0 | 0 | 28571.1 | 0.06 | 0.05 | 0% | NO | 475.2 | 0 | 28571.1 | 0 | 0 | 0 | 0 | 0 | 0% | 16.46% | 0% | 0% |  | 0 | [5 empty] | 4704
1741 | 2024-06-05 23:29 | P23458 | Spirit Belfast Tooling Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-08-11 | 0 |  |  | 101.3% | 94.65% | 94.65% | 0 | 8.64% | 30384 | 30784.9 | -400.9 | 0 | 0 | 0 | 0 | 400.9 | 29139.1 | 1974.96 | 1645.8 | 0% | NO | 1645.8 | 0 | 29139.1 | 0 | 0 | 0 | 0 | 0 | 7% | 15.64% | 0% | -7% |  | 42.2 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23365 | GKN 777x Lip Skin Fixture | Steven Lawton | 0 | TOO | GKN AEROSPACE SERVICES LTD | MPE | Level 3 | FIX | 2023-10-12 | 0 |  |  | 41.91% | 113.2% | 113.2% | 0 | -9.26% | 79161.46 | 33175.67 | 45985.79 | 0 | 5109.88 | 5109.88 | 0 | 0 | 37544.22 | 0 | -4368.55 | 0% | NO | -4368.55 | 0 | 37544.22 | 0 | 0 | 0 | 0 | 0 | 22% | 12.74% | 0% | -22% |  | 56 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P22768 | MRB Onsite Support - Spirit Belfast | Trevor Knox | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2023-07-27 | 0 |  |  |  | 0% | 0% | 0 | -17.07% | 0 | 34614 | -34614 | 0 | 0 | 0 | 36800 | 34614 | 0 | 41536.8 | 34614 | 0% | NO | 34614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | -7.07% | 0% | -10% |  | 36 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23831 | Contract DM/00113 for maintenance, repair and post | Harry James Kellett | 0 | BXW | MOD | EES | Level 2 | FIX |  |  |  | 8.0592 | 76.58% | 15.9% | 15.9% | 0 | 16.55% | 46455.9 | 35577.14 | 10878.76 | 1349.85 | 343 | 813.17 | 0 | 0 | 5655.9 | 114.7 | 29921.24 | 2217% | YES | 30391.41 | 0 | 5655.9 | 0 | 0 | 0 | 0 | 0 | 34% | 50.55% | 50.55% | 16.55% |  | 80.26 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23821 | Supply of Safety Engineer | Dinna Elkhalifa | 0 | BXW | STIRLING DYNAMICS LTD | EES | Level NC | REIM |  |  |  |  | 106.6% | 49% | 49% | 0 | 45.1% | 34006.44 | 36247.77 | -2241.33 | 0 | 0 | 0 | 0 | 2241.33 | 17760.6 | 104.2 | 18487.17 | 0% | NO | 18487.17 | 0 | 17760.6 | 0 | 0 | 0 | 0 | 0 | 0% | 45.1% | 45.1% | 45.1% |  | 80.73 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23433 | Cavendish | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 5.1107 | 86.09% | 104.1% | 38.11% | 0 | -0.43% | 42240 | 36365.2 | 5874.8 | 1149.5 | 0 | 0 | 0 | 0 | 37865.6 | 98.87 | -1500.4 | -130.5% | NO | -1500.4 | 28808 | 13858.9333 | 0 | 28807.68 | 0 | 0 | 0 | 7% | 6.57% | 6.51% | -0.49% |  | 46.59 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23842 | Tranche 1 Evolution Package Step 2 | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 15.4064 | 32.85% | 0% | 0% | 0 | -10.88% | 112526.3 | 36959.59 | 75566.71 | 4904.89 | 1000 | 1000 | 0 | 0 | 0 | 77 | 36959.59 | 753.5% | YES | 36959.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31% | 20.12% | 20.12% | -10.88% |  | 56.15 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23347 | WoT Fixed Leading Edge - Industrial 2023 | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 120.5% | 82.92% | 39.34% | 0 | -0.38% | 31034.12 | 37389.34 | -6355.22 | 0 | 0 | 0 | 10500 | 6355.22 | 31001.86 | 27214.54 | 6387.48 | 0% | NO | 6387.48 | 19550 | 14710.1933 | 0 | 19549.56 | 0 | 0 | 0 | 7% | 6.62% | 7.01% | 0.01% |  | 32.26 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23338 | Spirit 2023 - Blair Hainey | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 61.49% | 93.51% | 46.65% | 0 | -2.99% | 62893.71 | 38673.72 | 24219.99 | -287.32 | 0 | 0 | 0 | 0 | 36165.24 | 253.24 | 2508.48 | -873.1% | NO | 2508.48 | 21747 | 18042.74 | 0 | 21747.46 | 0 | 0 | 0 | 7% | 4.01% | -5.03% | -12.03% |  | 16.57 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23724 | GKN S McConnell 2024 | Matthew Tweed | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  | 6.7576 | 77.7% | 96.27% | 0.00093% | 0 | 0.95% | 49820 | 38710.17 | 11109.83 | 1644.06 | 0 | 0 | 0 | 0 | 37265.36 | 156.43 | 1444.81 | 87.88% | NO | 1444.81 | 44718 | 0.36 | 0 | 8369.76 | 19130.88 | 17217.79 | 0 | 19% | 19.95% | 19.95% | 0.95% |  | 49.63 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23051 | Spirit Shorts A350 PAX Door | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3A | REIM |  |  |  |  | 205.9% | 105.4% | 105.4% | 0 | -0.63% | 18216 | 37513 | -19297 | 0 | 0 | 0 | 0 | 19297 | 39537 | 0 | 0 | 0% | NO | 0 | 0 | 39537 | 0 | 0 | 0 | 0 | 0 | 30% | 29.37% | 0% | -30% |  | 46 | [5 empty] | 2024
1741 | 2024-06-05 23:29 | P23651 | PMO Spirit | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 7.8815 | 80.57% | 85.36% | 59.07% | 0 | -19.39% | 49284 | 39708 | 9576 | 1215 | 0 | 0 | 0 | 0 | 33894 | 99.12 | 5814 | 478.5% | YES | 5814 | 12528 | 23454 | 0 | 12528 | 0 | 0 | 0 | 43% | 23.61% | 23.1% | -19.9% |  | 36 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P22752 | Tooling WoT - 2021 (Spirit) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | REIM | 2023-05-03 | 0 |  |  | 101.1% | 74.02% | 74.02% | 0 | -8.5% | 41525.1 | 41982.28 | -457.18 | 0 | 0 | 0 | 0 | 457.18 | 31076.1 | 13087.42 | 10906.18 | 0% | NO | 10906.18 | 0 | 31076.1 | 0 | 0 | 0 | 0 | 0 | 0% | -8.5% | 0% | 0% |  | 39.09 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23874 | Environmental Engineering (Sea Venom/ANL) | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | -7.919 |  | 0% | 0% | 0 | -0.86% | 0 | 42193.75 | -42193.75 | 5328.19 | 0 | 0 | 49199 | 42193.75 | 0 | 56 | 42193.75 | 791.9% | YES | 42193.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 19.14% | 19.14% | -0.86% |  | 78.5 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23891 | A220 FLE Support | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -4 |  | 0% | 0% | 0 | 7.47% | 0 | 45821.76 | -45821.76 | 11455.44 | 0 | 0 | 46656.96 | 45821.76 | 0 | 66 | 45821.76 | 400% | YES | 45821.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 14.47% | 14.47% | 7.47% |  | 50.16 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23339 | Spirit 2023 - Stewart Russell | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 64.51% | 100% | 100% | 0 | 0.62% | 72766.8 | 46941.72 | 25825.08 | 0 | 0 | 0 | 0 | 0 | 46941.74 | 0 | -0.02 | 0% | NO | -0.02 | 0 | 46941.74 | 0 | 0 | 0 | 0 | 0 | 7% | 7.62% | 0% | -7% |  | 35.67 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23811 | Spirit T300 MRB Concessions | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -12.7211 |  | 0% | 0% | 0 | -7.33% | 0 | 50024.39 | -50024.39 | 3932.38 | 0 | 0 | 50000 | 50024.39 | 0 | 110.49 | 50024.39 | 1272% | YES | 50024.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21% | 13.67% | 13.67% | -7.33% |  | 47.48 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P22760 | SA Leading Edge Transport Media ('A' Frames) | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-11-15 | 1 |  |  | 85.99% | 110.7% | 116.3% | -3082.8 | 3.97% | 53480.8 | 45985.5 | 7495.3 | 0 | 42804 | 42804 | 0 | 0 | 50911.8 | 0 | -0.3 | 0% | NO | -0.3 | -3083 | 53480.9667 | 0 | 0 | 0 | -3082.8 | -3082.8 | 6% | 9.97% | 0% | -6% |  | 42 | [5 empty] | 4926
1741 | 2024-06-05 23:29 | P23823 | EXP-034 Spear 3 Test Equip Requirement Authority | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 9.0435 | 62.88% | 92.38% | 57.37% | 0 | 0.06% | 85825 | 53968.5 | 31856.5 | 3522.59 | 1000 | 1000 | 0 | 0 | 49858.26 | 45.19 | 4110.24 | 116.7% | NO | 4110.24 | 22677 | 30960.76 | 0 | 22676.56 | 0 | 0 | 0 | 14% | 14.06% | 14.06% | 0.06% |  | 94.25 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23740 | Phase 2 - EJ200 ESS EHM Platform Migration | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 3 | FIX |  |  |  | 25.853 | 24.89% | 172.2% | 57.4% | 0 | 17.49% | 175971 | 43797.5 | 132173.5 | 5112.5 | 0 | 0 | 0 | 0 | 75417 | 78.6 | -19619.5 | -383.8% | NO | -19619.5 | 60334 | 25138.6667 | 0 | 0 | 30166.8 | 30166.8 | 0 | 28% | 45.49% | 45.49% | 17.49% |  | 42.36 | [5 empty] | 12000
1741 | 2024-06-05 23:29 | P23349 | Spirit 2023 - Stress Approve Man Serv (SB) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 58.24% | 80.05% | 80.05% | 0 | -0.29% | 97920 | 57024 | 40896 | 0 | 0 | 0 | 0 | 0 | 45648 | 13651.2 | 11376 | 0% | NO | 11376 | 0 | 45648 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23642 | MRB Belfast Support | Paul Watson | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -40.9973 |  | 0% | 0% | 0 | -44.55% | 0 | 58369.97 | -58369.97 | 1423.75 | 3718.34 | 3718.34 | 53900 | 58369.97 | 0 | 240.37 | 58369.97 | 4100% | YES | 58369.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22% | -22.55% | -24.68% | -46.68% |  | 38.52 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23598 | MRB Onsite support | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 25.7093 | 45.39% | 0% | 0% | 0 | -9.82% | 133056 | 60395.17 | 72660.83 | 2826.25 | 8736.42 | 14079.58 | 0 | 0 | 0 | 150.28 | 60395.17 | 2137% | YES | 65738.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 18.18% | 18.45% | -9.55% |  | 42.5 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23760 | EXP-033 Systems Engineering Support | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 29.9415 | 43.22% | 96.81% | 72.88% | 0 | -0.02% | 142300 | 61504.75 | 80795.25 | 2698.44 | 0 | 0 | 0 | 0 | 59542.25 | 42.97 | 1962.5 | 72.73% | NO | 1962.5 | 17663 | 44823.0833 | 0 | 17662.5 | 0 | 0 | 0 | 29% | 28.98% | 28.98% | -0.02% |  | 78.5 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23106 | ME Support to NPD - Bobby Haggart | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  |  | 95.79% | 97.03% | 97.03% | 0 | 0.3% | 65675 | 62912.11 | 2762.89 | 0 | 0 | 0 | 0 | 0 | 61042.75 | 2243.24 | 1869.36 | 0% | NO | 1869.36 | 0 | 61042.75 | 0 | 0 | 0 | 0 | 0 | 15% | 15.3% | 0% | -15% |  | 35.65 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P22967 | Spirit 2022 - Channapa Laxmeshwar | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2023-01-26 | 2 |  |  | 69.69% | 121.3% | 121.3% | 0 | 9.53% | 75159.1 | 52376.15 | 22782.95 | 0 | 52376.15 | 54898.1 | 0 | 0 | 63508.8 | 0.42 | 0.35 | 0% | NO | 2522.3 | 0 | 63508.8 | 0 | 0 | 0 | 0 | 0 | 8% | 17.53% | 0% | -8% |  | 0 | [5 empty] | 11133
1741 | 2024-06-05 23:29 | P23193 | Spirit Shorts Stephen Greer | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -12.1532 | 114.5% | 86.28% | 86.28% | 0 | 8.81% | 61472 | 70369.97 | -8897.97 | 732.15 | 0 | 0 | 10878 | 8897.97 | 60712.78 | 98.8 | 9657.19 | 1319% | YES | 9657.19 | 0 | 60712.78 | 0 | 0 | 0 | 0 | 0 | 23% | 31.81% | 34.03% | 11.03% |  | 35.2 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23877 | Strategic Enablement | Owain Jones | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -16.99% | 0 | 71017.3 | -71017.3 | 0 | 4000 | 4000 | 67200 | 71017.3 | 0 | 120.54 | 71017.3 | 0% | NO | 71017.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 1.01% | 1.01% | -16.99% |  | 42 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23341 | Spirit 2023 - Tom McFarlane | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 25.8291 | 68.53% | 92.89% | 57.77% | 7110.19 | -0.01% | 108666.4 | 74472.52 | 34193.88 | 1323.85 | 0 | 0 | 0 | 0 | 69177.13 | 202.95 | 5295.39 | 400% | YES | 5295.39 | 31389 | 43019.63 | 0 | 5886.13 | 4683.36 | 20819.67 | 7110.19 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23600 | MBDA EXP-EE-023 Bristone Certification | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM | 2024-05-31 | 0 |  |  | 59.65% | 100% | 100% | 0 | 0.4% | 126600 | 75517 | 51083 | 0 | 0 | 0 | 0 | 0 | 75517 | 0 | 0 | 0% | NO | 0 | 0 | 75517 | 0 | 0 | 0 | 0 | 0 | 41% | 41.4% | 0% | -41% |  | 78.5 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23080 | Spirit Shorts DManagement Cairan Cullen | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 827.3176 | 51.18% | 99.92% | 96.91% | 0 | -1.31% | 149600 | 76564.4 | 73035.6 | 88.28 | 0 | 0 | 0 | 0 | 76500.2 | 111.11 | 64.2 | 72.72% | NO | 64.2 | 2761 | 74199.3667 | 0 | 2760.6 | 0 | 0 | 0 | 24% | 22.69% | 13.03% | -10.97% |  | 44.38 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P22505 | Spirit MRB Engineering Support 2021 | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 1 |  |  | 91.17% | 100% | 95.78% | 4020.48 | 21.2% | 87110.4 | 79414.95 | 7695.45 | 0 | 0 | 0 | 0 | 0 | 79414.95 | 4020.48 | 0 | 0% | NO | 0 | 4020 | 76064.95 | 0 | 0 | 0 | 4020.48 | 4020.48 | 0% | 21.2% | 0% | 0% |  | 41.88 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P22885 | ME Support (Baxi) | Trevor Knox | 0 | HUV | BAXI HEATING UK LIMITED | ME | Level 3 | FIX | 2023-01-12 | 0 |  |  | 68.78% | 108.7% | 108.7% | 0 | 13.05% | 106632.96 | 73340.24 | 33292.72 | 0 | 0 | 0 | 0 | 0 | 79748.12 | 1531.35 | 1276.12 | 0% | NO | 1276.12 | 0 | 79748.12 | 0 | 0 | 0 | 0 | 0 | 15% | 28.05% | 0% | -15% |  | 44.37 | [5 empty] | 7684
1741 | 2024-06-05 23:29 | P22965 | Spirit 2022 - Design Man Serv (AH) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 106.7% | 96.66% | 96.66% | 0 | 3.14% | 80079.56 | 85441.32 | -5361.76 | 0 | 0 | 0 | 0 | 5361.76 | 82588.96 | 3422.84 | 2852.36 | 0% | NO | 2852.36 | 0 | 82588.96 | 0 | 0 | 0 | 0 | 0 | 14% | 17.14% | 0% | -14% |  | 42.44 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23523 | Applique Armour Support | Dushan Fernando | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-18 | 1 |  |  | 72.43% | 138.1% | 98.47% | 40680 | 3.42% | 118200 | 85606.5 | 32593.5 | 0 | 0 | 0 | 0 | 0 | 118200 | 1567.8 | -32593.5 | 0% | NO | -32593.5 | 40680 | 84300 | 0 | 0 | 0 | 40680 | 40680 | 25% | 28.42% | 0% | -25% |  | 64.29 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P22964 | Spirit 2022 - MRB Man Serv (JC) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 100.6% | 97.95% | 97.95% | 0 | 1.91% | 85435.2 | 85960.26 | -525.06 | 0 | 0 | 0 | 0 | 525.06 | 84199.74 | 2112.62 | 1760.52 | 0% | NO | 1760.52 | 0 | 84199.74 | 0 | 0 | 0 | 0 | 0 | 16% | 17.91% | 0% | -16% |  | 42.69 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P22963 | Spirit 2022 - Design Man Serv (PC) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 108.6% | 104% | 104% | 0 | 3.18% | 80079.56 | 86926.74 | -6847.18 | 0 | 0 | 0 | 0 | 6847.18 | 90389.95 | 0 | -3463.21 | 0% | NO | -3463.21 | 0 | 90389.95 | 0 | 0 | 0 | 0 | 0 | 13% | 16.18% | 0% | -13% |  | 42.39 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23079 | Spirit Shorts Nomenclature | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -9.9699 | 106.5% | 82.99% | 82.99% | 0 | 15.2% | 88455 | 94215.6 | -5760.6 | 577.8 | 0 | 0 | 5136 | 5760.6 | 78185.2 | 174.79 | 16030.4 | 2774% | YES | 16030.4 | 0 | 78185.2 | 0 | 0 | 0 | 0 | 0 | 7% | 22.2% | 25.23% | 18.23% |  | 30.85 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23438 | A220 Spirit Shorts DTC - Stephen Corry | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 1.1291 | 98.37% | 68.31% | 68.31% | 0 | -7.1% | 95928.4 | 94364.4 | 1564 | 1385.18 | 0 | 0 | 0 | 0 | 64459.8 | 173.21 | 29904.6 | 2159% | YES | 29904.6 | 0 | 64459.8 | 0 | 0 | 0 | 0 | 0 | 23% | 15.9% | 17.03% | -5.97% |  | 49.92 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23375 | GKN Jaap Peters NL 2023 | Steven Lawton | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2024-03-01 | 1 |  |  | 93.37% | 105.3% | 97.18% | 0 | -15.93% | 97123.22 | 90686.41 | 6436.81 | 0 | 90686.41 | 90686.41 | 0 | 0 | 95456.72 | 7688.92 | -920.31 | 0% | NO | -920.31 | 8793 | 88129.22 | 0 | 0 | 0 | 8793.29 | 0 | 20% | 4.07% | 0% | -20% |  | 0 | [5 empty] | 3850
1741 | 2024-06-05 23:29 | P23171 | Spirt Shorts Weights Eng | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 69.18% | 141.4% | 133.5% | 0 | 13.12% | 103113.14 | 71329.32 | 31783.82 | 0 | 71329.32 | 85975.13 | 0 | 0 | 100870.18 | 0.27 | -5610.86 | 0% | NO | 9034.95 | 6733 | 95259.3467 | 0 | 0 | 6733.3 | 0 | 0 | 12% | 25.12% | 47.26% | 35.26% |  | 0 | [5 empty] | 23930
1741 | 2024-06-05 23:29 | P23340 | Spirit 2023 - John Cole | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 35.3514 | 65.34% | 94% | 64.07% | 0 | -0.01% | 150129.72 | 98097.48 | 52032.24 | 1471.86 | 0 | 0 | 0 | 0 | 92210.04 | 169.38 | 5887.44 | 400% | YES | 5887.44 | 35229 | 62852.54 | 0 | 8831.16 | 6826.25 | 19571.76 | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 39.78 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23583 | Castalla - Test Rig Design | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -0.057011 | 100% | 92.54% | 67.12% | 0 | -26.99% | 100520 | 100538.5 | -18.5 | 324.5 | 0 | 0 | 0 | 18.5 | 93036.5 | 224.89 | 7502 | 2312% | YES | 7502 | 30665 | 67482.3333 | 0 | 30665.28 | 0 | 0 | 0 | 41% | 14.01% | 14.71% | -26.29% |  | 42.79 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23700 | IPDT Leads | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 12.5614 | 59.5% | 24.75% | 24.75% | 0 | -1.72% | 169263.9 | 100716.68 | 68547.22 | 5456.99 | 0 | 0 | 0 | 0 | 24932.12 | 113.69 | 75784.56 | 1389% | YES | 75784.56 | 0 | 24932.12 | 0 | 0 | 0 | 0 | 0 | 26% | 24.28% | 23.09% | -2.91% |  | 49.91 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23336 | Spirit 2023 - Neil Rampling | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 23.7443 | 75.38% | 94.5% | 47.42% | 21586.03 | -0.01% | 133901.52 | 100940.6 | 32960.92 | 1388.16 | 0 | 0 | 0 | 0 | 95387.98 | 261.55 | 5552.62 | 400% | YES | 5552.62 | 57031 | 47862.1467 | 0 | 8238.46 | 7259.21 | 41532.89 | 21586.03 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23342 | Spirit 2023 - Channapa Laxmeshwar | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 17.4694 | 61.9% | 102.1% | 66.35% | 0 | -4.18% | 158696.7 | 98230.79 | 60465.91 | 3461.24 | 98230.79 | 108671.94 | 0 | 0 | 100331.3 | 91.4 | 749.49 | 21.65% | NO | 11190.64 | 42185 | 65177.1333 | -403.68 | 10092 | 22807.92 | 9688.32 | 0 | 7% | 2.82% | 0% | -7% |  | 0 | [5 empty] | 2850
1741 | 2024-06-05 23:29 | P23345 | Spirit 2023- Jonathan Escosio | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 28.208 | 70.46% | 89.69% | 54.64% | 7150.18 | -0.56% | 151941.24 | 107051.89 | 44889.35 | 1591.37 | 0 | 0 | 0 | 0 | 96014.16 | 217.19 | 11037.73 | 693.6% | YES | 11037.73 | 45020 | 58497.4933 | 0 | 16773.9 | 16361 | 11884.76 | 7150.18 | 7% | 6.44% | 16.71% | 9.71% |  | 43.01 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23465 | A220 ToW Design Offload (Wing) | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 59.6732 | 43.23% | 86.07% | 74.62% | 0 | -6.23% | 249700 | 107952.3 | 141747.7 | 2375.4 | 0 | 0 | 0 | 0 | 92918.8 | 96.58 | 15033.5 | 632.9% | YES | 15033.5 | 14843 | 80549.6333 | 0 | 0 | 14843.04 | 0 | 0 | 20% | 13.77% | 11.23% | -8.77% |  | 42.8 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23560 | NJEWCS TAF202302 SM | Natalie Sinclair | 0 | COB | CHELTON LIMITED | EES | Level 2 | FIX |  |  |  | 32.6497 | 57.99% | 72.04% | 72.04% | 0 | 9.82% | 191500 | 111048.21 | 80451.79 | 2464.09 | 0 | 0 | 0 | 0 | 80000 | 92.14 | 31048.21 | 1260% | YES | 31048.21 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 30% | 39.82% | 39.49% | 9.49% |  | 73.01 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23744 | Model Factory | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 27.2406 | 40.94% | 104.6% | 41.64% | 0 | 9.87% | 262300 | 107382.75 | 154917.25 | 5687 | 0 | 0 | 0 | 0 | 112290 | 97.08 | 92.75 | 1.631% | NO | 92.75 | 81089 | 44715.8333 | 0 | 27429.6 | 27429.6 | 26229.6 | 0 | 28% | 37.87% | 37.87% | 9.87% |  | 51.09 | [5 empty] | 5000
1741 | 2024-06-05 23:29 | P23551 | Ian Berry 2023 H2 | Natalie Sinclair | 0 | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  | 10.5358 | 78.13% | 59.27% | 59.27% | 0 | 13.81% | 145153.92 | 113404.41 | 31749.51 | 3013.5 | 0 | 0 | 0 | 0 | 67217.49 | 135.15 | 46186.92 | 1533% | YES | 46186.92 | 0 | 67217.49 | 0 | 0 | 0 | 0 | 0 | 22% | 35.81% | 37.71% | 15.71% |  | 78.02 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23586 | Project Management Support | Dushan Fernando | 0 | BDX | MBDA UK LIMITED | MPE | Level NC | REIM |  |  |  | 14.1292 | 73.03% | 96.18% | 84.03% | 0 | -27.07% | 160000 | 116848.17 | 43151.83 | 3054.08 | 1972 | 1972 | 0 | 0 | 112383.86 | 46.99 | 4464.31 | 146.2% | YES | 4464.31 | 17040 | 98183.86 | 0 | 17040 | 0 | 0 | 0 | 49% | 21.93% | 20.66% | -28.34% |  | 80 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23729 | Honda Tooling | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | FIX |  |  |  | -0.71433 | 104.8% | 63.07% | 27.24% | 0 | 2.69% | 113610 | 119091 | -5481 | 7672.88 | 0 | 0 | 21000 | 5481 | 75106.5 | 95.28 | 43984.5 | 573.2% | YES | 43984.5 | 51194 | 32444.8333 | 0 | 51193.8 | 0 | 0 | 0 | 10% | 12.69% | 12.69% | 2.69% |  | 42 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P22736 | WoT Fixed Leading Edge - Industrial | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 106.7% | 93.42% | 91.32% | 3019.54 | 0.01% | 112196.27 | 119668.47 | -7472.2 | 0 | 0 | 0 | 0 | 7472.2 | 111796.68 | 12465.69 | 7871.79 | 0% | NO | 7871.79 | 3020 | 109280.0133 | 0 | 0 | 0 | 3019.54 | 3019.54 | 7% | 7.01% | 0% | -7% |  | 32.26 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P22918 | Spirit Shorts Graduates | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 9.9685 | 93.6% | 87.72% | 87.72% | 0 | 9.52% | 130000 | 121681.69 | 8318.31 | 834.46 | 0 | 0 | 19800 | 0 | 106734.95 | 113.9 | 14946.74 | 1791% | YES | 14946.74 | 0 | 106734.95 | 0 | 0 | 0 | 0 | 0 | 7% | 16.52% | 17.24% | 10.24% |  | 23.34 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23353 | Spirit 2023 - MRB Man Serv (JC) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  | 23.2988 | 68.24% | 54.77% | 54.77% | 0 | 9.26% | 183600 | 125280 | 58320 | 2503.13 | 0 | 0 | 0 | 0 | 68615.25 | 247.76 | 56664.75 | 2264% | YES | 56664.75 | 0 | 68615.25 | 0 | 0 | 0 | 0 | 0 | 7% | 16.26% | 12.52% | 5.52% |  | 45 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P22861 | WoT FLE Lifting & Handling Tools | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2023-06-14 | 1 |  |  | 65.17% | 101.6% | 101.6% | 0 | 12.01% | 173987.21 | 113381.75 | 60605.46 | 0 | 50078 | 58423.58 | 0 | 0 | 115203.5 | 12813.9 | 10678.25 | 0% | NO | 19023.83 | 0 | 115203.5 | 0 | 0 | 0 | 0 | 0 | 1% | 13.01% | 0% | -1% |  | 45 | [5 empty] | 12500
1741 | 2024-06-05 23:29 | P23664 | Tempest Composites WP3 | Philip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -44.8702 | 105.9% | 66.38% | 66.38% | 0 | -5.14% | 122455.49 | 129719.98 | -7264.49 | 161.9 | 0 | 0 | 14830.4 | 7264.49 | 86110.38 | 180.64 | 43609.6 | 26936% | YES | 43609.6 | 0 | 86110.38 | 0 | 0 | 0 | 0 | 0 | 37% | 31.86% | 33.17% | -3.83% |  | 60.89 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23545 | Ultra CSS continuation 2023 H2 | Natalie Sinclair | 0 | ULT | ULTRA SONAR SYSTEMS LIMITED | EES | Level NC | REIM |  |  |  | 15.0535 | 75.43% | 93.83% | 56.83% | 0 | 14.17% | 176000 | 132754.4 | 43245.6 | 2872.8 | 0 | 0 | 0 | 0 | 124560.8 | 164.51 | 8193.6 | 285.2% | YES | 8193.6 | 58932 | 75450.8 | 34819.2 | 24112.32 | 0 | 0 | 0 | 11% | 25.17% | 25% | 14% |  | 80 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23810 | Strategic Enablement | Owain Jones | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -20.63% | 0 | 133694.4 | -133694.4 | 0 | 0 | 0 | 134000 | 133694.4 | 0 | 19311.41 | 133694.4 | 0% | NO | 133694.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | -2.63% | -2.63% | -20.63% |  | 42 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P22883 | Spirit Shorts Evtol PMO C. Hatton | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 160.4447 | 72.45% | 101.1% | 80.93% | 0 | -10.87% | 185800 | 134618.15 | 51181.85 | 319 | 0 | 0 | 0 | 0 | 136116.73 | 189.28 | -1498.58 | -469.8% | NO | -1498.58 | 32604 | 108946.73 | 0 | 32604 | 0 | 0 | 0 | 26% | 15.13% | 22.96% | -3.04% |  | 37.41 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23588 | BAE Typhoon MRB MC Shop Concessions | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 10.9801 | 78.84% | 81.24% | 72.54% | 14399.76 | -4.07% | 175060.5 | 138017.88 | 37042.62 | 3373.6 | 0 | 0 | 0 | 0 | 112121.71 | 112.57 | 25896.17 | 767.6% | YES | 25896.17 | 14400 | 100121.71 | 0 | 0 | 0 | 14399.76 | 14399.76 | 31% | 26.93% | 27.66% | -3.34% |  | 55.8 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23282 | Tooling Support (MBDA) | Dushan Fernando | 0 | BDV | MBDA UK LIMITED | ME | Level NC | REIM |  |  |  | 31.2759 | 70.73% | 98.58% | 91.9% | 0 | -7.42% | 195672.4 | 138404.05 | 57268.35 | 1831.07 | 0 | 0 | 0 | 0 | 136432.63 | 44.05 | 1971.42 | 107.7% | NO | 1971.42 | 11095 | 127186.7967 | 0 | 11095 | 0 | 0 | 0 | 30% | 22.58% | 30.37% | 0.37% |  | 49.74 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23270 | Shorts Project X | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 2.1198 | 97.52% | 93.17% | 83.58% | 0 | 0.3% | 142248 | 138723.2 | 3524.8 | 1662.78 | 0 | 0 | 0 | 0 | 129246.58 | 95.89 | 9476.62 | 569.9% | YES | 9476.62 | 15963 | 115944.08 | 0 | 7981.34 | 7981.34 | 0 | 0 | 13% | 13.3% | 10.99% | -2.01% |  | 45.3 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23533 | External Stowage Design and Detail Support | Dushan Fernando | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 1 |  |  | 102.4% | 97.65% | 73.24% | 42000 | 3.33% | 140000 | 143368.75 | -3368.75 | 0 | 0 | 0 | 3369 | 3368.75 | 140000 | 41999.7 | -0.25 | 0% | NO | -0.25 | 42000 | 105000 | 0 | 0 | 0 | 42000 | 42000 | 27% | 30.33% | 0% | -27% |  | 60.04 | [5 empty] | -3369
1741 | 2024-06-05 23:29 | P22954 | Technical Support Step 1 | Owain Jones | 0 | HUV | HUARUI SPIRIT AEROSPACE MANUFACT | ME | Level 2 | REIM |  |  |  |  | 94.81% | 58.01% | 58.01% | 0 | 0.31% | 155501.18 | 147431.58 | 8069.6 | 0 | 23043 | 23043 | 0 | 0 | 85525.49 | 61906.09 | 61906.09 | 0% | NO | 61906.09 | 0 | 85525.49 | 0 | 0 | 0 | 0 | 0 | 30% | 30.31% | 0% | -30% |  | 60.79 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23386 | Software Development - BMS | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 98.78% | 100% | 100% | 0 | 4.31% | 149650 | 147823.35 | 1826.65 | 0 | 0 | 0 | 0 | 0 | 147823.35 | 0 | 0 | 0% | NO | 0 | 0 | 147823.35 | 0 | 0 | 0 | 0 | 0 | 18% | 22.31% | 22.61% | 4.61% |  | 78.5 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23437 | Embedded Software Engineer | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 98.73% | 100% | 96.08% | 6970.8 | -6.29% | 150150 | 148239.36 | 1910.64 | 0 | 737.86 | 737.86 | 0 | 0 | 148239.36 | 182 | 0 | 0% | NO | 0 | 6971 | 142430.1933 | 0 | 0 | 0 | 6970.8 | 6970.8 | 22% | 15.71% | 16.24% | -5.76% |  | 78.5 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23352 | Spirit 2023 - Stress Approve Man Serv (CC) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  | 7.2752 | 77% | 46.36% | 46.36% | 0 | 4.51% | 195840 | 150792 | 45048 | 6192 | 0 | 0 | 0 | 0 | 69912 | 184.96 | 80880 | 1306% | YES | 80880 | 0 | 69912 | 0 | 0 | 0 | 0 | 0 | 7% | 11.51% | 4.69% | -2.31% |  | 48 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P22440 | Spirit Managed Service - F&DT and Static Approval | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 3 |  |  | 88.56% | 92.56% | 92.56% | 0 | 11.51% | 173500 | 153656.25 | 19843.75 | 0 | 52115 | 55720 | 0 | 0 | 142225.12 | 13717.36 | 11431.13 | 0% | NO | 15036.13 | 0 | 142225.12 | 0 | 0 | 0 | 0 | 0 | 0% | 11.51% | 0% | 0% |  | 44.73 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23550 | Tempest Composites | Philip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -11.7941 | 103.8% | 96.37% | 96.37% | 0 | 5.1% | 149494.92 | 155127.88 | -5632.96 | 477.61 | 0 | 0 | 4209.4 | 5632.96 | 149494.92 | 97.06 | 5632.96 | 1179% | YES | 5632.96 | 0 | 149494.92 | 0 | 0 | 0 | 0 | 0 | 26% | 31.1% | 33.54% | 7.54% |  | 61.64 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P22982 | Spirit 2022 - Hugh Sloan | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 74.2406 | 64.61% | 97.05% | 79.4% | 8217.17 | -0.8% | 247473 | 159890.62 | 87582.38 | 1179.71 | 0 | 0 | 0 | 0 | 155171.78 | 214.45 | 4718.84 | 400% | YES | 4718.84 | 33869 | 126947.6133 | 0 | 5747.76 | 5364.58 | 22756.88 | 8217.17 | 7% | 6.2% | 0.68% | -6.32% |  | 35.48 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23753 | Tempest Composites Maturation | Philip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | -3.6456 | 130.4% | 63.74% | 42.61% | 0 | -5.31% | 127848.45 | 166683.8 | -38835.35 | 10652.54 | 0 | 0 | 49419.2 | 38835.35 | 106238.78 | 68.45 | 60445.02 | 567.4% | YES | 60445.02 | 42256 | 71025.4467 | 0 | 42255.9 | 0 | 0 | 0 | 29% | 23.69% | 23.69% | -5.31% |  | 64.17 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23508 | Verification and Validation | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM | 2024-05-31 | 0 |  |  | 80.77% | 100% | 100% | 0 | 10.77% | 212950 | 171993.5 | 40956.5 | 0 | 0 | 0 | 0 | 0 | 171993.53 | 0 | -0.03 | 0% | NO | -0.03 | 0 | 171993.53 | 0 | 0 | 0 | 0 | 0 | 24% | 34.77% | 33.6% | 9.6% |  | 78.5 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23822 | FCASW Requirements Management | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 40.0759 | 29.86% | 95.96% | -4.685e-05% | 0 | -2.31% | 595703 | 177881 | 417822 | 10425.78 | 0 | 0 | 0 | 0 | 170698.25 | 114.48 | 7182.75 | 68.89% | NO | 7182.75 | 204838 | -0.083333 | 0 | 204837.9 | 0 | 0 | 0 | 17% | 14.69% | 14.69% | -2.31% |  | 78.5 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23518 | Systems Engineering support to FCAS | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 5.1348 | 92.87% | 88.41% | 88.41% | 0 | -6.58% | 193736.8 | 179931.25 | 13805.55 | 2688.63 | 3927.4 | 3927.4 | 0 | 0 | 159084.68 | 60.64 | 20846.57 | 775.4% | YES | 20846.57 | 0 | 159084.68 | 0 | 0 | 0 | 0 | 0 | 30% | 23.42% | 3.5% | -26.5% |  | 69.1 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23464 | A220 Project X Design Offload | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 118.1628 | 55.11% | 94.65% | 81.11% | 27862.8 | -9.75% | 332340 | 183147.7 | 149192.3 | 1262.6 | 0 | 0 | 0 | 0 | 173346.5 | 152.33 | 9801.2 | 776.3% | YES | 9801.2 | 29763 | 148544 | 0 | 0 | 1900.32 | 27862.8 | 27862.8 | 26% | 16.25% | 13.56% | -12.44% |  | 42.87 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23667 | Safety Systems Engineer | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 54.3241 | 48.2% | 98.17% | 87.84% | 0 | -11.23% | 398000 | 191840 | 206160 | 3795 | 0 | 0 | 0 | 0 | 188320 | 41.85 | 3520 | 92.75% | NO | 3520 | 23760 | 168520 | 0 | 23760 | 0 | 0 | 0 | 47% | 35.77% | 29.32% | -17.68% |  | 110 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23421 | A220 DTC | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 7.0223 | 88.99% | 81.86% | 62.25% | 0 | -28.14% | 217089.12 | 193183.89 | 23905.23 | 3404.21 | 0 | 0 | 0 | 0 | 158146.02 | 124.12 | 35037.87 | 1029% | YES | 35037.87 | 45461 | 120261.8533 | 0 | 33057.86 | 12403.44 | 0 | 0 | 29% | 0.86% | 4.96% | -24.04% |  | 45.88 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23008 | Spirit Shorts Project Rachel | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 68.49% | 91.32% | 91.32% | 0 | -9.7% | 286960 | 196531.2 | 90428.8 | 0 | 0 | 0 | 0 | 0 | 179472.8 | 20470.08 | 17058.4 | 0% | NO | 17058.4 | 0 | 179472.8 | 0 | 0 | 0 | 0 | 0 | 15% | 5.3% | 0.31% | -14.69% |  | 46.04 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23019 | EXP034-B Actuator Development | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 103.1% | 89.91% | 89.91% | 0 | -16.68% | 215541.2 | 222215.54 | -6674.34 | 0 | 12297.9 | 12297.9 | 0 | 6674.34 | 199796.76 | 477.34 | 397.78 | 0% | NO | 397.78 | 0 | 199796.76 | 0 | 0 | 0 | 0 | 0 | 34% | 17.32% | 79.64% | 45.64% |  | 58.45 | [5 empty] | -22021
1741 | 2024-06-05 23:29 | P23242 | Physical Architecture & System Engineering Support | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 29.6152 | 74.31% | 98.64% | 92.4% | 0 | 6.48% | 305459 | 226996.96 | 78462.04 | 2649.38 | 775.55 | 775.55 | 0 | 0 | 223914.55 | 42.63 | 2728.41 | 103% | NO | 2728.41 | 17003 | 209745.3833 | 0 | 17003.1 | 0 | 0 | 0 | 15% | 21.48% | 7.35% | -7.65% |  | 78.23 | [5 empty] | -354
1741 | 2024-06-05 23:29 | P23506 | ASTER Mid-Life Refurbishment Project Manager | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 30.2428 | 69.9% | 97.48% | 90.55% | 0 | 1.01% | 326900 | 228505.37 | 98394.63 | 3253.49 | 3830.37 | 3830.37 | 0 | 0 | 222751.41 | 39.58 | 5753.96 | 176.9% | YES | 5753.96 | 19008 | 206911.41 | 0 | 19008 | 0 | 0 | 0 | 25% | 26.01% | 26.13% | 1.13% |  | 110 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23505 | EXP-022 Meteor TBUS T&E support | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 4.1043 | 93.49% | 98.47% | 89.71% | 0 | -1.55% | 246744.4 | 230683.44 | 16060.96 | 3913.22 | 0 | 0 | 0 | 0 | 227157.63 | 45.87 | 3525.81 | 90.1% | NO | 3525.81 | 24254 | 206945.9633 | 0 | 24254.1 | 0 | 0 | 0 | 20% | 18.45% | 15.67% | -4.33% |  | 89.83 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23524 | Bombardier Regional Jets (BRJ) | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -34.6169 | 161% | 46.21% | 44.9% | 3694.07 | -3.63% | 146287.84 | 235554.56 | -89266.72 | 2578.7 | 0 | 0 | 113075 | 89266.72 | 108838.22 | 338.73 | 126716.34 | 4914% | YES | 126716.34 | 3694 | 105759.8867 | 0 | 0 | 0 | 3694.07 | 3694.07 | 18% | 14.37% | 17.58% | -0.42% |  | 43.71 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23373 | Raytheon Michael Bellini | Natalie Sinclair | 0 | RAS | RAYTHEON UNITED KINGDOM LIMITED | EES | Level NC | REIM |  |  |  | 31.7411 | 56.53% | 86.86% | 70.61% | 24734.7 | -7.6% | 428734.8 | 242367.55 | 186367.25 | 5871.48 | 0 | 0 | 0 | 0 | 210519.78 | 128.93 | 31847.77 | 542.4% | YES | 31847.77 | 47271 | 171127.28 | 0 | 22536.06 | 0 | 24734.7 | 24734.7 | 45% | 37.4% | 38.74% | -6.26% |  | 91.61 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23754 | Tempest Composites WP4 | Philip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 3.5593 | 78.9% | 0% | 0% | 0 | -2.69% | 310945.68 | 245346.96 | 65598.72 | 18430.41 | 1784.87 | 1784.87 | 0 | 0 | 0 | 121.82 | 245346.96 | 1331% | YES | 245346.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36% | 33.31% | 33.31% | -2.69% |  | 60.29 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23741 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  | 29.8222 | 38.92% | 102.5% | 35.6% | 0 | 2.51% | 640812 | 249385.2 | 391426.8 | 13125.35 | 0 | 0 | 0 | 0 | 255639 | 93.45 | -253.8 | -1.934% | NO | -253.8 | 200243 | 88769.8333 | 0 | 68808 | 68808 | 62626.8 | 0 | 28% | 30.51% | 30.51% | 2.51% |  | 38.78 | [5 empty] | 6000
1741 | 2024-06-05 23:29 | P23648 | EXP-032 Delivery of Datalink Eng support - FCAS AP | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 8.9851 | 72.47% | 68.17% | 60.74% | 0 | 7.54% | 371000 | 268859.2 | 102140.8 | 11367.81 | 1032.95 | 1032.95 | 0 | 0 | 183267.95 | 76.8 | 85591.25 | 752.9% | YES | 85591.25 | 23958 | 163302.95 | 0 | 23958 | 0 | 0 | 0 | 22% | 29.54% | 30.19% | 8.19% |  | 101.99 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23739 | Lifing Services DACs | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  | 29.116 | 39.28% | 107.2% | 42.82% | 0 | 6.08% | 656508 | 257869.25 | 398638.75 | 13691.39 | 0 | 0 | 0 | 0 | 276545 | 96.18 | -6675.75 | -48.76% | NO | -6675.75 | 199352 | 110418.3333 | 0 | 66850.8 | 66850.8 | 65650.8 | 0 | 28% | 34.08% | 34.08% | 6.08% |  | 37.78 | [5 empty] | 12000
1741 | 2024-06-05 23:29 | P23472 | Tempest Wing Design | Philip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 156.5932 | 53.48% | 125.5% | 117.8% | 0 | -11.85% | 483869.78 | 258767.11 | 225102.67 | 1437.5 | 242887.5 | 356900 | 0 | 0 | 324639.1 | 0 | -40872 | -2843% | NO | 73140.5 | 23858 | 304757.4333 | 0 | 23857.58 | 0 | 0 | 0 | 23% | 11.15% | 27.86% | 4.86% |  | 46.74 | [5 empty] | 25000
1741 | 2024-06-05 23:29 | P23007 | EXP-006A - Brimstone 3 | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 49.0912 | 70.96% | 99.35% | 96.16% | 0 | -2.36% | 406450 | 288431.91 | 118018.09 | 2404.06 | 0 | 0 | 0 | 0 | 286547.91 | 38.23 | 1854 | 77.12% | NO | 1854 | 11021 | 277363.7433 | 0 | 11021.44 | 0 | 0 | 0 | 25% | 22.64% | 29.94% | 4.94% |  | 70.24 | [5 empty] | -30
1741 | 2024-06-05 23:29 | P23308 | NATO JEWCS | Natalie Sinclair | 0 | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  | 17.7561 | 87.65% | 91.82% | 87.6% | 0 | -4.18% | 356307 | 312306.71 | 44000.29 | 2478.04 | 613.89 | 613.89 | 0 | 0 | 286767.43 | 144.38 | 25539.28 | 1031% | YES | 25539.28 | 15829 | 273576.5967 | 0 | 15829.13 | 0 | 0 | 0 | 24% | 19.82% | 11.88% | -12.12% |  | 75.81 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P22953 | Spirit Shorts eVTOL | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-05-08 | 1 |  |  | 103.1% | 80.83% | 80.83% | 0 | -9.51% | 324272 | 334483.6 | -10211.6 | 0 | 66696.6 | 67387.9 | 0 | 10211.6 | 270366 | 64941.12 | 54117.6 | 0% | NO | 54808.9 | 0 | 270366 | 0 | 0 | 0 | 0 | 0 | 17% | 7.49% | 100% | 83% |  | 46.19 | [5 empty] | -10000
1741 | 2024-06-05 23:29 | P21463 | Safety & Monitoring Systems at DM Beith & Gosport | Harry James Kellett | 0 | BXW | MOD | EES | Level 2 | FIX |  |  |  | 4.1126 | 88.19% | 113.4% | 113.4% | 0 | -23.48% | 378612.83 | 333886.3 | 44726.53 | 10875.39 | 75631.47 | 79790.28 | 45616.14 | 0 | 378594.83 | 0 | -44708.53 | -411.1% | NO | -40549.72 | 0 | 378594.83 | 0 | 0 | 0 | 0 | 0 | 48% | 24.52% | 39.48% | -8.52% |  | 56.29 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P22515 | Shorts A220 100/300 ALI Phase III | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 43.5932 | 84.65% | 96.79% | 94.55% | 0 | 0.53% | 400628.76 | 339151.07 | 61477.69 | 1410.26 | 3450.98 | 3450.98 | 0 | 0 | 328273.11 | 83.56 | 10877.96 | 771.3% | YES | 10877.96 | 9121 | 320672.2767 | 0 | 0 | 9121.46 | 0 | 0 | 10% | 10.53% | 6.59% | -3.41% |  | 40.58 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23629 | F35 FTI | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level NC | REIM |  |  |  | -33.533 |  | 82.57% | 76.27% | 0 | -1.76% | 0 | 340648.29 | -340648.29 | 10158.6 | 0 | 0 | 0 | 340648.29 | 281269.67 | 49.83 | 59378.62 | 584.5% | YES | 59378.62 | 25742 | 259818.0033 | 0 | 25742.41 | 0 | 0 | 0 | 31% | 29.24% | 28.24% | -2.76% |  | 61.4 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P22842 | ME Support (Aim Altitude) | Trevor Knox | 0 | AVI | AIM ALTITUDE UK LIMITED | ME | Level 3 | FIX | 2023-06-14 | 4 |  |  | 99.31% | 100.5% | 86.63% | 57290.84 | 0.49% | 346293.67 | 343918.08 | 2375.59 | 0 | 2909.86 | 2909.86 | 0 | 0 | 345673.01 | 55184.93 | -1754.93 | 0% | NO | -1754.93 | 57291 | 297930.51 | 0 | 0 | 0 | 57290.84 | 57290.84 | 13% | 13.49% | 0% | -13% |  | 46.3 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23816 | Typhoon FTI Works - 2024 Fixed Price Element | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 180.8745 | 84.3% | 84.93% | 4.109e-05% | 220195.2 | -1.78% | 404176.65 | 340731.31 | 63445.34 | 350.77 | 0 | 0 | 0 | 0 | 289390.14 | 130.45 | 61341.17 | 17488% | YES | 61341.17 | 347268 | 0.14 | 0 | 127072.97 | 220195.2 | 0 | 220195.2 | 30% | 28.22% | 28.22% | -1.78% |  | 50.96 | [5 empty] | 10000
1741 | 2024-06-05 23:29 | P22391 | GE System Engineering support | Vinayakumar Sugur | 0 | GEE | EXPERIS LIMITED | EES | Level NC | REIM | 2024-04-08 | 0 |  |  | 82.01% | 100.7% | 100.7% | 0 | 0.13% | 434434.25 | 356260.63 | 78173.62 | 0 | 0 | 0 | 0 | 0 | 358805.6 | 0 | -2544.97 | 0% | NO | -2544.97 | 0 | 358805.6 | 0 | 0 | 0 | 0 | 0 | 6% | 6.13% | 6.09% | 0.09% |  | 57.33 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23617 | Tempest Composites WP2 | Philip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -31.7453 | 155.4% | 26.64% | 20.15% | 29536.68 | 11.57% | 244405.26 | 379761.91 | -135356.65 | 4263.83 | 0 | 0 | 153486.97 | 135356.65 | 101150.9 | 411.41 | 278611.01 | 6534% | YES | 278611.01 | 29537 | 76536.7333 | 0 | 0 | 0 | 29536.68 | 29536.68 | 22% | 33.57% | 33.18% | 11.18% |  | 62.16 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23743 | EHM Cloud Migration | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 35.8024 | 34.08% | 123.5% | 49.31% | 0 | 8.25% | 1016000 | 346257.63 | 669742.37 | 18706.63 | 0 | 0 | 0 | 0 | 427656 | 80.85 | -46398.38 | -248% | NO | -46398.38 | 308285 | 170751.8333 | 0 | 102336 | 103612.8 | 102336 | 0 | 28% | 36.25% | 36.25% | 8.25% |  | 55.67 | [5 empty] | 35000
1741 | 2024-06-05 23:29 | P23603 | Typhoon IMDLR | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | -3.5434 | 132.2% | 75.63% | 29.7% | 0 | 1.08% | 305067.09 | 403367.44 | -98300.35 | 27741.82 | 1500 | 1500 | 152797.11 | 98300.35 | 305064.02 | 276.48 | 98303.42 | 354.4% | YES | 98303.42 | 222307 | 119808.1867 | 0 | 222307.42 | 0 | 0 | 0 | 28% | 29.08% | 27.5% | -0.5% |  | 56.21 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23432 | Spirit Belfast MRB On-Site Support (Mon & Clear) | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 65.77% | 138.7% | 128.6% | 0 | -11.53% | 449545 | 295665.27 | 153879.73 | 0 | 295665.27 | 451827.33 | 0 | 0 | 410199.75 | 32916.62 | -2534.48 | 0% | NO | 153627.58 | 35958 | 380234.75 | 0 | 35958 | 0 | 0 | 0 | 39% | 27.47% | 0% | -39% |  | 0 | [5 empty] | 112000
1741 | 2024-06-05 23:29 | P23045 | Shotgun Adaptors - 10 Sets | Harry James Kellett | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | FIX | 2024-02-27 | 3 |  | 14.3628 | 78.74% | 127% | 127% | 0 | 2.55% | 399276.11 | 314390.3 | 84885.81 | 5910.11 | 214550.47 | 214550.47 | 0 | 0 | 399276.11 | 349.55 | 15877.19 | 268.6% | YES | 15877.19 | 0 | 399276.11 | 0 | 0 | 0 | 0 | 0 | 31% | 33.55% | 93.96% | 62.96% |  | 58.52 | [5 empty] | 100763
1741 | 2024-06-05 23:29 | P23677 | ME Managed Service - Phase 1 | Paul Watson | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  | 25.0228 | 38.19% | 78.73% | 0% | 0 | -10.71% | 1116000 | 426153.85 | 689846.15 | 27568.75 | 0 | 38000 | 0 | 0 | 335497.5 | 133.86 | 90656.35 | 328.8% | YES | 128656.35 | 402597 | 0 | 116181 | 71536.5 | 214879.5 | 0 | 0 | 30% | 19.29% | 21.01% | -8.99% |  | 44.2 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23023 | Spirit Shorts R Foster/M Gourley | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 94.6247 | 71.74% | 107.3% | 99.17% | 0 | -1.11% | 590659.44 | 423730.09 | 166929.35 | 1764.12 | 237621.5 | 267726 | 0 | 0 | 454499.72 | 59.5 | -8403.63 | -476.4% | NO | 21700.87 | 41139 | 420217.22 | 0 | 20921.8 | 20217.14 | 0 | 0 | 9% | 7.89% | 11.18% | 2.18% |  | 29.7 | [5 empty] | 22366
1741 | 2024-06-05 23:29 | P22906 | Spirit Shorts - MRB JD Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 3.4083 | 98.37% | 82.68% | 65.19% | 99451.32 | -7.97% | 481714 | 473884.18 | 7829.82 | 2297.25 | 0 | 0 | 0 | 0 | 391817.62 | 423.22 | 90066.56 | 3921% | YES | 90066.56 | 99451 | 308941.7867 | 0 | 0 | 0 | 99451.32 | 99451.32 | 13% | 5.03% | 2.32% | -10.68% |  | 36.97 | [5 empty] | 8000
1741 | 2024-06-05 23:29 | P22652 | L3 - Saftey Engineering | Sean Simmons | 0 | LHW | L3HARRIS MAPPS LIMITED | EES | Level NC | FIX |  |  |  |  | 95.63% | 95.66% | 95.66% | 0 | 5.66% | 523390 | 500497.5 | 22892.5 | 0 | 0 | 0 | 0 | 0 | 478783.75 | 26056.5 | 21713.75 | 0% | NO | 21713.75 | 0 | 478783.75 | 0 | 0 | 0 | 0 | 0 | 21% | 26.66% | 25.88% | 4.88% |  | 83.05 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23281 | Systems Portfolio | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM | 2024-02-28 | 0 |  |  | 44.43% | 97.31% | 97.31% | 0 | -17.25% | 1177697.24 | 523236.96 | 654460.28 | 0 | 2133.28 | 2133.28 | 0 | 0 | 509179.87 | 15792.1 | 13160.09 | 0% | NO | 13160.09 | 0 | 509179.87 | 0 | 0 | 0 | 0 | 0 | 25% | 7.75% | 100% | 75% |  | 70.48 | [5 empty] | -897
1741 | 2024-06-05 23:29 | P23531 | BAe Systems F35 MRB Support | Richard Brook | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | -74.8774 |  | 95.33% | 93.52% | 0 | 3.68% | 0 | 531572.02 | -531572.02 | 7099.23 | 287.44 | 287.44 | 0 | 531572.02 | 506774.08 | 26.93 | 24797.94 | 349.3% | YES | 24797.94 | 11582 | 497122.4133 | 0 | 11582.32 | 0 | 0 | 0 | 25% | 28.68% | 31.82% | 6.82% |  | 60.1 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23699 | A220 Stress Checkers | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -2.6524 | 131.9% | 70.52% | 4.953e-05% | 0 | 7.04% | 408328.79 | 538388.41 | -130059.62 | 49034.95 | 12000 | 12000 | 185592 | 130059.62 | 379653.6 | 173.02 | 158734.81 | 323.7% | YES | 158734.81 | 455584 | 0.26667 | 0 | 455584.32 | 0 | 0 | 0 | 13% | 20.04% | 20.06% | 7.06% |  | 61.88 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23554 | Dornier Seawings 328 2023 H2 Support | Natalie Sinclair | 0 | DAX | EXPLEO GERMANY GMBH (EC) | MPE | Level 2 | REIM |  |  |  | -3.2519 | 106.2% | 79.29% | 79.29% | 0 | 5.26% | 508481.81 | 540126.73 | -31644.92 | 9731.18 | 4046.44 | 4046.44 | 32100 | 31644.92 | 428252.8 | 87.5 | 111873.93 | 1150% | YES | 111873.93 | 0 | 428252.8 | 0 | 0 | 0 | 0 | 0 | 21% | 26.26% | 22.47% | 1.47% |  | 65.49 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23001 | Spirit Shorts A220 Design | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -26.4442 | 114.5% | 74.8% | 71.52% | 0 | 11.3% | 486640 | 557095.2 | -70455.2 | 2664.3 | 0 | 0 | 65953.2 | 70455.2 | 416705.3 | 391.81 | 140389.9 | 5269% | YES | 140389.9 | 21931 | 398429.4667 | 0 | 0 | 21930.72 | 0 | 0 | 9% | 20.3% | 11.49% | 2.49% |  | 43.55 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23520 | FCAS AP Portfolio Systems | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 27.7122 | 70.68% | 98.08% | 89.41% | 0 | -6.47% | 810821 | 573059.55 | 237761.45 | 8579.66 | 423 | 423 | 0 | 0 | 562047.44 | 35.04 | 6729.11 | 78.43% | NO | 6729.11 | 59604 | 512377.44 | 0 | 59604 | 0 | 0 | 0 | 22% | 15.53% | 16.45% | -5.55% |  | 81.26 | [5 empty] | -4283
1741 | 2024-06-05 23:29 | P23219 | Tornado Air 800 Engineering Support | Richard Brook | 0 | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 3 | REIM |  |  |  | 39.1172 | 98.62% | 95.35% | 95.35% | 0 | -1.51% | 615046 | 606579.09 | 8466.91 | 216.45 | 459.21 | 459.21 | 0 | 0 | 578373.17 | 20.96 | 3298.92 | 1524% | YES | 3298.92 | 0 | 578373.17 | 0 | 0 | 0 | 0 | 0 | 31% | 29.49% | 350.6% | 319.6% |  | 81.66 | [5 empty] | -24907
1741 | 2024-06-05 23:29 | P23140 | Spirit Shorts A220 MLG Stress Support | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  | 10.1871 | 77.95% | 94.34% | 64.68% | 0 | -8.01% | 735573.4 | 573378.69 | 162194.71 | 15921.54 | 20870.3 | 87811.88 | 111743 | 0 | 540939.4 | 155.54 | 57439.29 | 360.8% | YES | 124380.87 | 204098 | 370857.7333 | 0 | 0 | 204098.4 | 0 | 0 | 17% | 8.99% | -9.78% | -26.78% |  | 44.5 | [5 empty] | 25000
1741 | 2024-06-05 23:29 | P23372 | BAE Carbon Tooling Off-load | Gary Kempster | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | 1.684 | 90.48% | 95.39% | 71.45% | 0 | -3.23% | 674141.57 | 609936.68 | 64204.89 | 38125.84 | 0 | 0 | 0 | 0 | 581806.73 | 171.1 | 28129.95 | 73.78% | NO | 28129.95 | 175225 | 435785.8967 | 0 | 175224.95 | 0 | 0 | 0 | 25% | 21.77% | 18.53% | -6.47% |  | 53.99 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23473 | Tempest Vertical Tail | Philip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 28.7374 | 71.6% | 97.85% | 91.62% | 0 | -7.08% | 846017.62 | 605780.39 | 240237.23 | 8359.73 | 109975 | 129075 | 0 | 0 | 592767.31 | 39.65 | 18013.08 | 215.5% | YES | 37113.08 | 45333 | 554989.81 | 0 | 45333.23 | 0 | 0 | 0 | 29% | 21.92% | 24.13% | -4.87% |  | 62.67 | [5 empty] | 5000
1741 | 2024-06-05 23:29 | P23605 | Typhoon Work Package 2 Continuation | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM |  |  |  |  | 101.6% | 95.36% | 85.52% | 0 | 4.82% | 627011.01 | 637291.81 | -10280.8 | -3672.07 | 5554 | 5554 | 0 | 10280.8 | 607723.77 | 2374.72 | 29568.04 | -805.2% | NO | 29568.04 | 75285 | 544986.27 | 0 | 75284.54 | 0 | 0 | 0 | 23% | 27.82% | 27.48% | 4.48% |  | 55.63 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23323 | CNC-CMM Programming Support | Stephen Young | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  | -4.2951 | 105.2% | 94.96% | 88.37% | 0 | -1.93% | 617809.74 | 650080.88 | -32271.14 | 7513.44 | 15941.56 | 17789.56 | 99488.9 | 32271.14 | 617295.69 | 59.73 | 32785.19 | 436.4% | YES | 34633.19 | 51363 | 574493.19 | 51362.6 | 0 | 0 | 0 | 0 | 32% | 30.07% | 36.7% | 4.7% |  | 57.65 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P22790 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | REIM | 2024-04-28 | 0 |  |  | 197.4% | 89.11% | 89.11% | 0 | 1.11% | 352240 | 695460.45 | -343220.45 | 0 | 1611.52 | 1611.52 | 44500 | 343220.45 | 619743.88 | 396.6 | 44446.57 | 0% | NO | 44446.57 | 0 | 619743.88 | 0 | 0 | 0 | 0 | 0 | 13% | 14.11% | -2.72% | -15.72% |  | 45.08 | [5 empty] | -31270
1741 | 2024-06-05 23:29 | P23366 | Business Analyst Support | Peter Williams | 0 | BDZ | MBDA UK LIMITED | DET | Level 3 | REIM |  |  |  | 84.4114 | 28.5% | 169.5% | 152% | 0 | 0.55% | 1302200 | 371174.36 | 931025.64 | 11029.62 | 299014.25 | 900840.72 | 0 | 0 | 629120 | 62.1 | 35189.36 | 319% | YES | 637015.83 | 77952 | 564160 | 0 | 77952 | 0 | 0 | 0 | 43% | 43.55% | 20.94% | -22.06% |  | 46.8 | [5 empty] | 293135
1741 | 2024-06-05 23:29 | P23694 | Systems Portfolio EXP-011a | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | -1.6732 | 105.4% | 79.92% | 62.52% | 0 | 1.85% | 648492.8 | 683562.76 | -35069.96 | 20960.37 | 809.51 | 809.51 | 0 | 35069.96 | 546332.19 | 79 | 137230.57 | 654.7% | YES | 137230.57 | 142737 | 427384.69 | 0 | 0 | 142737.46 | 0 | 0 | 21% | 22.85% | 20.51% | -0.49% |  | 88.59 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23685 | DAC LUC Support and Recompliance | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 26.8093 | 32.66% | 169.1% | 69.03% | 0 | 8.08% | 2180000 | 711881.93 | 1468118.07 | 54761.42 | 0 | 0 | 0 | 0 | 1203934 | 62.35 | -378288.07 | -690.8% | NO | -378288.07 | 855007 | 491428.1667 | 0 | 283279.2 | 297441.6 | 274286.4 | 0 | 30% | 38.08% | 38.08% | 8.08% |  | 57.29 | [5 empty] | 113764
1741 | 2024-06-05 23:29 | P23426 | BAE Tempest WP 3 Harness Maturation | Philip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 0.85731 | 97.85% | 86.45% | 68.41% | 107757.52 | -6.22% | 884012.04 | 864974.72 | 19037.32 | 22205.95 | 213.34 | 213.34 | 0 | 0 | 747777.74 | 99.84 | 117196.98 | 527.8% | YES | 117196.98 | 187209 | 591770.24 | 0 | 79451.21 | 107757.52 | 0 | 107757.52 | 33% | 26.78% | 26.97% | -6.03% |  | 52.4 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23105 | Raytheon Supply Engineering Support | Natalie Sinclair | 0 | RAY | RAYTHEON UNITED KINGDOM LIMITED | MPE | Level 3A | REIM | 2023-07-13 | 2 |  |  | 74.28% | 94.49% | 90.07% | 49156.8 | -2.02% | 1248458.75 | 927395.25 | 321063.5 | 0 | 0 | 0 | 0 | 0 | 876291.5 | 107644.5 | 48739.75 | 0% | NO | 48739.75 | 49157 | 835327.3333 | 0 | 0 | 0 | 49156.8 | 49156.8 | 26% | 23.98% | 100% | 74% |  | 48.97 | [5 empty] | -2364
1741 | 2024-06-05 23:29 | P23117 | BAE Typhoon Eng Support | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | 2024-03-12 | 3 |  |  | 103.2% | 96.92% | 96.92% | 0 | -1.09% | 950771.99 | 980837.59 | -30065.6 | -4930.23 | 19213.34 | 20141.26 | 4921.28 | 30065.6 | 950609.41 | 2311.1 | 3132.18 | -63.53% | NO | 4060.1 | 0 | 950609.41 | 0 | 0 | 0 | 0 | 0 | 30% | 28.91% | 20.68% | -9.32% |  | 52.29 | [5 empty] | -27096
1741 | 2024-06-05 23:29 | P23451 | BAE Tempest - DFM-ASO Planning | Stephen Young | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | 11.4449 | 84.52% | 90.69% | 65.87% | 27224.9 | -3.07% | 1145785.42 | 968444.08 | 177341.34 | 15495.27 | 0 | 0 | 0 | 0 | 878305.81 | 128.89 | 89055.27 | 574.7% | YES | 89055.27 | 288455 | 637926.6433 | 75655.99 | 185573.64 | 0 | 27224.9 | 27224.9 | 28% | 24.93% | 26.29% | -1.71% |  | 53.83 | [5 empty] | -1083
1741 | 2024-06-05 23:29 | P23602 | EXP-025 Portfolio Software Engineering Support | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 10.7761 | 75.93% | 91.99% | 80.8% | 0 | -1.12% | 1327080 | 1007663.53 | 319416.47 | 29641.13 | 4348.66 | 929790.21 | 0 | 0 | 926909.33 | 43.75 | 80754.2 | 272.4% | YES | 1006195.75 | 135246 | 814204.33 | 0 | 135246.31 | 0 | 0 | 0 | 24% | 22.88% | 22.58% | -1.42% |  | 83.44 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P22350 | EMP 2020-2021 | Natalie Sinclair | 0 | ARY | GUIDANT GLOBAL UK LIMITED | PCPR | Level NC | REIM |  |  |  | -1.0206 | 100.4% | 98.36% | 95.21% | 0 | -2.09% | 1017579.76 | 1021345.15 | -3765.39 | 3689.56 | 400 | 400 | 0 | 3765.39 | 1004590.04 | 70.61 | 16755.11 | 454.1% | YES | 16755.11 | 38594 | 972428.3733 | 0 | 16129.64 | 22464.33 | 0 | 0 | 32% | 29.91% | 28.08% | -3.92% |  | 44.16 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P22671 | Spirit Shorts Pylon and Fairing Package | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX | 2023-05-03 | 0 |  |  | 105% | 95.26% | 95.26% | 0 | -7.21% | 1198494.77 | 1258071.09 | -59576.32 | 0 | 106494.89 | 106494.89 | 0 | 59576.32 | 1198494.77 | 2544.39 | 2120.32 | 0% | NO | 2120.32 | 0 | 1198494.77 | 0 | 0 | 0 | 0 | 0 | 20% | 12.79% | 0% | -20% |  | 45.4 | [5 empty] | -57456
1741 | 2024-06-05 23:29 | P23152 | Project Aragon - Design and Stress Support | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | -4.3479 | 103.4% | 88.48% | 73.85% | 0 | 0.46% | 1333452.21 | 1378257.33 | -44805.12 | 10304.92 | 0 | 0 | 49524 | 44805.12 | 1219477.02 | 224.87 | 158780.31 | 1541% | YES | 158780.31 | 241970 | 1017835.3533 | 0 | 241969.72 | 0 | 0 | 0 | 29% | 29.46% | 29.31% | 0.31% |  | 52 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23292 | BAE Tempest WP 4 AV Trays | Philip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 3.3992 | 95.39% | 92.22% | 86.45% | 0 | 1.31% | 1498284.22 | 1429202.02 | 69082.2 | 20322.82 | 0 | 0 | 0 | 0 | 1317945.86 | 62.32 | 111256.16 | 547.4% | YES | 111256.16 | 98848 | 1235572.5267 | 0 | 98847.53 | 0 | 0 | 0 | 32% | 33.31% | 31.67% | -0.33% |  | 53.98 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23411 | Agile & Scrum Delivery Service | Peter Williams | 0 | BDZ | MBDA UK LIMITED | DET | Level 2 | REIM | 2023-08-14 | 0 |  |  | 36.3% | 170.5% | 170.5% | 0 | 13.08% | 2487000 | 902903.79 | 1584096.21 | 0 | 894178.59 | 894178.59 | 0 | 0 | 1539600 | 19368.95 | 16140.79 | 0% | NO | 16140.79 | 0 | 1539600 | 0 | 0 | 0 | 0 | 0 | 29% | 42.08% | 0% | -29% |  | 74.57 | [5 empty] | 652837
1741 | 2024-06-05 23:29 | P23519 | Mechanical and Electrical Design Eng Support | Dushan Fernando | 0 | BAX | SAFRAN SEATS GB LIMITED | MPE | Level 2 | REIM |  |  |  | 8.4254 | 86.5% | 96.66% | 89.12% | 0 | -1.58% | 1807261.3 | 1563309.95 | 243951.35 | 28954.33 | 1004.45 | 1504.45 | 0 | 0 | 1511140.05 | 39.23 | 52169.9 | 180.2% | YES | 52669.9 | 141528 | 1393200.05 | 0 | 141528.3 | 0 | 0 | 0 | 33% | 31.42% | 31.41% | -1.59% |  | 56.67 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P22278 | TAI Supply Engineers to Ankara | Natalie Sinclair | 0 | TAI | TUSAS-TURK HAVACILIK VE UZAY | MPE | Level 3A | REIM |  |  |  | 1600.5087 | 19.89% | 456.3% | 456.3% | 0 | -15.84% | 2105282 | 418745.91 | 1686536.09 | 1053.75 | 49400.29 | 49400.29 | 0 | 0 | 1910696.33 | 139.91 | 18449.58 | 1751% | YES | 18449.58 | 0 | 1910696.33 | 0 | 0 | 0 | 0 | 0 | 95% | 79.16% | 64.99% | -30.01% |  | 34.1 | [5 empty] | 1510400
1741 | 2024-06-05 23:29 | P23175 | BAe Aero Typhoon Package 2 | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM | 2024-03-12 | 2 |  |  | 103.8% | 96.32% | 96.32% | 0 | -1.63% | 1984265.09 | 2060011.83 | -75746.74 | 0 | 57677.87 | 86030.82 | 15444.64 | 75746.74 | 1984257.03 | 84731.75 | 70609.8 | 0% | NO | 98962.75 | 0 | 1984257.03 | 0 | 0 | 0 | 0 | 0 | 29% | 27.37% | 0% | -29% |  | 51.76 | [5 empty] | -5145
1741 | 2024-06-05 23:29 | P23006 | Spirit Shorts A350 Freighter Toulouse | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 37.5602 | 89.52% | 108.7% | 98.36% | 0 | 22.49% | 1925837.92 | 1724004.29 | 201833.63 | 5373.61 | 1086670.26 | 2010741.94 | 0 | 0 | 1873531.68 | 203.25 | 227746.61 | 4238% | YES | 1151818.29 | 213293 | 1695787.5133 | 0 | 213292.5 | 0 | 0 | 0 | 5% | 27.49% | 46.82% | 41.82% |  | 48.3 | [5 empty] | 377274
1741 | 2024-06-05 23:29 | P19020 | Spirit Concessions - 2018 | Carl Warren | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2024-01-23 | 0 |  |  | 86.3% | 111.8% | 111.8% | 0 | 2.09% | 2015043.23 | 1739018.14 | 276025.09 | 0 | 44317.61 | 44317.61 | 0 | 0 | 1944710.76 | 236384.86 | 196987.38 | 0% | NO | 196987.38 | 0 | 1944710.76 | 0 | 0 | 0 | 0 | 0 | 25% | 27.09% | 9.32% | -15.68% |  | 40.87 | [5 empty] | 402680
1741 | 2024-06-05 23:29 | P23257 | BAE Tempest WP 5 Centre Fuselage | Philip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | -0.13342 | 100.1% | 97.53% | 95.03% | 0 | -5.72% | 2265401.51 | 2267496.57 | -2095.06 | 15702.8 | 78100 | 78100 | 0 | 2095.06 | 2211380.12 | 49.63 | 56116.45 | 357.4% | YES | 56116.45 | 67821 | 2154862.62 | 0 | 67820.9 | 0 | 0 | 0 | 33% | 27.28% | 28.02% | -4.98% |  | 61.07 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23435 | Andy Baker Portfolio | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 38.8873 | 58.28% | 97.2% | 88.02% | 0 | -7.34% | 4023207.4 | 2344782.43 | 1678424.97 | 43161.23 | 2717.38 | 2717.38 | 0 | 0 | 2279167.78 | 42.14 | 65614.65 | 152% | YES | 65614.65 | 258468 | 2063777.78 | 0 | 296652.44 | -38184.52 | 0 | 0 | 25% | 17.66% | 18.96% | -6.04% |  | 81.1 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23179 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX |  |  |  | -6.3675 | 101.5% | 96.64% | 93.43% | 0 | -9.18% | 2542643.04 | 2581984.82 | -39341.78 | 6178.48 | 156991.12 | 248243.92 | 0 | 39341.78 | 2495342.85 | 327.26 | 86641.97 | 1402% | YES | 177894.77 | 99729 | 2412235.35 | 99728.59 | 0 | 0 | 0 | 0 | 22% | 12.82% | 18.43% | -3.57% |  | 44.4 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P19731 | Hapri HPC Rear Bearing Housing PDR & CDR | Steven Lawton | 0 | ATC | AECC Hunan Aviation Powerplant | MPE | Level 1 | FIX | 2024-05-13 | 3 |  | -419.2815 | 100.3% | 99.67% | 99.67% | 0 | -15.41% | 2980000 | 2989861.5 | -9861.5 | 23.52 | 366376.22 | 500476.22 | 0 | 9861.5 | 2980000 | 0 | -215138.5 | -914705% | NO | -81038.5 | 0 | 2980000 | 0 | 0 | 0 | 0 | 0 | 38% | 22.59% | 15.42% | -22.58% |  | 64.85 | [5 empty] | -225000
1741 | 2024-06-05 23:29 | P23207 | A350 Approvers - Design and Stress Support | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  | 2.8699 | 94.45% | 93.64% | 83.02% | 0 | -4.31% | 3135290 | 2961250.94 | 174039.06 | 60642.25 | 40525.59 | 40525.59 | 0 | 0 | 2772971.66 | 59.51 | 188279.28 | 310.5% | YES | 188279.28 | 377387 | 2458482.4933 | 0 | 275235.34 | 102151.98 | 0 | 0 | 22% | 17.69% | 16.81% | -5.19% |  | 54.54 | [5 empty] | 0
1741 | 2024-06-05 23:29 | P23487 | Tornado Air 800 Engineering Support | Richard Brook | 0 | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 2 | FIX |  |  |  | 12.532 | 81.68% | 87.8% | 73.59% | 333359.75 | -2.83% | 4286367.76 | 3501088.85 | 785278.91 | 62661.73 | 500 | 500 | 0 | 0 | 3073852.1 | 116.96 | 499236.75 | 796.7% | YES | 499236.75 | 596787 | 2576529.6 | 0 | 263427.34 | 285969.17 | 47390.58 | 333359.75 | 40% | 37.17% | 40.47% | 0.47% |  | 79.02 | [5 empty] | 72000
Extend Table

## AP6-2
WIP No | Date Created | Project ID | Project Description | Project Manager | Agency (1=yes, 0=no) | Department Id | Client | CBU | Complexity | Type | Stop Booking Hrs | Closing Project: Action(s) to close | RAG | Approx. PO Burndown (weeks) | Turnover vs Contract Value | Invoice To Date vs Turnover | Cash in vs Turnover | Open Amount Overdue | Actual PM% to Baseline PM% delta | Contract Value | Total Project Turnover | Contract Value - Total Turnover | Run Rate (based on total turnover) | Total BOI Spend to Date | Total Committed PO (supplier/best shore) | Current AA in PT3 | Exposure (turnover - contract value) | Invoiced To Date | DSO | Unbilled (WIP) | WIP / Run rate | WIP / Run rate >1.3 | WIP + Remaining Committed PO for BOI | Total Open Amount | Cash in (Invoiced - (Open amount -VAT)) | Debt - <=30 Days since invoice | Debt - 31 - 60 Days since invoice | Debt - 61 - 90 Days since invoice | Debt - >= 90 Days since invoice | Open Amount Overdue2 | Baseline Project Margin | Project To Date (PTD) PM | Year to Date (YTD) PM | YTD Delta Actual PM% to BPM% | Forecast PM at Completion (Manual input from PTT) | Average Sale Rate | CSat score for last quarter (Manual input from PTT) | Comments and Actions | Judged income adjustment at completion | Profit to take now | Provision required now | Fully Traded | Last Months Comments and Actions
1742 | 2024-06-12 23:30 | P23552 | FCAS AP Product Technology Development | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -25% | 597871 | 0 | 597871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0% | -25% |  | 0 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23912 | EXP-042 Software Engineering Support to Elec Eng | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 0% |  |  | 0 | -22% | 620890 | 0 | 620890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22% | 0% | 0% | -22% |  | 0 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23543 | EXP-024 FCAS AP Transformation & Change Enablers | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -26% | 385921 | 0 | 385921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26% | 0% | 0% | -26% |  | 0 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23784 | Tempest Tooling Offload 2024 | Gary Kempster | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM | 2024-05-09 | 0 | [5 empty] | 0 | -25% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0% | -25% |  | 0 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23628 | Design Assurance | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | -7% | 0 | 0 | 0 | 0 | 0 | 0 | 4454.8 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 0% | 0.33% | -6.67% |  | 0 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23711 | DO NOT USE - RAISED IN ERROR | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23915 | A220 FLE Design | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 18707.94 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23810 | Strategic Enablement | Owain Jones | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -34302543% | 0 | 133694.4 | -133694.4 | -33423.5 | 0 | 0 | 134000 | 133694.4 | 0 | 0.48 | 0.4 | -0.001197% | NO | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | -34302525% | -34302525% | -34302543% |  | 42 | [5 empty] | -133694
1742 | 2024-06-12 23:30 | P23650 | MBDA Recruitment Management costs | Andrew Slaney | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM | 2024-02-01 | 1 |  | -963886 |  | 0% | 0% | 0 | -33042321% | 0 | 240971.5 | -240971.5 | 0.25 | 0 | 0 | 266000 | 240971.5 | 0 | 0.6 | 0.5 | 200% | YES | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | -33042318% | 165.6% | 162.6% |  | 82.3 | [5 empty] | -240971
1742 | 2024-06-12 23:30 | P23730 | FLE Project | Siyun Fan | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -18.03% | 0 | 1120 | -1120 | 0 | 0 | 0 | 24000 | 1120 | 0 | 1344 | 1120 | 0% | NO | 1120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | -18.03% | -18.03% | -18.03% |  | 35 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23463 | A220 Wing MaMo Design Checking | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-03-07 | 0 |  |  |  | 0% | 0% | 0 | 7.85% | 0 | 1628 | -1628 | 0 | 0 | 0 | 15000 | 1628 | 0 | 1953.6 | 1628 | 0% | NO | 1628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | 10.85% | 0% | -3% |  | 44 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P21028 | Rebate Collection (BACC) | David Catchpole | 0 | TOO | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | [5 empty] | 0% | 0% | 0 | 0% | 0 | 2680 | -2680 | 0 | 2680 | 2680 | 0 | 2680 | 0 | 3216 | 2680 | 0% | NO | 2680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23881 | Bulldog Fuel System Design | Trevin Fernandopulle | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM |  |  |  |  | 32.85% | 0% | 0% | 0 | -0.08% | 8288 | 2722.5 | 5565.5 | -810.38 | 0 | 0 | 0 | 0 | 0 | 49 | 2722.5 | -336% | NO | 2722.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13% | 12.92% | 12.92% | -0.08% |  | 52.86 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23892 | Warrior Environmental Control Unit | Trevin Fernandopulle | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM |  |  |  | 0 | 100% | 0% | 0% | 0 | 3.58% | 3920 | 3920 | 0 | 980 | 0 | 0 | 0 | 0 | 0 | 35 | 3920 | 400% | YES | 3920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32% | 35.58% | 35.58% | 3.58% |  | 56 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23578 | ESN Work Package | Hannah Mead | 0 | COZ | CHELTON LIMITED | DET | Level 3 | FIX | 2024-01-01 | 1 |  | 4 | 86.17% | 116.1% | 116.1% | 0 | 41.42% | 4410 | 3800 | 610 | 152.5 | 0 | 0 | 0 | 0 | 4410 | 0 | 0 | 0% | NO | 0 | 0 | 4410 | 0 | 0 | 0 | 0 | 0 | 24% | 65.42% | 100% | 76% |  | 95 | [5 empty] | 610
1742 | 2024-06-12 23:30 | P23283 | Spirit Tooling Audit | Charidimos Valadakis | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-05-03 | 1 |  |  | 97.22% | 48.57% | 48.57% | 0 | -114.9% | 9910.08 | 9634.8 | 275.28 | -1238.75 | 0 | 0 | 0 | 0 | 4679.76 | 0.05 | 0.04 | -0.003229% | NO | 0.04 | 0 | 4679.76 | 0 | 0 | 0 | 0 | 0 | 7% | -107.9% | 100% | 93% |  | 34.41 | [5 empty] | -4955
1742 | 2024-06-12 23:30 | P23909 | A220-300 Wing L5v01M09 Loads Increase | Siyun Fan | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -3 |  | 0% | 0% | 0 | -12.89% | 0 | 4864.56 | -4864.56 | 1621.52 | 0 | 0 | 9920 | 4864.56 | 0 | 26 | 4864.56 | 300% | YES | 4864.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | -12.89% | -12.89% | -12.89% |  | 41.58 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23880 | Warrior Crew Heater Design | Trevin Fernandopulle | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM |  |  |  | 12 | 90.91% | 0% | 0% | 0 | 3.58% | 5544 | 5040 | 504 | 42 | 0 | 0 | 0 | 0 | 0 | 56 | 5040 | 12000% | YES | 5040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32% | 35.58% | 35.58% | 3.58% |  | 56 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23002 | WoT MAJ Transit Flag Stress | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2024-04-03 | 1 |  |  | 62.41% | 160.2% | 160.2% | 0 | 38.54% | 4735 | 2955.29 | 1779.71 | 0 | 1492.79 | 2242.5 | 0 | 0 | 4735 | 91.03 | 1493.29 | 0% | NO | 2243 | 0 | 4735 | 0 | 0 | 0 | 0 | 0 | 10% | 48.54% | 0% | -10% |  | 45 | [5 empty] | 3273
1742 | 2024-06-12 23:30 | P23899 | Turret Test Rig | Trevin Fernandopulle | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM |  |  |  | 11.7168 | 25.45% | 0% | 0% | 0 | 0.52% | 24864 | 6328 | 18536 | 1582 | 0 | 0 | 0 | 0 | 0 | 21 | 6328 | 400% | YES | 6328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16% | 16.52% | 16.52% | 0.52% |  | 56 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23607 | SAFRAN - A330neo Turnover Frame | Gary Kempster | 0 | TOO | SAFRAN SEATS GB LIMITED | MPE | Level 3 | FIX |  |  |  |  | 95.69% | 104.5% | 104.5% | 0 | -19.52% | 8736 | 8359.05 | 376.95 | 0 | 0 | 0 | 0 | 0 | 8736 | 0.06 | 0.05 | 0% | NO | 0.05 | 0 | 8736 | 0 | 0 | 0 | 0 | 0 | 23% | 3.48% | 8.5% | -14.5% |  | 50.46 | [5 empty] | 377
1742 | 2024-06-12 23:30 | P23274 | ME Support (Aim Altitude - Cambridge) | Trevor Knox | 0 | AVI | AVIC CABIN SYSTEMS (UK) LIMITED | ME | Level 3 | FIX | 2023-08-18 | 0 |  |  | 51.88% | 56.3% | 56.3% | 0 | -0.17% | 17280 | 8964 | 8316 | 0 | 0 | 0 | 0 | 0 | 5046.3 | 4701.24 | 3917.7 | 0% | NO | 3917.7 | 0 | 5046.3 | 0 | 0 | 0 | 0 | 0 | 21% | 20.83% | 0% | -21% |  | 48 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23886 | A220 F&DT Support | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -6.1893 |  | 0% | 0% | 0 | -9.07% | 0 | 9556.04 | -9556.04 | 1543.96 | 0 | 0 | 12199.2 | 9556.04 | 0 | 42 | 9556.04 | 618.9% | YES | 9556.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 8.93% | 8.93% | -9.07% |  | 50.83 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23127 | Loft Hall Design Support | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-04-19 | 1 |  |  | 101% | 99.06% | 99.06% | 0 | -10.2% | 9680 | 9772 | -92 | -23 | 0 | 0 | 0 | 92 | 9680 | 0 | 0 | 0% | NO | 0 | 0 | 9680 | 0 | 0 | 0 | 0 | 0 | 41% | 30.8% | 100% | 59% |  | 44 | [5 empty] | -92
1742 | 2024-06-12 23:30 | P23630 | 2Excel CFD Analysis Support | Dushan Fernando | 0 | BAX | STIRLING DYNAMICS LTD | MPE | Level NC | FIX |  |  |  |  | 61.2% | 100% | 100% | 0 | -1.87% | 16195.49 | 9911.34 | 6284.15 | 0 | 0 | 0 | 0 | 0 | 9911.63 | 0 | -0.29 | 0% | NO | -0.29 | 0 | 9911.63 | 0 | 0 | 0 | 0 | 0 | 26% | 24.13% | 0% | -26% |  | 64.78 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23864 | REACH Coordinator | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 38.9371 | 21.09% | 87.5% | 0% | 0 | -10.24% | 52920 | 11160 | 41760 | 1072.5 | 0 | 0 | 0 | 0 | 9765 | 84 | 1395 | 130.1% | YES | 1395 | 11718 | 0 | 0 | 11718 | 0 | 0 | 0 | 27% | 16.76% | 16.76% | -10.24% |  | 30 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23313 | Laser Trim Fixtures | Gary Kempster | 0 | TOO | ALKEN ENGINEERING LIMITED | MPE | Level 3 | FIX | 2023-11-20 | 0 |  |  | 89.87% | 111.3% | 111.3% | 0 | 0.53% | 13770 | 12375 | 1395 | 0 | 0 | 0 | 0 | 0 | 13770 | 0 | -1395 | 0% | NO | -1395 | 0 | 13770 | 0 | 0 | 0 | 0 | 0 | 17% | 17.53% | 0% | -17% |  | 45 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P22761 | Red Bull Chassis Spit | Trevor Knox | 0 | TOO | MANUFAX ENGINEERING LTD | MPE | Level 3 | FIX | 2022-11-15 | 0 |  |  | 72.18% | 96.98% | 96.98% | 0 | 7.92% | 12961.2 | 9355.5 | 3605.7 | 0 | 0 | 0 | 0 | 0 | 9072.84 | 4666.39 | 3888.66 | 0% | NO | 3888.66 | 0 | 9072.84 | 0 | 0 | 0 | 0 | 0 | 23% | 30.92% | 0% | -23% |  | 42.19 | [5 empty] | 3606
1742 | 2024-06-12 23:30 | P23894 | EE Test and Integration Lead | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 41.9401 | 12.21% | 0% | 0% | 0 | 0.89% | 110602 | 13508.25 | 97093.75 | 2315.06 | 0 | 0 | 0 | 0 | 0 | 42 | 13508.25 | 583.5% | YES | 13508.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32% | 32.89% | 32.89% | 0.89% |  | 63.88 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23350 | Spirit 2023 - Stress Approve Man Serv (DH) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 14.15% | 72.64% | 72.64% | 0 | -0.29% | 97920 | 13860 | 84060 | 0 | 0 | 0 | 0 | 0 | 10068 | 4550.4 | 3792 | 0% | NO | 3792 | 0 | 10068 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23344 | Spirit A320 Spoilers Support 2023 | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 38.75% | 100% | 100% | 0 | 5.82% | 35786.4 | 13867.23 | 21919.17 | 0 | 0 | 0 | 0 | 0 | 13867.23 | 0 | 0 | 0% | NO | 0 | 0 | 13867.23 | 0 | 0 | 0 | 0 | 0 | 7% | 12.82% | 0% | -7% |  | 34.41 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23337 | Spirit 2023 - Steve Grimley | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 25.28% | 100% | 100% | 0 | 0.01% | 56812.9 | 14362.47 | 42450.43 | 0 | 0 | 0 | 0 | 0 | 14362.47 | 0 | 0 | 0% | NO | 0 | 0 | 14362.47 | 0 | 0 | 0 | 0 | 0 | 7% | 7.01% | 0% | -7% |  | 30.11 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23898 | EXP-041 ISV Engineering Support | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 123.2691 | 3.703% | 58.74% | 0.001124% | 0 | -13.2% | 400584 | 14833.12 | 385750.88 | 3129.34 | 310.62 | 310.62 | 0 | 0 | 8713.5 | 34.73 | 6119.62 | 195.6% | YES | 6119.62 | 10456 | 0.16667 | 0 | 10456.2 | 0 | 0 | 0 | 21% | 7.8% | 7.8% | -13.2% |  | 78.5 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23888 | HondaJet FWD Assy Jig Tool Design | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | FIX |  |  |  | 7.6524 | 47.9% | 0% | 0% | 0 | 4.07% | 31500 | 15088.5 | 16411.5 | 2144.63 | 0 | 0 | 0 | 0 | 0 | 56 | 15088.5 | 703.5% | YES | 15088.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 14.07% | 14.07% | 4.07% |  | 42 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23597 | MRB Onsite support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-02-16 | 1 |  |  |  | 0% | 0% | 0 | -10.04% | 0 | 15100.57 | -15100.57 | 0 | 9448.07 | 17381.62 | 24200 | 15100.57 | 0 | 18120.68 | 15100.57 | 0% | NO | 23034.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 7.96% | 8.95% | -9.05% |  | 42.5 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23718 | Requalification of EJ200 GSS ESS EHM SW module | Vijayakumara Nanjundappa | 0 | ARZ | MTU AERO ENGINES AG | DET | Level 3 | FIX |  |  |  | 103.5507 | 13.78% | 396.1% | 213.2% | 0 | 23.13% | 74463 | 10261.57 | 64201.43 | 620 | 991.93 | 991.93 | 0 | 0 | 40648 | 0 | -25386.43 | -4095% | NO | -25386.43 | 22523 | 21878.8333 | 0 | 22523 | 0 | 0 | 0 | 28% | 51.13% | 51.13% | 23.13% |  | 80 | [5 empty] | 5000
1742 | 2024-06-12 23:30 | P23869 | EXP-037 Land Ceptor Development Hardware Test Def | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 1089.0476 | 9.801% | 0% | 0% | 0 | 0.81% | 162694 | 15944.83 | 146749.17 | 134.75 | 0 | 0 | 0 | 0 | 0 | 77 | 15944.83 | 11833% | YES | 15944.83 | 0 | 0 | 0 | -10617.91 | 10617.91 | 0 | 0 | 26% | 26.81% | 26.81% | 0.81% |  | 89.83 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23343 | Spirit 2023 - John Agnew | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-08-09 | 0 |  |  | 24.64% | 100% | 100% | 0 | -0.02% | 65120.37 | 16047.15 | 49073.22 | 0 | 0 | 0 | 0 | 0 | 16047.15 | 0 | 0 | 0% | NO | 0 | 0 | 16047.15 | 0 | 0 | 0 | 0 | 0 | 7% | 6.98% | 6.98% | -0.02% |  | 34.51 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23635 | Engineering Services: FAI Support | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 49.9% | 100% | 0.0008972% | 0 | -3.4% | 37230 | 18576 | 18654 | 0 | 0 | 0 | 0 | 0 | 18576 | 22291.2 | 0 | 0% | NO | 0 | 22291 | 0.16667 | 0 | 0 | 7058.88 | 15232.32 | 0 | 8% | 4.6% | 5.04% | -2.96% |  | 38.7 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23843 | EXP-035 FT15 Exemplar information set | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 56.8109 | 11.54% | 69.27% | -0.0003448% | 0 | -9.57% | 175985.16 | 20300.12 | 155685.04 | 2740.41 | 0 | 0 | 0 | 0 | 14062.43 | 84 | 6237.69 | 227.6% | YES | 6237.69 | 16875 | -0.07 | 0 | 16874.92 | 0 | 0 | 0 | 20% | 10.43% | 10.43% | -9.57% |  | 71.96 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23355 | Spirit Tooling Support 2023 | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-23 | 0 |  |  | 22.93% | 89.02% | 89.02% | 0 | -0.82% | 91800 | 21053.34 | 70746.66 | 0 | 0 | 0 | 0 | 0 | 18742.5 | 2773.01 | 2310.84 | 0% | NO | 2310.84 | 0 | 18742.5 | 0 | 0 | 0 | 0 | 0 | 20% | 19.18% | 0% | -20% |  | 44.46 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23839 | Stirling Dynamics - ST002-GFEM | Matthew Dodd | 0 | BAX | STIRLING DYNAMICS LTD | MPE | Level 3 | REIM |  |  |  | 11.0026 | 89.35% | 92.63% | 0.0009304% | 0 | -3.93% | 24057.34 | 21496.26 | 2561.08 | 232.77 | 2126.93 | 2126.93 | 0 | 0 | 19912.7 | 277.59 | 1583.56 | 680.3% | YES | 1583.56 | 23895 | 0.2 | 0 | 23895.24 | 0 | 0 | 0 | 6% | 2.07% | 2.07% | -3.93% |  | 43.77 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23873 | FCAS Systems Engineering Support | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 49.8563 | 14.02% | 76.21% | -0.001519% | 0 | -9.72% | 156475 | 21940.75 | 134534.25 | 2698.44 | 0 | 0 | 0 | 0 | 16720.5 | 56 | 5220.25 | 193.5% | YES | 5220.25 | 20065 | -0.33333 | 0 | 20064.6 | 0 | 0 | 0 | 18% | 8.28% | 8.28% | -9.72% |  | 78.5 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23663 | Spirit Tooling Verification and Inspection | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  | 1.5 | 98.66% | 100% | -0.001476% | 0 | -6.39% | 23123.52 | 22813.83 | 309.69 | 206.46 | 0 | 0 | 0 | 0 | 22813.83 | 254.57 | 0 | 0% | NO | 0 | 27377 | -0.33667 | 1982.02 | 4831.16 | 12635.35 | 7928.06 | 0 | 11% | 4.61% | 4.82% | -6.18% |  | 34.41 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23351 | Spirit 2023 - Design Man Serv (KL) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 26.47% | 93.15% | 93.15% | 0 | 0.09% | 93840 | 24840 | 69000 | 0 | 0 | 0 | 0 | 0 | 23138 | 2042.4 | 1702 | 0% | NO | 1702 | 0 | 23138 | 0 | 0 | 0 | 0 | 0 | 26% | 26.09% | 0% | -26% |  | 46 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23356 | Spirit 2023 - Design Man Serv (AH) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX | 2023-08-09 | 1 |  |  |  | 76.66% | 0.001332% | 23018.4 | 0.48% | 0 | 25023.08 | -25023.08 | 0 | 0 | 0 | 25300 | 25023.08 | 19182 | 30027.7 | 5841.08 | 0% | NO | 5841.08 | 23018 | 0.33333 | 0 | 0 | 0 | 23018.4 | 23018.4 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P22884 | Spirit Shorts Config Eng | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 66.3% | 100.1% | 100.1% | 0 | 0.56% | 38976 | 25841.9 | 13134.1 | 0 | 0 | 0 | 0 | 0 | 25863.2 | 0 | -0.3 | 0% | NO | -0.3 | 0 | 25863.2 | 0 | 0 | 0 | 0 | 0 | 7% | 7.56% | 0% | -7% |  | 20.3 | [5 empty] | 21
1742 | 2024-06-12 23:30 | P23742 | Cyber Security Support | Hannah Mead | 0 | COZ | CHELTON LIMITED | DET | Level 3 | FIX | 2024-06-05 | 1 |  |  | 94.91% | 105.4% | 0% | 33000 | -0.96% | 27500 | 26100 | 1400 | 0 | 0 | 0 | 0 | 0 | 27500 | 175.93 | -1400 | 0% | NO | -1400 | 33000 | 0 | 0 | 33000 | 0 | 0 | 33000 | 32% | 31.04% | 31.04% | -0.96% |  | 100 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23354 | Spirit 2023 - Design Man Serv (PC) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 27.97% | 99.36% | 99.36% | 0 | 0.48% | 93840 | 26248.98 | 67591.02 | 0 | 0 | 0 | 0 | 0 | 26082 | 200.38 | 166.98 | 0% | NO | 166.98 | 0 | 26082 | 0 | 0 | 0 | 0 | 0 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P22756 | A350 FLE Design Checker | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2022-03-23 | 1 |  |  | 68.39% | 119.7% | 119.7% | 0 | 16.46% | 34898.4 | 23867.15 | 11031.25 | 0 | 23867.15 | 24342.3 | 0 | 0 | 28571.1 | 0.06 | 0.05 | 0% | NO | 475.2 | 0 | 28571.1 | 0 | 0 | 0 | 0 | 0 | 0% | 16.46% | 0% | 0% |  | 0 | [5 empty] | 4704
1742 | 2024-06-12 23:30 | P23458 | Spirit Belfast Tooling Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-08-11 | 0 |  |  | 101.3% | 94.65% | 94.65% | 0 | 8.64% | 30384 | 30784.9 | -400.9 | 0 | 0 | 0 | 0 | 400.9 | 29139.1 | 1974.96 | 1645.8 | 0% | NO | 1645.8 | 0 | 29139.1 | 0 | 0 | 0 | 0 | 0 | 7% | 15.64% | 0% | -7% |  | 42.2 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23365 | GKN 777x Lip Skin Fixture | Steven Lawton | 0 | TOO | GKN AEROSPACE SERVICES LTD | MPE | Level 3 | FIX | 2023-10-12 | 0 |  |  | 41.91% | 113.2% | 113.2% | 0 | -9.26% | 79161.46 | 33175.67 | 45985.79 | 0 | 5109.88 | 5109.88 | 0 | 0 | 37544.22 | 0 | -4368.55 | 0% | NO | -4368.55 | 0 | 37544.22 | 0 | 0 | 0 | 0 | 0 | 22% | 12.74% | 0% | -22% |  | 56 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P22768 | MRB Onsite Support - Spirit Belfast | Trevor Knox | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2023-07-27 | 0 |  |  |  | 0% | 0% | 0 | -17.07% | 0 | 34614 | -34614 | 0 | 0 | 0 | 36800 | 34614 | 0 | 41536.8 | 34614 | 0% | NO | 34614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | -7.07% | 0% | -10% |  | 36 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23831 | Contract DM/00113 for maintenance, repair and post | Harry James Kellett | 0 | BXW | MOD | EES | Level 2 | FIX |  |  |  | 12.6079 | 77.01% | 15.81% | 15.81% | 0 | 16.27% | 46455.9 | 35773.89 | 10682.01 | 847.25 | 413.33 | 883.5 | 0 | 0 | 5655.9 | 122.49 | 30117.99 | 3555% | YES | 30588.16 | 0 | 5655.9 | 0 | 0 | 0 | 0 | 0 | 34% | 50.27% | 50.27% | 16.27% |  | 80.26 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23821 | Supply of Safety Engineer | Dinna Elkhalifa | 0 | BXW | STIRLING DYNAMICS LTD | EES | Level NC | REIM |  |  |  |  | 106.6% | 49% | 49% | 0 | 45.1% | 34006.44 | 36247.77 | -2241.33 | 0 | 0 | 0 | 0 | 2241.33 | 17760.6 | 127.85 | 18487.17 | 0% | NO | 18487.17 | 0 | 17760.6 | 0 | 0 | 0 | 0 | 0 | 0% | 45.1% | 45.1% | 45.1% |  | 80.73 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23347 | WoT Fixed Leading Edge - Industrial 2023 | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 120.5% | 82.92% | 39.34% | 0 | -0.38% | 31034.12 | 37389.34 | -6355.22 | 0 | 0 | 0 | 10500 | 6355.22 | 31001.86 | 27214.54 | 6387.48 | 0% | NO | 6387.48 | 19550 | 14710.1933 | 0 | 19549.56 | 0 | 0 | 0 | 7% | 6.62% | 7.01% | 0.01% |  | 32.26 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23902 | Typhoon Rear Fuselage | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -4 |  | 0% | 0% | 0 | -0.1% | 0 | 38679.69 | -38679.69 | 9669.92 | 0 | 0 | 45382.5 | 38679.69 | 0 | 34 | 38679.69 | 400% | YES | 38679.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 29.9% | 29.9% | -0.1% |  | 55.38 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23338 | Spirit 2023 - Blair Hainey | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 62.26% | 98.77% | 46.08% | 0 | -3.01% | 62893.71 | 39156.12 | 23737.59 | -335.81 | 0 | 0 | 0 | 0 | 38673.72 | 261.79 | 482.4 | -143.7% | NO | 482.4 | 24758 | 18042.0533 | 3010.18 | 21747.46 | 0 | 0 | 0 | 7% | 3.99% | -4.79% | -11.79% |  | 16.56 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23051 | Spirit Shorts A350 PAX Door | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3A | REIM |  |  |  |  | 68.19% | 105.4% | 105.4% | 0 | 3.37% | 55016 | 37513 | 17503 | 0 | 0 | 0 | 0 | 0 | 39537 | 0 | 0 | 0% | NO | 0 | 0 | 39537 | 0 | 0 | 0 | 0 | 0 | 26% | 29.37% | 0% | -26% |  | 46 | [5 empty] | 2024
1742 | 2024-06-12 23:30 | P23651 | PMO Spirit | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 10.2308 | 80.57% | 85.36% | 59.07% | 0 | -19.39% | 49284 | 39708 | 9576 | 936 | 0 | 0 | 0 | 0 | 33894 | 108.84 | 5814 | 621.2% | YES | 5814 | 12528 | 23454 | 0 | 12528 | 0 | 0 | 0 | 43% | 23.61% | 23.1% | -19.9% |  | 36 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23433 | Cavendish | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 1.1214 | 94.57% | 94.79% | 34.69% | 0 | -0.44% | 42240 | 39946.8 | 2293.2 | 2044.9 | 0 | 0 | 0 | 0 | 37865.6 | 105.48 | 2081.2 | 101.8% | NO | 2081.2 | 28808 | 13858.9333 | 0 | 28807.68 | 0 | 0 | 0 | 7% | 6.56% | 6.51% | -0.49% |  | 46.75 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23724 | GKN S McConnell 2024 | Matthew Tweed | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  | 5.3143 | 81.4% | 91.89% | 0.0008877% | 0 | 0.98% | 49820 | 40553.51 | 9266.49 | 1743.7 | 0 | 0 | 0 | 0 | 37265.36 | 163.88 | 3288.15 | 188.6% | YES | 3288.15 | 44718 | 0.36 | 0 | 8369.76 | 19130.88 | 17217.79 | 0 | 19% | 19.98% | 19.98% | 0.98% |  | 49.64 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P22752 | Tooling WoT - 2021 (Spirit) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | REIM | 2023-05-03 | 0 |  |  | 101.1% | 74.02% | 74.02% | 0 | -8.5% | 41525.1 | 41982.28 | -457.18 | 0 | 0 | 0 | 0 | 457.18 | 31076.1 | 13087.42 | 10906.18 | 0% | NO | 10906.18 | 0 | 31076.1 | 0 | 0 | 0 | 0 | 0 | 0% | -8.5% | 0% | 0% |  | 39.09 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23842 | Tranche 1 Evolution Package Step 2 | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 12.3325 | 37.64% | 0% | 0% | 0 | -10.78% | 112526.3 | 42359.09 | 70167.21 | 5689.61 | 1000 | 1000 | 0 | 0 | 0 | 84 | 42359.09 | 744.5% | YES | 42359.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31% | 20.22% | 20.22% | -10.78% |  | 56.29 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23874 | Environmental Engineering (Sea Venom/ANL) | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 119.1236 | 6.63% | 0% | 0% | 0 | -4.08% | 687295 | 45569.25 | 641725.75 | 5387.06 | 0 | 0 | 0 | 0 | 0 | 63 | 45569.25 | 845.9% | YES | 45569.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23% | 18.92% | 18.92% | -4.08% |  | 78.5 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23339 | Spirit 2023 - Stewart Russell | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 64.51% | 100% | 100% | 0 | 0.62% | 72766.8 | 46941.72 | 25825.08 | 0 | 0 | 0 | 0 | 0 | 46941.74 | 0 | -0.02 | 0% | NO | -0.02 | 0 | 46941.74 | 0 | 0 | 0 | 0 | 0 | 7% | 7.62% | 0% | -7% |  | 35.67 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23811 | Spirit T300 MRB Concessions | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -22.6396 |  | 0% | 0% | 0 | -7.33% | 0 | 50024.39 | -50024.39 | 2209.6 | 0 | 0 | 50000 | 50024.39 | 0 | 119.59 | 50024.39 | 2264% | YES | 50024.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21% | 13.67% | 13.67% | -7.33% |  | 47.48 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P22760 | SA Leading Edge Transport Media ('A' Frames) | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-11-15 | 1 |  |  | 85.99% | 110.7% | 116.3% | -3082.8 | 3.97% | 53480.8 | 45985.5 | 7495.3 | 0 | 42804 | 42804 | 0 | 0 | 50911.8 | 0 | -0.3 | 0% | NO | -0.3 | -3083 | 53480.9667 | 0 | 0 | 0 | -3082.8 | -3082.8 | 6% | 9.97% | 0% | -6% |  | 42 | [5 empty] | 4926
1742 | 2024-06-12 23:30 | P23891 | A220 FLE Support | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -8.21 |  | 0% | 0% | 0 | 7.8% | 0 | 54878.4 | -54878.4 | 6684.36 | 0 | 0 | 56680.32 | 54878.4 | 0 | 73 | 54878.4 | 821% | YES | 54878.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 14.8% | 14.8% | 7.8% |  | 50.28 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23823 | EXP-034 Spear 3 Test Equip Requirement Authority | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 8.4232 | 66.12% | 87.86% | 54.56% | 0 | 0.07% | 85825 | 56748.88 | 29076.12 | 3451.91 | 1000 | 1000 | 0 | 0 | 49858.26 | 51.97 | 6890.62 | 199.6% | YES | 6890.62 | 22677 | 30960.76 | 0 | 22676.56 | 0 | 0 | 0 | 14% | 14.07% | 14.07% | 0.07% |  | 94.25 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23349 | Spirit 2023 - Stress Approve Man Serv (SB) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 58.24% | 80.05% | 80.05% | 0 | -0.29% | 97920 | 57024 | 40896 | 0 | 0 | 0 | 0 | 0 | 45648 | 13651.2 | 11376 | 0% | NO | 11376 | 0 | 45648 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23642 | MRB Belfast Support | Paul Watson | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -40.9973 |  | 0% | 0% | 0 | -44.55% | 0 | 58369.97 | -58369.97 | 1423.75 | 3718.34 | 3718.34 | 53900 | 58369.97 | 0 | 262.56 | 58369.97 | 4100% | YES | 58369.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22% | -22.55% | -24.68% | -46.68% |  | 38.52 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23760 | EXP-033 Systems Engineering Support | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 41.1696 | 43.22% | 96.81% | 72.88% | 0 | -0.02% | 142300 | 61504.75 | 80795.25 | 1962.5 | 0 | 0 | 0 | 0 | 59542.25 | 46.88 | 1962.5 | 100% | NO | 1962.5 | 17663 | 44823.0833 | 0 | 17662.5 | 0 | 0 | 0 | 29% | 28.98% | 28.98% | -0.02% |  | 78.5 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23740 | Phase 2 - EJ200 ESS EHM Platform Migration | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 3 | FIX |  |  |  | 34.1318 | 27% | 158.7% | 52.92% | 30166.8 | 18.45% | 175971 | 47507.5 | 128463.5 | 3763.75 | 0 | 0 | 0 | 0 | 75417 | 89.65 | -13909.5 | -369.6% | NO | -13909.5 | 60334 | 25138.6667 | 0 | 0 | 30166.8 | 30166.8 | 30166.8 | 28% | 46.45% | 46.45% | 18.45% |  | 42.34 | [5 empty] | 14000
1742 | 2024-06-12 23:30 | P23106 | ME Support to NPD - Bobby Haggart | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  |  | 95.79% | 97.03% | 97.03% | 0 | 0.3% | 65675 | 62912.11 | 2762.89 | 0 | 0 | 0 | 0 | 0 | 61042.75 | 2243.24 | 1869.36 | 0% | NO | 1869.36 | 0 | 61042.75 | 0 | 0 | 0 | 0 | 0 | 15% | 15.3% | 0% | -15% |  | 35.65 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P22967 | Spirit 2022 - Channapa Laxmeshwar | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2023-01-26 | 2 |  |  | 69.69% | 121.3% | 121.3% | 0 | 9.53% | 75159.1 | 52376.15 | 22782.95 | 0 | 52376.15 | 54898.1 | 0 | 0 | 63508.8 | 0.42 | 0.35 | 0% | NO | 2522.3 | 0 | 63508.8 | 0 | 0 | 0 | 0 | 0 | 8% | 17.53% | 0% | -8% |  | 0 | [5 empty] | 11133
1742 | 2024-06-12 23:30 | P23598 | MRB Onsite support | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 23.2835 | 47.75% | 0% | 0% | 0 | -9.67% | 133056 | 63540.17 | 69515.83 | 2985.63 | 8736.42 | 14079.58 | 0 | 0 | 0 | 158.11 | 63540.17 | 2128% | YES | 68883.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 18.33% | 18.59% | -9.41% |  | 42.5 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23877 | Strategic Enablement | Owain Jones | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -27.81% | 0 | 71017.3 | -71017.3 | -1750 | 4000 | 4000 | 67200 | 71017.3 | 0 | 132.48 | 64017.3 | -3658% | NO | 64017.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | -9.81% | -9.81% | -27.81% |  | 42 | [5 empty] | -7000
1742 | 2024-06-12 23:30 | P23193 | Spirit Shorts Stephen Greer | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -16.1708 | 114.5% | 86.28% | 86.28% | 0 | 8.81% | 61472 | 70369.97 | -8897.97 | 550.25 | 0 | 0 | 10878 | 8897.97 | 60712.78 | 106.65 | 9657.19 | 1755% | YES | 9657.19 | 0 | 60712.78 | 0 | 0 | 0 | 0 | 0 | 23% | 31.81% | 34.03% | 11.03% |  | 35.2 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23438 | A220 Spirit Shorts DTC - Stephen Corry | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 73.97% | 90.84% | 90.84% | 0 | -7.56% | 95928.4 | 70961.9 | 24966.5 | -4465.45 | 0 | 0 | 0 | 0 | 64459.8 | 7802.52 | 6502.1 | -145.6% | NO | 6502.1 | 0 | 64459.8 | 0 | 0 | 0 | 0 | 0 | 23% | 15.44% | 5.63% | -17.37% |  | 49.69 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23341 | Spirit 2023 - Tom McFarlane | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 26.5745 | 69.41% | 98.73% | 57.03% | 7110.19 | -0.01% | 108666.4 | 75430.48 | 33235.92 | 1250.67 | 0 | 0 | 0 | 0 | 74472.52 | 209.39 | 957.96 | 76.6% | NO | 957.96 | 37744 | 43019.1867 | 6354.47 | 5886.13 | 4683.36 | 20819.67 | 7110.19 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23600 | MBDA EXP-EE-023 Bristone Certification | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM | 2024-05-31 | 0 |  |  | 59.65% | 100% | 100% | 0 | 0.4% | 126600 | 75517 | 51083 | 0 | 0 | 0 | 0 | 0 | 75517 | 0 | 0 | 0% | NO | 0 | 0 | 75517 | 0 | 0 | 0 | 0 | 0 | 41% | 41.4% | 0% | -41% |  | 78.5 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23080 | Spirit Shorts DManagement Cairan Cullen | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 827.3176 | 51.18% | 99.92% | 96.91% | 0 | -1.31% | 149600 | 76564.4 | 73035.6 | 88.28 | 0 | 0 | 0 | 0 | 76500.2 | 134.97 | 64.2 | 72.72% | NO | 64.2 | 2761 | 74199.3667 | 0 | 2760.6 | 0 | 0 | 0 | 24% | 22.69% | 13.03% | -10.97% |  | 44.38 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P22505 | Spirit MRB Engineering Support 2021 | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 1 |  |  | 91.17% | 100% | 95.78% | 4020.48 | 21.2% | 87110.4 | 79414.95 | 7695.45 | 0 | 0 | 0 | 0 | 0 | 79414.95 | 4020.48 | 0 | 0% | NO | 0 | 4020 | 76064.95 | 0 | 0 | 0 | 4020.48 | 4020.48 | 0% | 21.2% | 0% | 0% |  | 41.88 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P22885 | ME Support (Baxi) | Trevor Knox | 0 | HUV | BAXI HEATING UK LIMITED | ME | Level 3 | FIX | 2023-01-12 | 1 |  |  | 68.78% | 108.7% | 108.7% | 0 | 11.9% | 106632.96 | 73340.24 | 33292.72 | -319 | 0 | 0 | 0 | 0 | 79748.12 | 0.15 | 0.12 | -0.03762% | NO | 0.12 | 0 | 79748.12 | 0 | 0 | 0 | 0 | 0 | 15% | 26.9% | 100% | 85% |  | 44.37 | [5 empty] | 6408
1742 | 2024-06-12 23:30 | P22965 | Spirit 2022 - Design Man Serv (AH) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 106.7% | 96.66% | 96.66% | 0 | 3.14% | 80079.56 | 85441.32 | -5361.76 | 0 | 0 | 0 | 0 | 5361.76 | 82588.96 | 3422.84 | 2852.36 | 0% | NO | 2852.36 | 0 | 82588.96 | 0 | 0 | 0 | 0 | 0 | 14% | 17.14% | 0% | -14% |  | 42.44 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P22964 | Spirit 2022 - MRB Man Serv (JC) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 100.6% | 97.95% | 97.95% | 0 | 1.91% | 85435.2 | 85960.26 | -525.06 | 0 | 0 | 0 | 0 | 525.06 | 84199.74 | 2112.62 | 1760.52 | 0% | NO | 1760.52 | 0 | 84199.74 | 0 | 0 | 0 | 0 | 0 | 16% | 17.91% | 0% | -16% |  | 42.69 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P22963 | Spirit 2022 - Design Man Serv (PC) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 1 |  | -7.909 | 108.6% | 104% | 104% | 0 | 6.39% | 80079.56 | 86926.74 | -6847.18 | 865.75 | 0 | 0 | 0 | 6847.18 | 90389.95 | 0 | -0.21 | -0.02426% | NO | -0.21 | 0 | 90389.95 | 0 | 0 | 0 | 0 | 0 | 13% | 19.39% | 100% | 87% |  | 42.39 | [5 empty] | 3463
1742 | 2024-06-12 23:30 | P23079 | Spirit Shorts Nomenclature | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 16.0271 | 90.21% | 82.42% | 82.42% | 0 | 15.22% | 105147 | 94857.6 | 10289.4 | 642 | 0 | 0 | 0 | 0 | 78185.2 | 181.79 | 16672.4 | 2597% | YES | 16672.4 | 0 | 78185.2 | 0 | 0 | 0 | 0 | 0 | 7% | 22.22% | 25.23% | 18.23% |  | 30.86 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23375 | GKN Jaap Peters NL 2023 | Steven Lawton | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2024-03-01 | 2 |  | 27.9861 | 93.37% | 105.3% | 97.18% | 0 | -15% | 97123.22 | 90686.41 | 6436.81 | 230 | 90686.41 | 90686.41 | 0 | 0 | 95456.72 | 8792.92 | -0.31 | -0.1348% | NO | -0.31 | 8793 | 88129.22 | 0 | 0 | 0 | 8793.29 | 0 | 20% | 5% | 5.94% | -14.06% |  | 0 | [5 empty] | 4770
1742 | 2024-06-12 23:30 | P23340 | Spirit 2023 - John Cole | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 34.4813 | 66.31% | 98.54% | 63.14% | 0 | -0.01% | 150129.72 | 99549.45 | 50580.27 | 1466.89 | 0 | 0 | 0 | 0 | 98097.48 | 176.55 | 1451.97 | 98.98% | NO | 1451.97 | 42294 | 62852.48 | 7064.93 | 8831.16 | 6826.25 | 19571.76 | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 39.78 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23583 | Castalla - Test Rig Design | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 100% | 92.54% | 67.12% | 0 | -26.99% | 100520 | 100538.5 | -18.5 | 0 | 0 | 0 | 0 | 18.5 | 93036.5 | 256.05 | 7502 | 0% | NO | 7502 | 30665 | 67482.3333 | 0 | 30665.28 | 0 | 0 | 0 | 41% | 14.01% | 14.71% | -26.29% |  | 42.79 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23171 | Spirt Shorts Weights Eng | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 22.6582 | 69.18% | 141.4% | 133.5% | 0 | 17.29% | 103113.14 | 71329.32 | 31783.82 | 1402.75 | 71329.32 | 85975.13 | 0 | 0 | 100870.18 | 6733.47 | 0.14 | 0.00998% | NO | 14645.95 | 6733 | 95259.3467 | 0 | 0 | 6733.3 | 0 | 0 | 12% | 29.29% | 57.03% | 45.03% |  | 0 | [5 empty] | 29541
1742 | 2024-06-12 23:30 | P23336 | Spirit 2023 - Neil Rampling | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 32.173 | 75.38% | 100% | 47.42% | 21586.03 | -0.01% | 133901.52 | 100940.6 | 32960.92 | 1024.49 | 0 | 0 | 0 | 0 | 100940.6 | 284.21 | 0 | 0% | NO | 0 | 63694 | 47862.2667 | 6663.14 | 8238.46 | 7259.21 | 41532.89 | 21586.03 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23700 | IPDT Leads | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 14.3706 | 61.25% | 24.05% | 24.05% | 0 | -1.45% | 169263.9 | 103676.03 | 65587.87 | 4564.04 | 0 | 0 | 0 | 0 | 24932.12 | 123.71 | 78743.91 | 1725% | YES | 78743.91 | 0 | 24932.12 | 0 | 0 | 0 | 0 | 0 | 26% | 24.55% | 23.42% | -2.58% |  | 49.89 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23342 | Spirit 2023 - Channapa Laxmeshwar | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 13.7575 | 63.72% | 105.6% | 64.45% | 0 | -4.26% | 158696.7 | 101124.93 | 57571.77 | 4184.77 | 101124.93 | 111566.08 | 0 | 0 | 106807 | 98.77 | -2832.07 | -67.68% | NO | 7609.08 | 49955 | 65177.8333 | 7367.16 | 10092 | 22807.92 | 9688.32 | 0 | 7% | 2.74% | 0% | -7% |  | 0 | [5 empty] | 2850
1742 | 2024-06-12 23:30 | P23345 | Spirit 2023- Jonathan Escosio | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 27.208 | 71.5% | 94.23% | 53.84% | 7150.18 | -0.57% | 151941.24 | 108643.26 | 43297.98 | 1591.37 | 0 | 0 | 0 | 0 | 102379.64 | 224.31 | 6263.62 | 393.6% | YES | 6263.62 | 52658 | 58497.9733 | 7638.58 | 16773.9 | 16361 | 11884.76 | 7150.18 | 7% | 6.43% | 16.26% | 9.26% |  | 43.01 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23560 | NJEWCS TAF202302 SM | Natalie Sinclair | 0 | COB | CHELTON LIMITED | EES | Level 2 | FIX |  |  |  | 29.8787 | 59.42% | 70.31% | 70.31% | 0 | 9.81% | 191500 | 113786.09 | 77713.91 | 2600.98 | 0 | 0 | 0 | 0 | 80000 | 98.51 | 33786.09 | 1299% | YES | 33786.09 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 30% | 39.81% | 39.49% | 9.49% |  | 73.01 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23465 | A220 ToW Design Offload (Wing) | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 38.0044 | 45.77% | 94.46% | 70.48% | 0 | -6.49% | 249700 | 114286.7 | 135413.3 | 3563.1 | 0 | 0 | 0 | 0 | 107952.3 | 100.43 | 6334.4 | 177.8% | YES | 6334.4 | 32883 | 80549.8 | 18040.2 | 0 | 14843.04 | 0 | 0 | 20% | 13.51% | 11% | -9% |  | 42.8 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23744 | Model Factory | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 27.2188 | 43.14% | 99.24% | 39.52% | 26229.6 | 9.77% | 262300 | 113154.75 | 149145.25 | 5479.5 | 0 | 0 | 0 | 0 | 112290 | 101.94 | 5864.75 | 107% | NO | 5864.75 | 81089 | 44715.8333 | 0 | 27429.6 | 27429.6 | 26229.6 | 26229.6 | 28% | 37.77% | 37.77% | 9.77% |  | 51.13 | [5 empty] | 5000
1742 | 2024-06-12 23:30 | P23523 | Applique Armour Support | Dushan Fernando | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-18 | 2 |  | 3.9999 | 72.43% | 138.1% | 98.47% | 40680 | 23.16% | 118200 | 85606.5 | 32593.5 | 8148.5 | 0 | 0 | 0 | 0 | 118200 | 40680.6 | 0.5 | 0.006136% | NO | 0.5 | 40680 | 84300 | 0 | 0 | 0 | 40680 | 40680 | 25% | 48.16% | 100% | 75% |  | 64.29 | [5 empty] | 32594
1742 | 2024-06-12 23:30 | P23551 | Ian Berry 2023 H2 | Natalie Sinclair | 0 | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  | 6.4808 | 81.84% | 56.59% | 56.59% | 0 | 13.9% | 145153.92 | 118788.53 | 26365.39 | 4068.23 | 0 | 0 | 0 | 0 | 67217.49 | 138.3 | 51571.04 | 1268% | YES | 51571.04 | 0 | 67217.49 | 0 | 0 | 0 | 0 | 0 | 22% | 35.9% | 37.71% | 15.71% |  | 78.12 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P22736 | WoT Fixed Leading Edge - Industrial | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 106.7% | 93.42% | 91.32% | 3019.54 | 0.01% | 112196.27 | 119668.47 | -7472.2 | 0 | 0 | 0 | 0 | 7472.2 | 111796.68 | 12465.69 | 7871.79 | 0% | NO | 7871.79 | 3020 | 109280.0133 | 0 | 0 | 0 | 3019.54 | 3019.54 | 7% | 7.01% | 0% | -7% |  | 32.26 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23586 | Project Management Support | Dushan Fernando | 0 | BDX | MBDA UK LIMITED | MPE | Level NC | REIM |  |  |  | 12.544 | 74.88% | 93.8% | 81.95% | 0 | -27.08% | 160000 | 119808.17 | 40191.83 | 3204.08 | 1972 | 1972 | 0 | 0 | 112383.86 | 54.44 | 7424.31 | 231.7% | YES | 7424.31 | 17040 | 98183.86 | 0 | 17040 | 0 | 0 | 0 | 49% | 21.92% | 20.71% | -28.29% |  | 80 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P22918 | Spirit Shorts Graduates | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 8.3568 | 94.29% | 87.08% | 87.08% | 0 | 9.53% | 130000 | 122573.39 | 7426.61 | 888.69 | 0 | 0 | 19800 | 0 | 106734.95 | 130.44 | 15838.44 | 1782% | YES | 15838.44 | 0 | 106734.95 | 0 | 0 | 0 | 0 | 0 | 7% | 16.53% | 17.25% | 10.25% |  | 23.35 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23729 | Honda Tooling | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | FIX |  |  |  | -1.5705 | 109% | 82.55% | 26.19% | 0 | 2.69% | 113610 | 123879 | -10269 | 6538.88 | 0 | 0 | 21000 | 10269 | 102259.5 | 102.51 | 21619.5 | 330.6% | YES | 21619.5 | 83777 | 32445.3333 | 32583.6 | 51193.8 | 0 | 0 | 0 | 10% | 12.69% | 12.69% | 2.69% |  | 42 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23353 | Spirit 2023 - MRB Man Serv (JC) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  | 36.3788 | 68.24% | 100.3% | 54.77% | 0 | 9.26% | 183600 | 125280 | 58320 | 1603.13 | 0 | 0 | 0 | 0 | 125664 | 271.22 | -384 | -23.95% | NO | -384 | 68459 | 68614.8333 | 68458.5 | 0 | 0 | 0 | 0 | 7% | 16.26% | 12.52% | 5.52% |  | 45 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P22861 | WoT FLE Lifting & Handling Tools | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2023-06-14 | 1 |  |  | 65.17% | 101.6% | 101.6% | 0 | 12.01% | 173987.21 | 113381.75 | 60605.46 | 0 | 50078 | 58423.58 | 0 | 0 | 115203.5 | 12813.9 | 10678.25 | 0% | NO | 19023.83 | 0 | 115203.5 | 0 | 0 | 0 | 0 | 0 | 1% | 13.01% | 0% | -1% |  | 45 | [5 empty] | 12500
1742 | 2024-06-12 23:30 | P23664 | Tempest Composites WP3 | Philip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -108.1613 | 106.1% | 84.84% | 66.29% | 0 | -5.13% | 122455.49 | 129898.07 | -7442.58 | 68.81 | 0 | 0 | 29530.92 | 7442.58 | 110210.96 | 224.81 | 19687.11 | 28611% | YES | 19687.11 | 28921 | 86110.1267 | 28920.7 | 0 | 0 | 0 | 0 | 37% | 31.87% | 33.18% | -3.82% |  | 60.89 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23545 | Ultra CSS continuation 2023 H2 | Natalie Sinclair | 0 | ULT | ULTRA SONAR SYSTEMS LIMITED | EES | Level NC | REIM |  |  |  | 20.8916 | 75.43% | 93.83% | 56.83% | 24112.32 | 14.17% | 176000 | 132754.4 | 43245.6 | 2070 | 0 | 0 | 0 | 0 | 124560.8 | 179.4 | 8193.6 | 395.8% | YES | 8193.6 | 58932 | 75450.8 | 34819.2 | 24112.32 | 0 | 0 | 24112.32 | 11% | 25.17% | 25% | 14% |  | 80 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P22883 | Spirit Shorts Evtol PMO C. Hatton | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 72.45% | 101.1% | 80.93% | 0 | -10.87% | 185800 | 134618.15 | 51181.85 | 0 | 0 | 0 | 0 | 0 | 136116.73 | 218.04 | -1498.58 | 0% | NO | -1498.58 | 32604 | 108946.73 | 0 | 32604 | 0 | 0 | 0 | 26% | 15.13% | 22.96% | -3.04% |  | 37.41 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23282 | Tooling Support (MBDA) | Dushan Fernando | 0 | BDV | MBDA UK LIMITED | ME | Level NC | REIM |  |  |  | 39.4815 | 70.73% | 98.58% | 91.9% | 0 | -7.42% | 195672.4 | 138404.05 | 57268.35 | 1450.51 | 0 | 0 | 0 | 0 | 136432.63 | 48.07 | 1971.42 | 135.9% | YES | 1971.42 | 11095 | 127186.7967 | 0 | 11095 | 0 | 0 | 0 | 30% | 22.58% | 30.37% | 0.37% |  | 49.74 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23533 | External Stowage Design and Detail Support | Dushan Fernando | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 1 |  |  | 102.4% | 97.65% | 73.24% | 42000 | 3.33% | 140000 | 143368.75 | -3368.75 | 0 | 0 | 0 | 3369 | 3368.75 | 140000 | 41999.7 | -0.25 | 0% | NO | -0.25 | 42000 | 105000 | 0 | 0 | 0 | 42000 | 42000 | 27% | 30.33% | 0% | -27% |  | 60.04 | [5 empty] | -3369
1742 | 2024-06-12 23:30 | P23270 | Shorts Project X | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 1.159 | 98.69% | 92.07% | 82.59% | 0 | 0.27% | 142248 | 140385.98 | 1862.02 | 1606.61 | 0 | 0 | 0 | 0 | 129246.58 | 102.89 | 11139.4 | 693.3% | YES | 11139.4 | 15963 | 115944.08 | 0 | 7981.34 | 7981.34 | 0 | 0 | 13% | 13.27% | 10.99% | -2.01% |  | 45.29 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23588 | BAE Typhoon MRB MC Shop Concessions | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 13.3718 | 80.36% | 79.7% | 71.17% | 14399.76 | -4.03% | 175060.5 | 140682.16 | 34378.34 | 2570.95 | 0 | 0 | 0 | 0 | 112121.71 | 119.64 | 28560.45 | 1111% | YES | 28560.45 | 14400 | 100121.71 | 0 | 0 | 0 | 14399.76 | 14399.76 | 31% | 26.97% | 27.71% | -3.29% |  | 55.82 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P22954 | Technical Support Step 1 | Owain Jones | 0 | HUV | HUARUI SPIRIT AEROSPACE MANUFACT | ME | Level 2 | REIM |  |  |  |  | 94.81% | 58.01% | 58.01% | 0 | 0.31% | 155501.18 | 147431.58 | 8069.6 | 0 | 23043 | 23043 | 0 | 0 | 85525.49 | 61906.09 | 61906.09 | 0% | NO | 61906.09 | 0 | 85525.49 | 0 | 0 | 0 | 0 | 0 | 30% | 30.31% | 0% | -30% |  | 60.79 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23386 | Software Development - BMS | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 98.78% | 100% | 100% | 0 | 4.31% | 149650 | 147823.35 | 1826.65 | 0 | 0 | 0 | 0 | 0 | 147823.35 | 0 | 0 | 0% | NO | 0 | 0 | 147823.35 | 0 | 0 | 0 | 0 | 0 | 18% | 22.31% | 22.61% | 4.61% |  | 78.5 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23437 | Embedded Software Engineer | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 98.73% | 100% | 96.08% | 6970.8 | -6.29% | 150150 | 148239.36 | 1910.64 | 0 | 737.86 | 737.86 | 0 | 0 | 148239.36 | 182 | 0 | 0% | NO | 0 | 6971 | 142430.1933 | 0 | 0 | 0 | 6970.8 | 6970.8 | 22% | 15.71% | 16.24% | -5.76% |  | 78.5 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P22440 | Spirit Managed Service - F&DT and Static Approval | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 3 |  |  | 88.56% | 92.56% | 92.56% | 0 | 11.51% | 173500 | 153656.25 | 19843.75 | 0 | 52115 | 55720 | 0 | 0 | 142225.12 | 13717.36 | 11431.13 | 0% | NO | 15036.13 | 0 | 142225.12 | 0 | 0 | 0 | 0 | 0 | 0% | 11.51% | 0% | 0% |  | 44.73 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23352 | Spirit 2023 - Stress Approve Man Serv (CC) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  | 6.1763 | 78.96% | 87.86% | 45.21% | 0 | 4.48% | 195840 | 154632 | 41208 | 6672 | 0 | 0 | 0 | 0 | 135864 | 193.75 | 18768 | 281.3% | YES | 18768 | 79142 | 69912.3333 | 79142.4 | 0 | 0 | 0 | 0 | 7% | 11.48% | 5.03% | -1.97% |  | 48 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23550 | Tempest Composites | Philip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -11.7941 | 103.8% | 96.37% | 96.37% | 0 | 5.1% | 149494.92 | 155127.88 | -5632.96 | 477.61 | 0 | 0 | 4209.4 | 5632.96 | 149494.92 | 100.02 | 5632.96 | 1179% | YES | 5632.96 | 0 | 149494.92 | 0 | 0 | 0 | 0 | 0 | 26% | 31.1% | 33.54% | 7.54% |  | 61.64 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P22982 | Spirit 2022 - Hugh Sloan | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 77.0236 | 64.94% | 99.49% | 78.99% | 8217.17 | -0.83% | 247473 | 160706.66 | 86766.34 | 1126.49 | 0 | 0 | 0 | 0 | 159890.62 | 222.02 | 816.04 | 72.44% | NO | 816.04 | 39532 | 126947.2867 | 5662.61 | 5747.76 | 5364.58 | 22756.88 | 8217.17 | 7% | 6.17% | 0.71% | -6.29% |  | 35.48 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23508 | Verification and Validation | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM | 2024-05-31 | 0 |  |  | 80.77% | 100% | 100% | 0 | 10.77% | 212950 | 171993.5 | 40956.5 | 0 | 0 | 0 | 0 | 0 | 171993.53 | 0 | -0.03 | 0% | NO | -0.03 | 0 | 171993.53 | 0 | 0 | 0 | 0 | 0 | 24% | 34.77% | 33.6% | 9.6% |  | 78.5 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23753 | Tempest Composites Maturation | Philip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | -3.8715 | 137.8% | 60.29% | 40.3% | 0 | -4.84% | 127848.45 | 176221.93 | -48373.48 | 12494.71 | 0 | 0 | 49419.2 | 48373.48 | 106238.78 | 74.58 | 69983.15 | 560.1% | YES | 69983.15 | 42256 | 71025.4467 | 0 | 42255.9 | 0 | 0 | 0 | 29% | 24.16% | 24.16% | -4.84% |  | 64.03 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23518 | Systems Engineering support to FCAS | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 3.446 | 94.7% | 86.71% | 86.71% | 0 | 2.02% | 193736.8 | 183460.31 | 10276.49 | 2982.14 | 4551.96 | 4551.96 | 39680 | 0 | 159084.68 | 70.91 | 24375.63 | 817.4% | YES | 24375.63 | 0 | 159084.68 | 0 | 0 | 0 | 0 | 0 | 21% | 23.02% | 3.47% | -17.53% |  | 69.24 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23464 | A220 Project X Design Offload | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 111.7668 | 55.56% | 95.93% | 80.45% | 27862.8 | -9.85% | 332340 | 184645.7 | 147694.3 | 1321.45 | 0 | 0 | 0 | 0 | 177134.3 | 172.88 | 7511.4 | 568.4% | YES | 7511.4 | 34308 | 148544.3 | 4545.36 | 0 | 1900.32 | 27862.8 | 27862.8 | 26% | 16.15% | 13.26% | -12.74% |  | 42.87 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23822 | FCASW Requirements Management | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 33.8657 | 32.41% | 88.43% | -4.317e-05% | 0 | -2.07% | 595703 | 193040.06 | 402662.94 | 11889.98 | 0 | 0 | 0 | 0 | 170698.25 | 121.76 | 22341.81 | 187.9% | YES | 22341.81 | 204838 | -0.083333 | 0 | 204837.9 | 0 | 0 | 0 | 17% | 14.93% | 14.93% | -2.07% |  | 78.28 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23421 | A220 DTC | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 6.6702 | 89.61% | 81.3% | 61.82% | 0 | -28.03% | 217089.12 | 194532.09 | 22557.03 | 3381.74 | 0 | 0 | 0 | 0 | 158146.02 | 143.12 | 36386.07 | 1076% | YES | 36386.07 | 45461 | 120261.8533 | 0 | 33057.86 | 12403.44 | 0 | 0 | 29% | 0.97% | 5.14% | -23.86% |  | 45.87 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23667 | Safety Systems Engineer | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 51.3897 | 49.22% | 96.13% | 86.02% | 0 | -11.36% | 398000 | 195910 | 202090 | 3932.5 | 0 | 0 | 0 | 0 | 188320 | 49.15 | 7590 | 193% | YES | 7590 | 23760 | 168520 | 0 | 23760 | 0 | 0 | 0 | 47% | 35.64% | 29.32% | -17.68% |  | 110 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23008 | Spirit Shorts Project Rachel | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 68.49% | 91.32% | 91.32% | 0 | -9.7% | 286960 | 196531.2 | 90428.8 | 0 | 0 | 0 | 0 | 0 | 179472.8 | 20470.08 | 17058.4 | 0% | NO | 17058.4 | 0 | 179472.8 | 0 | 0 | 0 | 0 | 0 | 15% | 5.3% | 0.31% | -14.69% |  | 46.04 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23019 | EXP034-B Actuator Development | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 103.1% | 89.91% | 89.91% | 0 | -16.68% | 215541.2 | 222215.54 | -6674.34 | 0 | 12297.9 | 12297.9 | 0 | 6674.34 | 199796.76 | 477.34 | 397.78 | 0% | NO | 397.78 | 0 | 199796.76 | 0 | 0 | 0 | 0 | 0 | 34% | 17.32% | 79.64% | 45.64% |  | 58.45 | [5 empty] | -22021
1742 | 2024-06-12 23:30 | P23242 | Physical Architecture & System Engineering Support | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 27.2089 | 75.26% | 97.4% | 91.23% | 0 | 6.31% | 305459 | 229901.46 | 75557.54 | 2776.94 | 775.55 | 775.55 | 0 | 0 | 223914.55 | 50.18 | 5632.91 | 202.8% | YES | 5632.91 | 17003 | 209745.3833 | 0 | 17003.1 | 0 | 0 | 0 | 15% | 21.31% | 7.38% | -7.62% |  | 78.23 | [5 empty] | -354
1742 | 2024-06-12 23:30 | P23506 | ASTER Mid-Life Refurbishment Project Manager | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 27.4079 | 71.18% | 96.17% | 88.92% | 0 | 1.02% | 326900 | 232685.37 | 94214.63 | 3437.5 | 3830.37 | 3830.37 | 0 | 0 | 223775.37 | 47.19 | 8910 | 259.2% | YES | 8910 | 20237 | 206911.2033 | 1228.75 | 19008 | 0 | 0 | 0 | 25% | 26.02% | 26.15% | 1.15% |  | 110 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23505 | EXP-022 Meteor TBUS T&E support | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 3.1952 | 95.02% | 96.89% | 88.27% | 0 | -1.59% | 246744.4 | 234456.3 | 12288.1 | 3845.85 | 0 | 0 | 0 | 0 | 227157.63 | 53.47 | 7298.67 | 189.8% | YES | 7298.67 | 24254 | 206945.9633 | 0 | 24254.1 | 0 | 0 | 0 | 20% | 18.41% | 15.67% | -4.33% |  | 89.83 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23373 | Raytheon Michael Bellini | Natalie Sinclair | 0 | RAS | RAYTHEON UNITED KINGDOM LIMITED | EES | Level NC | REIM |  |  |  | 37.2646 | 56.53% | 86.86% | 70.61% | 24734.7 | -7.6% | 428734.8 | 242367.55 | 186367.25 | 5001.19 | 0 | 0 | 0 | 0 | 210519.78 | 140.44 | 31847.77 | 636.8% | YES | 31847.77 | 47271 | 171127.28 | 0 | 22536.06 | 0 | 24734.7 | 24734.7 | 45% | 37.4% | 38.74% | -6.26% |  | 91.61 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23754 | Tempest Composites WP4 | Philip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 2.5531 | 84.54% | 0% | 0% | 0 | -2.85% | 310945.68 | 262860.25 | 48085.43 | 18833.8 | 1784.87 | 1784.87 | 0 | 0 | 0 | 127.09 | 262860.25 | 1396% | YES | 262860.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36% | 33.15% | 33.15% | -2.85% |  | 60.12 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23524 | Bombardier Regional Jets (BRJ) | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 2.5896 | 91.61% | 40.98% | 39.82% | 3694.07 | -8.28% | 289916.08 | 265601.23 | 24314.85 | 9389.52 | 0 | 0 | 0 | 0 | 108838.22 | 266.39 | 156763.01 | 1670% | YES | 156763.01 | 3694 | 105759.8867 | 0 | 0 | 0 | 3694.07 | 3694.07 | 22% | 13.72% | 14.95% | -7.05% |  | 43.81 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23741 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  | 28.2417 | 41.16% | 96.93% | 33.66% | 62626.8 | 2.44% | 640812 | 263726.4 | 377085.6 | 13352.1 | 0 | 0 | 0 | 0 | 255639 | 100.59 | 14087.4 | 105.5% | NO | 14087.4 | 200243 | 88769.8333 | 0 | 68808 | 68808 | 62626.8 | 62626.8 | 28% | 30.44% | 30.44% | 2.44% |  | 38.78 | [5 empty] | 6000
1742 | 2024-06-12 23:30 | P23648 | EXP-032 Delivery of Datalink Eng support - FCAS AP | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 8.2919 | 75.59% | 65.35% | 58.23% | 0 | 7.71% | 371000 | 280434.2 | 90565.8 | 10922.19 | 1032.95 | 1032.95 | 0 | 0 | 183267.95 | 82.8 | 97166.25 | 889.6% | YES | 97166.25 | 23958 | 163302.95 | 0 | 23958 | 0 | 0 | 0 | 22% | 29.71% | 30.37% | 8.37% |  | 101.9 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23739 | Lifing Services DACs | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  | 31.4322 | 40.97% | 102.8% | 41.06% | 65650.8 | 6.04% | 656508 | 268946.8 | 387561.2 | 12330.05 | 0 | 0 | 0 | 0 | 276545 | 103.3 | 4401.8 | 35.7% | NO | 4401.8 | 199352 | 110418.3333 | 0 | 66850.8 | 66850.8 | 65650.8 | 65650.8 | 28% | 34.04% | 34.04% | 6.04% |  | 37.82 | [5 empty] | 12000
1742 | 2024-06-12 23:30 | P23007 | EXP-006A - Brimstone 3 | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 43.4577 | 71.7% | 98.33% | 95.18% | 0 | -2.28% | 406450 | 291414.91 | 115035.09 | 2647.06 | 0 | 0 | 0 | 0 | 286547.91 | 47.52 | 4867 | 183.9% | YES | 4867 | 11021 | 277363.7433 | 0 | 11021.44 | 0 | 0 | 0 | 25% | 22.72% | 29.98% | 4.98% |  | 70.32 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23308 | NATO JEWCS | Natalie Sinclair | 0 | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  | 20.4813 | 87.89% | 91.57% | 87.36% | 15829.13 | -4.21% | 356307 | 313169.4 | 43137.6 | 2106.19 | 756.39 | 756.39 | 0 | 0 | 286767.43 | 157.37 | 26401.97 | 1254% | YES | 26401.97 | 15829 | 273576.5967 | 0 | 15829.13 | 0 | 0 | 15829.13 | 24% | 19.79% | 11.85% | -12.15% |  | 75.81 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P22953 | Spirit Shorts eVTOL | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-05-08 | 1 |  |  | 103.1% | 80.83% | 80.83% | 0 | -9.51% | 324272 | 334483.6 | -10211.6 | 0 | 66696.6 | 67387.9 | 0 | 10211.6 | 270366 | 64941.12 | 54117.6 | 0% | NO | 54808.9 | 0 | 270366 | 0 | 0 | 0 | 0 | 0 | 17% | 7.49% | 100% | 83% |  | 46.19 | [5 empty] | -10000
1742 | 2024-06-12 23:30 | P21463 | Safety & Monitoring Systems at DM Beith & Gosport | Harry James Kellett | 0 | BXW | MOD | EES | Level 2 | FIX |  |  |  | 71.0552 | 88.21% | 113.4% | 113.4% | 0 | -23.47% | 378612.83 | 333964.6 | 44648.23 | 628.36 | 75631.47 | 79790.28 | 45616.14 | 0 | 378594.83 | 0 | -44630.23 | -7103% | NO | -40471.42 | 0 | 378594.83 | 0 | 0 | 0 | 0 | 0 | 48% | 24.53% | 39.5% | -8.5% |  | 56.3 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23472 | Tempest Wing Design | Philip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 14.5517 | 55.62% | 120.6% | 113.2% | 0 | -0.45% | 483869.78 | 269104.61 | 214765.17 | 14758.75 | 253225 | 356900 | 0 | 0 | 324639.1 | 83.97 | 14250.51 | 96.56% | NO | 117925.51 | 23858 | 304757.4333 | 0 | 23857.58 | 0 | 0 | 0 | 23% | 22.55% | 45.77% | 22.77% |  | 46.74 | [5 empty] | 69785
1742 | 2024-06-12 23:30 | P22515 | Shorts A220 100/300 ALI Phase III | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 51.9199 | 84.69% | 98.6% | 94.52% | 0 | 0.52% | 400628.76 | 339281.75 | 61347.01 | 1181.57 | 3450.98 | 3450.98 | 0 | 0 | 334523.97 | 90.62 | 4757.78 | 402.7% | YES | 4757.78 | 16622 | 320672.3033 | 7501.03 | 0 | 9121.46 | 0 | 0 | 10% | 10.52% | 6.57% | -3.43% |  | 40.58 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P22842 | ME Support (Aim Altitude) | Trevor Knox | 0 | AVI | AIM ALTITUDE UK LIMITED | ME | Level 3 | FIX | 2023-06-14 | 4 |  |  | 99.31% | 100.5% | 86.63% | 57290.84 | 0.49% | 346293.67 | 343918.08 | 2375.59 | 0 | 2909.86 | 2909.86 | 0 | 0 | 345673.01 | 55184.93 | -1754.93 | 0% | NO | -1754.93 | 57291 | 297930.51 | 0 | 0 | 0 | 57290.84 | 57290.84 | 13% | 13.49% | 0% | -13% |  | 46.3 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23816 | Typhoon FTI Works - 2024 Fixed Price Element | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  |  | 83.49% | 85.76% | 54.38% | 0 | -1.67% | 404176.65 | 337446.98 | 66729.67 | -2531.91 | 0 | 0 | 0 | 0 | 289390.14 | 64.44 | 58056.84 | -2293% | NO | 58056.84 | 127073 | 183495.9733 | 0 | 127072.97 | 0 | 0 | 0 | 30% | 28.33% | 28.33% | -1.67% |  | 50.47 | [5 empty] | 10000
1742 | 2024-06-12 23:30 | P23629 | F35 FTI | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level NC | REIM |  |  |  | -33.0413 |  | 79.77% | 79.77% | 0 | -1.85% | 0 | 352619.13 | -352619.13 | 10672.06 | 0 | 0 | 0 | 352619.13 | 281269.67 | 44.4 | 71349.46 | 668.6% | YES | 71349.46 | 0 | 281269.67 | 0 | 0 | 0 | 0 | 0 | 31% | 29.15% | 28.16% | -2.84% |  | 61.39 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P22391 | GE System Engineering support | Vinayakumar Sugur | 0 | GEE | EXPERIS LIMITED | EES | Level NC | REIM | 2024-04-08 | 1 |  | 122.8662 | 82.01% | 100.7% | 100.7% | 0 | 0.8% | 434434.25 | 356260.63 | 78173.62 | 636.25 | 0 | 0 | 0 | 0 | 358805.6 | 0.04 | 0.03 | 0.004715% | NO | 0.03 | 0 | 358805.6 | 0 | 0 | 0 | 0 | 0 | 6% | 6.8% | 60.63% | 54.63% |  | 57.33 | [5 empty] | 2545
1742 | 2024-06-12 23:30 | P23617 | Tempest Composites WP2 | Philip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -21.4672 | 159.6% | 52.19% | 19.62% | 29536.68 | 11.5% | 244405.26 | 390155.89 | -145750.63 | 6789.47 | 0 | 0 | 153486.97 | 145750.63 | 203633.76 | 392.13 | 186522.13 | 2747% | YES | 186522.13 | 152516 | 76537.0933 | 122979.42 | 0 | 0 | 29536.68 | 29536.68 | 22% | 33.5% | 33.03% | 11.03% |  | 62.22 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23743 | EHM Cloud Migration | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 37.2685 | 35.94% | 117.1% | 46.76% | 102336 | 8.72% | 1016000 | 365174.63 | 650825.37 | 17463.13 | 0 | 0 | 0 | 0 | 427656 | 90.36 | -23481.38 | -134.5% | NO | -23481.38 | 308285 | 170751.8333 | 0 | 102336 | 103612.8 | 102336 | 102336 | 28% | 36.72% | 36.72% | 8.72% |  | 55.78 | [5 empty] | 39000
1742 | 2024-06-12 23:30 | P23045 | Shotgun Adaptors - 10 Sets | Harry James Kellett | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | FIX | 2024-02-27 | 3 |  | 384.5859 | 78.74% | 127% | 127% | 0 | 2.55% | 399276.11 | 314390.3 | 84885.81 | 220.72 | 214550.47 | 214550.47 | 0 | 0 | 399276.11 | 349.55 | 15877.19 | 7193% | YES | 15877.19 | 0 | 399276.11 | 0 | 0 | 0 | 0 | 0 | 31% | 33.55% | 93.96% | 62.96% |  | 58.52 | [5 empty] | 100763
1742 | 2024-06-12 23:30 | P23603 | Typhoon IMDLR | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | -3.6093 | 136.4% | 73.33% | 28.8% | 0 | 0.98% | 305067.09 | 416002.47 | -110935.38 | 30735.58 | 1500 | 1500 | 152797.11 | 110935.38 | 305064.02 | 295.96 | 110938.45 | 360.9% | YES | 110938.45 | 222307 | 119808.1867 | 0 | 222307.42 | 0 | 0 | 0 | 28% | 28.98% | 27.41% | -0.59% |  | 56.21 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23432 | Spirit Belfast MRB On-Site Support (Mon & Clear) | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 61.5519 | 65.77% | 138.7% | 128.6% | 0 | -9.79% | 449545 | 295665.27 | 153879.73 | 2500 | 295665.27 | 451827.33 | 0 | 0 | 410199.75 | 44916.62 | 7465.52 | 298.6% | YES | 163627.58 | 35958 | 380234.75 | 0 | 35958 | 0 | 0 | 0 | 39% | 29.21% | 100% | 61% |  | 0 | [5 empty] | 122000
1742 | 2024-06-12 23:30 | P23023 | Spirit Shorts R Foster/M Gourley | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 90.2238 | 72.1% | 106.7% | 98.68% | 0 | -1.12% | 590659.44 | 425851.29 | 164808.15 | 1826.66 | 237621.5 | 267726 | 0 | 0 | 454499.72 | 64.82 | -6282.43 | -343.9% | NO | 23822.07 | 41139 | 420217.22 | 0 | 20921.8 | 20217.14 | 0 | 0 | 9% | 7.88% | 11.11% | 2.11% |  | 29.71 | [5 empty] | 22366
1742 | 2024-06-12 23:30 | P23677 | ME Managed Service - Phase 1 | Paul Watson | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  | 22.7445 | 40.84% | 73.61% | 0% | 0 | -10.52% | 1116000 | 455756.35 | 660243.65 | 29028.75 | 0 | 38000 | 0 | 0 | 335497.5 | 138.59 | 120258.85 | 414.3% | YES | 158258.85 | 402597 | 0 | 116181 | 71536.5 | 214879.5 | 0 | 0 | 30% | 19.48% | 21.09% | -8.91% |  | 44.21 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P22906 | Spirit Shorts - MRB JD Support | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 2.8814 | 98.61% | 82.48% | 65.04% | 99451.32 | -7.97% | 481714 | 475039.18 | 6674.82 | 2316.5 | 0 | 0 | 0 | 0 | 391817.62 | 442.13 | 91221.56 | 3938% | YES | 91221.56 | 99451 | 308941.7867 | 0 | 0 | 0 | 99451.32 | 99451.32 | 13% | 5.03% | 2.39% | -10.61% |  | 36.97 | [5 empty] | 8000
1742 | 2024-06-12 23:30 | P22652 | L3 - Saftey Engineering | Sean Simmons | 0 | LHW | L3HARRIS MAPPS LIMITED | EES | Level NC | FIX |  |  |  |  | 95.63% | 95.66% | 95.66% | 0 | 5.66% | 523390 | 500497.5 | 22892.5 | 0 | 0 | 0 | 0 | 0 | 478783.75 | 26056.5 | 21713.75 | 0% | NO | 21713.75 | 0 | 478783.75 | 0 | 0 | 0 | 0 | 0 | 21% | 26.66% | 25.88% | 4.88% |  | 83.05 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23281 | Systems Portfolio | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM | 2024-02-28 | 0 |  |  | 44.43% | 97.31% | 97.31% | 0 | -17.25% | 1177697.24 | 523236.96 | 654460.28 | 0 | 2133.28 | 2133.28 | 0 | 0 | 509179.87 | 15792.1 | 13160.09 | 0% | NO | 13160.09 | 0 | 509179.87 | 0 | 0 | 0 | 0 | 0 | 25% | 7.75% | 100% | 75% |  | 70.48 | [5 empty] | -897
1742 | 2024-06-12 23:30 | P23531 | BAe Systems F35 MRB Support | Richard Brook | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | -69.1009 |  | 93.95% | 93.95% | 0 | 3.73% | 0 | 539431.94 | -539431.94 | 7806.44 | 287.44 | 287.44 | 0 | 539431.94 | 506774.08 | 26.43 | 32657.86 | 418.3% | YES | 32657.86 | 0 | 506774.08 | 0 | 0 | 0 | 0 | 0 | 25% | 28.73% | 31.83% | 6.83% |  | 60.17 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23554 | Dornier Seawings 328 2023 H2 Support | Natalie Sinclair | 0 | DAX | EXPLEO GERMANY GMBH (EC) | MPE | Level 2 | REIM |  |  |  | -4.2229 | 109% | 77.26% | 77.26% | 0 | 5.12% | 508481.81 | 554291.67 | -45809.86 | 10847.84 | 4046.44 | 4046.44 | 48522.5 | 45809.86 | 428252.8 | 94.07 | 126038.87 | 1162% | YES | 126038.87 | 0 | 428252.8 | 0 | 0 | 0 | 0 | 0 | 21% | 26.12% | 22.35% | 1.35% |  | 65.32 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23699 | A220 Stress Checkers | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -4.6252 | 137.9% | 67.42% | 4.735e-05% | 0 | 7.04% | 408328.79 | 563132.36 | -154803.57 | 33469.5 | 12000 | 12000 | 185592 | 154803.57 | 379653.6 | 177.26 | 183478.76 | 548.2% | YES | 183478.76 | 455584 | 0.26667 | 0 | 455584.32 | 0 | 0 | 0 | 13% | 20.04% | 20.06% | 7.06% |  | 61.88 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23001 | Spirit Shorts A220 Design | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -13.3739 | 118.3% | 73.46% | 69.19% | 0 | 11.18% | 486640 | 575863 | -89223 | 6671.45 | 0 | 0 | 65953.2 | 89223 | 423039.7 | 307.84 | 152823.3 | 2291% | YES | 152823.3 | 29532 | 398429.7 | 7601.28 | 0 | 21930.72 | 0 | 0 | 9% | 20.18% | 12.58% | 3.58% |  | 43.53 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23520 | FCAS AP Portfolio Systems | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 21.4557 | 72.31% | 95.87% | 87.4% | 0 | -6.37% | 810821 | 586274.8 | 224546.2 | 10465.56 | 423 | 423 | 0 | 0 | 562047.44 | 43.14 | 19944.36 | 190.6% | YES | 19944.36 | 59604 | 512377.44 | 0 | 59604 | 0 | 0 | 0 | 22% | 15.63% | 16.64% | -5.36% |  | 81.36 | [5 empty] | -4283
1742 | 2024-06-12 23:30 | P23219 | Tornado Air 800 Engineering Support | Richard Brook | 0 | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 3 | REIM |  |  |  | -1.0576 | 100.5% | 93.53% | 93.53% | 0 | -1.45% | 615046 | 618400.61 | -3354.61 | 3171.83 | 459.21 | 459.21 | 0 | 3354.61 | 578373.17 | 77.46 | 15120.44 | 476.7% | YES | 15120.44 | 0 | 578373.17 | 0 | 0 | 0 | 0 | 0 | 31% | 29.55% | -236.9% | -267.9% |  | 81.22 | [5 empty] | -24907
1742 | 2024-06-12 23:30 | P23140 | Spirit Shorts A220 MLG Stress Support | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  | 16.7912 | 77.99% | 94.29% | 64.64% | 0 | -8.17% | 735573.4 | 573706.98 | 161866.42 | 9639.98 | 20870.3 | 87811.88 | 111743 | 0 | 540939.4 | 168.76 | 57767.58 | 599.2% | YES | 124709.16 | 204098 | 370857.7333 | 0 | 0 | 204098.4 | 0 | 0 | 17% | 8.83% | -10.29% | -27.29% |  | 44.54 | [5 empty] | 25000
1742 | 2024-06-12 23:30 | P23372 | BAE Carbon Tooling Off-load | Gary Kempster | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | 7.8961 | 91.62% | 98.75% | 70.55% | 0 | -3.25% | 674141.57 | 617657.02 | 56484.55 | 7153.44 | 0 | 0 | 0 | 0 | 609936.5 | 178.9 | 7720.52 | 107.9% | NO | 7720.52 | 208981 | 435785.6667 | 33755.72 | 175224.95 | 0 | 0 | 0 | 25% | 21.75% | 18.61% | -6.39% |  | 54.01 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P22790 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | REIM | 2024-04-28 | 0 |  |  | 184.8% | 95.2% | 95.2% | 0 | 0.57% | 352240 | 651013.87 | -298773.87 | -11111.65 | 1611.52 | 1611.52 | 44500 | 298773.87 | 619743.88 | 0 | -0.01 | 9e-05% | NO | -0.01 | 0 | 619743.88 | 0 | 0 | 0 | 0 | 0 | 13% | 13.57% | 28.82% | 15.82% |  | 45.02 | [5 empty] | -31270
1742 | 2024-06-12 23:30 | P23473 | Tempest Vertical Tail | Philip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 25.1379 | 72.94% | 96.06% | 89.93% | 0 | -7.13% | 846017.62 | 617107.46 | 228910.16 | 9106.19 | 112700 | 129075 | 0 | 0 | 592767.31 | 48.48 | 29340.15 | 322.2% | YES | 45715.15 | 45333 | 554989.81 | 0 | 45333.23 | 0 | 0 | 0 | 29% | 21.87% | 23.9% | -5.1% |  | 62.7 | [5 empty] | 5000
1742 | 2024-06-12 23:30 | P23605 | Typhoon Work Package 2 Continuation | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM |  |  |  |  | 103.4% | 93.76% | 84.08% | 0 | 4.87% | 627011.01 | 648187.81 | -21176.8 | -948.07 | 5554 | 5554 | 0 | 21176.8 | 607723.77 | 2579.03 | 40464.04 | -4268% | NO | 40464.04 | 75285 | 544986.27 | 0 | 75284.54 | 0 | 0 | 0 | 23% | 27.87% | 27.69% | 4.69% |  | 55.6 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23323 | CNC-CMM Programming Support | Stephen Young | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  | -5.1778 | 107.3% | 93.13% | 86.67% | 0 | -1.82% | 617809.74 | 662866.55 | -45056.81 | 8701.91 | 15941.56 | 17789.56 | 99488.9 | 45056.81 | 617295.69 | 68.16 | 45570.86 | 523.7% | YES | 47418.86 | 51363 | 574493.19 | 51362.6 | 0 | 0 | 0 | 0 | 32% | 30.18% | 36.64% | 4.64% |  | 57.7 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23366 | Business Analyst Support | Peter Williams | 0 | BDZ | MBDA UK LIMITED | DET | Level 3 | REIM |  |  |  | 81.8771 | 29.13% | 182% | 148.7% | 0 | -0.46% | 1302200 | 379377.66 | 922822.34 | 11270.82 | 302582.15 | 900840.72 | 0 | 0 | 690640 | 64.67 | -23392.34 | -207.5% | NO | 574866.23 | 151776 | 564160 | 73824 | 77952 | 0 | 0 | 0 | 43% | 42.54% | 18.93% | -24.07% |  | 46.72 | [5 empty] | 287870
1742 | 2024-06-12 23:30 | P23694 | Systems Portfolio EXP-011a | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | -2.5596 | 105.4% | 80.02% | 62.52% | 0 | 1.85% | 648492.8 | 683562.76 | -35069.96 | 13701.12 | 809.51 | 809.51 | 0 | 35069.96 | 546983.95 | 86.18 | 136578.81 | 996.8% | YES | 136578.81 | 143520 | 427383.95 | 782.11 | 0 | 142737.46 | 0 | 0 | 21% | 22.85% | 20.51% | -0.49% |  | 88.59 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23426 | BAE Tempest WP 3 Harness Maturation | Philip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 0.094924 | 99.76% | 96.13% | 67.1% | 107757.52 | -6.23% | 884012.04 | 881921.33 | 2090.71 | 22025.17 | 213.34 | 213.34 | 0 | 0 | 847792.24 | 105.43 | 34129.09 | 155% | YES | 34129.09 | 307226 | 591770.5733 | 120017.4 | 79451.21 | 107757.52 | 0 | 107757.52 | 33% | 26.77% | 26.94% | -6.06% |  | 52.46 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23685 | DAC LUC Support and Recompliance | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 30.597 | 34.67% | 159.3% | 65.03% | 274286.4 | 9.25% | 2180000 | 755724.36 | 1424275.64 | 46549.46 | 0 | 0 | 0 | 0 | 1203934 | 73.72 | -312445.64 | -671.2% | NO | -312445.64 | 855007 | 491428.1667 | 0 | 283279.2 | 297441.6 | 274286.4 | 274286.4 | 30% | 39.25% | 39.25% | 9.25% |  | 57.28 | [5 empty] | 135764
1742 | 2024-06-12 23:30 | P23105 | Raytheon Supply Engineering Support | Natalie Sinclair | 0 | RAY | RAYTHEON UNITED KINGDOM LIMITED | MPE | Level 3A | REIM | 2023-07-13 | 3 |  |  | 74.19% | 99.35% | 90.07% | 49156.8 | -2.02% | 1250075.75 | 927395.25 | 322680.5 | 0 | 0 | 0 | 0 | 0 | 921359.25 | 107644.5 | 3672 | 0% | NO | 3672 | 103238 | 835327.5833 | 54081.3 | 0 | 0 | 49156.8 | 49156.8 | 26% | 23.98% | 100% | 74% |  | 48.97 | [5 empty] | -2364
1742 | 2024-06-12 23:30 | P23117 | BAE Typhoon Eng Support | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | 2024-03-12 | 3 |  |  | 103.2% | 96.92% | 96.92% | 0 | -1.09% | 950771.99 | 980837.59 | -30065.6 | -4930.23 | 19213.34 | 20141.26 | 4921.28 | 30065.6 | 950609.41 | 2311.1 | 3132.18 | -63.53% | NO | 4060.1 | 0 | 950609.41 | 0 | 0 | 0 | 0 | 0 | 30% | 28.91% | 20.68% | -9.32% |  | 52.29 | [5 empty] | -27096
1742 | 2024-06-12 23:30 | P23451 | BAE Tempest - DFM-ASO Planning | Stephen Young | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | 9.4775 | 86.27% | 91.03% | 64.53% | 27224.9 | -3.05% | 1145785.42 | 988517 | 157268.42 | 16593.83 | 0 | 0 | 0 | 0 | 899799.63 | 137.06 | 87634.37 | 528.1% | YES | 87634.37 | 314247 | 637927.13 | 75655.99 | 211366.22 | 0 | 27224.9 | 27224.9 | 28% | 24.95% | 26.28% | -1.72% |  | 53.85 | [5 empty] | -1083
1742 | 2024-06-12 23:30 | P22350 | EMP 2020-2021 | Natalie Sinclair | 0 | ARY | GUIDANT GLOBAL UK LIMITED | PCPR | Level NC | REIM |  |  |  | -2.0575 | 100.9% | 98.79% | 94.74% | 10748.57 | -2.08% | 1017579.76 | 1026385.66 | -8805.9 | 4279.89 | 400 | 400 | 0 | 8805.9 | 1013989.91 | 80.02 | 12395.75 | 289.6% | YES | 12395.75 | 49874 | 972428.2433 | 5231.22 | 22178.24 | 22464.33 | 0 | 10748.57 | 32% | 29.92% | 28.22% | -3.78% |  | 44.16 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23602 | EXP-025 Portfolio Software Engineering Support | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 9.5544 | 78.32% | 89.18% | 78.33% | 0 | -1.12% | 1327080 | 1039391.12 | 287688.88 | 30110.76 | 4348.66 | 929790.21 | 0 | 0 | 926909.33 | 51.13 | 112481.79 | 373.6% | YES | 1037923.34 | 135246 | 814204.33 | 0 | 135246.31 | 0 | 0 | 0 | 24% | 22.88% | 22.6% | -1.4% |  | 83.45 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P22671 | Spirit Shorts Pylon and Fairing Package | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX | 2023-05-03 | 1 |  |  | 105% | 95.26% | 95.26% | 0 | -7.36% | 1198494.77 | 1258071.09 | -59576.32 | -530 | 106494.89 | 106494.89 | 0 | 59576.32 | 1198494.77 | 0.39 | 0.32 | -0.06038% | NO | 0.32 | 0 | 1198494.77 | 0 | 0 | 0 | 0 | 0 | 20% | 12.64% | 102.1% | 82.09% |  | 45.4 | [5 empty] | -59576
1742 | 2024-06-12 23:30 | P23152 | Project Aragon - Design and Stress Support | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | -5.1105 | 104.8% | 87.29% | 72.85% | 0 | 0.46% | 1333452.21 | 1397106.83 | -63654.62 | 12455.59 | 0 | 0 | 49524 | 63654.62 | 1219477.02 | 227.78 | 177629.81 | 1426% | YES | 177629.81 | 241970 | 1017835.3533 | 0 | 241969.72 | 0 | 0 | 0 | 29% | 29.46% | 29.32% | 0.32% |  | 52.01 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23292 | BAE Tempest WP 4 AV Trays | Philip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 2.1628 | 96.9% | 97.96% | 85.1% | 0 | 1.28% | 1498284.22 | 1451884.42 | 46399.8 | 21453.52 | 0 | 0 | 0 | 0 | 1422222.18 | 69.5 | 29662.24 | 138.3% | YES | 29662.24 | 223979 | 1235573.0133 | 125131.58 | 98847.53 | 0 | 0 | 0 | 32% | 33.28% | 31.66% | -0.34% |  | 54.02 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23411 | Agile & Scrum Delivery Service | Peter Williams | 0 | BDZ | MBDA UK LIMITED | DET | Level 2 | REIM | 2023-08-14 | 0 |  |  | 36.3% | 170.5% | 170.5% | 0 | 13.08% | 2487000 | 902903.79 | 1584096.21 | 0 | 894178.59 | 894178.59 | 0 | 0 | 1539600 | 19368.95 | 16140.79 | 0% | NO | 16140.79 | 0 | 1539600 | 0 | 0 | 0 | 0 | 0 | 29% | 42.08% | 0% | -29% |  | 74.57 | [5 empty] | 652837
1742 | 2024-06-12 23:30 | P23519 | Mechanical and Electrical Design Eng Support | Dushan Fernando | 0 | BAX | SAFRAN SEATS GB LIMITED | MPE | Level 2 | REIM |  |  |  | 8.5951 | 88.07% | 94.94% | 87.53% | 0 | -2.55% | 1807261.3 | 1591691.75 | 215569.55 | 25080.51 | 1004.45 | 1504.45 | 0 | 0 | 1511140.05 | 41.37 | 58651.7 | 233.9% | YES | 59151.7 | 141528 | 1393200.05 | 0 | 141528.3 | 0 | 0 | 0 | 33% | 30.45% | 29.25% | -3.75% |  | 56.67 | [5 empty] | -21900
1742 | 2024-06-12 23:30 | P22278 | TAI Supply Engineers to Ankara | Natalie Sinclair | 0 | TAI | TUSAS-TURK HAVACILIK VE UZAY | MPE | Level 3A | REIM |  |  |  | 1598.6155 | 19.99% | 454.1% | 454.1% | 0 | -15.91% | 2105282 | 420740.91 | 1684541.09 | 1053.75 | 49400.29 | 49400.29 | 0 | 0 | 1910696.33 | 144.39 | 20444.58 | 1940% | YES | 20444.58 | 0 | 1910696.33 | 0 | 0 | 0 | 0 | 0 | 95% | 79.09% | 63.05% | -31.95% |  | 34.07 | [5 empty] | 1510400
1742 | 2024-06-12 23:30 | P23175 | BAe Aero Typhoon Package 2 | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM | 2024-03-12 | 2 |  |  | 103.3% | 96.79% | 96.79% | 0 | -1.62% | 1984265.09 | 2050055.96 | -65790.87 | -2488.97 | 57677.87 | 86030.82 | 15444.64 | 65790.87 | 1984257.03 | 72784.72 | 60653.93 | -2437% | NO | 89006.88 | 0 | 1984257.03 | 0 | 0 | 0 | 0 | 0 | 29% | 27.38% | 24.84% | -4.16% |  | 51.77 | [5 empty] | -5145
1742 | 2024-06-12 23:30 | P19020 | Spirit Concessions - 2018 | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2024-01-23 | 0 |  |  | 86.3% | 111.8% | 111.8% | 0 | 2.09% | 2015043.23 | 1739018.14 | 276025.09 | 0 | 44317.61 | 44317.61 | 0 | 0 | 1944710.76 | 236384.86 | 196987.38 | 0% | NO | 196987.38 | 0 | 1944710.76 | 0 | 0 | 0 | 0 | 0 | 25% | 27.09% | 9.32% | -15.68% |  | 40.87 | [5 empty] | 402680
1742 | 2024-06-12 23:30 | P23006 | Spirit Shorts A350 Freighter Toulouse | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 5.475 | 92.45% | 105.2% | 95.24% | 0 | 22.75% | 1925837.92 | 1780470.57 | 145367.35 | 26551.08 | 1086670.26 | 2010741.94 | 0 | 0 | 1873531.68 | 244.63 | 294212.89 | 1108% | YES | 1218284.57 | 213293 | 1695787.5133 | 0 | 213292.5 | 0 | 0 | 0 | 5% | 27.75% | 45.24% | 40.24% |  | 48.17 | [5 empty] | 387274
1742 | 2024-06-12 23:30 | P23257 | BAE Tempest WP 5 Centre Fuselage | Philip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | -1.0298 | 100.7% | 100.3% | 94.49% | 0 | -5.72% | 2265401.51 | 2280608.58 | -15207.07 | 14767.5 | 78100 | 78100 | 0 | 15207.07 | 2286342.68 | 57.17 | -5734.1 | -38.83% | NO | -5734.1 | 157776 | 2154862.68 | 89955.07 | 67820.9 | 0 | 0 | 0 | 33% | 27.28% | 27.99% | -5.01% |  | 61.08 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23435 | Andy Baker Portfolio | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 36.762 | 59.49% | 95.24% | 86.23% | 0 | -7.37% | 4023207.4 | 2393294.85 | 1629912.55 | 44336.94 | 2818.87 | 2818.87 | 0 | 0 | 2279411.46 | 49.92 | 113883.39 | 256.9% | YES | 113883.39 | 258760 | 2063778.1267 | 292.42 | 296652.44 | -38184.52 | 0 | 0 | 25% | 17.63% | 18.84% | -6.16% |  | 81.15 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23179 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX |  |  |  | -6.857 | 101.6% | 96.57% | 93.35% | 0 | -9.17% | 2542643.04 | 2584017.62 | -41374.58 | 6033.94 | 156991.12 | 248243.92 | 0 | 41374.58 | 2495342.85 | 352.15 | 88674.77 | 1470% | YES | 179927.57 | 99729 | 2412235.35 | 99728.59 | 0 | 0 | 0 | 0 | 22% | 12.83% | 18.54% | -3.46% |  | 44.4 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P19731 | Hapri HPC Rear Bearing Housing PDR & CDR | Steven Lawton | 0 | ATC | AECC Hunan Aviation Powerplant | MPE | Level 1 | FIX | 2024-05-13 | 3 |  | -2.6755 | 104.8% | 95.39% | 95.39% | 0 | -14.32% | 2980000 | 3123961.5 | -143961.5 | 53808.02 | 500476.22 | 500476.22 | 0 | 143961.5 | 2980000 | 0 | -0.5 | -0.0009292% | NO | -0.5 | 0 | 2980000 | 0 | 0 | 0 | 0 | 0 | 38% | 23.68% | 34.67% | -3.33% |  | 64.85 | [5 empty] | -143962
1742 | 2024-06-12 23:30 | P23207 | A350 Approvers - Design and Stress Support | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  | 1.9229 | 96.25% | 91.89% | 81.47% | 0 | -4.37% | 3135290 | 3017740.8 | 117549.2 | 61132.74 | 42996.59 | 51469.93 | 0 | 0 | 2772971.66 | 66.72 | 244769.14 | 400.4% | YES | 253242.48 | 377387 | 2458482.4933 | 0 | 275235.34 | 102151.98 | 0 | 0 | 22% | 17.63% | 16.71% | -5.29% |  | 54.53 | [5 empty] | 0
1742 | 2024-06-12 23:30 | P23487 | Tornado Air 800 Engineering Support | Richard Brook | 0 | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 2 | FIX |  |  |  | 7.7912 | 82.93% | 85.36% | 72.48% | 333359.75 | -0.19% | 4286367.76 | 3554688.3 | 731679.46 | 93910.66 | 500 | 500 | 0 | 0 | 3034359.96 | 143.66 | 752328.34 | 801.1% | YES | 752328.34 | 549397 | 2576529.1267 | -47390.58 | 263427.34 | 285969.17 | 47390.58 | 333359.75 | 40% | 39.81% | 46.31% | 6.31% |  | 79.02 | [5 empty] | 232000
Extend Table

## AP6-3
WIP No | Date Created | Project ID | Project Description | Project Manager | Agency (1=yes, 0=no) | Department Id | Client | CBU | Complexity | Type | Stop Booking Hrs | Closing Project: Action(s) to close | RAG | Approx. PO Burndown (weeks) | Turnover vs Contract Value | Invoice To Date vs Turnover | Cash in vs Turnover | Open Amount Overdue | Actual PM% to Baseline PM% delta | Contract Value | Total Project Turnover | Contract Value - Total Turnover | Run Rate (based on total turnover) | Total BOI Spend to Date | Total Committed PO (supplier/best shore) | Current AA in PT3 | Exposure (turnover - contract value) | Invoiced To Date | DSO | Unbilled (WIP) | WIP / Run rate | WIP / Run rate >1.3 | WIP + Remaining Committed PO for BOI | Total Open Amount | Cash in (Invoiced - (Open amount -VAT)) | Debt - <=30 Days since invoice | Debt - 31 - 60 Days since invoice | Debt - 61 - 90 Days since invoice | Debt - >= 90 Days since invoice | Open Amount Overdue2 | Baseline Project Margin | Project To Date (PTD) PM | Year to Date (YTD) PM | YTD Delta Actual PM% to BPM% | Forecast PM at Completion (Manual input from PTT) | Average Sale Rate | CSat score for last quarter (Manual input from PTT) | Comments and Actions | Judged income adjustment at completion | Profit to take now | Provision required now | Fully Traded | Last Months Comments and Actions
1743 | 2024-06-19 23:34 | P23937 | A350 Modifications | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | REIM | [7 empty] | 0 | -24% | 0 | 0 | 0 | 0 | 0 | 0 | 49951 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24% | 0% | 0% | -24% |  | 0 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23552 | FCAS AP Product Technology Development | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -25% | 597871 | 0 | 597871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0% | -25% |  | 0 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23912 | EXP-042 Software Engineering Support to Elec Eng | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  |  | 0% |  |  | 0 | -22% | 620890 | 0 | 620890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22% | 0% | 0% | -22% |  | 0 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23543 | EXP-024 FCAS AP Transformation & Change Enablers | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 0% |  |  | 0 | -26% | 385921 | 0 | 385921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26% | 0% | 0% | -26% |  | 0 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23784 | Tempest Tooling Offload 2024 | Gary Kempster | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM | 2024-05-09 | 0 | [5 empty] | 0 | -25% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0% | -25% |  | 0 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23711 | DO NOT USE - RAISED IN ERROR | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23628 | Design Assurance | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [7 empty] | 0 | -7% | 0 | 0 | 0 | 0 | 0 | 0 | 4454.8 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 0% | 0.33% | -6.67% |  | 0 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23928 | SAFRAN A330 NEO Tooling Design and Manufacture | Michael Stuart Frain | 0 | TOO | SAFRAN NACELLES LIMITED | MPE | Level 2 | FIX |  |  |  |  | 0% |  |  | 0 | -20% | 44151.28 | 0 | 44151.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 0% | 0% | -20% |  | 0 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23886 | A220 F&DT Support | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [7 empty] | 0 | -18% | 0 | 0 | 0 | -845.05 | 0 | 0 | 12199.2 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 0% | 0% | -18% |  | 0 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23915 | A220 FLE Design | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | [7 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23933 | MBDA HW/SW Requirements Engineer | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM | [7 empty] | 0 | -21% | 0 | 0 | 0 | 0 | 0 | 0 | 26120 | 0 | 0 | 0 | 0 | 0% | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21% | 0% | 0% | -21% |  | 0 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23810 | Strategic Enablement | Owain Jones | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -34302543% | 0 | 133694.4 | -133694.4 | -33423.5 | 0 | 0 | 134000 | 133694.4 | 0 | 0.48 | 0.4 | -0.001197% | NO | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | -34302525% | -34302525% | -34302543% |  | 42 | [5 empty] | -133694
1743 | 2024-06-19 23:34 | P23650 | MBDA Recruitment Management costs | Andrew Slaney | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM | 2024-02-01 | 1 |  | -963886 |  | 0% | 0% | 0 | -33042321% | 0 | 240971.5 | -240971.5 | 0.25 | 0 | 0 | 266000 | 240971.5 | 0 | 0.6 | 0.5 | 200% | YES | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | -33042318% | 165.6% | 162.6% |  | 82.3 | [5 empty] | -240971
1743 | 2024-06-19 23:34 | P23730 | FLE Project | Siyun Fan | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -18.03% | 0 | 1120 | -1120 | 0 | 0 | 0 | 24000 | 1120 | 0 | 1344 | 1120 | 0% | NO | 1120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | -18.03% | -18.03% | -18.03% |  | 35 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23463 | A220 Wing MaMo Design Checking | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-03-07 | 0 |  |  |  | 0% | 0% | 0 | 7.85% | 0 | 1628 | -1628 | 0 | 0 | 0 | 15000 | 1628 | 0 | 1953.6 | 1628 | 0% | NO | 1628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3% | 10.85% | 0% | -3% |  | 44 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P21028 | Rebate Collection (BACC) | David Catchpole | 0 | TOO | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | [5 empty] | 0% | 0% | 0 | 0% | 0 | 2680 | -2680 | 0 | 2680 | 2680 | 0 | 2680 | 0 | 3216 | 2680 | 0% | NO | 2680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23881 | Bulldog Fuel System Design | Trevin Fernandopulle | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM |  |  |  |  | 46.24% | 0% | 0% | 0 | -3.1% | 8288 | 3832.5 | 4455.5 | -868.88 | 0 | 0 | 0 | 0 | 0 | 56 | 3832.5 | -441.1% | NO | 3832.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13% | 9.9% | 9.9% | -3.1% |  | 47.02 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23892 | Warrior Environmental Control Unit | Trevin Fernandopulle | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM |  |  |  | 0 | 100% | 0% | 0% | 0 | 3.58% | 3920 | 3920 | 0 | 602 | 0 | 0 | 0 | 0 | 0 | 42 | 3920 | 651.2% | YES | 3920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32% | 35.58% | 35.58% | 3.58% |  | 56 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23578 | ESN Work Package | Hannah Mead | 0 | COZ | CHELTON LIMITED | DET | Level 3 | FIX | 2024-01-01 | 1 |  | 4 | 86.17% | 116.1% | 116.1% | 0 | 41.42% | 4410 | 3800 | 610 | 152.5 | 0 | 0 | 0 | 0 | 4410 | 0 | 0 | 0% | NO | 0 | 0 | 4410 | 0 | 0 | 0 | 0 | 0 | 24% | 65.42% | 100% | 76% |  | 95 | [5 empty] | 610
1743 | 2024-06-19 23:34 | P23283 | Spirit Tooling Audit | Charidimos Valadakis | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-05-03 | 1 |  |  | 97.22% | 48.57% | 48.57% | 0 | -114.9% | 9910.08 | 9634.8 | 275.28 | -1238.75 | 0 | 0 | 0 | 0 | 4679.76 | 0.05 | 0.04 | -0.003229% | NO | 0.04 | 0 | 4679.76 | 0 | 0 | 0 | 0 | 0 | 7% | -107.9% | 100% | 93% |  | 34.41 | [5 empty] | -4955
1743 | 2024-06-19 23:34 | P23880 | Warrior Crew Heater Design | Trevin Fernandopulle | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM |  |  |  |  | 90.91% | 0% | 0% | 0 | 3.58% | 5544 | 5040 | 504 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 5040 | 0% | NO | 5040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32% | 35.58% | 35.58% | 3.58% |  | 56 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23002 | WoT MAJ Transit Flag Stress | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2024-04-03 | 1 |  |  | 62.41% | 160.2% | 160.2% | 0 | 38.54% | 4735 | 2955.29 | 1779.71 | 0 | 1492.79 | 2242.5 | 0 | 0 | 4735 | 91.03 | 1493.29 | 0% | NO | 2243 | 0 | 4735 | 0 | 0 | 0 | 0 | 0 | 10% | 48.54% | 0% | -10% |  | 45 | [5 empty] | 3273
1743 | 2024-06-19 23:34 | P23909 | A220-300 Wing L5v01M09 Loads Increase | Siyun Fan | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -4 |  | 0% | 0% | 0 | -11.58% | 0 | 6884.92 | -6884.92 | 1721.23 | 0 | 0 | 9920 | 6884.92 | 0 | 33 | 6884.92 | 400% | YES | 6884.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | -11.58% | -11.58% | -11.58% |  | 41.98 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23899 | Turret Test Rig | Trevin Fernandopulle | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level NC | REIM |  |  |  | 7.5512 | 34.63% | 0% | 0% | 0 | 0.52% | 24864 | 8610 | 16254 | 2152.5 | 0 | 0 | 0 | 0 | 0 | 28 | 8610 | 400% | YES | 8610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16% | 16.52% | 16.52% | 0.52% |  | 56 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23607 | SAFRAN - A330neo Turnover Frame | Gary Kempster | 0 | TOO | SAFRAN SEATS GB LIMITED | MPE | Level 3 | FIX |  |  |  |  | 95.69% | 104.5% | 104.5% | 0 | -19.52% | 8736 | 8359.05 | 376.95 | 0 | 0 | 0 | 0 | 0 | 8736 | 0.06 | 0.05 | 0% | NO | 0.05 | 0 | 8736 | 0 | 0 | 0 | 0 | 0 | 23% | 3.48% | 8.5% | -14.5% |  | 50.46 | [5 empty] | 377
1743 | 2024-06-19 23:34 | P23274 | ME Support (Aim Altitude - Cambridge) | Trevor Knox | 0 | AVI | AVIC CABIN SYSTEMS (UK) LIMITED | ME | Level 3 | FIX | 2023-08-18 | 0 |  |  | 51.88% | 56.3% | 56.3% | 0 | -0.17% | 17280 | 8964 | 8316 | 0 | 0 | 0 | 0 | 0 | 5046.3 | 4701.24 | 3917.7 | 0% | NO | 3917.7 | 0 | 5046.3 | 0 | 0 | 0 | 0 | 0 | 21% | 20.83% | 0% | -21% |  | 48 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23127 | Loft Hall Design Support | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-04-19 | 1 |  |  | 101% | 99.06% | 99.06% | 0 | -10.2% | 9680 | 9772 | -92 | -23 | 0 | 0 | 0 | 92 | 9680 | 0 | 0 | 0% | NO | 0 | 0 | 9680 | 0 | 0 | 0 | 0 | 0 | 41% | 30.8% | 100% | 59% |  | 44 | [5 empty] | -92
1743 | 2024-06-19 23:34 | P23630 | 2Excel CFD Analysis Support | Dushan Fernando | 0 | BAX | STIRLING DYNAMICS LTD | MPE | Level NC | FIX |  |  |  |  | 61.2% | 100% | 100% | 0 | -1.87% | 16195.49 | 9911.34 | 6284.15 | 0 | 0 | 0 | 0 | 0 | 9911.63 | 0 | -0.29 | 0% | NO | -0.29 | 0 | 9911.63 | 0 | 0 | 0 | 0 | 0 | 26% | 24.13% | 0% | -26% |  | 64.78 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23864 | REACH Coordinator | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 37.9021 | 23.19% | 79.58% | 0% | 0 | -10.24% | 52920 | 12270 | 40650 | 1072.5 | 0 | 0 | 0 | 0 | 9765 | 91 | 2505 | 233.6% | YES | 2505 | 11718 | 0 | 0 | 11718 | 0 | 0 | 0 | 27% | 16.76% | 16.76% | -10.24% |  | 30 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23313 | Laser Trim Fixtures | Gary Kempster | 0 | TOO | ALKEN ENGINEERING LIMITED | MPE | Level 3 | FIX | 2023-11-20 | 0 |  |  | 89.87% | 111.3% | 111.3% | 0 | 0.53% | 13770 | 12375 | 1395 | 0 | 0 | 0 | 0 | 0 | 13770 | 0 | -1395 | 0% | NO | -1395 | 0 | 13770 | 0 | 0 | 0 | 0 | 0 | 17% | 17.53% | 0% | -17% |  | 45 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P22761 | Red Bull Chassis Spit | Trevor Knox | 0 | TOO | MANUFAX ENGINEERING LTD | MPE | Level 3 | FIX | 2022-11-15 | 0 |  |  | 72.18% | 96.98% | 96.98% | 0 | 7.92% | 12961.2 | 9355.5 | 3605.7 | 0 | 0 | 0 | 0 | 0 | 9072.84 | 4666.39 | 3888.66 | 0% | NO | 3888.66 | 0 | 9072.84 | 0 | 0 | 0 | 0 | 0 | 23% | 30.92% | 0% | -23% |  | 42.19 | [5 empty] | 3606
1743 | 2024-06-19 23:34 | P23350 | Spirit 2023 - Stress Approve Man Serv (DH) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 14.15% | 72.64% | 72.64% | 0 | -0.29% | 97920 | 13860 | 84060 | 0 | 0 | 0 | 0 | 0 | 10068 | 4550.4 | 3792 | 0% | NO | 3792 | 0 | 10068 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23344 | Spirit A320 Spoilers Support 2023 | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 38.75% | 100% | 100% | 0 | 5.82% | 35786.4 | 13867.23 | 21919.17 | 0 | 0 | 0 | 0 | 0 | 13867.23 | 0 | 0 | 0% | NO | 0 | 0 | 13867.23 | 0 | 0 | 0 | 0 | 0 | 7% | 12.82% | 0% | -7% |  | 34.41 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23337 | Spirit 2023 - Steve Grimley | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 25.28% | 100% | 100% | 0 | 0.01% | 56812.9 | 14362.47 | 42450.43 | 0 | 0 | 0 | 0 | 0 | 14362.47 | 0 | 0 | 0% | NO | 0 | 0 | 14362.47 | 0 | 0 | 0 | 0 | 0 | 7% | 7.01% | 0% | -7% |  | 30.11 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23597 | MRB Onsite support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2024-02-16 | 1 |  |  |  | 0% | 0% | 0 | -10.04% | 0 | 15100.57 | -15100.57 | 0 | 9448.07 | 17381.62 | 24200 | 15100.57 | 0 | 18120.68 | 15100.57 | 0% | NO | 23034.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | 7.96% | 8.95% | -9.05% |  | 42.5 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23718 | Requalification of EJ200 GSS ESS EHM SW module | Vijayakumara Nanjundappa | 0 | ARZ | MTU AERO ENGINES AG | DET | Level 3 | FIX |  |  |  | 103.2926 | 14% | 390% | 209.9% | 0 | 22.92% | 74463 | 10421.57 | 64041.43 | 620 | 991.93 | 991.93 | 0 | 0 | 40648 | 0 | -25226.43 | -4069% | NO | -25226.43 | 22523 | 21878.8333 | 0 | 22523 | 0 | 0 | 0 | 28% | 50.92% | 50.92% | 22.92% |  | 80 | [5 empty] | 5000
1743 | 2024-06-19 23:34 | P23894 | EE Test and Integration Lead | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 40.9191 | 14.35% | 0% | 0% | 0 | 0.99% | 110602 | 15871.81 | 94730.19 | 2315.06 | 0 | 0 | 0 | 0 | 0 | 49 | 15871.81 | 685.6% | YES | 15871.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32% | 32.99% | 32.99% | 0.99% |  | 63.88 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23869 | EXP-037 Land Ceptor Development Hardware Test Def | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 9.801% | 0% | 0% | 0 | 0.81% | 162694 | 15944.83 | 146749.17 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 15944.83 | 0% | NO | 15944.83 | 0 | 0 | 0 | -10617.91 | 10617.91 | 0 | 0 | 26% | 26.81% | 26.81% | 0.81% |  | 89.83 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23343 | Spirit 2023 - John Agnew | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | 2023-08-09 | 0 |  |  | 24.64% | 100% | 100% | 0 | -0.02% | 65120.37 | 16047.15 | 49073.22 | 0 | 0 | 0 | 0 | 0 | 16047.15 | 0 | 0 | 0% | NO | 0 | 0 | 16047.15 | 0 | 0 | 0 | 0 | 0 | 7% | 6.98% | 6.98% | -0.02% |  | 34.51 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23898 | EXP-041 ISV Engineering Support | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 119.2492 | 4.506% | 48.27% | 0.0009233% | 0 | -13.18% | 400584 | 18051.62 | 382532.38 | 3207.84 | 310.62 | 310.62 | 0 | 0 | 8713.5 | 41 | 9338.12 | 291.1% | YES | 9338.12 | 10456 | 0.16667 | 0 | 10456.2 | 0 | 0 | 0 | 21% | 7.82% | 7.82% | -13.18% |  | 78.5 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23635 | Engineering Services: FAI Support | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  |  | 49.9% | 100% | 0.0008972% | 0 | -3.4% | 37230 | 18576 | 18654 | 0 | 0 | 0 | 0 | 0 | 18576 | 22291.2 | 0 | 0% | NO | 0 | 22291 | 0.16667 | 0 | 0 | 7058.88 | 15232.32 | 0 | 8% | 4.6% | 5.04% | -2.96% |  | 38.7 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23888 | HondaJet FWD Assy Jig Tool Design | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | FIX |  |  |  | 3.5718 | 64.97% | 0% | 0% | 0 | 4.07% | 31500 | 20464.5 | 11035.5 | 3089.63 | 0 | 0 | 0 | 0 | 0 | 63 | 20464.5 | 662.4% | YES | 20464.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 14.07% | 14.07% | 4.07% |  | 42 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23355 | Spirit Tooling Support 2023 | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-23 | 0 |  |  | 22.93% | 89.02% | 89.02% | 0 | -0.82% | 91800 | 21053.34 | 70746.66 | 0 | 0 | 0 | 0 | 0 | 18742.5 | 2773.01 | 2310.84 | 0% | NO | 2310.84 | 0 | 18742.5 | 0 | 0 | 0 | 0 | 0 | 20% | 19.18% | 0% | -20% |  | 44.46 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23839 | Stirling Dynamics - ST002-GFEM | Matthew Dodd | 0 | BAX | STIRLING DYNAMICS LTD | MPE | Level 3 | REIM |  |  |  |  | 89.35% | 92.63% | 0.0009304% | 34071.47 | -3.93% | 24057.34 | 21496.26 | 2561.08 | 0 | 2126.93 | 2126.93 | 0 | 0 | 19912.7 | 392.82 | 1583.56 | 0% | NO | 1583.56 | 23895 | 0.2 | 0 | 23895.24 | 0 | 0 | 34071.47 | 6% | 2.07% | 2.07% | -3.93% |  | 43.77 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23663 | Spirit Tooling Verification and Inspection | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  |  | 98.66% | 100% | -0.001476% | 0 | -6.39% | 23123.52 | 22813.83 | 309.69 | 0 | 0 | 0 | 0 | 0 | 22813.83 | 283.25 | 0 | 0% | NO | 0 | 27377 | -0.33667 | 1982.02 | 4831.16 | 12635.35 | 7928.06 | 0 | 11% | 4.61% | 4.82% | -6.18% |  | 34.41 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23351 | Spirit 2023 - Design Man Serv (KL) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 26.47% | 93.15% | 93.15% | 0 | 0.09% | 93840 | 24840 | 69000 | 0 | 0 | 0 | 0 | 0 | 23138 | 2042.4 | 1702 | 0% | NO | 1702 | 0 | 23138 | 0 | 0 | 0 | 0 | 0 | 26% | 26.09% | 0% | -26% |  | 46 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23873 | FCAS Systems Engineering Support | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 48.7799 | 15.88% | 67.3% | -0.001342% | 0 | -9.72% | 156475 | 24845.25 | 131629.75 | 2698.44 | 0 | 0 | 0 | 0 | 16720.5 | 63 | 8124.75 | 301.1% | YES | 8124.75 | 20065 | -0.33333 | 0 | 20064.6 | 0 | 0 | 0 | 18% | 8.28% | 8.28% | -9.72% |  | 78.5 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23356 | Spirit 2023 - Design Man Serv (AH) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX | 2023-08-09 | 0 |  |  |  | 76.66% | 76.66% | 0 | 0.48% | 0 | 25023.08 | -25023.08 | 0 | 0 | 0 | 25300 | 25023.08 | 19182 | 7009.3 | 5841.08 | 0% | NO | 5841.08 | 0 | 19182 | 0 | 0 | 0 | 0 | 0 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23843 | EXP-035 FT15 Exemplar information set | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 48.4727 | 14.35% | 55.68% | -0.0002772% | 0 | -8.64% | 175985.16 | 25256.88 | 150728.28 | 3109.55 | 0 | 0 | 0 | 0 | 14062.43 | 91 | 11194.45 | 360% | YES | 11194.45 | 16875 | -0.07 | 0 | 16874.92 | 0 | 0 | 0 | 20% | 11.36% | 11.36% | -8.64% |  | 71.63 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P22884 | Spirit Shorts Config Eng | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 66.3% | 100.1% | 100.1% | 0 | 0.56% | 38976 | 25841.9 | 13134.1 | 0 | 0 | 0 | 0 | 0 | 25863.2 | 0 | -0.3 | 0% | NO | -0.3 | 0 | 25863.2 | 0 | 0 | 0 | 0 | 0 | 7% | 7.56% | 0% | -7% |  | 20.3 | [5 empty] | 21
1743 | 2024-06-19 23:34 | P23742 | Cyber Security Support | Hannah Mead | 0 | COZ | CHELTON LIMITED | DET | Level 3 | FIX | 2024-06-05 | 1 |  |  | 94.91% | 105.4% | 0% | 33000 | -0.96% | 27500 | 26100 | 1400 | 0 | 0 | 0 | 0 | 0 | 27500 | 197.93 | -1400 | 0% | NO | -1400 | 33000 | 0 | 0 | 33000 | 0 | 0 | 33000 | 32% | 31.04% | 31.04% | -0.96% |  | 100 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23354 | Spirit 2023 - Design Man Serv (PC) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 27.97% | 99.36% | 99.36% | 0 | 0.48% | 93840 | 26248.98 | 67591.02 | 0 | 0 | 0 | 0 | 0 | 26082 | 200.38 | 166.98 | 0% | NO | 166.98 | 0 | 26082 | 0 | 0 | 0 | 0 | 0 | 18% | 18.48% | 0% | -18% |  | 46 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P22756 | A350 FLE Design Checker | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2022-03-23 | 1 |  |  | 68.39% | 119.7% | 119.7% | 0 | 16.46% | 34898.4 | 23867.15 | 11031.25 | 0 | 23867.15 | 24342.3 | 0 | 0 | 28571.1 | 0.06 | 0.05 | 0% | NO | 475.2 | 0 | 28571.1 | 0 | 0 | 0 | 0 | 0 | 0% | 16.46% | 0% | 0% |  | 0 | [5 empty] | 4704
1743 | 2024-06-19 23:34 | P23458 | Spirit Belfast Tooling Support | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-08-11 | 0 |  |  | 101.3% | 94.65% | 94.65% | 0 | 8.64% | 30384 | 30784.9 | -400.9 | 0 | 0 | 0 | 0 | 400.9 | 29139.1 | 1974.96 | 1645.8 | 0% | NO | 1645.8 | 0 | 29139.1 | 0 | 0 | 0 | 0 | 0 | 7% | 15.64% | 0% | -7% |  | 42.2 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23365 | GKN 777x Lip Skin Fixture | Steven Lawton | 0 | TOO | GKN AEROSPACE SERVICES LTD | MPE | Level 3 | FIX | 2023-10-12 | 0 |  |  | 41.91% | 113.2% | 113.2% | 0 | -9.26% | 79161.46 | 33175.67 | 45985.79 | 0 | 5109.88 | 5109.88 | 0 | 0 | 37544.22 | 0 | -4368.55 | 0% | NO | -4368.55 | 0 | 37544.22 | 0 | 0 | 0 | 0 | 0 | 22% | 12.74% | 0% | -22% |  | 56 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P22768 | MRB Onsite Support - Spirit Belfast | Trevor Knox | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM | 2023-07-27 | 0 |  |  |  | 0% | 0% | 0 | -17.07% | 0 | 34614 | -34614 | 0 | 0 | 0 | 36800 | 34614 | 0 | 41536.8 | 34614 | 0% | NO | 34614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | -7.07% | 0% | -10% |  | 36 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23831 | Contract DM/00113 for maintenance, repair and post | Harry James Kellett | 0 | BXW | MOD | EES | Level 2 | FIX |  |  |  | 34.3906 | 77.12% | 15.79% | 15.79% | 0 | 16.19% | 46455.9 | 35828.17 | 10627.73 | 309.03 | 467.61 | 937.78 | 0 | 0 | 5655.9 | 130.87 | 30172.27 | 9764% | YES | 30642.44 | 0 | 5655.9 | 0 | 0 | 0 | 0 | 0 | 34% | 50.19% | 50.19% | 16.19% |  | 80.26 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23821 | Supply of Safety Engineer | Dinna Elkhalifa | 0 | BXW | STIRLING DYNAMICS LTD | EES | Level NC | REIM |  |  |  |  | 106.6% | 49% | 49% | 0 | 45.1% | 34006.44 | 36247.77 | -2241.33 | 0 | 0 | 0 | 0 | 2241.33 | 17760.6 | 164.74 | 18487.17 | 0% | NO | 18487.17 | 0 | 17760.6 | 0 | 0 | 0 | 0 | 0 | 0% | 45.1% | 45.1% | 45.1% |  | 80.73 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23347 | WoT Fixed Leading Edge - Industrial 2023 | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 120.5% | 82.92% | 39.34% | 0 | -0.38% | 31034.12 | 37389.34 | -6355.22 | 0 | 0 | 0 | 10500 | 6355.22 | 31001.86 | 27214.54 | 6387.48 | 0% | NO | 6387.48 | 19550 | 14710.1933 | 0 | 19549.56 | 0 | 0 | 0 | 7% | 6.62% | 7.01% | 0.01% |  | 32.26 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23051 | Spirit Shorts A350 PAX Door | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3A | REIM |  |  |  |  | 68.19% | 105.4% | 105.4% | 0 | 3.37% | 55016 | 37513 | 17503 | 0 | 0 | 0 | 0 | 0 | 39537 | 0 | 0 | 0% | NO | 0 | 0 | 39537 | 0 | 0 | 0 | 0 | 0 | 26% | 29.37% | 0% | -26% |  | 46 | [5 empty] | 2024
1743 | 2024-06-19 23:34 | P23338 | Spirit 2023 - Blair Hainey | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 38.6367 | 63.2% | 97.29% | 45.39% | 0 | -3.03% | 62893.71 | 39751.08 | 23142.63 | 598.98 | 0 | 0 | 0 | 0 | 38673.72 | 267.78 | 1077.36 | 179.9% | YES | 1077.36 | 24758 | 18042.0533 | 3010.18 | 21747.46 | 0 | 0 | 0 | 7% | 3.97% | -4.53% | -11.53% |  | 16.55 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23651 | PMO Spirit | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 7.3675 | 84.26% | 81.62% | 56.48% | 0 | -19.42% | 49284 | 41526 | 7758 | 1053 | 0 | 0 | 0 | 0 | 33894 | 116.83 | 7632 | 724.8% | YES | 7632 | 12528 | 23454 | 0 | 12528 | 0 | 0 | 0 | 43% | 23.58% | 23.09% | -19.91% |  | 36 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23433 | Cavendish | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 0.28055 | 98.81% | 90.72% | 33.2% | 0 | -0.44% | 42240 | 41737.6 | 502.4 | 1790.8 | 0 | 0 | 0 | 0 | 37865.6 | 112.72 | 3872 | 216.2% | YES | 3872 | 28808 | 13858.9333 | 0 | 28807.68 | 0 | 0 | 0 | 7% | 6.56% | 6.51% | -0.49% |  | 46.82 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P22752 | Tooling WoT - 2021 (Spirit) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | REIM | 2023-05-03 | 0 |  |  | 101.1% | 74.02% | 74.02% | 0 | -8.5% | 41525.1 | 41982.28 | -457.18 | 0 | 0 | 0 | 0 | 457.18 | 31076.1 | 13087.42 | 10906.18 | 0% | NO | 10906.18 | 0 | 31076.1 | 0 | 0 | 0 | 0 | 0 | 0% | -8.5% | 0% | 0% |  | 39.09 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23724 | GKN S McConnell 2024 | Matthew Tweed | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM |  |  |  | 4.2571 | 85.1% | 87.9% | 0.0008491% | 0 | 1% | 49820 | 42396.85 | 7423.15 | 1743.7 | 0 | 0 | 0 | 0 | 37265.36 | 171.33 | 5131.49 | 294.3% | YES | 5131.49 | 44718 | 0.36 | 0 | 8369.76 | 19130.88 | 17217.79 | 0 | 19% | 20% | 20% | 1% |  | 49.65 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23902 | Typhoon Rear Fuselage | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 6.0875 | 47.38% | 0% | 0% | 0 | -1% | 98574.84 | 46703.22 | 51871.62 | 8520.99 | 0 | 0 | 0 | 0 | 0 | 41 | 46703.22 | 548.1% | YES | 46703.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31% | 30% | 30% | -1% |  | 54.34 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23339 | Spirit 2023 - Stewart Russell | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  |  | 64.51% | 100% | 100% | 0 | 0.62% | 72766.8 | 46941.72 | 25825.08 | 0 | 0 | 0 | 0 | 0 | 46941.74 | 0 | -0.02 | 0% | NO | -0.02 | 0 | 46941.74 | 0 | 0 | 0 | 0 | 0 | 7% | 7.62% | 0% | -7% |  | 35.67 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23842 | Tranche 1 Evolution Package Step 2 | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 14.6177 | 41.86% | 0% | 0% | 0 | -10.6% | 112526.3 | 47108.22 | 65418.08 | 4475.28 | 1000 | 1000 | 0 | 0 | 0 | 91 | 47108.22 | 1053% | YES | 47108.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31% | 20.4% | 20.4% | -10.6% |  | 56.39 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P22760 | SA Leading Edge Transport Media ('A' Frames) | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-11-15 | 1 |  |  | 85.99% | 110.7% | 116.3% | -3082.8 | 3.97% | 53480.8 | 45985.5 | 7495.3 | 0 | 42804 | 42804 | 0 | 0 | 50911.8 | 0 | -0.3 | 0% | NO | -0.3 | -3083 | 53480.9667 | 0 | 0 | 0 | -3082.8 | -3082.8 | 6% | 9.97% | 0% | -6% |  | 42 | [5 empty] | 4926
1743 | 2024-06-19 23:34 | P23874 | Environmental Engineering (Sea Venom/ANL) | Trevin Fernandopulle | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 113.698 | 7.961% | 0% | 0% | 0 | -3.84% | 687295 | 54714.5 | 632580.5 | 5563.69 | 0 | 0 | 0 | 0 | 0 | 70 | 54714.5 | 983.4% | YES | 54714.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23% | 19.16% | 19.16% | -3.84% |  | 78.5 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23891 | A220 FLE Support | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -10.6659 |  | 0% | 0% | 0 | 7.8% | 0 | 54878.4 | -54878.4 | 5145.24 | 0 | 0 | 66703.68 | 54878.4 | 0 | 80 | 54878.4 | 1067% | YES | 54878.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7% | 14.8% | 14.8% | 7.8% |  | 50.28 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23823 | EXP-034 Spear 3 Test Equip Requirement Authority | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 11.8086 | 66.12% | 87.86% | 54.56% | 0 | 0.07% | 85825 | 56748.88 | 29076.12 | 2462.28 | 1000 | 1000 | 0 | 0 | 49858.26 | 56.7 | 6890.62 | 279.8% | YES | 6890.62 | 22677 | 30960.76 | 0 | 22676.56 | 0 | 0 | 0 | 14% | 14.07% | 14.07% | 0.07% |  | 94.25 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23349 | Spirit 2023 - Stress Approve Man Serv (SB) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-09 | 0 |  |  | 58.24% | 80.05% | 80.05% | 0 | -0.29% | 97920 | 57024 | 40896 | 0 | 0 | 0 | 0 | 0 | 45648 | 13651.2 | 11376 | 0% | NO | 11376 | 0 | 45648 | 0 | 0 | 0 | 0 | 0 | 18% | 17.71% | 0% | -18% |  | 48 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23642 | MRB Belfast Support | Paul Watson | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | -42.8504 |  | 0% | 0% | 0 | -44.55% | 0 | 58369.97 | -58369.97 | 1362.18 | 3718.34 | 3718.34 | 53900 | 58369.97 | 0 | 297.17 | 58369.97 | 4285% | YES | 58369.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22% | -22.55% | -24.68% | -46.68% |  | 38.52 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23106 | ME Support to NPD - Bobby Haggart | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  |  | 95.79% | 97.03% | 97.03% | 0 | 0.3% | 65675 | 62912.11 | 2762.89 | 0 | 0 | 0 | 0 | 0 | 61042.75 | 2243.24 | 1869.36 | 0% | NO | 1869.36 | 0 | 61042.75 | 0 | 0 | 0 | 0 | 0 | 15% | 15.3% | 0% | -15% |  | 35.65 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23811 | Spirit T300 MRB Concessions | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -13.5986 |  | 0% | 0% | 0 | -7.25% | 0 | 62974.99 | -62974.99 | 4631 | 0 | 0 | 70000 | 62974.99 | 0 | 119.95 | 62974.99 | 1360% | YES | 62974.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21% | 13.75% | 13.75% | -7.25% |  | 48.16 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P22967 | Spirit 2022 - Channapa Laxmeshwar | James Montgomery | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3A | REIM | 2023-01-26 | 2 |  |  | 69.69% | 121.3% | 121.3% | 0 | 9.53% | 75159.1 | 52376.15 | 22782.95 | 0 | 52376.15 | 54898.1 | 0 | 0 | 63508.8 | 0.42 | 0.35 | 0% | NO | 2522.3 | 0 | 63508.8 | 0 | 0 | 0 | 0 | 0 | 8% | 17.53% | 0% | -8% |  | 0 | [5 empty] | 11133
1743 | 2024-06-19 23:34 | P23877 | Strategic Enablement | Owain Jones | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM | [5 empty] | 0% | 0% | 0 | -27.81% | 0 | 71017.3 | -71017.3 | -1750 | 4000 | 4000 | 67200 | 71017.3 | 0 | 176.02 | 64017.3 | -3658% | NO | 64017.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18% | -9.81% | -9.81% | -27.81% |  | 42 | [5 empty] | -7000
1743 | 2024-06-19 23:34 | P23760 | EXP-033 Systems Engineering Support | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 38.1928 | 45.48% | 92% | 69.25% | 0 | -0.02% | 142300 | 64723.25 | 77576.75 | 2031.19 | 0 | 0 | 0 | 0 | 59542.25 | 55.45 | 5181 | 255.1% | YES | 5181 | 17663 | 44823.0833 | 0 | 17662.5 | 0 | 0 | 0 | 29% | 28.98% | 28.98% | -0.02% |  | 78.5 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23740 | Phase 2 - EJ200 ESS EHM Platform Migration | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 3 | FIX |  |  |  | 32.5004 | 29.38% | 145.9% | 97.25% | 0 | 17.53% | 175971 | 51697.5 | 124273.5 | 3823.75 | 0 | 0 | 0 | 0 | 75417 | 35.53 | -9719.5 | -254.2% | NO | -9719.5 | 30167 | 50277.8333 | 0 | 0 | 30166.8 | 0 | 0 | 28% | 45.53% | 45.53% | 17.53% |  | 42.51 | [5 empty] | 14000
1743 | 2024-06-19 23:34 | P23598 | MRB Onsite support | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 22.2301 | 50.12% | 0% | 0% | 0 | -9.53% | 133056 | 66685.17 | 66370.83 | 2985.63 | 8736.42 | 14079.58 | 0 | 0 | 0 | 165.93 | 66685.17 | 2234% | YES | 72028.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28% | 18.47% | 18.72% | -9.28% |  | 42.5 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23438 | A220 Spirit Shorts DTC - Stephen Corry | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 73.97% | 90.84% | 90.84% | 0 | -7.56% | 95928.4 | 70961.9 | 24966.5 | -5812.68 | 0 | 0 | 0 | 0 | 64459.8 | 7802.52 | 6502.1 | -111.9% | NO | 6502.1 | 0 | 64459.8 | 0 | 0 | 0 | 0 | 0 | 23% | 15.44% | 5.63% | -17.37% |  | 49.69 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23193 | Spirit Shorts Stephen Greer | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -17.469 | 115.9% | 85.22% | 85.22% | 0 | 8.84% | 61472 | 71243.09 | -9771.09 | 559.34 | 0 | 0 | 10878 | 9771.09 | 60712.78 | 115.27 | 10530.31 | 1883% | YES | 10530.31 | 0 | 60712.78 | 0 | 0 | 0 | 0 | 0 | 23% | 31.84% | 34.03% | 11.03% |  | 35.21 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23600 | MBDA EXP-EE-023 Bristone Certification | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM | 2024-05-31 | 0 |  |  | 59.65% | 100% | 100% | 0 | 0.4% | 126600 | 75517 | 51083 | 0 | 0 | 0 | 0 | 0 | 75517 | 0 | 0 | 0% | NO | 0 | 0 | 75517 | 0 | 0 | 0 | 0 | 0 | 41% | 41.4% | 0% | -41% |  | 78.5 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23341 | Spirit 2023 - Tom McFarlane | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 25.8227 | 70.28% | 97.51% | 64.09% | 0 | -0.01% | 108666.4 | 76370.7 | 32295.7 | 1250.67 | 0 | 0 | 0 | 0 | 74472.52 | 177.63 | 1898.18 | 151.8% | YES | 1898.18 | 30633 | 48945.02 | 6354.47 | 5886.13 | 4683.36 | 13709.48 | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23080 | Spirit Shorts DManagement Cairan Cullen | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 2730.3028 | 51.18% | 99.92% | 96.91% | 0 | -1.31% | 149600 | 76564.4 | 73035.6 | 26.75 | 0 | 0 | 0 | 0 | 76500.2 | 177.97 | 64.2 | 240% | YES | 64.2 | 2761 | 74199.3667 | 0 | 2760.6 | 0 | 0 | 0 | 24% | 22.69% | 13.03% | -10.97% |  | 44.38 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P22505 | Spirit MRB Engineering Support 2021 | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 1 |  |  | 91.17% | 100% | 95.78% | 4020.48 | 21.2% | 87110.4 | 79414.95 | 7695.45 | 0 | 0 | 0 | 0 | 0 | 79414.95 | 4020.48 | 0 | 0% | NO | 0 | 4020 | 76064.95 | 0 | 0 | 0 | 4020.48 | 4020.48 | 0% | 21.2% | 0% | 0% |  | 41.88 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P22885 | ME Support (Baxi) | Trevor Knox | 0 | HUV | BAXI HEATING UK LIMITED | ME | Level 3 | FIX | 2023-01-12 | 1 |  |  | 68.78% | 108.7% | 108.7% | 0 | 11.9% | 106632.96 | 73340.24 | 33292.72 | -319 | 0 | 0 | 0 | 0 | 79748.12 | 0.15 | 0.12 | -0.03762% | NO | 0.12 | 0 | 79748.12 | 0 | 0 | 0 | 0 | 0 | 15% | 26.9% | 100% | 85% |  | 44.37 | [5 empty] | 6408
1743 | 2024-06-19 23:34 | P22965 | Spirit 2022 - Design Man Serv (AH) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 106.7% | 96.66% | 96.66% | 0 | 3.14% | 80079.56 | 85441.32 | -5361.76 | 0 | 0 | 0 | 0 | 5361.76 | 82588.96 | 3422.84 | 2852.36 | 0% | NO | 2852.36 | 0 | 82588.96 | 0 | 0 | 0 | 0 | 0 | 14% | 17.14% | 0% | -14% |  | 42.44 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P22964 | Spirit 2022 - MRB Man Serv (JC) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 0 |  |  | 100.6% | 97.95% | 97.95% | 0 | 1.91% | 85435.2 | 85960.26 | -525.06 | 0 | 0 | 0 | 0 | 525.06 | 84199.74 | 2112.62 | 1760.52 | 0% | NO | 1760.52 | 0 | 84199.74 | 0 | 0 | 0 | 0 | 0 | 16% | 17.91% | 0% | -16% |  | 42.69 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P22963 | Spirit 2022 - Design Man Serv (PC) | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-05-03 | 1 |  | -7.909 | 108.6% | 104% | 104% | 0 | 6.39% | 80079.56 | 86926.74 | -6847.18 | 865.75 | 0 | 0 | 0 | 6847.18 | 90389.95 | 0 | -0.21 | -0.02426% | NO | -0.21 | 0 | 90389.95 | 0 | 0 | 0 | 0 | 0 | 13% | 19.39% | 100% | 87% |  | 42.39 | [5 empty] | 3463
1743 | 2024-06-19 23:34 | P23375 | GKN Jaap Peters NL 2023 | Steven Lawton | 0 | GKX | GKN AEROSPACE SERVICES LTD | MPE | Level NC | REIM | 2024-03-01 | 2 |  | 27.9861 | 93.37% | 105.3% | 97.18% | 0 | -15% | 97123.22 | 90686.41 | 6436.81 | 230 | 90686.41 | 90686.41 | 0 | 0 | 95456.72 | 8792.92 | -0.31 | -0.1348% | NO | -0.31 | 8793 | 88129.22 | 0 | 0 | 0 | 8793.29 | 0 | 20% | 5% | 5.94% | -14.06% |  | 0 | [5 empty] | 4770
1743 | 2024-06-19 23:34 | P23079 | Spirit Shorts Nomenclature | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 15.0271 | 90.82% | 81.87% | 81.87% | 0 | 15.24% | 105147 | 95499.6 | 9647.4 | 642 | 0 | 0 | 0 | 0 | 78185.2 | 188.79 | 17314.4 | 2697% | YES | 17314.4 | 0 | 78185.2 | 0 | 0 | 0 | 0 | 0 | 7% | 22.24% | 25.23% | 18.23% |  | 30.87 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23340 | Spirit 2023 - John Cole | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 46.0273 | 66.31% | 98.54% | 63.14% | 0 | -0.01% | 150129.72 | 99549.45 | 50580.27 | 1098.92 | 0 | 0 | 0 | 0 | 98097.48 | 191.44 | 1451.97 | 132.1% | YES | 1451.97 | 42294 | 62852.48 | 7064.93 | 8831.16 | 6826.25 | 19571.76 | 0 | 7% | 6.99% | 6.99% | -0.01% |  | 39.78 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23171 | Spirt Shorts Weights Eng | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 22.6582 | 69.18% | 141.4% | 133.5% | 0 | 17.29% | 103113.14 | 71329.32 | 31783.82 | 1402.75 | 71329.32 | 103471.32 | 0 | 0 | 100870.18 | 6733.47 | 0.14 | 0.00998% | NO | 32142.14 | 6733 | 95259.3467 | 0 | 0 | 6733.3 | 0 | 0 | 12% | 29.29% | 57.03% | 45.03% |  | 0 | [5 empty] | 29541
1743 | 2024-06-19 23:34 | P23336 | Spirit 2023 - Neil Rampling | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 31.5221 | 76.4% | 98.66% | 46.78% | 21586.03 | -0.01% | 133901.52 | 102306.58 | 31594.94 | 1002.31 | 0 | 0 | 0 | 0 | 100940.6 | 293.36 | 1365.98 | 136.3% | YES | 1365.98 | 63694 | 47862.2667 | 6663.14 | 8238.46 | 7259.21 | 41532.89 | 21586.03 | 7% | 6.99% | 6.99% | -0.01% |  | 35.48 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23342 | Spirit 2023 - Channapa Laxmeshwar | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | REIM |  |  |  | 13.7575 | 63.72% | 105.6% | 64.45% | 0 | -4.26% | 158696.7 | 101124.93 | 57571.77 | 4184.77 | 101124.93 | 113130.48 | 0 | 0 | 106807 | 196.25 | -2832.07 | -67.68% | NO | 9173.48 | 49955 | 65177.8333 | 7367.16 | 10092 | 22807.92 | 9688.32 | 0 | 7% | 2.74% | 0% | -7% |  | 0 | [5 empty] | 2850
1743 | 2024-06-19 23:34 | P23583 | Castalla - Test Rig Design | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -4.0091 | 108.1% | 85.61% | 62.09% | 0 | -26.93% | 100520 | 108678.5 | -8158.5 | 2035 | 0 | 0 | 17600 | 8158.5 | 93036.5 | 205.31 | 15642 | 768.6% | YES | 15642 | 30665 | 67482.3333 | 0 | 30665.28 | 0 | 0 | 0 | 41% | 14.07% | 14.71% | -26.29% |  | 42.88 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23700 | IPDT Leads | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 13.0349 | 64.54% | 22.82% | 22.82% | 0 | -1.66% | 169263.9 | 109241.92 | 60021.98 | 4604.72 | 0 | 0 | 0 | 0 | 24932.12 | 132.39 | 84309.8 | 1831% | YES | 84309.8 | 0 | 24932.12 | 0 | 0 | 0 | 0 | 0 | 26% | 24.34% | 23.26% | -2.74% |  | 49.94 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23345 | Spirit 2023- Jonathan Escosio | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 28.8734 | 72.21% | 93.31% | 53.32% | 7150.18 | -0.58% | 151941.24 | 109718.51 | 42222.73 | 1462.34 | 0 | 0 | 0 | 0 | 102379.64 | 235.08 | 7338.87 | 501.9% | YES | 7338.87 | 52658 | 58497.9733 | 7638.58 | 16773.9 | 16361 | 11884.76 | 7150.18 | 7% | 6.42% | 15.97% | 8.97% |  | 43.01 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23560 | NJEWCS TAF202302 SM | Natalie Sinclair | 0 | COB | CHELTON LIMITED | EES | Level 2 | FIX |  |  |  | 40.5497 | 59.42% | 76.02% | 70.31% | 0 | 9.81% | 191500 | 113786.09 | 77713.91 | 1916.51 | 0 | 0 | 0 | 0 | 86500 | 107.98 | 27286.09 | 1424% | YES | 27286.09 | 7800 | 80000 | 7800 | 0 | 0 | 0 | 0 | 30% | 39.81% | 39.49% | 9.49% |  | 73.01 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23465 | A220 ToW Design Offload (Wing) | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 48.2913 | 46.4% | 93.17% | 69.52% | 0 | -6.63% | 249700 | 115870.3 | 133829.7 | 2771.3 | 0 | 0 | 0 | 0 | 107952.3 | 105.14 | 7918 | 285.7% | YES | 7918 | 32883 | 80549.8 | 18040.2 | 0 | 14843.04 | 0 | 0 | 20% | 13.37% | 10.79% | -9.21% |  | 42.8 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23523 | Applique Armour Support | Matthew Tweed | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-18 | 2 |  | 3.9999 | 72.43% | 138.1% | 98.47% | 40680 | 23.16% | 118200 | 85606.5 | 32593.5 | 8148.5 | 0 | 0 | 0 | 0 | 118200 | 40680.6 | 0.5 | 0.006136% | NO | 0.5 | 40680 | 84300 | 0 | 0 | 0 | 40680 | 40680 | 25% | 48.16% | 100% | 75% |  | 64.29 | [5 empty] | 32594
1743 | 2024-06-19 23:34 | P23551 | Ian Berry 2023 H2 | Natalie Sinclair | 0 | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  | 6.4808 | 81.84% | 56.59% | 56.59% | 0 | 13.9% | 145153.92 | 118788.53 | 26365.39 | 4068.23 | 0 | 0 | 0 | 0 | 67217.49 | 151.78 | 51571.04 | 1268% | YES | 51571.04 | 0 | 67217.49 | 0 | 0 | 0 | 0 | 0 | 22% | 35.9% | 37.71% | 15.71% |  | 78.12 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P22736 | WoT Fixed Leading Edge - Industrial | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2023-08-18 | 1 |  |  | 106.7% | 93.42% | 91.32% | 3019.54 | 0.01% | 112196.27 | 119668.47 | -7472.2 | 0 | 0 | 0 | 0 | 7472.2 | 111796.68 | 12465.69 | 7871.79 | 0% | NO | 7871.79 | 3020 | 109280.0133 | 0 | 0 | 0 | 3019.54 | 3019.54 | 7% | 7.01% | 0% | -7% |  | 32.26 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23586 | Project Management Support | Dushan Fernando | 0 | BDX | MBDA UK LIMITED | MPE | Level NC | REIM |  |  |  | 11.9945 | 76.54% | 91.77% | 80.17% | 0 | -27.08% | 160000 | 122468.17 | 37531.83 | 3129.08 | 1972 | 1972 | 0 | 0 | 112383.86 | 61.89 | 10084.31 | 322.3% | YES | 10084.31 | 17040 | 98183.86 | 0 | 17040 | 0 | 0 | 0 | 49% | 21.92% | 20.75% | -28.25% |  | 80 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P22918 | Spirit Shorts Graduates | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 11.4663 | 94.29% | 87.08% | 87.08% | 0 | 9.53% | 130000 | 122573.39 | 7426.61 | 647.69 | 0 | 0 | 19800 | 0 | 106734.95 | 141.89 | 15838.44 | 2445% | YES | 15838.44 | 0 | 106734.95 | 0 | 0 | 0 | 0 | 0 | 7% | 16.53% | 17.25% | 10.25% |  | 23.35 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23744 | Model Factory | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 26.6478 | 45.21% | 94.69% | 56.14% | 0 | 9.68% | 262300 | 118581.75 | 143718.25 | 5393.25 | 0 | 0 | 0 | 0 | 112290 | 77.04 | 11291.75 | 209.4% | YES | 11291.75 | 54859 | 66574.1667 | 0 | 27429.6 | 27429.6 | 0 | 0 | 28% | 37.68% | 37.68% | 9.68% |  | 51.19 | [5 empty] | 5000
1743 | 2024-06-19 23:34 | P22861 | WoT FLE Lifting & Handling Tools | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2023-06-14 | 1 |  |  | 65.17% | 101.6% | 101.6% | 0 | 12.01% | 173987.21 | 113381.75 | 60605.46 | 0 | 50078 | 58423.58 | 0 | 0 | 115203.5 | 12813.9 | 10678.25 | 0% | NO | 19023.83 | 0 | 115203.5 | 0 | 0 | 0 | 0 | 0 | 1% | 13.01% | 0% | -1% |  | 45 | [5 empty] | 12500
1743 | 2024-06-19 23:34 | P23353 | Spirit 2023 - MRB Man Serv (JC) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  | 35.256 | 69.22% | 98.89% | 53.99% | 0 | 9.19% | 183600 | 127080 | 56520 | 1603.13 | 0 | 0 | 0 | 0 | 125664 | 279.83 | 1416 | 88.33% | NO | 1416 | 68459 | 68614.8333 | 68458.5 | 0 | 0 | 0 | 0 | 7% | 16.19% | 12.46% | 5.46% |  | 45 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23729 | Honda Tooling | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | FIX |  |  |  | -2.8832 | 113.1% | 79.57% | 25.25% | 0 | 2.68% | 113610 | 128520 | -14910 | 5171.25 | 0 | 0 | 21000 | 14910 | 102259.5 | 112.7 | 26260.5 | 507.8% | YES | 26260.5 | 83777 | 32445.3333 | 32583.6 | 51193.8 | 0 | 0 | 0 | 10% | 12.68% | 12.68% | 2.68% |  | 42 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23664 | Tempest Composites WP3 | Philip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -17.1007 | 107.7% | 83.53% | 65.27% | 0 | -5.15% | 122455.49 | 131938.01 | -9482.52 | 554.51 | 0 | 0 | 29530.92 | 9482.52 | 110210.96 | 234.43 | 21727.05 | 3918% | YES | 21727.05 | 28921 | 86110.1267 | 28920.7 | 0 | 0 | 0 | 0 | 37% | 31.85% | 33.08% | -3.92% |  | 60.95 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23545 | Ultra CSS continuation 2023 H2 | Natalie Sinclair | 0 | ULT | ULTRA SONAR SYSTEMS LIMITED | EES | Level NC | REIM |  |  |  | 21.806 | 75.43% | 93.83% | 71.97% | 0 | 14.17% | 176000 | 132754.4 | 43245.6 | 1983.2 | 0 | 0 | 0 | 0 | 124560.8 | 129.7 | 8193.6 | 413.2% | YES | 8193.6 | 34819 | 95544.9667 | 34819.2 | 0 | 0 | 0 | 0 | 11% | 25.17% | 25% | 14% |  | 80 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P22883 | Spirit Shorts Evtol PMO C. Hatton | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 72.45% | 101.1% | 80.93% | 0 | -10.87% | 185800 | 134618.15 | 51181.85 | 0 | 0 | 0 | 0 | 0 | 136116.73 | 257.11 | -1498.58 | 0% | NO | -1498.58 | 32604 | 108946.73 | 0 | 32604 | 0 | 0 | 0 | 26% | 15.13% | 22.96% | -3.04% |  | 37.41 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23282 | Tooling Support (MBDA) | Dushan Fernando | 0 | BDV | MBDA UK LIMITED | ME | Level NC | REIM |  |  |  | 41.0641 | 71.52% | 97.49% | 90.88% | 0 | -7.33% | 195672.4 | 139951.26 | 55721.14 | 1356.93 | 0 | 0 | 0 | 0 | 136432.63 | 55.71 | 3518.63 | 259.3% | YES | 3518.63 | 11095 | 127186.7967 | 0 | 11095 | 0 | 0 | 0 | 30% | 22.67% | 30.37% | 0.37% |  | 49.74 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23533 | External Stowage Design and Detail Support | Matthew Tweed | 0 | RBX | RHEINMETALL BAE SYSTEMS LAND LTD | MPE | Level 2 | FIX | 2023-12-08 | 0 |  |  | 102.4% | 97.65% | 97.65% | 0 | 3.33% | 140000 | 143368.75 | -3368.75 | 0 | 0 | 0 | 3369 | 3368.75 | 140000 | 0 | -0.25 | 0% | NO | -0.25 | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 27% | 30.33% | 0% | -27% |  | 60.04 | [5 empty] | -3369
1743 | 2024-06-19 23:34 | P23270 | Shorts Project X | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 0.12851 | 99.86% | 90.99% | 81.62% | 0 | 0.24% | 142248 | 142048.76 | 199.24 | 1550.43 | 0 | 0 | 9976.68 | 0 | 129246.58 | 109.89 | 12802.18 | 825.7% | YES | 12802.18 | 15963 | 115944.08 | 0 | 7981.34 | 7981.34 | 0 | 0 | 13% | 13.24% | 10.99% | -2.01% |  | 45.29 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23588 | BAE Typhoon MRB MC Shop Concessions | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 12.607 | 81.87% | 78.23% | 69.86% | 14399.76 | -4% | 175060.5 | 143323.8 | 31736.7 | 2517.38 | 0 | 0 | 0 | 0 | 112121.71 | 126.84 | 31202.09 | 1239% | YES | 31202.09 | 14400 | 100121.71 | 0 | 0 | 0 | 14399.76 | 14399.76 | 31% | 27% | 27.77% | -3.23% |  | 55.83 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P22954 | Technical Support Step 1 | Owain Jones | 0 | HUV | HUARUI SPIRIT AEROSPACE MANUFACT | ME | Level 2 | REIM |  |  |  |  | 94.81% | 58.01% | 58.01% | 0 | 0.31% | 155501.18 | 147431.58 | 8069.6 | 0 | 23043 | 23043 | 0 | 0 | 85525.49 | 61906.09 | 61906.09 | 0% | NO | 61906.09 | 0 | 85525.49 | 0 | 0 | 0 | 0 | 0 | 30% | 30.31% | 0% | -30% |  | 60.79 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23386 | Software Development - BMS | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 98.78% | 100% | 100% | 0 | 4.31% | 149650 | 147823.35 | 1826.65 | 0 | 0 | 0 | 0 | 0 | 147823.35 | 0 | 0 | 0% | NO | 0 | 0 | 147823.35 | 0 | 0 | 0 | 0 | 0 | 18% | 22.31% | 22.61% | 4.61% |  | 78.5 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23437 | Embedded Software Engineer | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  |  | 98.73% | 100% | 96.08% | 6970.8 | -6.29% | 150150 | 148239.36 | 1910.64 | 0 | 737.86 | 737.86 | 0 | 0 | 148239.36 | 6970.8 | 0 | 0% | NO | 0 | 6971 | 142430.1933 | 0 | 0 | 0 | 6970.8 | 6970.8 | 22% | 15.71% | 16.24% | -5.76% |  | 78.5 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P22440 | Spirit Managed Service - F&DT and Static Approval | Trevor Knox | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 3 | FIX | 2022-04-03 | 3 |  |  | 88.56% | 92.56% | 92.56% | 0 | 11.51% | 173500 | 153656.25 | 19843.75 | 0 | 52115 | 55720 | 0 | 0 | 142225.12 | 13717.36 | 11431.13 | 0% | NO | 15036.13 | 0 | 142225.12 | 0 | 0 | 0 | 0 | 0 | 0% | 11.51% | 0% | 0% |  | 44.73 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23550 | Tempest Composites | Philip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -14.949 | 103.4% | 96.71% | 96.71% | 0 | 5.1% | 149494.92 | 154577.42 | -5082.5 | 339.99 | 0 | 0 | 4209.4 | 5082.5 | 149494.92 | 101.1 | 5082.5 | 1495% | YES | 5082.5 | 0 | 149494.92 | 0 | 0 | 0 | 0 | 0 | 26% | 31.1% | 33.61% | 7.61% |  | 61.63 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23352 | Spirit 2023 - Stress Approve Man Serv (CC) | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level NC | FIX |  |  |  | 7.9623 | 81.9% | 84.71% | 43.59% | 0 | 4.24% | 195840 | 160392 | 35448 | 4452 | 0 | 0 | 0 | 0 | 135864 | 188.71 | 24528 | 550.9% | YES | 24528 | 79142 | 69912.3333 | 79142.4 | 0 | 0 | 0 | 0 | 7% | 11.24% | 5% | -2% |  | 48 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P22982 | Spirit 2022 - Hugh Sloan | Julliah Allen | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level NC | REIM |  |  |  | 75.8583 | 65.47% | 98.69% | 82.58% | 0 | -0.87% | 247473 | 162019.42 | 85453.58 | 1126.49 | 0 | 0 | 0 | 0 | 159890.62 | 180.98 | 2128.8 | 189% | YES | 2128.8 | 31315 | 133794.7867 | 5662.61 | 5747.76 | 5364.58 | 14539.71 | 0 | 7% | 6.13% | 0.75% | -6.25% |  | 35.48 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23508 | Verification and Validation | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM | 2024-05-31 | 0 |  |  | 80.77% | 100% | 100% | 0 | 10.77% | 212950 | 171993.5 | 40956.5 | 0 | 0 | 0 | 0 | 0 | 171993.53 | 0 | -0.03 | 0% | NO | -0.03 | 0 | 171993.53 | 0 | 0 | 0 | 0 | 0 | 24% | 34.77% | 33.6% | 9.6% |  | 78.5 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23518 | Systems Engineering support to FCAS | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 3.3969 | 95.42% | 86.05% | 86.05% | 0 | 1.87% | 193736.8 | 184873.31 | 8863.49 | 2609.27 | 4551.96 | 4551.96 | 39680 | 0 | 159084.68 | 70.43 | 25788.63 | 988.3% | YES | 25788.63 | 0 | 159084.68 | 0 | 0 | 0 | 0 | 0 | 21% | 22.87% | 3.47% | -17.53% |  | 69.3 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23464 | A220 Project X Design Offload | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 98.5935 | 56.04% | 95.12% | 79.76% | 0 | -9.96% | 332340 | 186229.3 | 146110.7 | 1481.95 | 0 | 0 | 0 | 0 | 177134.3 | 196.87 | 9095 | 613.7% | YES | 9095 | 34308 | 148544.3 | 32408.16 | 0 | 1900.32 | 0 | 0 | 26% | 16.04% | 12.97% | -13.03% |  | 42.87 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23753 | Tempest Composites Maturation | Philip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | -4.9552 | 148.4% | 82.62% | 37.43% | 0 | -2.72% | 127848.45 | 189733.01 | -61884.56 | 12488.77 | 0 | 0 | 111193.2 | 61884.56 | 156749.66 | 80.92 | 32983.35 | 264.1% | YES | 32983.35 | 102869 | 71025.4933 | 60613.06 | 42255.9 | 0 | 0 | 0 | 29% | 26.28% | 26.28% | -2.72% |  | 64.01 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23008 | Spirit Shorts Project Rachel | Carl Warren | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  |  | 68.49% | 91.32% | 91.32% | 0 | -9.7% | 286960 | 196531.2 | 90428.8 | 0 | 0 | 0 | 0 | 0 | 179472.8 | 20470.08 | 17058.4 | 0% | NO | 17058.4 | 0 | 179472.8 | 0 | 0 | 0 | 0 | 0 | 15% | 5.3% | 0.31% | -14.69% |  | 46.04 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23667 | Safety Systems Engineer | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 50.3547 | 50.25% | 94.17% | 84.27% | 0 | -11.49% | 398000 | 199980 | 198020 | 3932.5 | 0 | 0 | 0 | 0 | 188320 | 56.46 | 11660 | 296.5% | YES | 11660 | 23760 | 168520 | 0 | 23760 | 0 | 0 | 0 | 47% | 35.51% | 29.32% | -17.68% |  | 110 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23019 | EXP034-B Actuator Development | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  |  | 103.1% | 89.91% | 89.91% | 0 | -16.68% | 215541.2 | 222215.54 | -6674.34 | 0 | 12297.9 | 12297.9 | 0 | 6674.34 | 199796.76 | 477.34 | 397.78 | 0% | NO | 397.78 | 0 | 199796.76 | 0 | 0 | 0 | 0 | 0 | 34% | 17.32% | 79.64% | 45.64% |  | 58.45 | [5 empty] | -22021
1743 | 2024-06-19 23:34 | P23822 | FCASW Requirements Management | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 31.4166 | 34.8% | 82.35% | -4.02e-05% | 0 | -1.84% | 595703 | 207296.37 | 388406.63 | 12363.12 | 0 | 0 | 0 | 0 | 170698.25 | 129.22 | 36598.12 | 296% | YES | 36598.12 | 204838 | -0.083333 | 0 | 204837.9 | 0 | 0 | 0 | 17% | 15.16% | 15.16% | -1.84% |  | 78.09 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23421 | A220 DTC | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 1.4298 | 96.26% | 75.68% | 57.55% | 0 | -26.75% | 217089.12 | 208972.05 | 8117.07 | 5677.23 | 0 | 0 | 0 | 0 | 158146.02 | 151.04 | 50826.03 | 895.3% | YES | 50826.03 | 45461 | 120261.8533 | 0 | 33057.86 | 12403.44 | 0 | 0 | 29% | 2.25% | 7.2% | -21.8% |  | 46.45 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23242 | Physical Architecture & System Engineering Support | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 25.9514 | 76.24% | 96.15% | 90.06% | 0 | 6.14% | 305459 | 232884.46 | 72574.54 | 2796.56 | 775.55 | 775.55 | 0 | 0 | 223914.55 | 57.86 | 8615.91 | 308.1% | YES | 8615.91 | 17003 | 209745.3833 | 0 | 17003.1 | 0 | 0 | 0 | 15% | 21.14% | 7.41% | -7.59% |  | 78.23 | [5 empty] | -354
1743 | 2024-06-19 23:34 | P23506 | ASTER Mid-Life Refurbishment Project Manager | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 28.1012 | 71.99% | 95.09% | 87.93% | 0 | 1.02% | 326900 | 235325.37 | 91574.63 | 3258.75 | 3830.37 | 3830.37 | 0 | 0 | 223775.37 | 52.9 | 11550 | 354.4% | YES | 11550 | 20237 | 206911.2033 | 1228.75 | 19008 | 0 | 0 | 0 | 25% | 26.02% | 26.16% | 1.16% |  | 110 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23505 | EXP-022 Meteor TBUS T&E support | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 2.2051 | 96.6% | 95.31% | 86.83% | 0 | -1.65% | 246744.4 | 238347.39 | 8397.01 | 3808.03 | 185.6 | 185.6 | 0 | 0 | 227157.63 | 61.14 | 11189.76 | 293.8% | YES | 11189.76 | 24254 | 206945.9633 | 0 | 24254.1 | 0 | 0 | 0 | 20% | 18.35% | 15.64% | -4.36% |  | 89.83 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23373 | Raytheon Michael Bellini | Natalie Sinclair | 0 | RAS | RAYTHEON UNITED KINGDOM LIMITED | EES | Level NC | REIM |  |  |  | 46.9372 | 56.53% | 86.86% | 70.61% | 47270.76 | -7.6% | 428734.8 | 242367.55 | 186367.25 | 3970.57 | 0 | 0 | 0 | 0 | 210519.78 | 154.22 | 31847.77 | 802.1% | YES | 31847.77 | 47271 | 171127.28 | 0 | 22536.06 | 0 | 24734.7 | 47270.76 | 45% | 37.4% | 38.74% | -6.26% |  | 91.61 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23524 | Bombardier Regional Jets (BRJ) | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 2.3039 | 92.59% | 40.54% | 39.4% | 3694.07 | -8.28% | 289916.08 | 268445.29 | 21470.79 | 9319.43 | 0 | 0 | 0 | 0 | 108838.22 | 277.59 | 159607.07 | 1713% | YES | 159607.07 | 3694 | 105759.8867 | 0 | 0 | 0 | 3694.07 | 3694.07 | 22% | 13.72% | 14.92% | -7.08% |  | 43.81 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23741 | Engine Health Monitoring (EHM) Data Services | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  | 27.4592 | 43.32% | 92.1% | 50.78% | 0 | 2.4% | 640812 | 277572.6 | 363239.4 | 13228.35 | 0 | 0 | 0 | 0 | 255639 | 78.12 | 27933.6 | 211.2% | YES | 27933.6 | 137616 | 140959 | 0 | 68808 | 68808 | 0 | 0 | 28% | 30.4% | 30.4% | 2.4% |  | 38.79 | [5 empty] | 6000
1743 | 2024-06-19 23:34 | P23648 | EXP-032 Delivery of Datalink Eng support - FCAS AP | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 3 | REIM |  |  |  | 7.5978 | 78.34% | 63.06% | 56.19% | 0 | 7.8% | 371000 | 290631.7 | 80368.3 | 10577.81 | 1032.95 | 1032.95 | 0 | 0 | 183267.95 | 88.47 | 107363.75 | 1015% | YES | 107363.75 | 23958 | 163302.95 | 0 | 23958 | 0 | 0 | 0 | 22% | 29.8% | 30.44% | 8.44% |  | 101.85 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23754 | Tempest Composites WP4 | Philip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | 0.95703 | 93.5% | 0% | 0% | 0 | 0.19% | 310945.68 | 290719.82 | 20225.86 | 21134.04 | 1784.87 | 1784.87 | 0 | 0 | 0 | 128.38 | 290719.82 | 1376% | YES | 290719.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36% | 36.19% | 36.19% | 0.19% |  | 62.95 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23007 | EXP-006A - Brimstone 3 | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level NC | REIM |  |  |  | 41.5067 | 72.42% | 97.35% | 94.23% | 0 | -2.21% | 406450 | 294339.03 | 112110.97 | 2701.03 | 0 | 0 | 0 | 0 | 286547.91 | 56.71 | 7791.12 | 288.4% | YES | 7791.12 | 11021 | 277363.7433 | 0 | 11021.44 | 0 | 0 | 0 | 25% | 22.79% | 29.97% | 4.97% |  | 70.39 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23739 | Lifing Services DACs | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE PLC - COUPA ONLY | DET | Level 3 | FIX |  |  |  | 30.2952 | 43.1% | 97.73% | 58.36% | 0 | 5.92% | 656508 | 282966.1 | 373541.9 | 12330.05 | 0 | 0 | 0 | 0 | 276545 | 77.28 | 18421.1 | 149.4% | YES | 18421.1 | 133702 | 165126.6667 | 0 | 66850.8 | 66850.8 | 0 | 0 | 28% | 33.92% | 33.92% | 5.92% |  | 37.83 | [5 empty] | 12000
1743 | 2024-06-19 23:34 | P23308 | NATO JEWCS | Natalie Sinclair | 0 | COB | CHELTON LIMITED | EES | Level NC | REIM |  |  |  | 30.7042 | 87.89% | 91.57% | 87.36% | 15829.13 | -4.21% | 356307 | 313169.4 | 43137.6 | 1404.94 | 756.39 | 756.39 | 0 | 0 | 286767.43 | 167.42 | 26401.97 | 1879% | YES | 26401.97 | 15829 | 273576.5967 | 0 | 15829.13 | 0 | 0 | 15829.13 | 24% | 19.79% | 11.85% | -12.15% |  | 75.81 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P22953 | Spirit Shorts eVTOL | Julliah Allen | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM | 2023-05-08 | 1 |  |  | 103.1% | 80.83% | 80.83% | 0 | -9.51% | 324272 | 334483.6 | -10211.6 | 0 | 66696.6 | 67387.9 | 0 | 10211.6 | 270366 | 64941.12 | 54117.6 | 0% | NO | 54808.9 | 0 | 270366 | 0 | 0 | 0 | 0 | 0 | 17% | 7.49% | 100% | 83% |  | 46.19 | [5 empty] | -10000
1743 | 2024-06-19 23:34 | P21463 | Safety & Monitoring Systems at DM Beith & Gosport | Harry James Kellett | 0 | BXW | MOD | EES | Level 2 | FIX |  |  |  | 583.0273 | 88.21% | 113.4% | 113.4% | 0 | -23.47% | 378612.83 | 333964.6 | 44648.23 | 76.58 | 75631.47 | 79790.28 | 45616.14 | 0 | 378594.83 | 0 | -44630.23 | -58279% | NO | -40471.42 | 0 | 378594.83 | 0 | 0 | 0 | 0 | 0 | 48% | 24.53% | 39.5% | -8.5% |  | 56.3 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23472 | Tempest Wing Design | Philip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 14.5517 | 55.62% | 127.2% | 113.2% | 0 | -0.45% | 483869.78 | 269104.61 | 214765.17 | 14758.75 | 253225 | 356900 | 0 | 0 | 342367.15 | 92.2 | -3477.55 | -23.56% | NO | 100197.45 | 45131 | 304757.9833 | 21273.66 | 23857.58 | 0 | 0 | 0 | 23% | 22.55% | 45.77% | 22.77% |  | 46.74 | [5 empty] | 69785
1743 | 2024-06-19 23:34 | P22515 | Shorts A220 100/300 ALI Phase III | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 170.0905 | 69.37% | 98.45% | 94.37% | 0 | 0.51% | 489839.64 | 339804.47 | 150035.17 | 882.09 | 3450.98 | 3450.98 | 0 | 0 | 334523.97 | 95.85 | 5280.5 | 598.6% | YES | 5280.5 | 16622 | 320672.3033 | 7501.03 | 0 | 9121.46 | 0 | 0 | 10% | 10.51% | 6.5% | -3.5% |  | 40.59 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P22842 | ME Support (Aim Altitude) | Trevor Knox | 0 | AVI | AIM ALTITUDE UK LIMITED | ME | Level 3 | FIX | 2023-06-14 | 4 |  |  | 99.31% | 100.5% | 86.63% | 57290.84 | 0.49% | 346293.67 | 343918.08 | 2375.59 | 0 | 2909.86 | 2909.86 | 0 | 0 | 345673.01 | 55184.93 | -1754.93 | 0% | NO | -1754.93 | 57291 | 297930.51 | 0 | 0 | 0 | 57290.84 | 57290.84 | 13% | 13.49% | 0% | -13% |  | 46.3 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23816 | Typhoon FTI Works - 2024 Fixed Price Element | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  |  | 83.49% | 85.76% | 54.38% | 0 | -1.67% | 404176.65 | 337446.98 | 66729.67 | -1885.03 | 0 | 0 | 0 | 0 | 289390.14 | 70.28 | 58056.84 | -3080% | NO | 58056.84 | 127073 | 183495.9733 | 0 | 127072.97 | 0 | 0 | 0 | 30% | 28.33% | 28.33% | -1.67% |  | 50.47 | [5 empty] | 10000
1743 | 2024-06-19 23:34 | P22391 | GE System Engineering support | Vinayakumar Sugur | 0 | GEE | EXPERIS LIMITED | EES | Level NC | REIM | 2024-04-08 | 1 |  | 122.8662 | 82.01% | 100.7% | 100.7% | 0 | 0.8% | 434434.25 | 356260.63 | 78173.62 | 636.25 | 0 | 0 | 0 | 0 | 358805.6 | 0.04 | 0.03 | 0.004715% | NO | 0.03 | 0 | 358805.6 | 0 | 0 | 0 | 0 | 0 | 6% | 6.8% | 60.63% | 54.63% |  | 57.33 | [5 empty] | 2545
1743 | 2024-06-19 23:34 | P23629 | F35 FTI | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level NC | REIM |  |  |  | -32.0663 |  | 81.63% | 77.15% | 0 | -1.95% | 0 | 364594.38 | -364594.38 | 11370.02 | 0 | 0 | 0 | 364594.38 | 297632.62 | 52.43 | 66961.76 | 588.9% | YES | 66961.76 | 19636 | 281269.2867 | 19635.53 | 0 | 0 | 0 | 0 | 31% | 29.05% | 28.07% | -2.93% |  | 61.36 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23617 | Tempest Composites WP2 | Philip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | FIX |  |  |  | -20.1305 | 160.6% | 45.62% | 19.5% | 29536.68 | 11.48% | 244405.26 | 392406.3 | -148001.04 | 7352.07 | 0 | 0 | 153486.97 | 148001.04 | 179019.87 | 442.98 | 213386.43 | 2902% | YES | 213386.43 | 122979 | 76537.37 | 93442.74 | 0 | 0 | 29536.68 | 29536.68 | 22% | 33.48% | 33.01% | 11.01% |  | 62.24 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23045 | Shotgun Adaptors - 10 Sets | Harry James Kellett | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | FIX | 2024-02-27 | 3 |  |  | 78.74% | 127% | 127% | 0 | 2.55% | 399276.11 | 314390.3 | 84885.81 | 0 | 214550.47 | 214550.47 | 0 | 0 | 399276.11 | 349.55 | 15877.19 | 0% | NO | 15877.19 | 0 | 399276.11 | 0 | 0 | 0 | 0 | 0 | 31% | 33.55% | 93.96% | 62.96% |  | 58.52 | [5 empty] | 100763
1743 | 2024-06-19 23:34 | P23432 | Spirit Belfast MRB On-Site Support (Mon & Clear) | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 61.5519 | 65.77% | 138.7% | 128.6% | 0 | -9.79% | 449545 | 295665.27 | 153879.73 | 2500 | 295665.27 | 451827.33 | 0 | 0 | 410199.75 | 44916.62 | 7465.52 | 298.6% | YES | 163627.58 | 35958 | 380234.75 | 0 | 35958 | 0 | 0 | 0 | 39% | 29.21% | 100% | 61% |  | 0 | [5 empty] | 122000
1743 | 2024-06-19 23:34 | P23743 | EHM Cloud Migration | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 33.4732 | 38.02% | 110.7% | 66.29% | 0 | 8.5% | 1016000 | 386243.13 | 629756.87 | 18813.75 | 0 | 0 | 0 | 0 | 427656 | 64.77 | -2412.88 | -12.83% | NO | -2412.88 | 205949 | 256031.8333 | 0 | 102336 | 103612.8 | 0 | 0 | 28% | 36.5% | 36.5% | 8.5% |  | 55.92 | [5 empty] | 39000
1743 | 2024-06-19 23:34 | P23603 | Typhoon IMDLR | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | -4.0389 | 141% | 70.93% | 27.86% | 0 | 1.2% | 305067.09 | 430106.17 | -125039.08 | 30958.47 | 1500 | 1500 | 152797.11 | 125039.08 | 305064.02 | 296.26 | 125042.15 | 403.9% | YES | 125042.15 | 222307 | 119808.1867 | 0 | 222307.42 | 0 | 0 | 0 | 28% | 29.2% | 27.91% | -0.09% |  | 55.98 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23023 | Spirit Shorts R Foster/M Gourley | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 90.4038 | 72.49% | 106.1% | 98.14% | 0 | -1.11% | 590659.44 | 428183.06 | 162476.38 | 1797.23 | 237621.5 | 267726 | 0 | 0 | 454499.72 | 80.97 | -3950.66 | -219.8% | NO | 26153.84 | 41139 | 420217.22 | 0 | 20921.8 | 20217.14 | 0 | 0 | 9% | 7.89% | 11.04% | 2.04% |  | 29.72 | [5 empty] | 22366
1743 | 2024-06-19 23:34 | P23677 | ME Managed Service - Phase 1 | Paul Watson | 0 | STV | SPIRIT AEROSYSTEMS (EUROPE) LTD | ME | Level 3 | FIX |  |  |  | 22.4441 | 43.24% | 69.53% | 0% | 0 | -10.25% | 1116000 | 482556.35 | 633443.65 | 28223.13 | 0 | 38000 | 0 | 0 | 335497.5 | 143.34 | 147058.85 | 521.1% | YES | 185058.85 | 402597 | 0 | 116181 | 71536.5 | 214879.5 | 0 | 0 | 30% | 19.75% | 21.29% | -8.71% |  | 44.24 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P22906 | Spirit Shorts - MRB JD Support | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | 1.4553 | 99.19% | 65.81% | 64.65% | 99451.32 | -7.99% | 481714 | 477831.18 | 3882.82 | 2668 | 0 | 0 | 0 | 0 | 314468.62 | 466.52 | 171362.56 | 6423% | YES | 171362.56 | 6633 | 308941.12 | -92818.8 | 0 | 0 | 99451.32 | 99451.32 | 13% | 5.01% | 2.38% | -10.62% |  | 36.98 | [5 empty] | 8000
1743 | 2024-06-19 23:34 | P22652 | L3 - Saftey Engineering | Sean Simmons | 0 | LHW | L3HARRIS MAPPS LIMITED | EES | Level NC | FIX |  |  |  |  | 95.63% | 95.66% | 95.66% | 0 | 5.66% | 523390 | 500497.5 | 22892.5 | 0 | 0 | 0 | 0 | 0 | 478783.75 | 26056.5 | 21713.75 | 0% | NO | 21713.75 | 0 | 478783.75 | 0 | 0 | 0 | 0 | 0 | 21% | 26.66% | 25.88% | 4.88% |  | 83.05 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23281 | Systems Portfolio | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM | 2024-02-28 | 0 |  |  | 44.43% | 97.31% | 97.31% | 0 | -17.25% | 1177697.24 | 523236.96 | 654460.28 | 0 | 2133.28 | 2133.28 | 0 | 0 | 509179.87 | 15792.1 | 13160.09 | 0% | NO | 13160.09 | 0 | 509179.87 | 0 | 0 | 0 | 0 | 0 | 25% | 7.75% | 100% | 75% |  | 70.48 | [5 empty] | -897
1743 | 2024-06-19 23:34 | P23531 | BAe Systems F35 MRB Support | Richard Brook | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | -67.1172 |  | 95.17% | 92.53% | 0 | 3.76% | 0 | 547678.25 | -547678.25 | 8160.03 | 287.44 | 287.44 | 0 | 547678.25 | 521204.11 | 34.2 | 26474.14 | 324.4% | YES | 26474.14 | 17316 | 506774.11 | 17316.04 | 0 | 0 | 0 | 0 | 25% | 28.76% | 31.79% | 6.79% |  | 60.22 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23554 | Dornier Seawings 328 2023 H2 Support | Natalie Sinclair | 0 | DAX | EXPLEO GERMANY GMBH (EC) | MPE | Level 2 | REIM |  |  |  | -0.16238 | 100.4% | 74.58% | 74.58% | 0 | 4.88% | 572100.58 | 574208.99 | -2108.41 | 12984.75 | 4046.44 | 4046.44 | 29560.5 | 2108.41 | 428252.8 | 99.12 | 145956.19 | 1124% | YES | 145956.19 | 0 | 428252.8 | 0 | 0 | 0 | 0 | 0 | 21% | 25.88% | 22.08% | 1.08% |  | 65.07 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23001 | Spirit Shorts A220 Design | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -12.8865 | 119.6% | 72.7% | 68.47% | 0 | 11.1% | 486640 | 581919.2 | -95279.2 | 7393.7 | 0 | 0 | 84661.14 | 95279.2 | 423039.7 | 301.72 | 158879.5 | 2149% | YES | 158879.5 | 29532 | 398429.7 | 7601.28 | 0 | 21930.72 | 0 | 0 | 9% | 20.1% | 12.57% | 3.57% |  | 43.52 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23699 | A220 Stress Checkers | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | -7.4335 | 143.4% | 64.84% | 4.554e-05% | 0 | 7.05% | 408328.79 | 585534.78 | -177205.99 | 23838.96 | 12000 | 12000 | 185592 | 177205.99 | 379653.6 | 185.84 | 205881.18 | 863.6% | YES | 205881.18 | 455584 | 0.26667 | 0 | 455584.32 | 0 | 0 | 0 | 13% | 20.05% | 20.07% | 7.07% |  | 61.88 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23219 | Tornado Air 800 Engineering Support | Richard Brook | 0 | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 3 | REIM |  |  |  | -1.0985 | 100.5% | 93.53% | 93.53% | 0 | -1.45% | 615046 | 618400.61 | -3354.61 | 3053.77 | 459.21 | 459.21 | 0 | 3354.61 | 578373.17 | 94.65 | 15120.44 | 495.1% | YES | 15120.44 | 0 | 578373.17 | 0 | 0 | 0 | 0 | 0 | 31% | 29.55% | -236.9% | -267.9% |  | 81.22 | [5 empty] | -24907
1743 | 2024-06-19 23:34 | P23520 | FCAS AP Portfolio Systems | Matthew Tweed | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 17.8882 | 73.76% | 93.98% | 85.68% | 0 | -6.25% | 810821 | 598037.8 | 212783.2 | 11895.19 | 423 | 423 | 0 | 0 | 562047.44 | 50.87 | 31707.36 | 266.6% | YES | 31707.36 | 59604 | 512377.44 | 0 | 59604 | 0 | 0 | 0 | 22% | 15.75% | 16.86% | -5.14% |  | 81.47 | [5 empty] | -4283
1743 | 2024-06-19 23:34 | P23140 | Spirit Shorts A220 MLG Stress Support | Siyun Fan | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  | 18.7907 | 79.19% | 92.86% | 63.66% | 119449.2 | -8.64% | 735573.4 | 582516.28 | 153057.12 | 8145.38 | 20870.3 | 87811.88 | 111743 | 0 | 540939.4 | 175.29 | 66576.88 | 817.4% | YES | 133518.46 | 204098 | 370857.7333 | 0 | 0 | 204098.4 | 0 | 119449.2 | 17% | 8.36% | -10.92% | -27.92% |  | 44.37 | [5 empty] | 25000
1743 | 2024-06-19 23:34 | P22790 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | REIM | 2024-04-28 | 0 |  |  | 184.8% | 95.2% | 95.2% | 0 | 0.57% | 352240 | 651013.87 | -298773.87 | -11111.65 | 1611.52 | 1611.52 | 44500 | 298773.87 | 619743.88 | 0 | -0.01 | 9e-05% | NO | -0.01 | 0 | 619743.88 | 0 | 0 | 0 | 0 | 0 | 13% | 13.57% | 28.82% | 15.82% |  | 45.02 | [5 empty] | -31270
1743 | 2024-06-19 23:34 | P23372 | BAE Carbon Tooling Off-load | Gary Kempster | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | 7.5688 | 92.52% | 97.79% | 69.87% | 0 | -3.25% | 674141.57 | 623709.5 | 50432.07 | 6663.11 | 0 | 0 | 0 | 0 | 609936.5 | 188.95 | 13773 | 206.7% | YES | 13773 | 208981 | 435785.6667 | 33755.72 | 175224.95 | 0 | 0 | 0 | 25% | 21.75% | 18.75% | -6.25% |  | 54.05 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23473 | Tempest Vertical Tail | Philip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 24.5561 | 73.8% | 102.6% | 88.88% | 0 | -6.65% | 846017.62 | 624392.96 | 221624.66 | 9025.24 | 112700 | 129075 | 0 | 0 | 640463.05 | 55.51 | -11070.09 | -122.7% | NO | 5304.91 | 102568 | 554989.7167 | 57234.89 | 45333.23 | 0 | 0 | 0 | 29% | 22.35% | 25.03% | -3.97% |  | 62.73 | [5 empty] | 5000
1743 | 2024-06-19 23:34 | P23605 | Typhoon Work Package 2 Continuation | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM |  |  |  | -33.4769 | 104% | 93.17% | 83.55% | 0 | 4.81% | 627011.01 | 652279.37 | -25268.36 | 754.8 | 5554 | 5554 | 0 | 25268.36 | 607723.77 | 1262.6 | 44555.6 | 5903% | YES | 44555.6 | 75285 | 544986.27 | 0 | 75284.54 | 0 | 0 | 0 | 23% | 27.81% | 27.48% | 4.48% |  | 55.52 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23366 | Business Analyst Support | Peter Williams | 0 | BDZ | MBDA UK LIMITED | DET | Level 3 | REIM |  |  |  | 101.8482 | 28.95% | 183.2% | 149.6% | 0 | -1.41% | 1302200 | 377008.02 | 925191.98 | 9084.03 | 302582.15 | 900840.72 | 0 | 0 | 690640 | 79.53 | -25761.98 | -283.6% | NO | 572496.59 | 151776 | 564160 | 73824 | 77952 | 0 | 0 | 0 | 43% | 41.59% | 16.62% | -26.38% |  | 42.53 | [5 empty] | 287870
1743 | 2024-06-19 23:34 | P23323 | CNC-CMM Programming Support | Stephen Young | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level NC | REIM |  |  |  | -5.6225 | 108.9% | 91.76% | 85.4% | 0 | -1.72% | 617809.74 | 672706.7 | -54896.96 | 9763.78 | 15941.56 | 17789.56 | 99488.9 | 54896.96 | 617295.69 | 76.3 | 55411.01 | 567.5% | YES | 57259.01 | 51363 | 574493.19 | 51362.6 | 0 | 0 | 0 | 0 | 32% | 30.28% | 36.66% | 4.66% |  | 57.74 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23694 | Systems Portfolio EXP-011a | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 1.9464 | 93.61% | 71.3% | 71.22% | 0 | 1.69% | 819497.5 | 767112.89 | 52384.61 | 26913.9 | 809.51 | 809.51 | 0 | 0 | 546983.95 | 60.83 | 220128.94 | 817.9% | YES | 220128.94 | 782 | 546332.2833 | 782.11 | 0 | 0 | 0 | 0 | 21% | 22.69% | 20.64% | -0.36% |  | 88.42 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23426 | BAE Tempest WP 3 Harness Maturation | Philip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | -0.94071 | 102.2% | 93.87% | 65.52% | 107757.52 | -5.99% | 884012.04 | 903152.72 | -19140.68 | 20347.02 | 213.34 | 213.34 | 46440 | 19140.68 | 847792.24 | 111.79 | 55360.48 | 272.1% | YES | 55360.48 | 307226 | 591770.5733 | 120017.4 | 79451.21 | 107757.52 | 0 | 107757.52 | 33% | 27.01% | 27.43% | -5.57% |  | 52.52 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23105 | Raytheon Supply Engineering Support | Natalie Sinclair | 0 | RAY | RAYTHEON UNITED KINGDOM LIMITED | MPE | Level 3A | REIM | 2023-07-13 | 3 |  |  | 74.19% | 99.35% | 90.07% | 49156.8 | -2.02% | 1250075.75 | 927395.25 | 322680.5 | 0 | 0 | 0 | 0 | 0 | 921359.25 | 107644.5 | 3672 | 0% | NO | 3672 | 103238 | 835327.5833 | 54081.3 | 0 | 0 | 49156.8 | 49156.8 | 26% | 23.98% | 100% | 74% |  | 48.97 | [5 empty] | -2364
1743 | 2024-06-19 23:34 | P23685 | DAC LUC Support and Recompliance | Vijayakumara Nanjundappa | 0 | ARZ | ROLLS-ROYCE CONTROL AND | DET | Level 2 | FIX |  |  |  | 39.5949 | 30.35% | 150.3% | 89.87% | 0 | 8.83% | 2640000 | 801169.36 | 1838830.64 | 46441.14 | 0 | 0 | 0 | 0 | 1203934 | 39.44 | -267000.64 | -574.9% | NO | -267000.64 | 580721 | 719999.8333 | 0 | 283279.2 | 297441.6 | 0 | 0 | 30% | 38.83% | 38.83% | 8.83% |  | 57.15 | [5 empty] | 135764
1743 | 2024-06-19 23:34 | P23117 | BAE Typhoon Eng Support | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM | 2024-03-12 | 3 |  |  | 103.2% | 96.92% | 96.92% | 0 | -1.09% | 950771.99 | 980837.59 | -30065.6 | -4930.23 | 19213.34 | 20141.26 | 4921.28 | 30065.6 | 950609.41 | 2311.1 | 3132.18 | -63.53% | NO | 4060.1 | 0 | 950609.41 | 0 | 0 | 0 | 0 | 0 | 30% | 28.91% | 20.68% | -9.32% |  | 52.29 | [5 empty] | -27096
1743 | 2024-06-19 23:34 | P23451 | BAE Tempest - DFM-ASO Planning | Stephen Young | 0 | BAM | BAE Systems (Ops) Ltd - Warton | ME | Level 3 | REIM |  |  |  | 8.0889 | 87.97% | 89.27% | 63.29% | 27224.9 | -3.03% | 1145785.42 | 1007986.56 | 137798.86 | 17035.53 | 0 | 0 | 0 | 0 | 899799.63 | 145.44 | 107103.93 | 628.7% | YES | 107103.93 | 314247 | 637927.13 | 75655.99 | 211366.22 | 0 | 27224.9 | 27224.9 | 28% | 24.97% | 26.28% | -1.72% |  | 53.87 | [5 empty] | -1083
1743 | 2024-06-19 23:34 | P22350 | EMP 2020-2021 | Natalie Sinclair | 0 | ARY | GUIDANT GLOBAL UK LIMITED | PCPR | Level NC | REIM |  |  |  | -2.9161 | 100.9% | 99.54% | 94.74% | 10748.57 | -2.08% | 1017579.76 | 1026385.66 | -8805.9 | 3019.77 | 400 | 400 | 0 | 8805.9 | 1021709.62 | 89.86 | 4676.04 | 154.8% | YES | 4676.04 | 59137 | 972428.7867 | 14494.86 | 22178.24 | 22464.33 | 0 | 10748.57 | 32% | 29.92% | 28.22% | -3.78% |  | 44.16 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23602 | EXP-025 Portfolio Software Engineering Support | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 8.695 | 80.53% | 86.73% | 76.18% | 0 | -1.15% | 1327080 | 1068738.54 | 258341.46 | 29711.63 | 4793.63 | 966858.2 | 0 | 0 | 926909.33 | 58.42 | 141829.21 | 477.4% | YES | 1103893.78 | 135246 | 814204.33 | 0 | 135246.31 | 0 | 0 | 0 | 24% | 22.85% | 22.57% | -1.43% |  | 83.51 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P22671 | Spirit Shorts Pylon and Fairing Package | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX | 2023-05-03 | 1 |  |  | 105% | 95.26% | 95.26% | 0 | -7.36% | 1198494.77 | 1258071.09 | -59576.32 | -530 | 106494.89 | 106494.89 | 0 | 59576.32 | 1198494.77 | 0.39 | 0.32 | -0.06038% | NO | 0.32 | 0 | 1198494.77 | 0 | 0 | 0 | 0 | 0 | 20% | 12.64% | 102.1% | 82.09% |  | 45.4 | [5 empty] | -59576
1743 | 2024-06-19 23:34 | P23152 | Project Aragon - Design and Stress Support | Paul Watson | 0 | STX | SHORT BROTHERS PLC | MPE | Level 3 | REIM |  |  |  | -6.0666 | 105.6% | 86.61% | 72.29% | 0 | 0.46% | 1333452.21 | 1407966.11 | -74513.9 | 12282.6 | 0 | 0 | 49524 | 74513.9 | 1219477.02 | 238.6 | 188489.09 | 1535% | YES | 188489.09 | 241970 | 1017835.3533 | 0 | 241969.72 | 0 | 0 | 0 | 29% | 29.46% | 29.32% | 0.32% |  | 52.02 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23292 | BAE Tempest WP 4 AV Trays | Philip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | 1.1064 | 98.41% | 96.46% | 83.8% | 0 | 1.46% | 1498284.22 | 1474431.34 | 23852.88 | 21558.72 | 0 | 0 | 0 | 0 | 1422222.18 | 76.74 | 52209.16 | 242.2% | YES | 52209.16 | 223979 | 1235573.0133 | 125131.58 | 98847.53 | 0 | 0 | 0 | 32% | 33.46% | 32.23% | 0.23% |  | 54.01 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23411 | Agile & Scrum Delivery Service | Peter Williams | 0 | BDZ | MBDA UK LIMITED | DET | Level 2 | REIM | 2023-08-14 | 0 |  |  | 36.3% | 170.5% | 170.5% | 0 | 13.08% | 2487000 | 902903.79 | 1584096.21 | 0 | 894178.59 | 894178.59 | 0 | 0 | 1539600 | 19368.95 | 16140.79 | 0% | NO | 16140.79 | 0 | 1539600 | 0 | 0 | 0 | 0 | 0 | 29% | 42.08% | 0% | -29% |  | 74.57 | [5 empty] | 652837
1743 | 2024-06-19 23:34 | P23519 | Mechanical and Electrical Design Eng Support | Michael Stuart Frain | 0 | BAX | SAFRAN SEATS GB LIMITED | MPE | Level 2 | REIM |  |  |  | 7.7753 | 89.62% | 93.29% | 86.01% | 0 | -2.53% | 1807261.3 | 1619756.05 | 187505.25 | 24115.43 | 1004.45 | 1504.45 | 0 | 0 | 1511140.05 | 48.92 | 86716 | 359.6% | YES | 87216 | 141528 | 1393200.05 | 0 | 141528.3 | 0 | 0 | 0 | 33% | 30.47% | 29.33% | -3.67% |  | 56.67 | [5 empty] | -21900
1743 | 2024-06-19 23:34 | P22278 | TAI Supply Engineers to Ankara | Natalie Sinclair | 0 | TAI | TUSAS-TURK HAVACILIK VE UZAY | MPE | Level 3A | REIM |  |  |  | 2170.1012 | 19.99% | 454.1% | 454.1% | 0 | -15.91% | 2105282 | 420740.91 | 1684541.09 | 776.25 | 49400.29 | 49400.29 | 0 | 0 | 1910696.33 | 158 | 20444.58 | 2634% | YES | 20444.58 | 0 | 1910696.33 | 0 | 0 | 0 | 0 | 0 | 95% | 79.09% | 63.05% | -31.95% |  | 34.07 | [5 empty] | 1510400
1743 | 2024-06-19 23:34 | P23175 | BAe Aero Typhoon Package 2 | Richard Brook | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 2 | REIM | 2024-03-12 | 2 |  |  | 103.3% | 96.79% | 96.79% | 0 | -1.62% | 1984265.09 | 2050055.96 | -65790.87 | -2488.97 | 57677.87 | 86030.82 | 8889.78 | 65790.87 | 1984257.03 | 72784.72 | 60653.93 | -2437% | NO | 89006.88 | 0 | 1984257.03 | 0 | 0 | 0 | 0 | 0 | 29% | 27.38% | 24.84% | -4.16% |  | 51.77 | [5 empty] | -5145
1743 | 2024-06-19 23:34 | P19020 | Spirit Concessions - 2018 | Julliah Allen | 0 | STX | SPIRIT AEROSYSTEMS (EUROPE) LTD | MPE | Level 2 | FIX | 2024-01-23 | 0 |  |  | 86.3% | 111.8% | 111.8% | 0 | 2.09% | 2015043.23 | 1739018.14 | 276025.09 | 0 | 44317.61 | 44317.61 | 0 | 0 | 1944710.76 | 236384.86 | 196987.38 | 0% | NO | 196987.38 | 0 | 1944710.76 | 0 | 0 | 0 | 0 | 0 | 25% | 27.09% | 9.32% | -15.68% |  | 40.87 | [5 empty] | 402680
1743 | 2024-06-19 23:34 | P23006 | Spirit Shorts A350 Freighter Toulouse | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level NC | REIM |  |  |  | 4.7604 | 93.23% | 104.3% | 94.44% | 0 | 22.81% | 1925837.92 | 1795548.27 | 130289.65 | 27369.21 | 1086670.26 | 2010741.94 | 0 | 0 | 1873531.68 | 255.47 | 309290.59 | 1130% | YES | 1233362.27 | 213293 | 1695787.5133 | 0 | 213292.5 | 0 | 0 | 0 | 5% | 27.81% | 44.94% | 39.94% |  | 48.2 | [5 empty] | 387274
1743 | 2024-06-19 23:34 | P23257 | BAE Tempest WP 5 Centre Fuselage | Philip Anderson | 0 | BAE | BAE Systems (Ops) Ltd - Warton | MPE | Level 3 | REIM |  |  |  | -2.1136 | 101.2% | 99.74% | 94% | 0 | -5.59% | 2265401.51 | 2292330.54 | -26929.03 | 12740.57 | 78100 | 78100 | 0 | 26929.03 | 2286342.68 | 65.12 | 5987.86 | 47% | NO | 5987.86 | 157776 | 2154862.68 | 89955.07 | 67820.9 | 0 | 0 | 0 | 33% | 27.41% | 28.73% | -4.27% |  | 61.09 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23435 | Andy Baker Portfolio | Dushan Fernando | 0 | BDW | MBDA UK LIMITED | EES | Level 2 | REIM |  |  |  | 35.4888 | 60.69% | 93.36% | 84.52% | 0 | -7.39% | 4023207.4 | 2441778.66 | 1581428.74 | 44561.41 | 2818.87 | 2818.87 | 0 | 0 | 2279634.08 | 57.59 | 162144.58 | 363.9% | YES | 162144.58 | 259027 | 2063778.2467 | 559.56 | 296652.44 | -38184.52 | 0 | 0 | 25% | 17.61% | 18.75% | -6.25% |  | 81.22 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23179 | Spirit Shorts Atlas A350 Freighter | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 1 | FIX |  |  |  | -9.0009 | 101.8% | 96.4% | 93.19% | 0 | -9.15% | 2542643.04 | 2588584.82 | -45941.78 | 5104.11 | 156991.12 | 248243.92 | 0 | 45941.78 | 2495342.85 | 341.81 | 93241.97 | 1827% | YES | 184494.77 | 99729 | 2412235.35 | 99728.59 | 0 | 0 | 0 | 0 | 22% | 12.85% | 18.67% | -3.33% |  | 44.4 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P19731 | Hapri HPC Rear Bearing Housing PDR & CDR | Steven Lawton | 0 | ATC | AECC Hunan Aviation Powerplant | MPE | Level 1 | FIX | 2024-05-13 | 3 |  | -2.6755 | 104.8% | 95.39% | 95.39% | 0 | -14.32% | 2980000 | 3123961.5 | -143961.5 | 53808.02 | 500476.22 | 500476.22 | 0 | 143961.5 | 2980000 | 0 | -0.5 | -0.0009292% | NO | -0.5 | 0 | 2980000 | 0 | 0 | 0 | 0 | 0 | 38% | 23.68% | 34.67% | -3.33% |  | 64.85 | [5 empty] | -143962
1743 | 2024-06-19 23:34 | P23207 | A350 Approvers - Design and Stress Support | Derek Oakley | 0 | STX | SHORT BROTHERS PLC | MPE | Level 2 | FIX |  |  |  | 11.1158 | 82.89% | 90.41% | 80.16% | 0 | -2.39% | 3700250 | 3067051.91 | 633198.09 | 56963.57 | 44532.47 | 53005.81 | 0 | 0 | 2772971.66 | 74.31 | 294080.25 | 516.3% | YES | 302553.59 | 377387 | 2458482.4933 | 0 | 275235.34 | 102151.98 | 0 | 0 | 20% | 17.61% | 16.72% | -3.28% |  | 54.54 | [5 empty] | 0
1743 | 2024-06-19 23:34 | P23487 | Tornado Air 800 Engineering Support | Richard Brook | 0 | BAW | BAE Systems (Ops) Ltd - Warton | EES | Level 2 | FIX |  |  |  | 10.7661 | 77.78% | 83.8% | 71.15% | 285969.17 | 7.9% | 4655748.75 | 3621150.91 | 1034597.84 | 96097.76 | 500 | 500 | 0 | 0 | 3034359.96 | 151.07 | 818790.95 | 852% | YES | 818790.95 | 549397 | 2576529.1267 | 0 | 263427.34 | 285969.17 | 0 | 285969.17 | 32% | 39.9% | 46.25% | 14.25% |  | 79.04 | [5 empty] | 232000
Extend Table